Type of Review: Annual Review

Project Title: Scaling Up Family Planning in Zambia

Date started:	March 1, 2012
Date review undertaken: December 2013 to January 2014
## Introduction and Context
What support is the UK providing?
The UK is providing up to £14.8 million over a period of four years from 2012 to 2016 to scale up family planning services in Zambia. This funding includes £2.9 million for the procurement of family planning commodities. / The programme is addressing immediate needs through the rapid scale up of family planning services for under-served areas and populations in 26 districts and it is building the capacity of the public sector to deliver quality comprehensive family planning services beyond the programme timeframe. The programme is being implemented by Abt Associates Inc. A map of the districts is given in the figure below. Districts were chosen with the government based on low contraceptive prevalence rates (DHS 2007), high unmet need (DHS 2007), the presence of other partners and also the targets that the programme has to achieve. / The programme is working with community health workers, traditional and religious leaders to sensitise communities on the uptake of family planning services and to provide accurate information to address myths and misconceptions. Outreach services are being delivered in partnership with the Ministry of Community Development Mother and Child Health (MCDMCH) working with health facilities. A focus of the programme is on adolescents, a particularly vulnerable but hard to reach group. The programme works with adolescent peer educators and schools to broaden its reach with this group. / DFID is supporting UNFPA to procure reproductive health commodities under this programme, based on identified gaps by the government’s Reproductive Health Commodity Security Committee. Supplies are warehoused and distributed by Medical Stores Ltd (MSL) through the public drug supply system, helping to address commodity gaps in Zambia. Abt Associates is working with health facilities and districts to streamline their systems to ensure adequate supplies are available to support delivery of family planning services.

What are the expected results?
The impact will be improved maternal health in Zambia. By 2015 the programme will: / Reduce maternal mortality from 591/100,000 to 443/100,000. / Avert 92,450 unintended pregnancies (13,868 in adolescents) / Avert 13,059 unsafe abortions (1,958 in adolescents) / Avert 298 maternal deaths (45 in adolescents) / 80% of these results will be attributable to DFID. / The outcome will be increased use of family planning in Zambia. This will be measured by: / Increase the contraceptive prevalence rate in programme intervention areas from 20.4% to 27.2%. / A decrease in the percentage of women and girls with unmet need for family planning in programme areas from 27% to 5%. / The outputs and output indicators of the programme are outlined in detail below.

What is the context in which UK support is provided?
Zambia has one the highest maternal mortality rates in the world, with 591 women dying for every 100,000 live births[1]. High maternal death rates are associated with complications of pregnancy and childbirth, unintended pregnancy and unsafe abortion. Zambia has also a high and rising fertility rate at 6.2. Although the contraceptive prevalence rate has increased to 32.7% in 2007, use of modern reliable methods of family planning remains low. An estimated 27% of married women have an unmet need for family planning, 42% of pregnancies are unintended and unsafe abortion accounts for 30% of maternal deaths[2]. / Adolescent girls are particularly vulnerable to maternal death yet are poorly served by family planning services. They are less likely to be able to choose whether and when to have a child than older women, and have a much higher unmet need for family planning[3].Pregnancy is the leading cause of death in adolescent girls in developing countries, and girls aged 15-19 are twice as likely to die in pregnancy and childbirth as older women[4]. The 2007 Demographic Health Survey (DHS) showed that only 22% of married women aged 15-19 use a modern method of contraception. In addition, 28.5% of 15-19 year old girls have been pregnant or have had a child, and a higher proportion of adolescent girls in rural areas have begun childbearing (35%) than in urban areas (20%). / Unmet need for family planning and fertility, are highest in rural areas and among poorer, less educated and young women. Women in urban areas have 4.3 children on average, compared with 7.5 children per woman in rural areas[5]. Women who have more than secondary education have an average of 2.4 children, while women with no education have almost four times as many children. The poorest women have 8.4 children on average, compared with 3.4 children per woman in the wealthiest households. If all unwanted births were prevented, women would have an average of 5.2 live births (DHS, 2007). / The Government of the Republic of Zambia has committed to increase the contraceptive prevalence rate for modern methods (women married or in union) from 33% in 2007 to 58% by 2020. The development and implementation of the eight year integrated family planning scale up plan 2013 to 2020 with the support of partners will enable the Government reach this objective. The plan and the national commitments have been triggered by strong leadership from the MCDMCH, the high level family planning event in the UK in July 2012, coordinated joint working in country by all partners and the commitment of the First Lady. / In the scale up plan, strategic priorities identified include: FP demand generation and behaviour change communication, adolescents and youth, staff and training, rural and underserved access to FP services, stock-outs at service delivery points, and FP governance and programme coordination. The cost of the plan is $109 million US dollars which will increase the number of women in Zambia using modern contraception from approximately 1 million to over 1.8 million between 2013 and 2020.
[1] DHS 2007.
[2] MOH (2009). Standards and guidelines for reducing unsafe abortion morbidity and mortality in Zambia.
[3] UNFPA, 2010. How universal is access to reproductive health? A review of evidence
[4] WHO (2001). The Second Decade: Improving Adolescent Health and Development. Department of Child Adolescent Health and Development, Family and Community Health. Geneva.
[5] Zambia Demographic and Health Survey 2007, Ministry of Health Annex 1 Commodity Procurement Status as of 30th November, 2013 (reported by UNFPA) Contraceptive Commodity	Quantities Requested for	Estimated Total Cost (USD)	Estimated Date of Receipt	Comment Depo Provera	300,000	277, 000.00	November 2013	Shipment Received at MSL. Depo Provera	500,000	465, 000.00	March 2014	Purchase Order Dispatched to Supplier Noristerate	500,000	730,000.02	March 2014	Purchase Dispatched to Supplier Jadelle	72,000	657,000.00	March 2014	Purchase Order Dispatched to Supplier Total		2,129,000.00

## Section A: Detailed Output Scoring
Output 1: Expanded availability of choice of family planning methods
Output 1 score and performance description: A+ - output moderately exceeded expectations
Progress against expected results: / Indicators Results expected by Feb 2014 Results achieved as of Dec 2013 Related comments and activities / Output indicator 1.1: Number of additional women and girls using FP methods (short term (pills and Depo-provera) and long term (implants, IUDs and sterilization)) Total New Clients: 50,000 / Total Short term: 29,000 / Rural: 18,000 / 15 -19: 6000 / 20+: 12000; / Urban: 11000 / 15 -19: 2000 / 20+: 9000 / Total Long term: 21,000 / Rural: 12000 / 15 -19: 2,000 / 20+: 10,000 / Urban: 9,000 / 15 -19: 1700 / 20+: 7300 Total New Clients: / 62,278 / Total Short term: / 52,468 / Rural: 41,737 / 15-19: 11,013 / 20+: 30,725 / Urban:10,731 / 15-19: 1,922 / 20+: 8,809 / Total Long term: / 9,810 / Rural: 8,426 / 15-19: 1779 / 20+: 6647 / Urban: 1,384 / 15-19: 226 / 20+: 1,158 The overall target has been exceeded as has the number of rural users. / The programme has underachieved in the number of users of long term family planning. Strategies such as greater integration with the HIV prevention programme, increased mentoring of staff to feel confident promoting long acting methods and increased outreach could be considered to improve these numbers and SUFP has begun considering these. / The programme should consider whether the gender of the nursing staff trained is affecting IUD insertion and, if possible, collect data on this. / Output indicator 1.2: % of public sector facilities covered by the programme that experienced a stock-out of the full comprehensive package of FP methods last 12 months (defined as implants, IUDs, Depo and oral contraceptives) 2% 2% (2 out of 97 clinics) / This figure is from the first 7 phase 1 SUFP districts only as data collection in the 2nd phase 13 on this is not yet established. / Output indicator 1.3: Couple Years of Protection (CYP) generated attributable to the programme (CYP does not include pill users) Total: 80,000 / Total Rural: 50,000 / 15-19: 15,000 / 20+: 35,000 / Total Urban: 30,000 / 15-19: 8,000 / 20+: 22,000 Total: 91,536 / Total Rural: 72,022 / 15-19: 12,976 / 20+: 59,046 / Total Urban: 19,514 / 15-19: 2,853 / 20+: 16,660 Despite lower numbers of long term family planning users than expected, the couple years protection is higher than the target. / Output indicator 1.4: Percentage of national forecasted need in reproductive health commodities (RHCs) met by the programme 4% 17% $2.13m out of a funding gap of $12.3m (according to national quantification for reproductive health commodities) is being covered by the programme. A summary of commodities procured is given in Annex 1. / Key Points: SUFP has achieved a rapid scale up this year to 20 districts, resulting in a significant increase in the number of women reached with family planning with, unexpectedly, large numbers coming from rural areas. In order to collect the disaggregated data for age that DFID requires however, SUFP has had to ask facility staff to collect data on family planning users aside from the HMIS, a situation which is not ideal. SUFP district officers should always be aware of the extra burden this data collection is placing on staff and be prepared to collate data themselves if needed. / UNFPA is procuring reproductive health commodities on behalf of DFID. There have been some delays due to global stock outs as well as competing priorities with the needs of other programmes but the commodity procurement is on track currently. Close monitoring however is still required. / Summary of Responses to Issues raised in annual review 2013 (details in SUFP annual report): / 1. Commodity monitoring: Though the actual procurement of RH commodities is being done by UNFPA, the coordination and reporting on the contribution of the programme to the national pool and medical stores limited remains the responsibility of SUFP through their subcontracted partner RTT. RTT maintain a close relationship with district pharmacists through weekly phone calls to troubleshoot issues around reproductive health commodity stock and reviewing the health centre orders on a monthly basis. They are able to track potential stock outs and institute mitigating actions for example the redistribution of district stock or discussions with MSL. / 48 health care workers from 4 districts were trained in logistics and commodity management for Essential Medicines; this is only 4 out of the 13 districts with the rest planned for year 3. All health centre heads are trained in supply chain and commodity systems management and they in turn strengthen the capacity of community based distributors. Where they exist, community health assistants have been trained as ‘depot holders’ for contraceptive commodities by SUFP and are able to provide injectable contraceptives at community level. The RTT staff member positioned within SUFP receives technical assistance from his head office but is not aware of what support is available to him or of the SUFP budget envelope with RTT. / 2. Sustainability: In order to promote sustainability, SUFP has taken part in planning activities in district level, advocating for the integration of family planning, including costs, into plans. The sustainability of reproductive health commodity procurement should also be a focus. The government has doubled its own budget to these commodities in 2014 but this still remains inadequate to cover the entire gap. / 3. Integration of nutrition: In response to a nutrition audit carried out in DFID, nutrition modules have been developed that focus on improving post-partum nutrition and infant and young child feeding. The first 30 family planning trainers will be trained in these modules in March 2014 with expected district roll out to be undertaken in May 2014 / 4. Integration of HIV: This programme is planned to run side by side with DFID’s HIV Prevention programme focused on voluntary couples counselling and testing (CVCT) and the insertion of long acting family planning methods, run by ZEHRP. ZEHRP is providing CVCT training to health care providers from the SUFP districts to increase the long acting family planning method uptake. 110 health care providers have so far been trained but uptake of CVCT is still low in many districts. The integration of the two programmes should be further strengthened by, for example, using CBDs to mobilise communities for CVCT and using district outreach coordinators (DOCs), hired by SUFP to assist with data collection and follow up. / Future actions and recommendations: / Focus on increasing the numbers of long acting family planning users. Further integration with ZEHRP and better quality mentoring may be good strategies. A simple analysis of whether the gender of the providers trained is affecting IUD insertion should be considered or, at least, data on the gender disaggregation of those trained collected. / Explore the options of disaggregating for age within the existing HMIS system. / Ensure that the seconded RTT staff member is given information on the support and budget available to him through SUFP in order to maximise his effectiveness. / Further integrate the HIV Prevention programme to optimise the value for money of both programmes and use existing staff in rural areas. Produce a roadmap for this integration and share with DFID. / Carry out close monitoring of UNFPA to ensure commodity procurements are on track. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 2: Increased access to family planning services for under-served areas and populations
Output 2 score and performance description: A+ - output moderately exceeded expectations / Indicators Results expected by Feb 2014 Results achieved by Dec 2013 Comments / Percentage of target communities covered by outreach services (comprising both community mobilisation and service provision) by the programme in target districts Total: 20%: / Rural: 32%, / Urban: 8% Total: 32% / Rural: 40% / Urban: 24% From February 2013 to December 2013, 379 outreach activities took place, reaching 758 communities/health facilities zones.
Key Points: Outreach services refer to reproductive health and family planning services that are held within target communities, beyond what is usually expected or offered at health facilities. This is conducted by district health staff and CBDs and some have been integrated into other district programs such as child health week and World AIDS Day. / A comprehensive outreach will comprise community mobilization, BCC messaging, and service provision. In districts where SUFP has finished camping, drama groups and traditional leaders where possible, should be part of the outreach. Outreach activities can be conducted anywhere e.g. fishing camps, health posts, markets, etc. The role of the community based distributors, comprehensive sensitisation of the community and male involvement have been found to be success factors in outreach. / Kabompo Outreach in December 2013 / Although a highly successful strategy that utilizes government health care providers, the sustainability of outreach activities after the SUFP programme is over is not clear. The programme should increase the number of routine health centre outreach, integrated with other primary healthcare services that can be sustained after the programme period. / Summary of Responses to Issues raised in annual review 2013 (details in SUFP annual report): / Share lessons of camping approach: This has been presented at two international conferences and a program brief for the MCDMCH is in process. The Ministry is considering using the camping approach for the roll out of future programs. / Behaviour change strategy finalisation: This was completed and TV/radio spots; translation of messages into local languages; training of drama groups as well as 143 adolescent peer educators have taken place. / Validated orientation and training packages: This is still in process, being led by the national family planning technical working group. The American College of Nurse Midwives (ACNM) is a subcontracted partner of SUFP that could provide valuable input into training packages but appear to be underutilised at present. / Approach to adolescents: SUFP, PPAZ (subcontracted partner tasked with working on improving adolescent reach) and UNFPA have been working on a comprehensive evidence-based strategy to appropriately target adolescents in SUFP districts that is nearing completion and will be in line with the new National Adolescent SRH Communication Strategy (not yet distributed). The strategy will include the use of adolescent peer educators, champions and leaders but has taken some time to complete. / SUFP have continued to work in schools to sensitise adolescents and have been welcomed in all but one school. The program continues to segregate different age groups when conducting sensitizations and in some cases girls/boys were separated. / Formative research on adolescents: SUFP may undertake a small study on gatekeepers which will aim at finding out more about the challenges and opportunities that exist among parents, teachers, community leaders and other influencer audiences with regard to adolescents and family planning. In addition, SUFP will pre-test messages and communication channels with adolescents and gatekeepers. Deeply embedded cultural and religious beliefs as well as inadequate engagement of district level government staff in this issue are current barriers. / Future actions and recommendations: / Promote regular outreach, integrated with other services where possible with a view to sustainability after the project period. / Utilise the strengths of ACNM more to improve the quality of training. / Urgently complete the adolescent strategy and begin full implementation (although many adolescents are being reached now). Liaise with other relevant organisations to ensure a coherent approach especially the Population Council that is being funded by DFID for the Adolescent Girls Empowerment programme. / Carry out formative research to remove barriers to reaching adolescents. / Impact Weighting (%): 30% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: Increased community support for family planning
Output 3 score and performance description: A+ - output moderately exceeded expectations / Indicators Results expected by Feb 2014 Results achieved by Dec 2013 Comments / Number of Safe Motherhood Action Group members (SMAGs) trained as CBDs Total = 175 / Urban=50 / Rural=125 Total = 195 / Urban = 60 / Rural = 135 / Number of community leaders trained as CBDs Total = 105 / Urban = 30 / Rural = 75 Total = 445 / Urban = 105 / Rural = 340 / Percentage of community leaders sampled who report favourable attitudes towards family planning Baseline 59% No reporting required this year.
Key Points: Community based distributors are the backbone of this programme in terms of community mobilisation, promoting outreach as well as supplying condoms and oral contraceptives. The CBDs are, however, a volunteer cadre so their ability to sustain their work after the project period needs to be considered. Tight links with district structures such as community development assistants, community health assistants and district offices will help. In addition, PPAZ has been encouraging all SUFP districts to apply to open local PPAZ branches. Whilst these branches do not receive funding, they do receive inputs from PPAZ head office and the International Planned Parenthood Foundation globally which can contribute to the motivation of volunteers. / SUFP has found that chiefs are very supportive of the programme and have promoted acceptance by the community. / Summary of Responses to Issues raised in annual review 2013 (details in SUFP annual report): / Male versus female CBDs: 640 CBDs have been trained this year. 427 are female and 213 are male. / Training of district based facilitators: Trainings for both health care providers and CBDs involve active participation of district health officials under the direct supervision of the District MCH Coordinators. / Local media training: This will take place in March 2014. / Future actions and recommendations: / Promote even tighter links between CBDs and existing district structures. / Promote the opening of PPAZ local branches at district level to sustain volunteer motivation. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? Yes – previously High

Output 4: Increased public sector capacity to provide comprehensive family planning services
Output 4 score and performance description: A - output met expectations.
Indicators Results expected by Feb 2014 Results achieved by Dec 2013 Comments / Number of public sector health facilities in programme districts with the capacity to provide Long Term Reversible Methods Total =60 / Urban=15 / Rural=45 Total = 146 / Urban= 66 / Rural= 80 This will need ongoing monitoring due to the lower use of long term methods in facilities. Further follow up and mentoring is likely to be needed. / Number of public sector health facilities in programme districts providing Adolescent Friendly Health Services Total =60 / Urban=15 / Rural=45 Total = 43 / Urban= 12 / Rural= 31 This year, the programme has defined Adolescent Friendly Health Services (AFHS) as health care services that are accessible and acceptable to adolescents. AFHS should attract adolescents, meet the varying needs of adolescents comfortably and responsively, and succeed in retaining these adolescent clients for continuing care. Providers should be specially trained to comprehend and implement according to established standards. / Percentage of health workers in facilities covered by the programme trained in Long Term Reversible Methods and Adolescent Friendly Health Services Total = 57%; / Urban = 22.8%; / Rural = 91.2% Total = 44% / Urban= 20% / Rural= 84% This indicator requires two trainings to be completed in one individual so has proved slightly harder to meet. / Key Points: The programme has succeeded in having a clearer definition of adolescent friendly health services although further detail is needed. As mentioned above, a comprehensive strategy for reaching adolescents and creating AFHS’s is not clear. / Summary of Responses to Issues raised in annual review 2013 (details in SUFP annual report): / Procurement of equipment to create centres of excellence: ‘Centres of excellence’ have been established in 10 of the 20 districts. These will act as training centres conducting long term training and refresher training. / Mentorship activities: Mentorship activities are currently taking place in all the districts. The mentorship program is on two fronts, the health providers mentoring fellow health providers and CBDs working with other CBDs. The program also has a centre to centre mentorship programme, where one centre works with another centre. / Supportive supervision: At least 50% of the districts will have had supportive supervision by the end of February. This should be conducted by the district staff but can be facilitated by SUFP. / Training materials: More training materials have been procured. / Future actions and recommendations: / Ensure the development of AFHS is properly defined and part of a comprehensive strategy to reach adolescents. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

Has the logframe been updated since last review? No but the following updates are being suggested now: / - Impact indicator 1: Maternal mortality ratio milestone for 2014 should change to 512 to bring this in line with the departmental results framework. / - Outcome indicator 1: % Contraceptive prevalence rate (CPR). When the SUFP baseline figures became available in 2013, the baseline figure of 20.4% was examined more closely and its source was not clear. The DHS 2007 figure for contraceptive prevalence rate of modern methods for rural currently married women is 27.6% and this should be used for this outcome. This figure can be changed when the new DHS figures come out in 2014/15. / - Outcome indicator 1: % Contraceptive prevalence rate (CPR). The SUFP baseline study was carried out in 8 randomly selected districts of the total 26. The question of current use was asked to 1619 women aged between 15 and 49 years, most of whom are married or sexually active. This showed a contraceptive prevalence rate of modern methods of 48.5%. The DHS 2007 figure of CPR for this group of married or sexually active women is 38.1% (average of 32.7% married women and 43.5 sexually active unmarried). It is likely that the national CPR has risen since 2007 and less likely that the situation is better in programme districts than nationally given the rural nature of most of the districts and the rigour with which they were chosen. / We therefore propose that the log frame monitors both the national contraception rate (source DHS) for rural currently married women as well as the rate in the sample of 8 programme districts. Therefore there will be two baselines (27.6% (2007) for national average) and 48.5% (2013) for the sample of 8 programme districts. Targets and milestones for both estimates have been suggested in the log frame. / Overall Output Score and Description: / Overall Output score A+ - moderately exceeded expectations / 1.3 Direct feedback from beneficiaries / Two field trips were conducted as part of this review to Kaputa in Northern Province and to Siavonga in Southern Province. Both found that the programme has been universally well received by beneficiaries who felt family planning is needed to allow them to space their families. One woman in Siavonga, for example, explained how the Jadelle implant has enabled her to space her family after her third child so that she can now attend teacher training college and increase her family’s income. / Chiefs and headmen were particularly supportive and felt the messages around ‘spacing’ of children as opposed to stopping having children are working well. All raised the issue of teenage pregnancies and recommended more work in schools and with young people. / During a village meeting for outreach and after a drama group performance, the discussion was being led by the men in the community, weighing up the pros and cons of family planning as well as discussing whether a male nurse should be allowed to give contraception to their wives. Generally, the discussions were lively but not hostile and people were genuinely interested. / Unfortunately no adolescents were interviewed during the annual review and even the village meeting was dominated by older, married people. Group outreach, such as this, may not be reaching this vulnerable group due to social stigma although the programme has already reached over 11,000 young people. DFID staff should attempt to meet and discuss with adolescents specifically in future visits. / Health care workers and CBDs were content with the training received although some partners suggested that the training on IUDs could be strengthened. Some CBDs also requested more incentives for the work they are doing.
1.4Summary of overall progress / The programme has made very good progress this year and has overachieved on 3 out of 4 outputs. The decision was made to scale up the number of districts fast and use the last two years of the programme to consolidate the work and this is likely to be possible. Specific successes are outlined above.
1.5Key challenges / Specific challenges and recommendations are outlined above but the main areas include the need for a more coherent approach to adolescents (including formative research), increasing the use of long acting family planning methods, more accountability and maximised use of subcontracted partners, further integration with the HIV prevention programme and attention to sustainability. UNFPA has experienced challenges with their head office in prioritising the DFID Zambia funds to be spent on commodities and this needs close follow up by DFID and UNFPA country office to their head office.
1.6Annual Outcome Assessment / The outcomes will be measured at the time of the next DHS (likely end of 2014) and at the end of the project. It does, however, seem on track to achieve its outcomes.

2. Costs and timescale -
2.1 Is the project on-track against financial forecasts: / For the component of the programme implemented through Abt Associates: / Expenditures January to December 31st = £3,680,002 / Disbursement by DFID January to December 31st 2013 = £3,730,518 / Expenditures April to December 31st (FY 2013-2014) = £2,682,987 / Cumulative forecasts April to December 31st (FY 2013-2014) = £2,533,439 / The project is relatively on-track against FY 2013-2014 financial forecasts with a positive variance of 5.9% between forecasts and actual expenditures. / Expenditure by output (January through December 2013): / Output 1 - Expanded availability of choice of family planning methods 692,384 / Output 2 - Increased access to family planning services for underserved areas and populations 1,211,246 / Output 3 - Increased community support for family planning 1,116,754 / Output 4 - Increased public sector capacity to provide quality / comprehensive family planning services 581,246 / Milestone Awards 78,372 / TOTAL 3,680,002 / For the component of the programme implemented by UNFPA (Commodity procurement): / Total expenditure on commodities 550,715 / Total committed for commodities (purchase order stage) 830,038 / Total disbursed by DFID to UNFPA (last disbursement January 2014) 2,158,551 / Balance to be spent 777,798 / 2.2 Key cost drivers / Labour – the programme requires a large number of staff in the field and technical assistance from head office and this was expected. / Training and workshop expenditures – as the focus of the programme is improving skills and raising awareness, training costs are the majority of field expenses. This will decrease however as the programme is launched in all 26 districts and it is likely that travel (mentorship) costs will increase. / Travel – the programme works in extremely rural areas so high travel costs for monitoring are expected. / Commodities (for UNFPA) / Graph showing the breakdown of cost drivers for Abt Associates / 2.3 Is the project on-track against original timescale: / The project is on-track on most of the planned activities under each of the four project outputs. The only areas that are slightly behind are the commodity management trainings and finalisation of the approach to adolescents.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The national FP 8 year scale up plan has been released by the government but the contents are complementary to what is being implemented by SUFP already. / The SUFP 8 district baseline showed a higher than expected CPR (see results section) and 59% of rural women had started having sex aged between 10 and 14 years. The availability of methods was reasonably good except for IUDs which were only available in 10% of programme districts. The qualitative results for adolescents were particularly important with high rates of transactional sex (for lotion or creams); a reluctance to use condoms; a feeling that an abortion is preferable to using family planning; and a fear of the reactions of parents, traditional and religious leaders around family planning. / The misconceptions amongst adolescent boys were of particular note and the programme should have specific strategies to involve this group. The baseline findings should inform the adolescent strategy and behaviour and communication strategy of the programme. / 3.2 Where an evaluation is planned what progress has been made? / Not planned

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / Three out of four outputs are rated as Medium risk. Output 1 has remained as high risk due to the delays in commodity procurement as well as the risks of not reaching the ambitious 2015 targets. Output 3 has been changed from high to medium risk as the community acceptance of the programme has been high.
Risk of funds not being used as intended / Abt Associates have strict financial reporting and procedures and follow up (confirmed by recent internal audit) and there is a very small risk of funds not being used as intended. The programme has encountered three instances of fraud which were responsively and appropriately dealt with by the programme and have been reported to the Counter Fraud Unit. There has been no loss of money to DFID. / The DFID Internal audit did highlight the lack of information on Abt’s relationship with its subcontracted partners. This review has confirmed these weaknesses, mainly with ACNM, with a lack of clarity on where ACNM’s input fits with the broader programme and some questions on value for money (see later recommendations). A spot check that took place on 13th February 2014 of the systems in the office did however show strong systems in place (final report awaited). / Internal Audit highlighted the need for more robust monitoring of UNFPA over their lack of delivery in the programme and the risks of non-delivery and poor performance. As mentioned above, there have been delays in UNFPA procurements. The programme team has quarterly progress meetings but closer monitoring of UNFPA with bi-weekly phone calls has now been decided to follow up on progress. / UNFPA has its own financial procedures common to all offices. In addition, in the recent Multilateral Aid Review update showed that the organisation has made some progress in all areas measured. DFID is due to carry out a due diligence exercise on the local office however in February. / The Internal Audit also highlighted the lack of a formalised agreement between Abt Associates and both the Ministries of Health and Community Development and Mother and Child Health with whom they are working. However, an agreement has since been drafted and approved and awaiting signature. / Climate and Environment Risk / This risk has not changed since the last annual review. The project uses one extra vehicle now (old DFID vehicle donated) and the major environmental risks concern the travel conducted by district, Lusaka based and international staff.

5. Value for Money
5.1 Performance on VfM measures / In 2013, SUFP developed a VfM framework which combines quantitative and qualitative data to generate indicators and evidence on a quarterly or annual basis. The framework includes a set of eight VfM measures. Performance against indicators is benchmarked against comparators, an internal target or trend. The framework also includes collection and documentation of case study examples of good VfM. Progress against indicators and summaries of evidence is shown below with a comparison from the 2013 annual review. / Performance against SUFP VfM framework / VFM Stage Indicator Performance in Year 1 (to Dec 2012 or Jan 2013) Performance in Year 2 (Feb 2013 to Dec 2013 or Jan 2014) Benchmark/Trend and analysis / Economy Average International TA rates / Average National TA rates / Ratio of national to international TA days £686 / £400 / Nat 69% - Int 31% (days) £695 / £345 / Nat 87% - Int 13% (days) Average National TA rates have reduced since Year 1 but average International TA rates have increased slightly. / These are weighted average rates based on daily rates agreed in the contract and the number of days worked. Rates are benchmarked and compare favourably against competitors working in the international health field. Changes in the average rates since last year will therefore be largely due to the mix of consultants. / The level of National TA days has already exceeded the internal target which set to increase them over the term of the project to 75% at a mid-point rising to 80% by the end of the programme. / VFM Stage Indicator Performance in Year 1 and Year 2 Benchmark/Trend and analysis / Efficiency Administration and Management % of total expenditure / Unit cost per training participant / Unit cost of providing services to each additional user of family planning Year 1* Year 2 / Outputs 42% 65% / M&E 19% 6% / Admin & Mgmt 39% 29% / *Since implementation / Based on partial data collection for year 2, the average cost of training per participant per day is: / health worker £75 / community based distribution £79 / Year 1 Year 2 / Total expenditure on Output activities (not cumulative) £673,707 £1,936,143 / Additional users of FP / (not cumulative) 12,944 49,334 / Unit cost £44 £39 Administration and management costs in year 1 were high compared to external benchmarks. This was due to set up costs during inception. However, in Year 2 Admin and Management costs have reduced. This is in line with expected reduction to 30% then to 25% during the life of the project. / M&E costs have decreased since year 1 implementation in line with expected reduction to between 5% and 10%, in line with external benchmarks. / Unit costs are in line with external benchmarks for comparable training courses. (range = £30 - £106). To reduce the unit costs further, other projects have increased the use of government staff as trainers and facilitators in later years. This also builds in sustainability. / Unit cost has been calculated based on Year 2 expenditure and results data. Costs used do not include administration and management (29%). This is below the unit cost expected in Year 2, £45 based on the trajectory, and is on track to meet Year 3 target. There is an expected downward trend of unit cost to provide services to each additional user of family planning as shown below. / Year 1 Year 2 Year 3 Year 4 / £191 £45 £15 £6 / Measures used to increase economy / Use of qualified government officers and government vehicles for supply chain trainings, commodity security assessments instead of consultants and hired cars. / £22,400 was saved by using provincial health office trucks to distribute medical equipment to 16 districts bought by the programme. / £86,000 has been saved in office rental space and utilities by placing the district outreach coordinators within the district community health offices. / A vendors database has been created that allows quick quotes from existing vendors and negotiation based on competitive prices. This includes a contract negotiated with a vehicle hiring company. All purchase requisitions are reviewed by the operations team. / The work planning process supports efficiency by detailed budgeting and then ensuring activities have a clear scope of work and do not exceed the workplan budgets. The programme has also prioritised and cancelled activities that are not target drivers, except when deemed strategic e.g. integration to national planning activities. / Measures used to increase efficiency / The Camping approach has been modified to create efficiencies in year 2 by using only one technical officer to coordinate activities and travel to the district as opposed to the whole team. This has cut costs hugely and has allowed scale up to many districts within a shorter space of time. / Integration of family planning activities with World Aids day (WAD), Child Health Week and national TB day. / The project worked closely with JSI to share the costs of training health care workers from Kaputa, Kasama, Luwingu and Mpulungu districts in Essential Medicines Logistics Improved Program (EMLIP). / VFM Stage Indicator Performance in Year 1 and Year 2 Benchmark/Trend and analysis / Effectiveness Cost per Couple Year Protection / Value of government contributions to SUFP activities Cost per CYP in Year 2 was estimated to be £32 / £629,000 worth of government contributions were made at district level between February and November 2013. Although the unit cost is slightly higher than the Business Case benchmark, it is lower than internal trend projections, with a Year 2 target of £50. This is due to higher than planned number of additional users reached and lower costs in Year 2. / Expected downward trend of unit cost per CYP / Year 1 Year 2 Year 3 Year 4 Whole project / Plan £217 £50 £14 £6 £18 / Actual £298 £32 / This equates to 32.5% of the SUFP budget. Other DFID projects target 10% -50% in terms of government contributions to project activities. It demonstrates both the commitment of government to these activities and indicates sustainability. / Cost effectiveness Cost per DALY Cost per DALY calculated since inception is £206. The forecast cost per DALY at the end of the programme is £73. The project is on track to be cost effective. The Cost per DALY calculated in the business case is £116 which is significantly below the GDP per capita in Zambia (£763 at time of writing business case). This indicator acknowledges that benefits being brought by this project will last beyond 2015. / Measures used to increase effectiveness / The involvement of influential district and community leaders has enhanced community support and dealt with certain myths and misconceptions. / Community members, trained as CBDs, have spearheaded the acceptance of family planning in the community. / Community outreach has helped to combine community mobilisation with service provision and has increased the chances of the most vulnerable accessing services. / Only trainings that are thought to improve programme outputs at a reasonable cost are considered for funding. / Strong links with the government at district level have improved programme effectiveness. / 5.2 Commercial Improvement and Value for Money / DFID Procurement awarded the contract through a competitive bidding process. This is based on fee rates, which were benchmarked to competitive rates, and a low cost approach which utilises government resources such as health workers, government officers and works through existing health systems. As well as keeping costs low, this approach makes optimal use of government resources which have already been purchased and strengthens government role in direct provision of family planning services which will be sustained beyond the lifetime of the project. This is especially the case for commodities that are procured but rely on the government system for distribution. / The procurement procedures of the project routinely support value for money through competitive bidding and negotiation. In Year 2, SUFP instituted a purchasing system with a vendors database that allows quick contact with a pool of existing vendors when goods and services are needed and negotiate prices down based on competitive prices. / 5.3 Role of project partners / The programme works closely with both MOH and MCDMCH as well as other organisations within the national technical working group and JSI in terms of commodity management. / ZERHP and SUFP have signed a memorandum of understanding to outline roles and responsibilities in integrating the HIV prevention with family planning. After a slow start, collaboration has improved but could be strengthened. / There are three subcontracted partner working with the programme. All three were contacted during the review. A summary of their involvement in the programme and costs is given below. Partners are generally paid on deliverables. / RTT (2013 costs - £238,719): RTT has a supply chain specialist seconded into the SUFP office, thus avoiding the need for international TA for this support. The specialist has a clear, agreed workplan that fits well with the broader programme and has been performing his role well. He does get support from his head office but is not aware of what support is available and what the agreed budget is between his head office and Abt Associates. / American College of Nurse Midwives (2013 costs - £204,095): ACNM has carried out some training of health care providers and CBDs in mentorship and contribute to Output 3. The ACNM staff contacted however, had an extremely limited idea of the programme as a whole and were not able to explain the broader implications of their contribution to the programme or indeed, the details of what had been done. ACNM has skills in training and these appear to have been underutilized and there is a clear lack of communication. ACNM expressed a wish to be part of the annual work planning of the programme. ACNM is a partner to another Abt Associates programme in Zambia called ZISSP and it may be that there is confusion because of their dual role in Zambia. Work is needed to maximize the use of ACNM and ensure value for money. / Planned Parenthood Association of Zambia (2013 costs - £66,909): PPAZ is a long standing local NGO that is leading the work with adolescents for SUFP, including the training of peer educators. The organization works closely with SUFP and presents some solutions to questions of sustainability due to their district offices and affiliation to IPPF. PPAZ has also led the development of the adolescent strategy but this has taken well over a year to complete. The costs of PPAZ’s services are low and appear to present the best value for money of all the partners at present. / 5.4 Does the project still represent Value for Money : / Yes, the project is on track with economy, efficiency and effectiveness measures and results and has shown a huge improvement since year 1. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
The SUFP programme has made commendable progress this year with a huge increase in the number of additional women reached and overachievement on almost all indicators. Real thought have been given to the value for money issues of the last review and these have been comprehensively addressed. As a result, the economy, efficiency and effectiveness of the programme are all increasing very significantly. The programme has refined its camping approach, community mobilisation and inputs to supply chain management and these are working well. The next year, the programme should focus on consolidation of these gains, mentorship of health workers, reaching the most vulnerable and putting in place measures to ensure sustainability. / Key suggested actions are outlined in the outputs section above but are summarised below: / Focus on increasing the use of long acting family planning methods. This may include continued mentorship and skill development of health workers. Responsibility Abt Associates – ongoing. / Comprehensive roll out of the adolescent strategy ensuring adequate focus on educating boys as well as girls and drawing on lessons from other DFID supported programmes such as with the Population Council. Responsibility Abt Associates – by March 31st 2014. / Conduct the formative research on barriers to access to care by adolescents. Responsibility Abt Associates – by 31st July 2014. / Strengthening the integration with the HIV programme through joint community mobilisation and data collection. Responsibility Abt Associates and ZEHRP – ongoing. / Strengthening the relationship with all sub contracted partners. Ensuring regular communication, regular reporting, joint work planning, clear budgeting, clear accountability and maximising the varied strengths. If possible, including some value for money metrics within the partner work. Responsibility Abt Associates – ongoing. / Strengthening the communication and follow up with UNFPA and between the UNFPA country office and their head office to ensure commodity expenditure is on time. Responsibility DFID and UNFPA – ongoing. / Putting in measures to ensure sustainability. These could include promoting districts to set up as local PPAZ branches, further strengthening family planning in district planning, ensuring outreach is health centre led and integrated with other services, lobbying for more government allocation to commodities etc. Responsibility Abt Associates and UNFPA – ongoing.

8. Review Process
This review was conducted between December 15th and February 18th 2014 by the DFID health adviser and programme officer. Two field trips were undertaken to Kaputa and Siavonga districts by two teams comprising DFID staff (including the head of office in Siavonga), the MCDMCH family planning officer, staff from PPAZ and ZEHRP. Discussions were had with district staff, male and female beneficiaries, chiefs, headmen, health care workers, community health assistants and community based distributors. ACNM was contacted through a phone call. Preliminary findings were discussed with both SUFP and ZEHRP.