Type of Review: Annual Review

Project Title: Financial Sector Deepening Zambia (FSDZ)[1]
[1] Programme was previously called Access to Finance Programme

Date started:	May 2013
Date review undertaken: January-February 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is providing up to £13.1m over a five year period to support increases in financial inclusion in Zambia. The programme targets increased access to a wide range of financial services from savings, through to loans, payment mechanisms, insurance and pension services. / The programme takes a making markets work for the poor approach and will tackle a broad array of sector constraints at the policy level, through to interventions direct with financial service providers. This will include commercial banks, microfinance institutions and community based finance initiatives. / The programme is managed by a supplier, DAI, and is in the early stages of implementation after having completed a 4 month inception phase from May to September 2013.

What are the expected results?
The impact of the programme is to make sustainable improvements in the livelihoods of poor people by supporting 138,750 people with increased incomes or a reduction in vulnerability. / The outcome of the programme is a financial sector capable of delivering a wide range of financial services to more people and businesses in Zambia. It will provide: / 300,000 additional people with access to finance (of which 65% will be women) / 50,000 smallholder farmers with access to agricultural finance (of which 50% will be women) / 12,000 additional SMEs with finance from banks and MFIs. / At impact and outcome level these figures are directly attributable to DFID funding.

What is the context in which UK support is provided?
Zambia has experienced significant growth in the last decade but with little change in poverty especially in rural areas. Poverty levels now stand at around 60% nationally and 78% in rural areas and have been relatively static for a number of years. Economic growth is narrowly focused around a booming mining, services and construction sector. However most Zambians rely on agriculture as their primary source of income and have livelihoods that are poorly linked to the growth sectors of the economy. / The poor need access to efficient and functioning markets that matter for their livelihoods and consumption needs. Financial service markets are a key part of this. Evidence points to the development of this sector being an important driver of the rural economy and a means to smooth out income streams and encourage investment in productive capacity. / Financial exclusion in Zambia is high. 67% of the rural population have no access to any financial services, whether formal or informal. 60% of the adult population don’t save at all and are living day to day without any formal accumulation of wealth or means to reduce risks to their livelihoods. / The Government of Zambia has shown strong commitment to expanding financial inclusion and has a Financial Sector Development Plan II (2010 to 2014) that specifically targets the broad based development of the financial sector. Improvements in financial inclusion, have, however, been relatively slow to date with only minimal increases being noted between the last two FinScope surveys conducted in 2006 and 2009. Although some issues have been identified at the policy level, many of the constraints to financial sector development arise from significant market failure and the focus and strategies of individual banks and other non-bank financial institutions (NBFIs). Most do not provide accessible financial services to the rural population in any significant way. Thus without catalytic actions most Zambians will continue to be financially excluded.

## Section A: Detailed Output Scoring

Output 1: More and better industry data and public information on the financial sector is available and used by stakeholders
Output 1 score and performance description: C Outputs substantially did not meet expectation / Indicators Results expected by March 2014 Results achieved by January 2014 Related comments / Output indicator 1.1 Number of financial sector stakeholders using new and industry data and public information products 0 0 No results expected at this early stage of the programme implementation / Output indicator 1.2 Number of target beneficiaries receiving financial education 7500 2042 Milestone not met. Other financial education activities were due to be captured through a larger grant to support community based saving and loan groups. The issuing of this grant was delayed until later in Q4 2013/14 (Jan-Mar).
Progress against expected results: / Progress against output indicator 1.2 did not meet expectations. A number of financial education activities were due to be achieved through a larger grant to support community based savings and loan groups. The due diligence process and negotiations took longer than anticipated and resulted in the whole grant being restructured. Value for money concerns were one of the key drivers for this change and the programme rightly took the decision to delay issuing the grant. / However, the programme did provide some support in this area. In this reporting period FSDZ provided support to Careers Expo Zambia, a youth careers development organisation in Zambia, to promote Financial Education training for Youths targeting secondary school pupils and tertiary students. / FSDZ provided a matching grant and technical support to the Insurers Association of Zambia (IAZ) and the Insurance sector Technical Advisory Group (TAG) to complete financial education activities during Zambia Insurance Week 2013. The Insurance Week included the launch of a microinsurance promotional strategy and a Microinsurance marketplace that showcased existing microinsurance products and demonstrated distribution opportunities to aggregators. Educational videos were also produced on microinsurance for low income populations and aired on 2 national television stations. Recordings were also aired on community radio stations. Informal feedback of the impact of these products was positive, although it is too early to assess the effectiveness of broad based consumer education investments such as these. All recordings have been made available to insurance companies for usage in their consumer education efforts. / Despite the target for this year not being met, the programme has an ambitious strategy for financial education and has set in place the foundations for rolling this out over the coming year. This includes support to the national Financial Education Coordinating Unit (FECU) to coordinate and roll out the national strategy for financial education. This will include (but not be limited to) on-going support to integrate financial education into the national curriculum, piloting and roll out of workplace financial education programmes (including for SMEs) and the design of initiatives aimed at smallholder farmers and members of community based providers. / Recommendations: / Programme to continue momentum to set in place financial education initiatives that will enable 14/15 target to be met. / Impact Weighting (20%) / Revised since last Annual Review? Y/N The weighting for this output was temporarily increased to 20% for this annual review as a number of other outputs had no milestone, are yet to be scored and have been given a 0% rating. It will revert back to 10% at the next annual review. / Risk: Low / Revised since last Annual Review? Y/N N/A

Output 2: Improved policy and regulatory environment for the delivery of financial services
Output 2 score and performance description: No results expected at this early stage / Indicators Results expected by March 2014 Results achieved by January 2014 Related comments / Output indicator 2.1 Number of organisations demonstrating improved effectiveness in advocating for financial sector reform 0 0 No results expected at this early stage of the programme implementation / Output indicator 2.2 / % change in capacity of policy making bodies to formulate and implement effective financial sector policies and regulation 0% 0% No results expected at this early stage of the programme implementation
Progress against expected results: / Given the early stage of programme implementation no specific milestones were planned for this period. The programme has begun a process of developing relationships with key policy making bodies which will set the foundations for greater collaboration next year. This includes both the Bank of Zambia and the Insurance Association of Zambia. The Bank of Zambia in particular is the key policy partner for the programme and FSDZ is in the process of defining an MoU with the BoZ which will clearly define areas for future collaboration. During discussions the BoZ expressed a desire to accelerate the partnership with the programme. / Recommendations: / Given the importance of the Bank of Zambia in the financial inclusion agenda, the programme should ensure additional effort is placed on solidifying this relationship and early concrete action taken on supporting the BoZ on key policy interventions. / Impact Weighting (0%): / Revised since last Annual Review? Y/N N/A This output has been temporarily been set at 0% for this annual review given no milestone was due to be achieved. It will revert back to 10% at the next annual review. / Risk: Medium / Revised since last Annual Review? Y/N N/A

Output 3: Adequate infrastructure and support services in place to support financial sector development
Output 3 score and performance description: No results expected at this early stage / Indicators Results expected by March 2014 Results achieved by January 2014 Related comments / Output indicator 3.1 Number of financial service providers benefitting from new or improved support services 0 0 No results expected at this early stage of the programme implementation / Output indicator 3.2 Number of categories of financial infrastructure recording improved service delivery to financial service providers 0 0 No results expected at this early stage of the programme implementation
Progress against expected results: / Given the early stage of programme implementation no specific milestones were planned for this period / Recommendations: / N/A / Impact Weighting (0%): / Revised since last Annual Review? Y/N N/A This output has been temporarily set at 0% for this annual review given no milestone was due to be achieved. It will revert back to 10% at the next annual review. / Risk: Medium / Revised since last Annual Review? Y/N N/A

Output 4: Increased capacity of financial service providers to deliver products that are accessible, affordable and appropriate to poor men and women
Output 4 score and performance description: A – output met expectations / Indicators Results expected by March 2014 Results achieved by January 2014 Related comments / Output indicator 4.1 Number of financial service providers with increased capacity to reach poor men and women with financial services 0 1 Indicator exceeded by early support to MicroEnsure to support life insurance for smallholder farmers resulting in 24,274 farmers with access to a life insurance product / Output indicator 4.2 Number of sustainable community based financial institutions providing financial services to poor men and women 375 0 This target was due to be met through a grant to support community based savings and loan associations which was subsequently delayed.
Progress against expected results: / The programme exceeded expectations for indicator 4.1. The programme has developed an early partnership with MicroEnsure a financial service provider working in the micro insurance sector. Support was provided to develop and pilot a new life insurance product for smallholder farmers working with NWK (a private sector agricultural input supplier and produce buyer). Support has been provided to enable 24,274 smallholder farmers to better understand and see value in a new Farmer Shield life insurance product. 9,710 of these are women. NWK pays for the life insurance and uses it as a means to increase loyalty to the company in a very competitive market. / Progress against indicator 4.2 did not meet expectations. The programme has rightly identified savings groups as a key mechanism to increase financial inclusion quickly to poor people in rural areas. The first large grant the programme was due to give to support savings group development did not take place as planned in Q4 2013. This was primarily because the due diligence and programmatic and financial negotiations for the grant took longer than anticipated. Although the grant will be given Q1 2014, results will now not appear until Q1 2014/15 (Apr-June). / Given the programme is in its early stages and in line with the annual review TOR, it is relevant to comment on how well the programme is setting itself up to deliver on this output next year. The work on savings groups needs to be highlighted in particular as this work will contribute substantially to the largest outcome level target. It should be noted that the programme has taken an extremely thorough and systematic approach to supporting and identifying good practice in savings group development and implementation. This has set the foundations for solid interventions in this area in the coming year. In line with M4P practice, the programme has placed emphasis on bringing in lessons and innovations from outside Zambia to organisations involved in savings group work to encourage best practice and sector wide scale up. It is too early to assess the wider impact of this type of sector wide information sharing, however this should be examined as part of the next annual review. / The programme has also begun to set in place a sound platform to support the insurance industry with scale up and expansion. This has included support to the insurance regulator on the development of microinsurance regulations; support on strategy development to the Insurance Association of Zambia (IAZ) which includes the promotion of an inclusive insurance sector; and research to assess the feasibility of using non-traditional distribution channels to deliver insurance products. The results of the latter activity will be used to inform insurance service providers on how to use these channels to achieve scale and outreach of their products. / Recommendations: / Next annual review to take early soundings on the impact of broader best practice and information sharing work taken forward by the programme in savings group work (or another sector if deemed appropriate). / Programme to ensure grants are issued to organisations supporting savings group development as early on in the financial year as possible to ensure outcome level targets for 14/15 are met. / Impact Weighting (60%): / Revised since last Annual Review? Y/N The weighting for this output was temporarily increased to 60% for this annual review as a number of other outputs had no milestones, are yet to be scored and have been given a 0% rating. It will revert back to 35% at the next annual review. / Risk: Low / Revised since last Annual Review? Y/N

Output 5: Increased capacity of financial service providers to deliver products that are accessible, affordable and appropriate to MSMEs and smallholder farmers
Output 5 score and performance description: No results expected at this early stage / Indicators Results expected by March 2014 Results achieved by January 2014 Related comments / Output indicator 5.1 Number of financial service providers with increased capacity to reach MSMEs with financial services 0 0 No results expected at this early stage of the programme implementation / Output indicator 4.2 / Number of financial service providers with increased capacity to reach smallholder farmers with financial services 0 0 No results expected at this early stage of the programme implementation
Progress against expected results: / No milestone results were expected for this reporting period. However early views of the direction the programme is taking on SME finance and agricultural finance are given below. / The programme has undertaken research to assess demand and supply side weaknesses in the delivery of SME finance and to identify appropriate entry points for potential support to financial service providers in this area. SME finance is a difficult area in which to intervene. Most banks find this a particularly risky lending area - the informality, weak governance structures and lack of capacity in many SMEs in the country mean many lack the capacity and know-how to even approach banks for banking services. These difficulties have been compounded by interest rate caps introduced in early 2012 reducing the ability of banks to price for risk and hence their appetite for further lending to this sector. / The programme has developed an SME capacity assessment tool which it is using to determine the needs and potential support that could be provided to financial service providers. The programme is using this tool to assess potential partnerships with financial service providers in this area. At the present time 5 potential partnerships have been identified and will be explored further in the coming quarter. / Work on agricultural finance is still in the early stages and will be progressed further in the coming quarter. / At present the programme is lacking personnel with enough technical knowledge of both SME and agricultural finance to progress these 2 areas at the pace required. It is not apparent at the present time that additional members of permanent full time staff are required, however, given the level of interactions required with senior members of government and CEOs of financial service providers, more senior level support will be needed to consolidate and progress work in this area. / Recommendations: / Programme to engage with DFID Economist and recently launched Zambia Economic Advocacy programme to explore linkages between the macro-economic environment (particularly high levels of Government domestic borrowing) and SME lending. Programme to assess opportunities and merits of highlighting this further through mechanisms such as the Economics Association of Zambia public debate series. / Programme to use technical assistance fund within the programme budget for longer term work in SME finance and agricultural finance to ensure work is consolidated and progresses at a significant pace. / Impact Weighting (0%): / Revised since last Annual Review? Y/N N/A This output has been temporarily set at 0% for this annual review given no milestone was due to be achieved. It will revert back to 25% at the next annual review. / Risk: Medium / Revised since last Annual Review? Y/N N/A

Output 6: Establishment and operation of Access to finance Zambia
Output 6 score and performance description: – B programme moderately did not meet expectations / Indicators Results expected by March 2014 Results achieved by January 2014 Related comments / Output indicator 6.1 Strategic plan and business plan completed Consultants mobilised and fully operational on the ground / Planning completed for 5 year strategic plan and 2 year business plan / Gender strategy and climate change assessment completed Team mobilised however some fundamental set up issues still remain / Strategic plans completed on time / Climate change assessment completed. Gender strategy not complete Start-up has been slower than expected and some fundamental programme management issues still remain to be tackled. / A thorough process put in motion to complete gender strategy. / Output indicator 6.2 Special purpose vehicle established and operational N/A N/A No progress on this indicator was envisaged during this period. However, see comments and recommendations below on this issue.
Progress against expected results: / The programme moderately did not meet expectations for output indicator 6.1. The strategic plan and business plan were merged into 1 document and delivered on time at the end of inception phase. However, the programme has suffered from weak programme management by the supplier. / Unclear reporting lines and management oversight of systems for financial reporting and forecasting were apparent during the inception phase. The management of the programme was moved from DAI South Africa office to DAI head office in London in September at the end of the inception phase and a new programme manager appointed. However, some fundamental programme management issues persisted well into the implementation phase and were not addressed quickly enough by the supplier. As at end of January the majority of the programme staff were still not contracted and it was apparent that the discussions of these issues had been long and protracted with many staff feeling unfairly treated by DAI. Inconsistencies in terms and conditions between staff and differences between offer letters and final contractual offers were apparent. This had a significant effect on staff morale. Although these issues are now being addressed by the supplier, these fundamental programme management issues should have been addressed during inception. It was agreed in December 2013 that the programme manager would be replaced. / Financial management of the programme also needs to be improved. It was apparent during discussions with programme staff in Lusaka that the programme team do not have adequate oversight of expenditure on the programme budget. The programme Finance Manager is extremely weak (he has now resigned) and is due to be replaced. It is important that the supplier fills this post with a suitably qualified individual as soon as possible. The flow of financial information between DAI head office and the programme team in Lusaka is weak and needs to be significantly improved, ensuring that the programme team have enough information to make informed decisions about contracting and expenditure. Clear roles and responsibilities and improved communication channels between the programme and head office finance team need to be developed. At present the combination of head office contracting and programme office payment processes are creating confusion which raises concern over fiduciary oversight. These issues need to be addressed quickly. / The programme should be commended for the work undertaken on establishing a monitoring and results measurement system. The system developed is both thorough and comprehensive setting the foundations for sound monitoring and validation of programme results. Programme staff have an excellent understanding of how the system will operate. Given the early stages of programme implementation the challenge is now to apply this system to multiple real time interventions on the ground. / The programme has undertaken an assessment on climate change. Ultimately the programme will impact positively on climate change resilience by reducing vulnerabilities of the poor people with which it works. However, the programme will also look for opportunities for interventions to more directly impact on climate change adaptation through the introduction of clean technologies. Further information can be found in Quest link: 4354922. / The programme has yet to develop a gender strategy. However, it is in the process of contracting additional expertise to take this forward. This work will help in determining the role the programme can have in increasing financial access for women and to bring awareness on the importance, and social and economic benefits on woman in gaining access to financial services through high level policy dialogue. This work will be completed in May 2013. / No progress was envisaged for output indicator 6.1 during this period. However, the groundwork to enable DFID to make an informed decision about the establishment of an SPV should be undertaken in this next reporting year. This should include a value for money assessment between the two delivery mechanisms (supplier versus SPV); an assessment of the appetite of other donors to joint fund such an initiative in Zambia; an assessment which highlights clearly the need to establish a long term intervention mechanism to support financial inclusion in Zambia, and a clear roadmap of the steps required to set up the SPV (procurement, legal, governance, internal DFID approval etc.). This should be taken forward with the support of the DFID Zambia PSD Adviser. / Recommendations: / Ensure all staff are fully contracted with fair terms and conditions (in progress by the supplier). / Confirm name of replacement programme manager and start date (in progress by the supplier). / With the utmost priority, contract a new programme Finance Manager, and with support from DAI head office, ensure he/she is adequately inducted and appropriate systems put in place to ensure programme team have the information they require to ensure adequate fiduciary oversight. An early site visit by the head office programme accountant to take this forward is recommended. DAI head office to provide additional feedback/assurance to DFID on how they have addressed this concern by 15th April 2014. DFID Lusaka programme team to ensure adequate action has been taken by interviews with programme and head office staff. / Next review to assess the programme’s strategy on gender drawing expertise from the DFID Zambia gender adviser. / Next review to include an assessment of how the MRM system has been applied to interventions on the ground and initial views taken on the robustness and validity of results data being reported. / Programme to take forward ground work required to allow DFID to make an informed decision about the establishment of an SPV to support financial inclusion in Zambia. / Programme to be reviewed again in September/October 2014 where these issues will be re-examined and the annual review timing realigned to the programmes reporting year. / Impact Weighting (10%) / Revised since last Annual Review? Y/N The weighting for this output was temporarily increased to 20% for this annual review as a number of other outputs are yet to be scored and have been given a 0% impact rating. It will revert back to 10% at the next annual review / Risk: Medium / Revised since last Annual Review? Y/N N/A

## Section B: Results and Value for Money.

1. Progress and results

Has the logframe been updated since last review? YES / This is the first annual review of the programme which covers the programme’s inception and very early stages of implementation. The Business Case clearly stated that the logframe would be reviewed and revised during the inception/final design stage of the programme. This was comprehensively done by the technical team. In reviewing the logframe the team focused on a number of core principles: / the measurability of indicators proposed; / improving and reinforcing the links in the casual chain from outputs to outcome and outcome to impact; / where feasible, trying to assess usage and benefits of any products and services developed; / applying best practice for measuring M4P programmes. / The team has also developed a comprehensive monitoring and results measurement manual which clearly explains how results will be measured and attribution determined. / The submission authorising these changes can be found at Quest ref 4360140. / A small number of changes to the logframe are proposed in this annual review. Authorisation is requested to amend the milestone indicators for output indicator 6.1. These should be amended to more adequately allow tracking of the programme management function of the supplier. The following text should added to each annual milestone for this indicator: / ‘….and the Programme managed effectively and efficiently by the supplier’ / In addition to the production of annual reports, budgets and workplans this indicator will now assess: / Timeliness and quality of reporting both financial and technical. This will include the financial forecasting of the supplier. / The effectiveness of back office programme management support by the supplier. / The effectiveness of the MRM function including systems to test validity of results reported. / Quality of due diligence processes and follow up undertaken on sub-grantees. / 1.2 Overall Output Score and Description: / Overall output score is B – moderately did not meet expectations. / 1.3 Direct feedback from beneficiaries / Due to the early stage of programme implementation interviews were not held with downstream programme beneficiaries (poor people and businesses). However, interviews were held with key private sector financial service providers with which the programme has or will work in the future. / Most organisations stressed the importance of the support provided by the programme. In one particular case a large commercial bank highlighted the catalytic role the small amount of support the programme had provided had played in defining their strategy and convincing their Board of the business case for greater outreach into rural areas. The scale up has already started and given the size of this bank this has the potential to make a large impact on increased rural outreach. / Another commercial bank with ambitious plans to increase outreach into rural areas saw enormous potential to work alongside the programme in the early stages of this process – drawing on additional expertise to solidify their strategy and helping to share some of the risk of their early entry into a new market. / A number of organisations pointed to the positive effect that the information sharing work the programme had undertaken on best practice and innovation in savings group and electronic banking had had in terms of opening their eyes to new ideas and approaches. It is too early to assess whether this resulted in a concrete change in strategy. / One organisation highlighted the need for the programme to better and more clearly communicate their ‘offer’ to private sector financial service providers. The programme applies an M4P approach whereby they work alongside stakeholders in the financial services market to ‘facilitate’ increases in financial sector inclusion. Their interventions can be small and will often be focused on bringing in expertise to help private sector companies think through new business models and find new ways to profitably enter new markets. They are not simply giving out grants. This approach is new to the Zambian market and the programme should continue to think carefully about how they explain this in a simple and easily understood manner. / One interviewee also highlighted that the programme should increase the visibility of its work and find better ways to communicate to a wider audience what it is doing.
1.4 Summary of overall progress / Given the early stage of implementation there were relatively few technical milestones for delivery during this period with a major emphasis being placed on programme set-up. Good work has taken place on setting the ground work for technical delivery of the programme in the coming year with good partnerships with financial service providers identified that have the potential to have a large impact on financial inclusion in Zambia. Two output milestones indicators were not met, however, the outcome level milestone for this period was met by over achievement on another output indicator. / Although a good number of systems have been put in place (office set-up, grant administration, funds management, basic accounting and monitoring and results management) a number of issues still remain to be resolved to ensure the programme has the systems and structures to allow the technical team to operate at pace in the coming year. This includes issues on human resource management, broader programme management and financial management.
1.5 Key challenges / Specific recommendations are highlighted above, however it is worth noting in particular the following: / The programme has suffered from a number of programme management issues that have slowed down the start-up of the programme and had impacts on staff morale. If left unchecked these issues will begin to significantly affect programme performance. These issues are now being tackled by the supplier, however the supplier needs to ensure that momentum is kept up and they are fully resolved to allow the team to focus without distraction on implementation and achievement of results. / The programme has done some good groundwork to set up relationships and partnerships with financial service providers that have the potential to have a large impact on financial inclusion in Zambia. The key challenge now is to ensure these partnerships are taken forward quickly to ensure delivery of results next year. / The programme needs additional senior level support to consolidate work in a number of specialist technical areas, including SME finance, electronic banking and agricultural finance. This additional expertise should be contracted as soon as possible to allow concrete action to happen at pace. / Achieving the outcome indicator on SME finance continues to remain a higher risk than other indicators. This is primarily as a result of the interest rate cap that was introduced in January 2012. This coupled with increased public sector borrowing and high treasury bill rates makes it relatively unattractive for financial institutions to lend to more risky small and medium enterprises. This risk was highlighted in the business case and should continue to be monitored. The programme will need to continue to think creatively about how to address this.
1.6 Annual Outcome Assessment / The programme will have exceeded the 13/14 milestone on numbers of people with access to a new financial service. Please refer to output 4 for more details. / Indicators Milestone target by March 2014 Milestone expected by March 2014 Related comments / Outcome indicator 1 Number of poor people and microenterprises accessing a new financial service 15,000 / (of which 9750 are women) 24,274 (of which 9710 are women) The outcome level milestone has been exceeded through the roll out of a life insurance product in collaboration with Microensure. / Outcome indicator 2 Number of smallholders accessing a new agricultural financial service 0 0 N/A / Outcome indicator 3 Number SMEs accessing a new financial service 0 0 N/A

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / Programme spend actual versus forecast May – December 2013 / Type of payment Inception Phase (May to Sept 2013) Implementation( Sep 2013 to Dec 2013) Total Expenditure / Forecast (£) Actual (£) £ / Milestone 426,970.00 453,210.00 302,578.00 729,548.00 / Programme 114,048.46 228,808.00 28,121.00 142,169.46 / 541,018.46 682,018.00 330,699.00 871,717.46 / Spend is behind schedule. This is because of delays in finalisation of one of the programme grants due to be given out in December 2013 and also due to a slight time lag between the use of STTA on the programme and when this is actually invoiced to DFID by the supplier. / Updated financial forecasts are received on a monthly basis. The supplier needs to ensure that updated quarterly forecasts are also given to allow DFID to better forward plan for expenditure on the programme. These forecasts need to take account of the above mentioned timelag between use of STTA and/or issuing of grants and actual invoicing to DFID. / 2.2 Key cost drivers / At the present time external consultancy support costs are one of the key cost drivers on this programme, including whether consultants are local or expatriate personnel. The programme should continue to assess value for money of consultants procured to deliver services checking carefully against salary history and managing closely the quality of outputs produced. Consultancy support required in many of the specialist areas required for this programme are not readily available in Zambia and as such use of expatriate personnel will continue to be required. / The programme will give a number of larger grants to organisations promoting community savings group in the coming year. The programme will need to ensure that interrogation of these budgets to ensure maximum value for money is taken forward. / 2.3 Is the project on-track against original timescale: Y/N / There have been some delays to the start-up. Spend has not been as high as originally anticipated. Given the programme is in the very early stages of implementation this is not a concern but will continue to be monitored on a regular basis by the DFID programme team.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No changes to report. / Where an evaluation is planned what progress has been made? / No evaluation planned.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The overall output risk rating is medium. Four outputs remain medium risk. / Output 2 remains medium because of the inherent difficulties of working on policy making processes and the risk of financial sector policy being influenced by essentially political decisions. / Output 3 is rated medium as improved financial infrastructure requires policy level decisions and action which is outside the direct control of the programme. / Output 5 remains medium because of the policy implications of interest rate caps on lending to the private sector. / Output 6 is medium because of the risks of poor programme management impacting on programme performance.
Risk of funds not being used as intended / The risk at present is low. However, it was evident that the programme team currently does not have adequate oversight of the totality and spend on the programme budget, which is held at the DAI head office. These issues are raised earlier in the review and appropriate actions recommended. / A proportion of the programme funds will be subcontracted to other organisations. The due diligence processes the programme puts in place are therefore key to minimising the risk of any of these funds not being used for the intended purpose. DFID has had sight of the first due diligence process that the programme undertook which was of an acceptable quality. It will be important that the new finance manager is thoroughly inducted on due diligence procedures and that any follow on actions identified for downstream partners are taken forward by the programme team. It is recommended that the relevant members of the programme team attend the commercial awareness training that DFID Zambia’s commercial adviser is due to run end of February. It is also recommended that a sampling of due diligence processes and relevant follow-ups form part of the next and subsequent annual reviews to provide assurance that the programme is adhering to good practice. / 4.4 Climate and Environment Risk / This programme has the potential to increase climate change resilience through the work it will undertake to reduce vulnerabilities of poor people and also offers some opportunities to improve climate change adaption by encouraging climate change adaption through encouraging use of clean technologies. The programme has in place a screening mechanism through its grant application form to mitigate negative impacts on climate change. As the programme begins to process grant applications it should assess whether this screening mechanism is adequate or whether further work needs to be done to avoid negative climate change impacts.

5. Value for Money
5.1 Performance on VfM measures / The Business Case for FSDZ highlighted a range of difficulties associated with assessing the cost benefit ratio for this type of project. In particular, the nature of the intervention means that neither the resources required for individual interventions, nor their intended outcomes are known ex-ante. This places additional emphasis on the need for strong monitoring of value for money during project implementation. / Given this, the business case recommended the measurement of three types of indicator: / The ratio of programme management to total costs (<20%); / Estimated economic returns on specific project activities (>15%), and; / The cost of financial inclusion for each additional person (<£24). / The September 2013 Inception Report built on this, and proposed a set of measures for the project, based on a standard VFM four “Es” model. / Table 1: Proposed FSDZ Value for Money Indicators, Inception Report, September 2013 / VFM Possible value for money indicator / Economy Admin: programme ratio per year for entire programme / Admin: ratio for programme fund / Cost per unit of travel and office space / Short-term to Long term staff ratio / Efficiency Benchmarking input costs for different activities and apply a ‘yardstick’ approach / % of Zambian entities engaged vs regional or international / Average daily rate of consultants / Grant fund leverage ration / Staff : grant ratio / Effectiveness Cost per FSDZ beneficiary reached / Return on investment / Number of beneficiaries reached per project / Funds spent on macro-, meso-, and micro-level activities/ programmes / Equity % women served / % rural beneficiaries served / We welcome the programme’s efforts in developing a coherent set of value for money indicators. We expect that these indicators will form part of the annual report June 2014. However, for this to happen, the programme needs to ensure that the measurement of these indicators is integrated into programme management. Specifically, the programme will need to: / Define the indicators: The level of detail in the inception report is sufficient to set a general structure for value for money tracking. However, the indicators are not sufficiently defined to be practical programme management tools. By the end of April the programme needs to fully define the indicators that will be used to track VFM, and the methodology that will be used to calculate the indicators. / Ensure there is a process for collection of indicators: Linked to the definition of the indicators, the programme needs to ensure that the data on which the VFM indicators will be based is being collected by the programme. In particular, by the end of April the programme should consider how the measurement of value for money links to its Monitoring and Results Measurement Framework. / The annual report in April will provide an opportunity to test, and finalise the value for money framework. In particular, we will need to take a view on our ability to interpret the proposed indicators, and their usefulness. / Interpretation of indicators: Some of the proposed indicators will require very careful interpretation. For example, the “daily fee rate of consultants” indicator. While in general a lower fee rate seems preferable, in many circumstances a more experienced, expensive, consultant may represent better value to the project. The annual report will need to assess whether the proposed indicators can be usefully interpreted – and hence whether we should continue to include them in the framework, or replace them. / Usefulness of indicators: Our contract with DAI is a milestone contract – where the expenses and fees for full time staff and head office support are contained within the milestone payment. This may limit our ability to make use of some of the proposed value for money indicators. For example, in the event that the unit cost of flights or other expenses in the milestone component of the programme is reduced, this does not affect the price to DFID of delivery – and hence has no effect on value for money of the project. At the time of the Annual Report in April we will need to consider the usefulness of all value for money indicators. Those which cannot be used in a practical way to drive value for money will need to be amended or replaced. / Recommendations: / By end-April 2014 the programme must clearly define the indicators it will use to measure value for money. These indicators must be based on data that the programme collects as part of its management processes. / Following the Annual Report in April 2014 the programme must assess the usefulness of each of its VFM indicators for driving value for money for DFID. By August 2014 it must finalise any revisions. / 5.2 Commercial Improvement and Value for Money / The contract is managed on a milestone basis with the costs and expenses of the core team in Lusaka and head office support being rolled into a quarterly milestone payment linked to delivery of a number of predefined deliverables – all of them technical in nature. The programme management issues highlighted above have consumed a significant amount of time of the technical team and DFID staff. The time and quality of support deployed by the suppliers head office has contributed to this. It is proposed that the DFID team in collaboration with Procurement Group explore including a milestone deliverable linked to the quality of head office support to increase the incentives of the supplier to improve performance in this area. / It is also difficult to drive value for money in a milestone contract once set up. The lack of transparency within the payment means that we are unable to identify possible areas where some aspects of value for money could be improved. In addition, where there is scope for cost savings, 100% of these accrue to the supplier – and so do not drive value for money improvements for DFID. Equally, there are benefits - DFID is not liable in the case where costs rise. / We should continue to monitor the programme closely to ensure that the milestone contract is not leading to perverse incentives – for example, the use of less programme management support, or cuts in staff benefits that lead to a drop in project morale/ staff turnover. / 5.3 Role of project partners / The programme will sub-grant funds to other organisations. The processes the programme is undertaking on due diligence of downstream partners has already been highlighted. It will also contract short term technical assistance and subcontract services from companies for data collection and surveys (e.g. Financial Diaries). In order to ensure quality and timeliness of delivery of outputs the programme is incorporating milestone payments for some downstream partners and subcontractors where payments are only made when outputs have been delivered. / 5.4 Does the project still represent Value for Money? / Yes – there is no reason at this stage for us to change the value for money assumptions set out in the business case. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The programme has made good progress in laying the foundations for sound delivery of support to the financial inclusion agenda in Zambia. Outcome level targets have been surpassed for this quarter through overachievement of one output indicator. Two other output indicators were not met. / A number of programme management issues remain to be resolved and need to be addressed before they begin to impact on programme performance. / Given the programme has been given a ‘B’ score, these recommendations will be packaged under a ‘Performance Improvement Plan (PIP). Progress against these recommendations will be assessed at the end of May to provide assurance that programme management issues have been resolved and technical work is on track. An additional annual review will be undertaken in September/October, and subject to satisfactory completion/progress on recommendations, the programme will then be reviewed every June/July assessing progress retrospectively against March milestones in each year. This will allow alignment with the programmes reporting year. / Key recommendations for the supplier’s head office team, Lusaka based technical team and for the next annual review are in the outputs section but also highlighted below. / The supplier should: / Programme management / As a matter of utmost priority address the flows of financial information and define a clear set of responsibilities between head office and programme office finance teams to ensure adequate fiduciary oversight of the programme budget and contracting process. The Head office accountant should visit FSDZ offices in Lusaka once the new Finance Manager is in place to help with induction and to ensure adequate systems for fiduciary oversight are in place. The head office accountant and programme Finance Manager should submit a short report to DFID highlighting action taken and confirming that these systems are now in place by 30th April 2014. (Action: DAI Head office and new Finance Manager) / Ensure that updated quarterly forecasts are given to allow DFID to more accurately forward plan for expenditure on the programme. These forecasts need to take account of the timelag between use of STTA and/or issuing of grants and actual invoicing to DFID. These should be given as per the timings in the agreed schedule of reporting. (Action: Finance Manager and Head Office Accountant) / Ensure new finance manager is adequately inducted in due diligence procedures (Action: DAI Head Office) / Finalise as a matter of priority the remaining contractual issues with programme staff, ensuring all staff are fully contracted with fair terms and conditions (Action: DAI Head Office – currently in progress). / As a matter of priority agree and communicate to DFID the name and start date of the replacement programme manager (Action: DAI Head Office – currently in progress). / Technical / Continue momentum to set in place financial education initiatives that will enable 14/15 target to be met (Action: Technical team). / Accelerate the partnership with Bank of Zambia (Action: Technical team). / Increase the programme’s visibility through a more focused communication strategy (Action: Technical team). / Ensure grants are issued to savings group promoters early on in the financial year to ensure 14/15 target is met (Action: Technical team). / Engage with DFID supported Economic Advocacy programme to assess opportunities for advocacy work on SME lending and domestic sector borrowing (Action: Technical team). / Procure additional expertise to consolidate and progress work on agricultural finance, SME finance and electronic banking (Action: Technical team). / Take forward ground work to allow DFID to make an informed decision on the establishment of an SPV (Action: Technical team). / Value for money / By end-April 2014 the programme must clearly define the indicators it will use to measure value for money. These indicators must be based on data that the programme collects as part of its management processes (Action: Programme Finance Manager and Head Office accountant). / Following the Annual Report in April 2014 the programme must assess the usefulness of each of its VFM indicators for driving value for money for DFID. By August 2014 it must finalise any revisions (Action: Programme Finance Manager and Head Office accountant). / Next annual review to: / Include early assessment of the impact of broader best practice and information sharing work undertaken by the programme / Assess the work on the development of a gender strategy / Assess the application of the MRM on interventions on the ground taking early views on validity of results / Sample due diligence reports and follow on actions by programme team. / Other actions / DFID team to plan additional review in September/October, / DFID team in collaboration with Procurement Group to explore including a milestone deliverable linked to the quality of DAI Head Office support to increase the incentives of the supplier to improve performance.

8. Review Process
Terms of reference for the review can be found at Quest ref: 4365242. The review took place between 11th and 14th February 2014. A field visit was not undertaken as the programme is in the very early stage of implementation and had only just made its first grant. The review draws from close interaction with the programme by the DFID Zambia PSD Adviser and programme team over the last 9 months and the first quarterly report. Interviews were also held programme staff in Lusaka, the Bank of Zambia and key financial sector stakeholders with which the programme has or will work with in the future (Microensure, Investrust, Zanaco and CRS).