Type of Review: Annual Review

Project Title: Statebuilding and Service Delivery Grant to the Palestinian Authority

Date started:	12 August 2011
Date review undertaken: February 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
Initially, a total amount of £122.2m over 4 years, comprising: / Core grant: of up to £110m to the Palestinian Authority (PA); / ‘Results compact’: Funding of £12m if the PA demonstrates high value for British taxpayers money; / £200,000 for an independent evaluation. / The annual schedule outlined in the Business Case is as follows: £30m in 2011/12; £35m in 2012/13; £35m in 2013/14; £22m in 2014/15. / However, following an additional contribution, the revised total amount the UK is providing over 4 years is £129.71m. The following is a breakdown of this revised figure. / An additional £7.5m (see Addendum to Business Case) was added to the total amount in October 2013 for the financial year 2013/14 thus amounting to a total of £42.5m for that year. / Disbursement of ‘results compact’ out of the potential £12m / - £4.1m out of £5m was disbursed in February 2013 / - £4.167m out of £5m was disbursed in February 2014 / Of the £200,000 allocated for an independent evaluation and results framework, £110,000 has been allocated for an independent evaluation; and £29,900 was allocated for an assessment of the PA accounts that will feed into the evaluation, / The revised annual schedule is as follows: £30m in 2011/2012 (actual); £34.1m in 2012/13 (actual); £41.6m in 2013/14 (actual); £22m in 2014/15 (budgeted).

What are the expected results?
The overall impact of this project is: Poverty reduced and a more peaceful and prosperous Palestinian state and society. / The PA will be better able to maintain access to public services, and in doing so, help maintain public support for statebuilding, non-violence and a negotiated Two-State Solution. / The Business Case highlighted the following output targets that will be attributable to DFID include: / Results funding public services bought by DFID support e.g. 2000 children under 5 immunised with measles. / Policy leverage: savings worth at least $100m to the PA from the implementation of reforms agreed with the World Bank and action plans to improve efficiency of health and education services. / Development effectiveness: the Grant sets the standard for improving the predictability of aid to the PA, with at least 75% of DFID’s disbursements released according to the amount and month specified in the UK-PA Memorandum of Understanding. The results expected from the World Bank’s Palestinian Reform and Development Plan (PRDP) Multi Donor Trust Fund agreed between the World Bank, PA and donors in order to increase the focus of all stakeholders on achieving better and more sustainable public services for Palestinian people. / We will check that these results have been achieved by funding an independent evaluation, which will be conducted between March - August 2014.

What is the context in which UK support is provided?
There have been various internationally sponsored attempts over many decades to resolve the conflict between Israel and the Palestinians by negotiating a ‘Two-State Solution’, most notably the Oslo Accords of 1993 which allowed for the establishment of the Palestinian Authority (PA), and for limited degrees of Palestinian Authority (PA) control over parts of the Occupied Palestinian Territories (OPTs). / Current US-led negotiations are due to draw to a conclusion in April. Support to the Middle East Peace Process is a high priority for the UK Government. The UK’s goal is the creation of a sovereign, independent, democratic, contiguous and viable Palestinian State living in peace and security side by side with Israel. We continue to support the work of the PA under the leadership of President Abbas and Prime Minister Hamdallah, which remains a vital element of efforts to achieve a two-state solution. As well as providing education, health, policing and other vital services to the Palestinian people, the PA represents a partner for peace with Israel. / The DFID Palestinian Programme Operational Plan for 2011 to 2015 sets out the context and vision for our work in the Occupied Palestinian Territories (OPTs). / Due to the effects of the occupation – movement and access restrictions - the Palestinian economy remains severely hampered, which in turn prevents the PA from raising adequate revenues to supply basic services to the Palestinian people. An IMF mission which visited the OPTs in January 2014 expects Palestinian GDP to fall, unemployment to rise, and the PA to face a revenue shortfall of $330m or 3% of GDP in 2014. / By providing predictable financial support, we help the PA in its statebuilding efforts by supporting the delivery of essential services such as health and education but also by linking our support to reform. The UK National Security Council has noted in its discussions the importance of a well-functioning, sustainable PA. The need we are trying to address is a chronic shortfall in funding for the PA’s annual budget caused by the ongoing effects of the Occupation that prevent the PA from raising sufficient revenues from a vibrant private sector led Palestinian economy. Unemployment is high, if PA salaries are not paid this could lead to increased poverty, and, alongside frustrations with the lack of progress in peace negotiations, contribute to risks of increased violence and instability. / The UK is tackling the problem in three principal ways: firstly, the UK Government is encouraging and working in support of serious efforts to move forward with the peace process in 2014, in particular supporting US Secretary of State Kerry’s efforts. Secondly, the UK is making firm representations to the Government of Israel to continue the transfer of Palestinian money to the PA and encouraging other donors to provide funds and deliver on aid pledges. Thirdly, the UK via DFID is providing money to the PA to help plug its funding shortfall in the short-term, whilst linking that continued financial assistance to reforms that can help solve the problem in the long-term by reducing the PA’s dependence on aid. These reforms will generate efficiency savings in the way the PA spends its money, and increase tax revenues. Even under conditions of Occupation, the PA has already reduced its dependence on donors to fund its recurrent budget, from 61% of the budget in 2008 to 41% in 2012, and to 30% in 2013. It should be noted however that sustainable job led economic growth will be dependent on movement and access restrictions being eased. / Our main implementing partner for this is the World Bank, who agree a reform plan with the PA each year and only transfer UK money to the PA during the year if the plan is on track. This has enabled the PA to save a lot of money over the last couple of years, by strengthening the hand of reformers to push difficult reforms through.

## Section A: Detailed Output Scoring

Output 1: Results funding – public services bought by DFID support
Output 1 score and performance description: / A+ - Outputs moderately exceeded expectation
Progress against expected results: According to the theory of change, the investment in statebuilding is intended to support prospects for achieving a peaceful political settlement and seeks to maintain and develop key state functions to support stability and meet public expectations. Due to the importance of service delivery and the continued financial crisis that the PA is facing, we changed the output 1 impact weighting from 50 to 60% in October 2013. / Methodology for calculating DFID’s attribution rate of 1.85% of recurrent PA expenditure in 2013 / Summary of UK budget support in 2013: planned and actual / UK budget support in 2013, planned at time of business case / (£m) UK budget support in 2013, actual / (£m) / Core tranche 30 30 / Performance tranche 5 4.1 / Additional funding to address the effects of the PA’s ongoing fiscal crisis 7.5 / Total 35 41.6 / The average DFID attribution rate for indicators 1.1 to 1.4 and 1.7 used for the overall four-year period of the programme was 1.57%. Given the additional funding of £7.5m in 2013, the attribution has been adjusted to reflect the fact that the UK can claim a larger share of the results. To calculate this new attribution rate for 2013, the following method was used: / PA’s recurrent budget (2013) = £2,377m / 1.57/100 * recurrent budget = £37.3m / Total actual budget support in 2013 (£41.6m) minus planned budget support (£35m) = £6.6m. This figure is the total additional funding for 2013. / £6.6m + £37.3m = £43.9m / £43.9m/ recurrent budget = 1.85% / We will use a revised attribution rate of 1.85% for the achieved milestones for these indicators in 2013 only. The milestones have not been revised for this year because the revenue assumptions (PA and donors) made in the 2013 budget did not hold, therefore our additional funding helped to compensate for this shortfall to ensure services continue to be provided. The budget deficit was actually 28% worse than anticipated. / See the table and text below for more detail about the achieved results. / Output Indicator 1.1 Baseline Academic year* (2010/11) Milestone 2011/12 Milestone 2012/13 ** Milestone 2013/14 Target 2014/15 / Education: Number of non-refugee children, boys (M) and girls (F) supported by DFID in primary education (grades 1 to 6) Planned 0 5,557; / (M) 2,789 / (F) 2,768 5,657; / (M) 2,842 / (F) 2,815 5,751; / (M) 2,889 / (F) 2,862 5,796; / (M) 2,913 / (F) 2,883 / Achieved 5,666; / (M) 2,836 / (F) 2,830 6,711; / (M) 3,362 / (F) 3,349 / Output Indicator 1.2 Baseline / Academic year* / (2010/11) Milestone / 2011/12 Milestone / 2012/13** Milestone / 2013/14 Target 2014/15 / (projected, but not published) / Education: Number of non-refugee children, boys (M) and girls (F) supported by DFID in lower secondary education (grades 7 to 8) Planned 0 1,691 / (M) 840 / (F) 851 1,711 / (M) 850 / (F) 861 1730 / (M) 860 / (F) 870 1,750 / (M) 870 / (F) 880 / Achieved 1,917 / (M) 948 / (F) 969 2,296 / (M) 1,146 / (F) 1,150F / Output Indicator 1.3 Baseline 2011 Milestone 2012 Milestone 2013 ** Milestone 2014 Target (2015) / Health: Number of pregnant women attending ante-natal care in the West Bank supported by DFID. Planned n/a n/a 482 512 541 / Achieved n/a 258 / (until 30 June 2013) / Output Indicator1.4 Baseline 2011 Milestone 2012 Milestone 2013** Milestone 2014 Target 2015 / Health: Number of children under 5 years old immunised for measles Planned 0 1,746 1,831 1,916 1,991 (2014) / Achieved 1,686 (MMR) 2,276 / (Measles) 9,194 / (unpublished data) / Output Indicator 1.5 Baseline / 2011 Milestone / 2012 Milestone / 2013 Milestone / 2014 Target 2015 / Health: Average number of daily medical consultations per doctor in general PHC clinic Planned n/a 47 47 47 47 / Achieved 47 55 / (until 30 June 2013 only) / Output Indicator 1.6 Baseline / 2011 Milestone / 2012 Milestone / 2013 Milestone / 2014 Target 2015 / Health: Proportion of medicines on the essential drug list that are reported at zero stock levels in the West Bank (WB) and Gaza (G) central drug stores (%) Planned 31%(WB) 37%(G) 30%(WB) 30(G) 25%(WB) 25%(G) 20%(WB) 20%(G) 15%(WB) 15%(G) / Achieved 29%(WB) 36%(G) 27.4%(WB) 28.5%(G) / Output Indicator 1.7 Baseline / 2011 Milestone / 2012 Milestone / 2013 Milestone / 2014 Target 2015 / Social protection: Number of non-refugee individuals covered by DFID-supported cash transfers Planned 4,825 5,779 6,528 7,283 8,052 (2014) / Achieved 8,857 11,665 / * PA academic years start from September and end in June. Therefore e.g. for 2013 figures, academic year 2012/13 figures were used. / **2013 Milestone achievements calculated using revised attribution rate of 1.85% / The annual review process showed that the definitions of the indicators needed to be more precise to reflect accurately what we are reporting. Indicators 1.1, 1.2 and 1.7 talk about the number of non-refugee children and individuals receiving basic services and cash transfers from the PA. The definition of non-refugees was intended to distinguish PA provision from UNRWA provision; this was the methodology used to calculate the milestones. However, some refugees access basic services through PA rather than UNRWA provision, and these are included in the logframe milestones, rendering the term ‘non-refugees’ misleading. We recommend reflecting this in more precise definitions in indicators 1.1, 1.2 and 1.7 as “number of children” and “number of individuals” supported by the PA with DFID. / Output indicator 1.1: Education: As illustrated in the table above, the milestone has been overachieved. / Output indicator 1.2: Education: This indicator on lower secondary education (grades 7 and 8) was added to the logframe following the last annual review in 2013 to reflect better the full nature of the PA’s basic service delivery, which covers more than primary school education (grades 1 to 6). The milestone has been overachieved. Note that the target is based on Ministry of Education projections. / For Health indicators 1.3, 1.5, the Ministry of Health expects to consolidate and release the data for the 2013 calendar year by the end of March 2014. The data reported for 1.3 and 1.5 relates to the first six months of 2013. This is what field offices have reported to the Ministry of Health to date. On the current trajectory, the project has already overachieved (1.3) or is likely to do so (1.5). In the case of 1.4, the data has yet to be published officially. We do not have evidence for any significant changes that would lead us to believe that these results will change once the official data has been published. / Output indicators 1.3 and 1.5: Health: These were introduced to the logframe following the 2012 annual review to reflect better the work of the whole sector. These indicators are also used by UNRWA, and UNRWA provision is used as one of our Operational Plan headline results. Our initial assumption on adding the indicators to the logframe was that we could make comparisons between UNRWA and PA service provision in the West Bank and Gaza. However, in the course of the current AR, we have found that the PA/Ministry of Health does not set targets or report on indicator 1.3 in the same way as UNWRA. While we have calculated a baseline for 2012 and milestones for 2013 as a projection of previous results based on figures provided by the Ministry of Health, we recommend removing indicator 1.3, as it is not based on official PA reporting. / Regarding output indicator 1.4, the Ministry of Health replaced the measles only vaccine with the combined measles, mumps and rubella (MMR) vaccine in 2013, which is given twice (at the ages of 12 and 18 months). This does not affect the indicator, as we are measuring the number of children under five years of age immunised against measles. / In 2013, the PA vaccinated a total of 11,470 children against measles with DFID support. This includes the regular course of MMR immunisations for 2,276 children and an additional 9,194 children immunised with the measles vaccination in response to an acute outbreak in 2013[1]. The PA did extremely well in exceeding the milestone of 1,831 children with the regular MMR immunisations alone. The additional response to the acute outbreak accounts for the PA over-achieving on the target by 526%. / Output indicator 1.6: Health: Although there has been a significant decrease of medicine shortages compared to figures from 2012, the 2013 milestones were not achieved with levels of 27.4% in West Bank and 28.5% in Gaza. / The main cause for this in the West Bank is the financial crisis the PA is facing (specifically, amounting arrears to the private sector including pharmaceutical companies) and the difficult budgeting choices the PA is managing. Another reason (reported by WHO) is that UNRWA has been on strike for almost two months, which has affected their patients’ accessing drugs from UNRWA and using PA supplies instead. In Gaza, the shortages are mostly due to the closure of the Rafah border crossing in 2013 and early 2014, which has put a large strain on Gaza supplies in general. / We recommend to discuss with the Ministry of Health and the WHO how the drugs shortages can be reduced in future. / Output indicator 1.7: Social protection: As illustrated in the table above, this milestone has been vastly overachieved. While it is good to see the PA’s success in providing cash transfers to those in need, we are checking with the PA what caused the substantial increase in people claiming cash transfers and how the underlying poverty issues necessitating cash transfers in the first place can best be addressed in future. / Recommendations: / Use “number of children” and “number of individuals” supported by the PA with DFID funding (to capture all those benefitting from PA service provision regardless of their refugee/non-refugee status) in the definitions of indicators 1.1, 1.2 and 1.7. / Remove indicator 1.3, as it is not based on official PA reporting. / Discuss with the Ministry of Health and WHO if there are any practical measures to bring drug shortages down despite the PA financial shortfalls. / Review the selection of health and education indicators with support from DFID Health and Education Advisers and in discussion with the Ministries of Health and Education and the Sector Working Group to ensure that a successor programme to the Statebuilding Grant reflects the key issues the PA is facing and addressing in these sectors. Ensure the evaluation of the SBG is aware of the rationale for including service delivery indicators, in order to assess whether this is appropriate for a successor programme. This work should be completed by the end of June 2014 to feed into our CPRD and business case planning.. This work should be completed by the end of June 2014 to feed into our CPRD and business case planning. / Check with the Ministry of Social Affairs what has caused the vast increase in Palestinians claiming cash transfers and how the underlying poverty issues can best be addressed in future. / Impact Weighting: 60% from 50% / Revised since last Annual Review? Yes / Risk: High / Revised since last Annual Review? No
[1] Note that the number of children immunised with the measles only vaccination in response to the acute outbreak of measles is not based on official PA reporting. We received an overall figure of 950,000 children up to eight years of age immunised and calculated the DFID attribution for an estimated number of children up to five years of age applying the DFID attribution rate of 1.85% for 2013.

Output 2: Policy leverage – improved PA systems and fiscal discipline, and spending more efficient
Output 2 score and performance description: B – Outputs moderately did not meet expectations
Progress against expected results: / Output Indicator 2.1 Baseline 2010 Milestone 2012 Milestone 2013 Milestone 22014 Target 2015 / Public finance reforms: Proportion of planned reforms in World Bank annual Development Policy Grant (DPG) Matrices that are over 50% completed (%) Planned 56% 60% 65% 70% 70% / Achieved 71% 66.7% / Output Indicator 2.2 Baseline 2011 Milestone 2012 Milestone 2013 Milestone 2014 Target 2015 / Public service efficiency reforms: Extent of completion of PA action plan for increasing efficiency of public spending on education and health (%) Planned 0% 30% 50% 70% 70% / Achieved 3.5% 45.8% / Output Indicator 2.3 Baseline 2011 Milestone 2012 Milestone 2013 Milestone 2014 Target 2015 / Accountability reforms: Number of high quality quarterly and annual monitoring reports on the Palestinian National Development Plan each year that meet agreed quality criteria. Planned 1 2 3 4 5 / Achieved 2 3 / Output indicator 2.1: Public finance reforms: According to the World Bank Reform matrix (DPG V) and our initial assessment of the PA’s performance against these indicators, there is evidence that the PA has achieved four out of six targets fully, thereby achieving 66.7%. Therefore, the milestone has been achieved, and has moderately exceeded expectation. / To explain this assessment, of the six ‘Programme Development Objectives’ in the Matrix for DPG V four were judged to be ‘Achieved’: / Domestic revenues from VAT, Customs and income tax in 2013 to have increased over 2012 by at least 10% in nominal terms and be a higher share of GDP; / Growth in the CG nominal wage bill over 2012 did not exceed 4.25% and is a lower share of GDP; / Number of “vulnerable households” do not exceed 19,200; / Stakeholders can easily access information on the amount of property tax collected, deductions from property tax collected by CG, and the breakdown of transfer expenditures, from MOF website. / Two targets were not achieved: / The share of outside referral costs to total public healthcare spending to decrease by at least 2 % points below the 31% in 2012; / Public procurement to be based on new Regulations, National Standard Bidding documents, and Procurement Manual. / The latest Public Expenditure and Financial Accountability (PEFA) assessment in 2013 did not make recommendations, but the WB did a workshop in October 2013 on the PEFA findings which included their recommendations with regard to: recording of arrears, better control of commitments, more detail in monthly reports, improved cash planning, insufficient linkage of budgets with strategic plans, lateness of annual financial statements and many audit criticisms. Most of these are being addressed by the MOF with TA from the WB. / Since the PEFA was completed, our own monitoring of the PA’s accounts and consultation with the World Bank has highlighted that the PA’s monthly accounting processes need to be strengthened. / Annual audited accounts are provided only two years after the end of the year (latest accounts are for 2010), so donors rely more on monthly accounts, which are produced from the same computerised system. These are up-to-date and classified closely to IMF–GFS standard, but show a large ‘residual’ or unexplained difference that built up between April – September 2013. This is material (equal to about 5% of expenditure or 7% of domestic revenue), and has not yet been fully explained. The World Bank, IMF and DFID experts are all in regular dialogue with Ministry of Finance officials to get a definitive explanation for this accounting anomaly. It appears that NIS 200m (approx. £35m) is due to an error with regard to a transfer to the Palestine Monetary Authority (PMA), and there may be further error in the accounting of the petroleum subsidy and on tax refunds. The World Bank, IMF and an independent consultant contracted by DFID to audit the PA accounts all agree that there is no suggestion that the difference is due to anything other than accounting and reporting errors. There is agreement with the World Bank that the MoF needs Technical Assistance to raise its capacity and prepare earlier and more accurate accounts. DFID has raised this issue with the Minister of Finance and the Prime Minister and offered technical support to help address capability gaps. / The World Bank will officially publish its Implementation Completion Report by early May 2014 with an official assessment of the PA’s reforms. We have drawn on initial discussion with the World Bank to inform the findings above. If the World Bank’s findings differ significantly, we will adjust the Annual Review prior to the date of the next annual review. / We are currently updating our mandatory Fiduciary Risk Assessment (FRA) that will assess the PA’s financial and fiduciary systems. The FRA will make recommendations on whether there are any further safeguards the DFID should put in place to ensure our aid is being used as intended. The FRA is due to be completed by April 2014. / Output indicator 2.2: Public service efficiency reforms: This indicator is scored by checking how many activities in the Ministry of Education and Ministry of Health Efficiency Action Plans (EAP) have been implemented in a calendar year. / Both the MoE and MoH EAPs list activities related to efficiency measures incorporated in annual work plans and programme budgets; reviewing and simplifying financial regulations; adopting a programme budget structure to align the budget more closely with the delivery of their main services; identifying major cost drivers and reporting trends; and taking measures specific to the Ministries to implement these efficiencies. / In the previous AR, we reported only completed activities as achieved, as the implementation of the EAPs had only just started. In the current AR, we recognise that progress on a broader range of reforms is in some cases more desirable than completion of a limited number of reforms. We have taken this as a basis to score completed activities as fully achieved and ongoing activities as half achieved and calculated the overall achievement as a percentage of the total number of activities listed in the EAPs. / Out of the 25 activities in the MoE EAP, the MoE reported eight as completed and three as being underway, while some depend on Ministry of Finance reforms to improve the efficiency of service delivery of the entire government. We judge the completion rate to be 38%. / Out of the 28 activities in the MoH EAP, the MoH reported nine as completed and 12 as underway, summarised in a completion rate of 53.6%. / The overall completion rate for both EAPs is therefore 45.8%. / This indicator provides a link to the technical assistance (TA) provided under the Palestinian Governance Facility (PGF). In response to a request from the Minister of Health to address growing health sector costs caused largely by salaries and referrals, the PGF TA team is supporting the MoH to implement a number of activities listed in the EAP. The MoH is making good progress. The PGF TA helped the MoE revise its programme structures. Since then, the MoE indicated that it does not currently need further support, partly because its costs are more stable (largely salaries and school books) and partly because its efficiency actions are covered by ongoing reforms to align budgeting and spending to defined programmes of delivery (programme budgeting). / With the approval of the MoE and MoH EAPs, the implementation rate of the activities has improved considerably since the last AR. However, both Ministries are still slightly under-performing against the milestone. We recommend discussing the 2014 milestone and 2015 target with both Ministries to make them stretching but realistically achievable with suitable support. / Output indicator 2.3: Accountability reforms: Number of high quality quarterly and annual monitoring reports on the Palestinian National Development Plan (PNDP) each year that meet previously defined quality criteria. The expectation was to reach a milestone of 3 by 2013, from a milestone of 2 in 2012. The Ministry of Planning and Development MoPAD has since produced one annual PNDP monitoring report that meets agreed quality criteria, and 2 AHLC reports, one in March 2013 and the other in September 2013. This milestone has therefore been achieved. / To explain this assessment, the MoPAD website shows 3 reports issued in 2013: (1) Summary of Palestinian Representation to the Ad Hoc Liaison Committee (AHLC) 19 March 2013, (2) “Unlocking Statehood”, the PA report to the AHLC in September 2013, (3) Second Annual NDP Monitoring Report on 2012. An assessment of the PNDP monitoring report for 2012 was assessed against the previously defined criteria, and was judged to be sufficient by DFID. / Recommendations: / Update the logframe to reflect the World Bank’s Implementation Completion Report that assesses the PA’s performance against the DPG V matrix, this report will be available in May 2014. / Agree with the PA, World Bank and other donors the degree and source of potential TA to support the PA in improving its annual audited accounts. Consider whether this might be an added activity under the existing PGF programme which seeks to improve the PA’s overall financial management capacity. This could include, but need not be limited to, discussing the use of the full financial accounting data base for both monthly and annual accounts to improve the accuracy of the accounts with the MoF. We will draw upon the FRA and available TA to assess the how far this is feasible without sacrificing the timeliness of the monthly reporting. / Discuss the 2014 milestone and 2015 target with MoE and MoH and the PGF TA team to make it more realistic based on an assessment of remaining activities. Set ambitious but achievable targets within three months of this annual review for both Ministries to achieve them in the remaining time of the programme. / Impact Weighting (%):25% / Revised since last Annual Review? Yes / Risk: Medium / Revised since last Annual Review? No

Output 3: Development effectiveness – aid to the PA is more predictable and results-focused
Output 3 score and performance description: / B – Outputs moderately did not meet expectation.
Progress against expected results: / Output Indicator 3.1 Baseline 2010 Milestone 2012 Milestone 2013 Milestone 2014 Target 2015 / Aid predictability - UK: Proportion of disbursements released by DFID according to the amount and month specified in the UK-PA Memorandum of Understanding, unless due to a breach of conditionality (%) Planned 50% 75% 75% 75% 75% (2014) / Achieved 100% 100% / Output Indicator 3.2 Baseline 2011 Milestone 2012 Milestone 2013 Milestone 2014 Target 2015 / Aid predictability - international: Proportion of scheduled aid reported as disbursed in government accounts through a reliable information system (%) Planned 0% 55% 60% 65% 71% / Achieved 40% 60%[2] / Output Indicator 3.3 Baseline 2011 Milestone 2012 Milestone 2013 Milestone 2014 Target 2015 / Results-focus: Extent to which a comprehensive results framework has been developed and implemented for the PRDP Trust Fund. Planned 1 3 4 4 5 (2015) / Achieved 2 3 / Output 3.1: Aid predictability – UK: DFID has performed exceptionally well on this indicator with an achievement of 100% of disbursements made on time. To explain this assessment, the UK-PA MoU does not specify a particular month, but mentions that a time schedule will be agreed between DFID and the PA. From discussion with the Ministry of Finance it was agreed that the time schedule is to provide £7.5m with each quarterly disbursement of the World Bank, and that it is not necessary to specify the month since the precise timing of the World Bank’s disbursement can differ from quarter to quarter. On this basis 100% of disbursements have been provided to the amount and time specified. The PA has made clear to high level visitors the importance of this approach. / Output 3.2: Aid predictability – international: The Ministry of Planning and Administrative Development reported 60% of aid captured directly through its DARP database (February 2014). To note, this percentage includes both humanitarian aid and budget support. We have asked MoPAD whether they can also provide figures excluding humanitarian aid and budget support, but at the time of finalising the annual review, we have not received these figures. We will include the breakdown in the revised logframe following this annual review. / Output 3.3: Results-focus: The expectation to reach the stage at which the majority of donors and PA agree on a results framework (score 3) has been achieved. To explain this assessment, PRDP Trust Fund donors are supportive of having a more comprehensive results framework in order to allow harmonised reporting on the services that are being bought by their funding of the PA. A results framework is already in place which reflects the Trust Funds objectives. This, in the form of the DPG Matrix, is for the PA’s progress against reforms. Donors would continue to use this but would develop additional frameworks. The Ministry of Finance is supportive in order to allow targets to be agreed with the donors to improve the aid effectiveness of direct financial assistance. The World Bank although understanding the rationale for additional frameworks have been justifiably concerned that these do not hold them accountable for results that were not originally conceived when the Trust Fund was designed. / The actual drafting of the common results framework has not yet taken place as it depends on the MoPAD finalising and publishing the new Palestinian National Development Plan (PNDP) for 2014 to 2018. We expect the PNDP to be finalised by June 2014. / A key innovation to improve the results-focus of aid to the PA that we have introduced in 2012, has been our 10% Performance Tranche. In 2012, a set of eleven targets were agreed with the PA to support the policy reforms in Output 2. And in 2013, a set of six targets were agreed with the PA to support policy reforms in Output 2; five from the World Bank’s DPG matrix; and one on monitoring the PNDP (indicator 2.3). Other donors have expressed interest in learning from this as a way to provide additional funding to the PA. The Performance Tranche is currently not captured in the logframe since it is a mechanism to promote Output 2, but its uptake by other donors could potentially be tracked by an additional indicator under Output 3. The upcoming evaluation of the Statebuilding Grant will review the progress and further potential of the Performance Tranche as a mechanism to lever policy reform. / We chose the six performance tranche indicators to focus on core reform areas where we have robust data to make an assessment. The PA performed well having achieved 83% of its performance target (and thus receiving 83% of the amount set aside for 2013). The work on PFM reforms should continue on this strong basis. / In view of the DFID Partnership Principles being replaced; the importance of other aspects of state accountability towards its citizens; current Middle East Peace Process (MEPP) negotiations; and a new DFID-supported programme helping civil society to demand transparency and accountability from the PA, we will use our regular MoU Dialogue to consider how the PA can strengthen its accountability to Palestinian citizens. / Recommendations: / Once the PNDP has been finalised, take forward the previous recommendation of drafting a common results framework / Take forward previous recommendation of altering indicator 3.2 to reflect any aid effectiveness indicators in the common results framework, and the wider adoption of the Performance Tranche. / Discuss with the PA within the forthcoming MOU Dialogue the PA’s existing commitments to transparency and good governance. / Impact Weighting (%): 15 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No
[2] Please note that this percentage includes both humanitarian aid and budget support, which should not be included. We have raised this with the MoPAD, but at the time of finalising the annual review, we have not received the corrected figure. We will include this update in the revised logframe following this annual review.

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y / Following the first annual review of the Statebuilding and Service Delivery Grant to the Palestinian Authority (PA) in February 2013 it became clear that the logframe did not fully cover the scope of the intervention and would benefit from some amendments. This included the highlighting of the importance of service delivery to the programme, and subsequently a redistribution of weights to the outputs. Therefore, Output 1: Service Delivery increased from 50% to 60% and Output 2: Policy Leverage was reduced to 25%. / At Outcome levels, a new indicator that helps measure education was introduced: “Mean score obtained by students in monitoring learning achievement scores in Maths and Arabic for boys and girls”. This is also the same indicator used by UNRWA to measure education outcomes among refugee children so will enable us to make direct comparisons. The indicator on number of children vaccinated was moved to Output 1 and replaced with a new indicator on “Percentage of deaths caused by cancer, cardiovascular disease and diabetes”. This is a better reflection of the broad nature of health services and the result on people’s health outcomes. And finally, the indicator on “number of individuals receiving cash transfers” was removed as it was already included in Output 1. / At Output levels, an additional indicator on education was introduced to Output 1: “Number of non-refugee children, boys (M) and girls (F) supported by DFID in lower secondary education (grades 7-8).” This indicator helps better reflect the full nature of PA’s basic service delivery. Also, two additional indicators on Health were added, that better reflect the work of the whole sector, but that also are useful in making direct comparisons to UNRWA indicators. The “Number of pregnant women attending ante-natal care in the West Bank supported by DFID” is useful as ante-natal care is a core part of the Ministry of Health’s work and so functions as a good measure of the service they provide. The “Average number of daily medical consultations per doctor” is an efficiency indicator and helps to measure any changes in efficiency. / Output 1 recommendations will help with more precise definitions to avoid confusion and focus on PA’s own targets and reporting. / 1.2 Overall Output Score and Description: / Outputs met expectation (A) / 1.3 Direct feedback from beneficiaries / There are two types of beneficiaries: PA ministries and Palestinians receiving PA services. Feedback from PA ministries on DFID support is very positive. Feedback from Palestinians on PA services is mixed. / In terms of PA Ministries: / Ministry of Finance (MoF): we have had regular meetings throughout 2013 with the Minister and the Director General of International Relations. The Minister of Finance MoF expressed his appreciation not just for our support but the predictable way in which it is provided, with the UK-PA MoU setting out how much we will provide over three years, and our Business Case stating how our support is timed over the year. / Ministry of Social Affairs (MoSA): The Deputy Director General of Combat Poverty of MoSA stated that the help that donors provide is much appreciated. The PA however in some cases continues to struggle to provide the minimum levels of support due to ongoing fiscal crisis. And even though the UK does not provide financial assistance directly, it does this through its contribution to the PA and the MoF. The PA has had to reduce its targets to align with the fiscal constraints but there is an ongoing risk that the most vulnerable will not receive the required assistance. In December 2013, the PA’s own contribution to the Cash Transfer Programme was delayed to a shortage of funds. / In terms of Palestinians receiving services: / Education: Due to the process of developing a new education sector strategy, a number of studies were conducted; one of these was a ‘Diagnosis of the School Reality as Evidence Base for the Development of the Third Strategic Plan’. As a result of focus groups with students, it showed that students desire a more interactive approach to learning, which is not focused only on the blackboard. Also, the focus groups indicate a lack in freedom to participate in class, and too many exams and tests. There are still complaints relating to the curriculum and the provision of textbooks, which were also reflected in the 2012 Annual Education Sector Review and the Public Expenditure Report conducted in September 2013. These reviews provided a number of recommendations which have been addressed in the new education strategy for 2014-17. / Security: The PA has not publicly reported progress against its PNDP 2013 target on increasing public satisfaction with the performance and services of the security establishment. A number of polls point to positive levels of satisfaction with Civil Defence and the Police, less so with other security services, with UK-funded polling in 2014 showing public ratings of the security services being broadly in line with ratings the previous year. DFID is also offering the Palestinian Ministry of Interior support for strengthening monitoring and reporting, including in this area. The UK assesses that despite the financial crisis and the ongoing impediments posed by Israeli movement and access restrictions and limits to the jurisdiction of the Palestinian security forces, the PA has generally maintained an effective level of security service in the areas of the West Bank in which it can operate. / Health: In a recent survey conducted by USAID for one its projects, it looks at how beneficiaries see the delivery of health services to them. Although this study looks at Area C specifically, it is also indicative of general satisfaction levels of the population by Ministry of Health clinics. For example, 84% of people surveyed felt that their treatment provider was professional, 92% felt they had been treated courteously, 89% felt they were able to ask questions, and 90% felt that their questions had been answered clearly.
1.4 Summary of overall progress / Outcome – To improve the Palestinian Authority’s management of its financial systems and to provide better access to services for the Palestinian people / In the 2011/12 academic year, the net enrolment rates in primary school dropped from the 2010 baseline. In 2012/13, rates improved significantly. While the PA has not met the 2012/13 milestone, it has made significant progress. We have asked the Ministry of Education for an explanation of these findings and will mobilise expertise within DFID to provide further expertise to understand the reasons and potential support either directly or with other donors. / For most of the Outcome milestones it is too early to comment on progress. We expect to have an update on the fiscal impact of PFM reforms by mid-2014. / Outputs / Results funding – public services bought by DFID support / Overall, the PA has scored very well with overachievement in a number of indicators. Where data for the full year has not been available. The slight under-achievement on the drug shortages can be explained by the two-month UNRWA strike, which put huge additional strains on the Palestinian Authority’s health care facilities to provide medicines to those who would normally get them from UNRWA facilities. / (2) Policy leverage – improved PA systems and fiscal discipline, and spending more efficient / This component has performed well with over-achievement on the PA’s implementation of reforms agreed with the World Bank to reduce its dependence on aid and improve its public financial management; and the achievement of better reporting on the M&E. / It was not possible to report as originally envisaged against the implementation of the MoH and MoE efficiency action plans. The indicator depended on efficiency actions to be defined in the DFID Performance Tranche matrix, but this did not happen. The PGF TA did work, however, with the MoH to implement project-level activities to make progress against the agreed EAP, and these activities have been implemented to a good standard. / (3) Development effectiveness – aid to the PA is more predictable and results-focused / The Statebuilding Grant is providing predictable funding to the PA, and the Minister of Finance acknowledged DFID’s timely, predictable and sustained support. A key innovation that we introduced in 2012 and that has incentivised good performance from the PA, has been our Performance Tranche. Leveraging our support to improve the effectiveness of others’ aid remains a challenge, however in a highly politicised environment this can be expected.
1.5 Key challenges / The summary above highlights some of the key challenges to achieving the Outputs and Outcomes: / Lack of progress on the peace process: The peace process, spearheaded currently by US Foreign Secretary John Kerry, is currently ongoing with a deadline for both parties to reach an agreement (or framework agreement) by April 2014. However, this period in between is still fragile, as there is a general disconnect between the political processes at the higher level, and the people on the ground. Hence there is scepticism on both sides, and so reaching an agreement by the deadline is still viewed to be a difficult challenge, and the period after April remains unclear as to what new challenges it may bring. The IMF has said that success in peace negotiations could boost Palestinian economic growth while failure could cause increased debt. A breakthrough in talks would likely result in the launch of major donor initiatives, which could boost annual real GDP growth to around 6.5% in 2014-19, while continuation of talks inconclusively could lead to growth of about 2.5%. Failure, meanwhile, could trigger a political and security crisis that would lead to accelerated arrears accumulation and economic contraction, according to IMF predictions. / PA fiscal crisis and the impact of the Israeli occupation: The limited progress in the peace process means that the PA still suffers from lack of complete control over its finances and there remain movement and access restrictions imposed on the Palestinians thereby constraining the economy. In early 2013 the non-transferal of clearance revenues by the Government of Israel to the PA resulted in strikes by PA employees who weren’t receiving salaries thus effecting delivery of services to the Palestinian People. In terms of movement and access, the World Bank reported in October 2013 that Israel’s control over Area C in the West Bank deprives the Palestinian economy of an estimated $3.4 billion a year. The report added that Area C is where the majority of the natural resources lie in the West Bank, therefore creating a considerable impact on the Palestinian economy. The report concluded that "the key to Palestinian prosperity continues to lie in the removal of these restrictions with due regard for Israel’s security." / Aid policies: As was stated in the previous Annual Review, achieving the milestones achieving the milestones for more predictable and results-focused aid is constrained by donor aid policies, which can be difficult to change. However there is some scope for progress on this. The UK is working with the PA and donors to encourage a greater provision of financial assistance as a percentage of overall aid budgets and for this to be given over in a long term, predictable way. DFID is leading the way on this, as evidenced by output indicator 3.1, which shows a 100% achievement of full and timely disbursements to the World Bank Trust Fund. The Minister of Finance expressed his appreciation of DFID’s predictable and timely support. The link between our support to reform of policy and public financial management is difficult to directly link to improved services. Our evaluation of the Statebuilding Grant will offer options on how to assess this link drawing on broader DFID experience in evaluation budget support.
1.6 Annual Outcome Assessment / The outcome of the programme is: to improve the Palestinian Authority's management of its financial systems and to provide better access to services for the Palestinian public. / The previous Annual Review highlighted the challenge in achieving outcomes due to the difficult and complex financial situation the PA faced. The PA continues to face these difficulties, which are mostly due to political processes. Nevertheless, the PA has managed to maintain the situation and prevent deterioration in the access to services for the Palestinian public, in addition to implementing reforms in its Public Financial Management. As such, it is still likely that the project will be able to achieve most of its Output targets. However, achieving the Outcome as defined by the logframe targets is still challenging. / The table bellows shows the progress to date where data is available / # Indicator Baseline (date) Target (2015) Progress to Feb 2014 Comments / 1 Education: Primary net enrolment rate for boys (M) and girls (F) (%) 95.2% (M) / 97.9% (F) / (2010) 97.9% (M) 97.9% (F) 94.5% (M) 95.2% (F) -0.7%(M) -2.7%(F) / against 2010 baseline, but / +4.5 (M) / +0.3 (F) / against 2012 results / 2 Education: Mean score obtained by students (boys and girls) in Monitoring Learning Achievements in Maths (grade 8) and Arabic (grade 7) 45(M)61(F) Arabic 25(M)34(F) Maths / (2011) 62.5(M) 62.5(F) Arabic 53(M) 53(F) Maths 52.1(M) 67.7(F) Arabic 34.3(M) 43.5(F) Maths [2013] +7.5(M) +1.5(F) Arabic +9.3(M) +0.5(F) Maths / Against 2010 baseline / 3 Health: Percentage of deaths caused by cancer, cardiovascular disease and diabetes 54% 48% 57% [2012] Too early to tell, as MoH consolidates this data in April 2014 / 4 Security: Proportion of the public who are satisfied with the performance and services of the security establishment (%) 42% (2010) 57% - No updated data available / 5 Fiscal sustainability: Net present value (NPV) of money saved for the PA by reforms in DPG Matrices 2011-2014 and reforms promoted by education and health efficiency technical assistance ($m) 0 (2010) 100 - No updated data available / 6 Public financial management and accountability (PFMA): Fiduciary risk rating for PA PFMA system. High (2010) Substantial - The FRA is underway, data will be available by April 2014. / The target to improve the fiduciary risk rating of the PA’s public financial management systems from High to Substantial depends upon whether mechanisms of external accountability over the budget are developed, which was identified as the main risk in the 2010 Fiduciary Risk Assessment. Even if there is no progress in re-establishing a legislature, if progress continues to be made in reforming and strengthening the auditor general, this risk will be mitigated. A new Fiduciary Risk Assessment underway in 2014 shall provide new evidence of progress made. / As the table above shows, net enrolment rates have picked up significantly since the last AR and the dip in the first milestone (2012) against the baseline. The PA’s targets in the PNDP for enrolment in basic education remain ambitious. The decision taken in last year’s AR to extend the target year from 2013 to 2014 in line with the duration of the Statebuilding Grant appears to have been a good one, as the current trend shows improvements. However, without an end to the occupation it will be hard for the PA to meet the very ambitious targets it set itself in the PNDP. We will discuss with the PA what it considers to be achievable. / We have used public polling to monitor the indicator on public satisfaction with PA security forces, which was reported as difficult to measure in the last AR. Therefore the PA needs to be encouraged to make this data available and as robust as possible.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / The primary cost drivers that were identified in the Business Case were concerned with the procurement of consultants for the Performance Tranche, Results Framework and the Independent Evaluation. The key drivers identified were the level of expertise and experience of consultants on monitoring and evaluation. The previous Annual review did state that it did not prove necessary to bring in a consultant for the Performance Tranche; however, a consultant has been hired to do a preliminary study that will feed into the evaluation. Furthermore, a company has been contracted to do an independent evaluation of the Statebuilding Grant programme and will provide recommendations on our future support to the PA. All procurement has been undertaken in line with DFID procurement rules to ensure value for money. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There have not been any major changes in evidence related to the Theory of Change which might affect the design and rationale for the project. Going briefly through the main aspects (with the labels for the Theory of Change assumptions given in brackets): / Impact of aid on PA public services (A, F): the immediate impact on public services of any shortfall in resources to the PA has been demonstrated in late 2012 and early 2013, due to the large funding shortfall and suspension of clearance revenues by the Government of Israel. The PA was at first unable to pay salaries in full at the beginning of the year, having to pay them later in the month once more funds were available. Then as clearance revenues were suspended from late November 2012 it was unable to pay more than 50% of salaries each month. This was no doubt a contributing factor to the strikes in January 2013 which resulted in PA staff only coming to work two days each week. According to the WHO, the UNRWA strike in late 2013/early 2014 impacted on the stock levels of essential medicines running low, as Palestinians who would normally get their medical supplies from UNRWA turned to the PA instead. While the impact on medication stocks was negative, it does show that the PA is providing an essential service to Palestinians. / Increased appreciation of public services (J): we currently do not have any evidence to prove that the assumption that increased funding results in increased appreciation of public services provided by the PA. It would be useful to collect evidence during the final project year. / Impact of the World Bank PRDP Trust Fund on improving PA systems (B, C, D, G, H): The evaluation will look in detail at the link between the WB Trust Fund and progress on reforms. / Impact of PA spending and services on poverty, growth and employment (O, P): The evaluation will provide evidence as to the impact of PA spending and services on the above mentioned areas. / Impact of PA spending and services on building a peaceful Palestinian state and society (R, T): the Strategic Case of the Business Case outlined that “By supporting the delivery of public services, and underpinning the Palestinian economy, we are supporting the survival and success of a pro-peace Palestinian leadership. This is particularly important at such a fragile time in the peace process. If the PA were to collapse, this would undermine voices of moderation and potentially precipitate a return to violence.” The UK Government is strongly encouraging and working in support of serious efforts to move forward with the peace process in 2014. We will also review our Operational Plan in 2014 in order to assess the evidence on the state of the peace process and whether the balance of the programme remains appropriate, including financial assistance to the PA. We will use the findings of the evaluation to shape any further potential support to the PA after March 2015 when the current programme ends. / 3.2 Where an evaluation is planned what progress has been made? / An independent evaluation of Statebuilding Grant programme is due to start shortly. An independent company, Fiscus Ltd., has been contracted to conduct this evaluation. We expect the full evaluation report with recommendations by August 2014. / The evaluation will review progress on results and consider options for future support to the PA. It will take into account to what extent value for money, policy reforms, sustainable development outcomes and improved public satisfaction with the performance of the PA are being achieved.

4. Risk
4.1 Output Risk Rating High / In the original Business Case, we assessed the overall risk as high due to the high risk environment and the project design. The key country level risks identified in the Operational Plan that could affect the delivery of the Statebuilding Grant remain: / Stalling of failing of the Middle East Peace Process to the point where a two-state solution is no longer viable; / Losing the PA as a credible and acceptable partner for peace; and / Conflict, civil unrest, settler violence or terrorist threats/attacks in Gaza, the West Bank and/or East/West Jerusalem raising the security threat level, with consequences for both staff duty of care and programme delivery. / 4.2 Assessment of the risk level / We assess project-level risks to the successful delivery of the Statebuilding Grant on a continual basis. In monthly meetings we flag any key changes to the risks and monitor risk mitigation actions, and on a quarterly basis we update the project Risk Matrix. There are three key project-level risks that are either High probability Medium impact, or Medium probability High impact: / • Suspension of parliament means lack of legislative scrutiny of the budget: see section 4.3. / • Salaries are paid to PA officials in Gaza who are unable to work: see section 4.3. / Also on a quarterly basis we assess country-level risks to the successful delivery of our Operational Plan, many of which affect the Statebuilding Grant. The key risks that are most relevant to the Grant are the following: / • Lack of progress in Middle East Peace Process: see section 3.1 above. / • PA does not meet our partnership commitments: see section 6 below. / • PA capacity insufficient to deliver results: the key risk here currently is that the PA’s fiscal crisis prevents it from being able to function effectively. We consider that this is now a High probability and a High impact, in that the current withholding of clearance revenues is having a serious effect on PA salaries and services. We are working very closely with the FCO in monitoring the PA’s fiscal crisis and taking action with the Government of Israel, donors and the PA itself to help address all aspects of the problem. / 4.3 Risk of funds not being used as intended / We continue to monitor the seven fiduciary risks identified in the 2010 Fiduciary Risk Assessment, these were 1) The suspension of the Parliamentary Legislative Council (PLC) means that there is no legislative scrutiny of budget preparation and execution; 2) Weak arrangements and poor performance by the MoF in collecting and enforcing domestic tax and non-tax revenue results in significant under-collection; 3)Salaries continue to be paid to PNA officials (civil and security) based in Gaza who are unable to work due to the political situation; 4) Limited expertise in cash forecasting, coupled with unpredictable flows from external revenue sources, especially donor financial support, means that there remains scope for incurring expenditure arrears; 5) There are weaknesses in, and some non-compliance with, the regulatory framework for carrying out procurement; 6) Limited capacity of civil servants impacts on the efficient and effective use of resources and may render PFM reform initiatives unsustainable; 7) Given on-going political instability, there is uncertain government ownership of the reform programme. / The most recent Annual Statement of Progress against these risks judged that the overall fiduciary risk rating remains High with a positive trajectory, and the risk of corruption remains Substantial again with a positive trajectory. We continue to judge that in practice the risks of providing assistance through the PA’s budgetary systems are acceptable for two reasons: / The budgetary systems of the PA itself are good and have been praised by the World Bank and IMF, with the overall fiduciary risk rating made High by issues external to them (lack of legislature and weak external audit). See reporting on Output 2.1. / The corruption risk rating is based on the anti-corruption systems that are in place rather than the actual incidence of corruption which is much lower than other countries in the region as evidenced by the World Bank ‘control of corruption’ data for the West Bank and Gaza up until 2012. / Of the seven risks, the two highest risks are the following: / Suspension of parliament means lack of legislative scrutiny of the budget: there is no parliament due to political reasons outside of our control - the lack of reconciliation between Fatah in the West Bank and Hamas in Gaza. We are therefore seeking to strengthen accountability over the budget through three other mechanisms: our ongoing Supporting Stability and Promoting Democracy project which strengthens civil society to hold the PA to account and works through Palestinian civil society; increasing budget transparency through the World Bank’s reform agenda with the PA supported by the World Bank PRDP Trust Fund; and ensuring that issues raised by the annual audit of the PA’s accounts by the auditor general are acted upon, through our continued co-funding a World Bank expert in public financial management to follow up on this. / Salaries to PA civil servants in Gaza who are unable to work: There are a number of PA civil servants in Gaza who are unable to work following the 2007 take-over of Gaza by Hamas but continue to receive salaries. These people are not on strike – despite wanting to work, they have been prevented from returning to their jobs by Hamas. We need to ensure the PA is able to fulfil its functions as the legitimate authority in Gaza. The fact that the PA is paying their salaries until they are able to return to work provides an essential safety net from further poverty and suffering. We are monitoring the situation closely together with the EU, World Bank and IMF. The latest report by the EU Court of Auditors, although positive of budget support to the PA, also questioned this element. Where possible, the PA has undertaken some difficult steps to reduce the allowances that are not directly related to salaries such as travel. We support the EU’s response and agree that support to PA workers in Gaza helps to maintain stability and strengthen the moderate PA leadership. Such an approach ensures the greatest chance of delivering a negotiated two state solution. / In order to track our finances even more closely, we introduced additional safeguards into our payment mechanism during 2013. We continue to pay our contributions to the World Bank PRDP Trust Fund and have agreed notional earmarking of these funds bilaterally with the PA. We can now specify for which individuals we are paying salaries; can allocate funding to PA salaries in general; and can also specify for which sectors we would like to pay salaries in future. The PA has contracted an international audit firm, from which we receive confirmation of how our funds are being spent. UK funding to the PA is used exclusively to pay the salaries of civil servants. UK money is not used to fund Palestinian prisoners or their families. We support the PA because we strongly believe that it is a firm partner for peace in the region. / Possible reconciliation between Palestinian factions: this could create uncertainty with regards to our funding. Should a technocratic government be formed it is likely that funding would continue as before as long as it upholds the principle of non-violence, is committed to a negotiated two-state solution and accepts previous agreements of the Palestinian Liberation Organisation. The UK has made it consistently clear that we will engage any Palestinian government that shows through their words and actions that they are committed to these principles. Should a national unity government be formed which includes Hamas we would have to re-examine the provision and modalities of any financial support. / As part of a stocktake of risks for our new Anti-corruption Strategy, we have added two additional fiduciary risks explicitly related to corruption: one about corruption at the level of service delivery; and one about PA staff fraudulently claiming benefits e.g. use of official mobiles for personal calls. We judge the probability and impact of the first to be Low since all evidence suggests that bribery is much lower in the OPTs compared to other countries in the region. We judge the probability and impact and impact of the second to be Medium given public debate about the issue, and are in discussion about it with the Ministry of Finance about the steps they are taking to address it. / A new Fiduciary Risk Assessment is underway as of February 2014 which will provide us with an update on the PA’s systems. We believe the safeguards described above provide us with maximum assurance but will review in the light of the Fiduciary Risk Assessment. / 4.4 Climate and Environment Risk (no change from the 2013 annual review) / The Business Case sets out the inherent risk that the lack of treatment of environment and climate issues as cross-cutting issues within the Palestinian National Development Plan will be further compounded by the provision of non-earmarked funds. It explains that this could be countered to an extent by active policy engagement by DFID with the PA and other donors on environment and climate, and the consideration of use of some of the funds towards technical assistance to specifically raise the profile and capacity as regards environment/climate across the Palestinian government. An SEA (Strategic Environmental Assessment) of the PNDP could be considered as a key element of such Technical Assistance to assess the full impact (both positive and negative) that the PNDP could have on the environment/climate. The Business Case also states that we could seek to use our policy dialogue with the PA to promote a more integrated approach to the environment which has been identified as a key weakness.

5. Value for Money
5.1 Performance on VfM measures / The Business Case identified poverty in the OPTs and promoting a peaceful Palestinian state and society as unit costs that would be tracked following our initial baseline study of costs between 2008 and 2010 and compared with UNRWA in the West Bank. / • Economy: salaries in health and education; medicines. / • Efficiency: cost per outpatient visit to a primary healthcare clinic; cost per child in primary education. / As reported in the last annual review, establishing the systems within the Ministry of Health and Ministry of Education to agree and track these unit costs and use them to inform decision-making was held up by the delay in them approving their efficiency action plans which set out the steps they plan to take with assistance from DFID and other donors. After identifying the main efficiency improvement areas with and a key list of data needed to undertake efficiency analyses with the Ministry of Health, the PGF TA is now working on data generation in the following areas: cases/visits and costs relating to referrals, non-communicable diseases and infection prevention. / DFID centrally has been reviewing research into measuring the value for money of direct financial assistance. The upcoming evaluation will draw on this work. Key questions for the evaluation will include: / What is the value for money of budget support to the PA through the SBG? / Economy: How do the PRDP-MDTF fees compare to other multi-donor trust funds, and how cheaply is the PA purchasing inputs in health and education? / Efficiency: How efficiently is the PA providing health, education and social protection services? / Cost effectiveness: How cost effective are PA health, education and social protection services? / Economic return: What is the potential range for the economic return, from varying those assumptions for which there is weak evidence? / 5.2 Commercial Improvement and Value for Money / Direct procurement / As outlined above, an evaluation of the Statebuilding Grant will allow us to make a fuller assessment of the value for money of our support to the PA and provide evidence for future programming decisions. Fiscus Ltd. Has been contracted to carry out this work. The commercial assessment of Fiscus Ltd. demonstrated value for money in relation to the current market. The proposal offered a good mix of technical inputs with competitive rates in terms of qualifications and experience. All costs including administration, travel and expenses were within published budget and offered at competitive market rates. A good financial plan was provided which clearly linked payment to outputs. / Indirect procurement / Having approved a new procurement law in July 2011 to adopt international best practice, during 2012 the PA has taken positive steps to implement it. In September the Cabinet approved establishment of the Higher Council for Public Procurement. This is a significant progress in a key reform that will improve accountability, integrity and transparency of the public procurement system. The Council will be the main regulatory body in charge of an efficient implementation of the law, and is currently focused on finalising the regulations of the law. As of January 2014, these regulations have not yet been presented to the cabinet, and hence have not been enacted yet. The World Bank is considering procurement in its mix of reform priorities with the PA. / 5.3 Role of project partners / The World Bank continues to operate the PRDP Trust Fund effectively and efficiently. In 2012 they altered their financial procedures to enable donor funds to be transferred more quickly. They continue to charge their minimum fee of 1.55% to administer the Trust Fund. In January 2014, the World Bank began procedures to extend the Trust Fund for another three years, starting February 2014 and ending August 2017. As part of the upcoming evaluation, DFID will assess the role of the World Bank in helping to incentivise the PA to deliver reforms and indirectly, improve service delivery. / As previously outlined, the UK’s relationship with the PA is governed by a robust MoU which centres on mutual accountability, good governance, transparency and commitment to non-violence. The next formal MoU Dialogue meeting will take place in March 2014 and will be an opportunity to reflect on this annual review and raise key issues such as the PA’s performance on primary education. The dialogue will also be an opportunity for the PA to hold the UK to our commitments on aid effectiveness. / 5.4 Does the project still represent Value for Money : Y / The project is performing well in delivering the expected Outputs with an overall score of A and positive feedback from PA beneficiaries. The Theory of Change remains valid. Maintaining access to public services at the current high level is an important objective both for reducing– Given the PA’s substantial revenue shortfall, without the Statebuilding Grant and support from other donors, public services would be much weaker and the PA would be unable to fulfil its duties to its citizens and as a partner for peace. / 5.5 If not, what action will you take? / Not applicable.

6. Conditionality
6.1 Update on specific conditions / In keeping with DFID policy on budget support, our main means of assessing and managing risks from UK financial assistance to the PA is through five partnership commitments agreed to in our Memorandum of Understanding with the PA. These cover the standard four commitments required by DFID (on poverty, governance, human rights and domestic accountability) plus an additional commitment to non-violence and a negotiated two state solution. The annual MoU dialogue with the PA will be held on February 28th 2014, when we will be able to assess if the PA is meeting its commitments.

7. Conclusions and actions
The Statebuilding Grant is performing well against expectations and continues to represent good value for money. The following is a summary of recommendations outlined in this annual review: / Outcome indicators / Education: DFID to mobilise internal education expertise and work with the PA to understand the issues relating / Output Indicator 1. Results funding – public services bought by DFID support / Use “number of children” and “number of individuals” supported by the PA with DFID funding (to capture all those benefitting from PA service provision regardless of their refugee/non-refugee status) in the definitions of indicators 1.1, 1.2 and 1.7. / Remove indicator 1.3, as it is not based on official PA reporting. / Discuss with the Ministry of Health and WHO if there are any practical measures to bring drug shortages down despite the PA financial shortfalls. / Review the selection of health and education indicators with support from DFID Health and Education Advisers and in discussion with the Ministries of Health and Education and the Sector Working Group to ensure that a successor programme to the SBG reflects the key issues the PA is facing and addressing in these sectors. This work should be completed by the end of June 2014 to feed into our CPRD and business case planning. / Check with the Ministry of Social Affairs what has caused the vast increase in Palestinians claiming cash transfers and how the underlying poverty issues can best be addressed in future. / Output Indicator 2. Policy leverage – improved PA systems and fiscal discipline, and spending more efficient / Update the logframe to reflect the World Bank’s ICR report that assesses the PA’s performance against the DPG V matrix, this report will be available in May 2014. / Agree with the PA, World Bank other donors the degree and source of potential TA to support the PA in improving its annual audited accounts. Consider whether this might be an added activity under the existing PGF programme which seeks to improve the PA’s overall financial management capacity. This could include, but need not be limited to, discussing the use of the full financial accounting data base for both monthly and annual accounts to improve the accuracy of the accounts with the MoF. There is a need for the TA to help decide how far this is feasible without sacrificing the timeliness of the monthly reporting. / Discuss the 2014 milestone and 2015 target with MoE and MoH and the PGF TA team to make it more realistic based on an assessment of remaining activities. Set ambitious but achievable targets within three months of this annual review for both Ministries to achieve them in the remaining time of the programme. / Development effectiveness – aid to the PA is more predictable and results-focused / Once the PNDP has been finalised, take forward the previous recommendation of drafting a common results framework / Take forward previous recommendation of altering indicator 3.2 to reflect any aid effectiveness indicators in the common results framework, and the wider adoption of the Performance Tranche. / Discuss with the PA within the forthcoming MOU Dialogue the introduction of broader transparency and accountability targets focusing on constructive dialogue with Palestinian citizens.

8. Review Process
The review was drafted based upon the following information sources: / DFID meetings with the Ministries of Finance, Health and Education in December-February 2014; / Monitoring reports and studies referenced in the text. / Conducted by DFID Jerusalem Statebuilding team (in particular Nicola Neuss, Interim Governance Adviser, and Buraq Nuseibeh, Programme Officer, DFID Jerusalem) and Head and Deputy Head of Office