Annual Review – post April 2018

Title: Health Transitions: Improving Reproductive Maternal and Child Health (RMCH) outcomes in Mozambique
Programme Value £ (full life): £34.4 million		Review Date: November 2017
Programme Code: 205074	Start Date: Nov 2016	End Date: March 2020

Summary of Programme Performance
Year	2017	2018
Programme Score	A	A
Risk Rating	Medium	Medium

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4833405.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/21215984.xlsx

A. Summary and Overview

Description of programme
The Mozambican health sector saw reductions in under five and maternal mortality rates of 46% and 58% respectively between the years 2000 and 2015 to 71/1,000 and 489/100,000. This was above the regional average.[1] Despite improvements in maternal mortality, 30 women a day continue to die either during childbirth or from complications associated with childbirth. Factors contributing to this include: the lack of health facility readiness in terms of unqualified staff and ill equipped health centres, a high number of women still giving birth at home and poor health of mothers. The latter is caused by the high burden of communicable diseases in Mozambique, which is above the regional average. The prevalence of HIV& AIDS for example was 12.3% in 2016 up from 10.4% in the year 2000. Malaria on the other hand still accounts for the most deaths resulting in 29% of all hospital deaths and 42% of infant deaths[2].
[1] UNICEF (2018) Health Budget Brief.
[2] Malaria Consortium (2018) Malaria surveillance system performance in Mozambique: a comprehensive assessment. Technical Brief.

The Reproductive and Maternal Health business case (BC) worth £34.4 million approved in September 2016, aims to contribute to reducing maternal mortality in Mozambique. It will do this by helping women to prevent undesired pregnancies through greater access to reproductive, maternal and child health (RMCH) services. This would be done through three main components:
- £23.5 million channelled through the UN Joint Programme (WHO, UNICEF and UNFPA) for strengthening service delivery and improving the quality of primary health services delivered by the Ministry of Health (MoH). This component funds a part of the Reproductive and Maternal Heath Investment Case which is also funded by the Global Financing Facility (GFF). It is therefore largely focused on supply-side interventions.
- £7.5million to generate demand for family planning with a particular focus on adolescents. This has now been increased to a total of £8.5m shared between two projects as set out below.
- £3.3million to improve coordination and coherence of all UK investments in the health sector and capture lessons from the programme. This included using the technical assistance funds for consultancies to that supported our influencing agenda. This figure has been drastically reduced to £400,000 a result of recommendations from Ministers during the approval of the business case and further reductions during the portfolio quality review process.
- £2 million to WHO for emergency preparedness.

In this second year of the UN Joint Programme the pace for implementing interventions picked up. As a result, the effect of interventions at district level in particular is beginning to be felt, leading to requests for additional financial and technical support from health authorities. The UN agencies have provided technical support ranging from prioritisation and planning of activities to implementation and monitoring at national, provincial and district level.

Due to the on-going political and economic crisis in Mozambique, the context for the programme is challenging The fiscal crisis is is affecting recurrent costs such as salaries, purchase of goods and services, supervision and distribution of medicines. Qualified human resources have continued to leave, preferring the private sector or NGOs who offer high remuneration. In response to a request from the Ministry of Health, DFID supported a consultancy to explore how to retain existing staff and attract new personnel to the sector (see section F below).

Despite this staff attrition, sector spending on personnel has increased above the rate of inflation. Recurrent costs accounted for 79% of the budget this year, an increase of 35% from a decade ago[3]. This highlights changes in the composition of the budget. While the Government covers recurrent costs, partners pay for investment costs consisting of capital investments, medical devices and training of staff. As the budget no longer includes donor funds which are increasingly off-budget, it is difficult to track the contribution of donors to the sector. As a result, although Government allocation (8.7% equivalent to £326 million) to the sector was a larger proportion of the budget in 2018 (up from 7.8% the previous year[4]), there is still a lot of reliance on off-budget donor support which accounted for 67% of the investment funding[5].
[3] UNICEF (2018) Health Budget Brief.
[4] UNICEF (2017) Health Budget Brief
[5] UNICEF (2018) Health Budget Brief.

Donors have become increasingly fragmented in their support. As partners have left or decreased their support to the Common Fund, alternative off-budget mechanisms to channel funds have been set up. Low Government capacity and leadership at the MoH has meant that each of these financing mechanisms has their own programme management unit (PMU), all placed within the MoH. The management burden of these PMUs for the Government is huge.There is currently a revision of the coordination mechanisms taking place, led by WHO.

Summary supporting narrative for the overall score in this review
The focus of the business case over the last year has been on the supply side through the UN Joint Programme. The overall BC now has five components, four of which are programmes and one technical support. One of the programmes scored an A+ and two an A. As the UN Joint Programme has a weighting of 80% in the logframe to reflect the focus on this programme over the last year, this has meant that although the other two components moderately did not meet expectations (B) and substantially did not meet expectations (C) the overall score for the year was an A.

The pace of implementation for the UN Joint Programme has picked up ranging from procuring commodities and equipment to supporting reforms, training nurses and delivering water, hygiene and sanitation (WASH) in health care facilities. The UN’s added value of supporting planning and prioritization of interventions at national and subnational level followed by the provision of technical and advisory support a the subnational level is leading to results, despite the increasingly resource-constrained environment.

The £7.5m demand side component has taken longer to start than initially planned, with PSI signing a £5.5m contract in August 2018, largely due to delays on DFID’s side in terms of the procurement process. For the second demand-side programme, the UK Government has opted to channel £3 million until December 2019, to the UN programme ‘Action for Girls and Young Women’ (known locally as ‘Rapariga Biz’). The programme works with four Government Ministries to deliver a comprehensive set of social behaviour change interventions that show potential to make a substantive impact on improving girls and women’s reproductive health and rights. The programme currently supported by Sweden, seeks to increase contraceptive use and reduce the number of unwanted pregnancies among adolescents in Nampula and Zambezia. Funds will be channelled to the UN (UNFPA, UNICEF, UNESCO and UN Women) Joint Programme, which includes £1m that has been reallocated from the programme management and coordination component of the business case. This brings the total for the demand-side component, to £8.5m.

Supporting an established programme offers the additional advantage of contributing to greater coherence in the family planning sector. Additional investment will strengthen the evidence base to understand which interventions are most cost-effective, improve coordination between the sectors, support more sustainable and transformative results through complimentary interventions that engage men and boys and scaling-up livelihoods/skills activities. Additional funding will also ensure the programme reaches the most vulnerable groups, including by strengthening work on disability inclusion across programme interventions. Programming is due to commence in October 2018
The constant disruption of routine service delivery due to annual disease outbreaks were also considered in the business case. DFID initially tested this by supporting WHO with $400,000 to respond to the cholera outbreak in Northern Mozambique. This was expanded in scope and value (up to £2 million) in August 2018 to include more systematic support to for disaster preparedness and response.
This business case is being implemented by 3 staff members - the Health Advisor who is also the Senior Responsible Owner, a Social Development Advisor dedicating part of their time to the Rapariga Biz Component, and a Project Officer responsible for programme management. This team is referred to as the “programme team” throughout the document.
Recommendations for the year ahead
The main recommendations to the programme are to ensure more lesson learning and communication between the demand and supply –side components and ensuring the risk register is part of the quarterly discussions with partners, particularly the UN. Below is a summary of the main recommendations for the year ahead:

	Recommendation	Responsible / Deadline
	Linked to Outputs 1 to 5
1	UNFPA to strengthen the delivery of long-term family planning methods in the maternal and child health (MCH) training curriculum.	UNFPA - August 2019
2	Discuss with the Ministry of Health how to ensure newly recruited MCH nurses are employed	UN/DFID – May 2019
3	Revise the logframe indicator for output 1 to measure quality	DFID /UN – March 2019
4	Hire staff to support supply chain and distribution– ensuring commodities are cleared from the port on time and then quickly distributed to where they are needed.	UNFPA – June 2019
5	WASH and Health teams to work together to accelerate the implementation of WASH in health centres.	DFID/ UNICEF - March 2019
6	Discuss how to improve the regularity with which subsidies are paid and increasing the quantity given with the Government.	DFID/ UN – May 2019
7	Discuss prioritising supervision at the district level with the UN and Government	DFID/UN –May 2019
8	Ensure greater collaboration between PSI, Rapariga Biz and the UN Joint Programme.	DFID/UN April 2019
9	Raise concerns with WHO about the delays in contracting staff and request measures to accelerate programme implementation.	DFID – December 2018
10	Expedite the speed with which UpScale is being rolled out in Zambezia province	UNICEF – June 2019
	General Recommendations
11	Revise the logframe to include the demand side components and reduce the number of outputs from the UN Joint Programme	DFID – December 2018
12	Assess whether the theory of change needs to be reworked and/or we take up the human resources issue at the highest levels and work with other partners to find a solution	DFID- February 2018
13	Evolve the theory of change to consider how the programme needs to flex to leverage results from other big funding channels	DFID – February 2019
14	WHO Programme to be put on a three month performance improvement plan after which a decision needed to be made with Management on whether the programme should continue	DFID – December 2019
15	Support the UN to improve their VfM indicators for the Joint and Emergency Preparedness programmes and include indicators to capture how under-served groups like people living with disability are benefitting from interventions.	DFID – March 2019
16	Include better safe-guarding risks in the risk register for the UN Supply-Side ensuring they consider all the areas where there are vulnerabilities in the system. This should be updated once the enhanced due diligence is complete.	DFID/UN- December 2018
17	Discuss risks more regularly (at a minimum on a quarterly basis) with the UN and use the risk register as a management tool.	DFID/UN – December 2018
18	Update the risk register with the issues mentioned in the programme management section of the mid-year report (page 17).	DFID/UN December 2018
19	Have a discussion with management about revising the risk assessment for the entire business case from Medium to High given the external risks to the programme	DFID – December 2018
20	UN to send the annual report and workplan to the Government at least a week before the Coordination meeting between the National Directors, UN agencies and DFID	UNICEF – May 2019
21	Programme team to discuss with management whether to extend the entire business case to August 2021 to align with the extension of the PSI Programme.	DFID – December 2019
22	Programme team to develop a systematic plan for spot checks and field visits next year.	DFID – December 2019
Recommendations that still need to be acted on fro previous annual review
23	Set up a Governance Structure for the RMNCH Investment Case that oversees the different funding streams for RMNCH including DFID’s. This will imply discussing with the World Bank about the GFF’s convening role	DFID/UN – June 2019
24	DFID to ensure strong links between the Demand for Family Planning (OJEU) component and the innovation and coordination component through MoU agreements if possible, and if not by informal coordination mechanisms.	DFID – February 2019
25	DFID Health and Governance teams to agree an effective way to get beneficiary feedback to verify the performance of the programme.	DFID – June 2019

## B: DETAILED OUTPUT SCORING

Output Title	Enhanced availability and quality of trained midwifery workforce at national level by 2020
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Revised since last AR?	Yes (increased by 10%)

Indicator(s)	Milestone(s) for this review	Progress
Number of maternal and child health (MCH) nurses available in health facilities	200 MCH nurses enrolled into pre-service training	Exceeded: 246 nurses enrolled since the programme began

Provide supporting narrative for the score

A total of 246 pre-service MCH nurses have been enrolled into the project: 153 in 2017 and 93 in in 2018. This figure doesn’t include the MCH nurses that were enrolled into health promotion courses that provide experienced nurses with broader health prevention competencies. MCH nurses represent 70% of the workforce in the sector, supporting the delivery of services in primary facilities and referral health centres[6]. However, on average the workload in primary health care facilities is high, with a MCH nurse serving 30,442 people in a basic health care facilities and 19,685 people in a rural hospital when they should be serving a maximum of 6,000 people on average[7].
[6] MISAU (2018) O estado da força de trabalo de enfermagem no SNS em 2017 (Presentation from the Department of Human Resources at the Ministry of Health shared with partners on the 24th September
[7] MISAU (2018) O estado da força de trabalo de enfermagem no SNS em 2017 (Presentation from the Department of Human Resources at the Ministry of Health shared with partners on the 24th September) good to include data sources. How confident are we in them?

The first group of MCH nurses will graduate in June 2019. The training consists of both theoretical and practical classes. As part of the latter, the students stay with local families in the communities they will be serving in for a few weeks. This allows the students to build relationships and have a better understanding of the socio-cultural dynamics where they will work.

The programme is improving the quality of the training by upgrading the medical and IT equipment in 11 institutions across nine provinces. UNFPA purchased equipment based on a needs analysis undertaken in 2016. In June 2017, the programme team saw in Massinga Training Centre in Inhambane Province, how the lack of equipment was undermining the training. The models of human body parts for students to practice invasive procedures were damaged or of insufficient number.

This output is not yet measuring quality because the emphasis of implementation has been on providing the inputs needed to improve this output. However, next year the results of these investments should be measured to assess if they are having the desired outcome on quality.

Lessons identified this year, and recommendations for the year ahead linked to this output
The training has to focus more on the insertion of long-term methods of family planning. The programme team saw at a recent field visit in Zambezia province, how the use of intra-uterine devices (IUDs) in a rural hospital was low because the nurses are not confident at inserting them.

Health authorities in Zambezia province reported that newly graduated MCH nurses are staying at home because the Government is unable to pay for their salaries. The nurses run the risk of losing their skills as they are unable to practice. In the meantime health care facilities continue to be understaffed. A policy discussion among partners at technical level and above the sector is needed to assess options to resolve this issue.

Recommendations
- UNFPA to strengthen the delivery of long-term family planning methods in the MCH Training Curriculum.
- DFID and UN to discuss with the Ministry of Health how to ensure newly recruited MCH nurses are employed.
- Revise the logframe indicator for output 1 to measure quality
- Convene a meeting with Head of office to formalise our concerns and share options on the way forward regarding the human resources situation in the sector.

Output Title	Improved facility readiness to provide essential and emergency obstetric and neonatal care (EMoNC), including safe abortion care and life saving commodities by 2020
Output number per LF		2	Output Score A+
Risk:		Medium	Impact weighting (%):25%
Risk revised since last AR?		Yes (reduced from Major)	Impact weighting % revised since last AR? Yes (increased by 15%)

Indicator(s)	Milestones	Progress
2.1Number of health facilities equipped with (i) ambulances and (ii) emergency obstetric and neonatal care (EmONC) Kits	(i) 26 ambulances (ii) 3 out 7 EmONC Kits procured.	Exceeded:(i) 32 ambulances procured by May 2018 (ii) Kits arrived in May 2018, now in distribution.

(i)The programme purchased 31 ambulances, five more than planned. UNICEF decided to purchase additional ambulances, to off-set their low expenditure on commodities in the first half of the year. This will not affect the total number of ambulances to be procured by the project (51), which will not change. The Government has committed to cover the maintenance costs of the ambulances. However, given the resource-constrained environment in the sector, the programme team need to monitor if they will have the ability to honour this commitment.

(ii) £3.1 million worth of kits arrived in March 2017. The EmONC kits include all the material for C sections, sterilisations and post-abortion care, delivered in bundles. Health centres lacked EmONC equipment having to transfer cases to referral health centres with the risk that some women might die along the way. UNFPA and UNICEF carry out spot checks of all the equipment and commodities purchased to ensure they reach their destination and are used for the intended purpose. They will be hiring additional staff to strengthen this monitoring.

Lessons identified this year, and recommendations for the year ahead linked to this output
One of the lessons from implementation this year has been that the Government needs oversight and support in managing the distribution chain of commodities and medicines more closely. The equipment that arrived in May 2018 is only being distributed to the districts now. Another effect is the stockout of injectable contraceptives (depo provera) in Zambezia province because these are not being distributed from the Central Warehouse when requested. Some community health workers in Zambezia mentioned that they had not had injectables in in their working kits for the past 2 months.

Recommendation
UNFPA to hire staff to support the distribution chain more closely – ensuring commodities are cleared from the port on time and then quickly distributed to where they are needed.
The programme team to discuss maintenance of ambulances with the Government on a regular basis.

Output Title	Improve health infrastructure, focused on closing water and sanitation (WASH) gaps in primary health care (PHC) facilities with maternities by 2020
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Number of primary health facilities provided with adequate water and sanitation services in priority districts	Agree the WASH standards for different kinds of health centres	Achieved: Standards agreed with the health and infrastructure sectors.

In the past year, UNICEF focused on agreeing the standards for Water Sanitation and Hygiene (WASH) services to be used in different kinds of health care facilities. A preliminary survey of a sample of 34 health centres in Zambezia and Nampula provinces was undertaken to identify their WASH needs. Results from the survey were then used to define standards to be used for WASH equipment in health centres. After much negotiation between the Ministries of Public Works and Health with UNICEF, there was agreement to use different standards for different kinds of health centre. For example, a rural hospital with laundry room, kitchen and surgical ward will require water in all these facilities.

This indicator did not have a target as UNICEF was still assessing what this should be. The proposal estimated that 100 Health Centres would be constructed. This was revised down to 50 last year and after agreeing the standards will now be 30. The initial estimate had relied on a minimum standard to be applied to all health care facilities, which is now not the case.

The discussions also included agreement on the criteria for selecting health centres to benefit from WASH facilities. These are:

- The district has to be one of the 42 prioritised in the RMNCH Investment Case,
- The coverage of WASH services in the district,
- Population served by the health centre and,
- Distance from the furthest household to the health centre.

Government with technical support from UNICEF have launched a procurement process to identify a company to construct the WASH systems in the health centres.

Having safe water and toilets in health centres is important to prevent and control infections particularly for newborn babies. Health workers also miss the opportunity of demonstrating how to prevent infections.

Lessons identified this year, and recommendations for the year ahead linked to this output

The collaboration between the Ministries of Public Works and Health at provincial level has been strengthened. However, it has taken a long time as discussions on the standards occurred at national level whereas the implementation will be in the two provinces. Nevertheless, having WASH standards for all health care facilities whether they are supported by donors or the Government is significant. UNICEF will be documenting this process to learn lessons and ensure the multiplier effect of this approach is achieved in the sector. The programme team are now concerned that not all target health centres will benefit from WASH facilities before the project ends.

Another lesson has been that the WASH standards agreed for the project can be used for rehabilitating WASH services throughout the country.

Recommendation
- DFID and UNICEF WASH and Health teams to work together to accelerate the implementation of WASH in health centres. UN to identify if WASH facilities can be implemented in health centres where demand-side activities are operating, to ensure complementarity and achieve improved outcomes for vulnerable women and girls.
- UNICEF to document and disseminate lessons from developing WASH standards for health care facilities.

Output Title	Platforms for community engagement focused on lowest performing districts strengthened by 2020 including the improving National Health Management Information Systems.
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Proportion of CHW (i) working in target districts (over total needed) (ii) receiving at least 1 supervision visit per quarter.	Trained an additional 700 CHW at national level (ii) 2 supervision visits to CHW carried out this year.	Not achieved: (i) 650 CHW have been trained (ii) Only 1 supervision visits was carried out to CHW in the last year.
4.2. Proportion of CHW equipped and using Upscale mobile platform in (i) Cabo Delgado (ii) Nampula province.	70% coverage in Cabo Delgado province (ii) 10% in Zambezia province.	Not achieved (i)50% (ii) Not started yet and switched to Zambezia

4.1 A total of 650 additional community health works (CHW) will be trained by the end of the year in Nampula, Tete and Manica using DFID funding. This is below the target of 700 because the trainings only began in October. By December 2018, a total of 930 CHW will be trained throughout the country with funding from DFID, EU and USAID. The training includes health promotion in the form of hygiene and sanitation practices as well as family planning. Prevention activities include malaria testing and treatment, diarrhoea, nutrition (Vitamin A supplementation and deworming) and encouraging people with HIV and TB to adhere to their treatment. This training is improving the coverage of CHW which is now 60% of the country, up by 20% from three years ago.

 During field visits in June and November 2018, the programme team heard reports from CHW in Inhambane and Zambezia provinces respectively, of delays of up to six months in the payment of subsidies ($20 equivalent) by the Government. This is contributing to some CHW leaving the service. Again this may undermine the theory of change for the programme.

Only one supervision visit took place in the last year. The reason for this was that UNICEF underestimated their budget for the first half of the year and was able to cover only a part the cost of supervision. They requested that the MoH use their own funds for supervision, which they would later reimburse. The Government was unable to cover this gap resulting in CHW getting supervised only once this year. The DFID programme team were not updated on these developments, so that they could consider filling in this funding gap.

The poor quantity and quality of supervision has been one of the main weaknesses of the CHW Programme. Supervision enables CHW to refresh their learning improves the quality and timeliness of reporting. The latest malaria health survey noted that only 42% of CHW reports were submitted on time in the previous three months[8].
[8] Malaria Consortium (2018) Malaria surveillance system performance in Mozambique: a comprehensive assessment. Technical Brief.

4.2 This activity would enable the digital platform (UpScale) used by CHW as a job aid and reporting tool to be expanded to Cabo Delgado and Zambezia provinces. DFID paid for the introduction and initial scale up of UpScale in Cabo Delgado in early 2017, through the Health Sector Development Programme. This has now expanded to 50% of the province. The introduction of UpScale to Zambezia province has faced delays because UNICEF has changed their approach. They would like the Government to have more ownership of the programme, using less technical support from Malaria Consortium and instead relying on provincial health staff. Over the medium term this approach should be more sustainable and cost less.

The digital platform will help address issues associated with the timeliness of reporting as data is immediately available in the health centre once inserted into the UpScale app in the mobile phone by the CHW (provided the network is functioning). UpScale will also improve the quality of services because it acts as a job aid guiding CHW through the steps needed to diagnose a patient. Furthermore, it doesn’t require any paper at a time when there is a recurrent stockout of reporting forms. However, delays in expanding the platform are undermining its potential to help solve issues the sector is facing.

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendations
- Discuss how to improve the regularity with which subsidies are paid and increasing the quantity given with the Government.
- Discuss prioritising supervision at the district level with the UN and Government
- Expedite the speed with which UpScale is being rolled out in Zambezia province by exploring the UN whether additional TA should be given to the province.

Output Title	Generating demand for family planning among adolescents
Output number per LF		5	Output Score	C
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes (up 5%)

Indicator(s)	Milestones	Progress
6.1 Additional family planning users in the target areas as a result of DFID interventions	OJEU tender for service provider completed by January 2018	Not achieved. Service provider was awarded a contract in August 2018.

6.1 Ministers approved the submission to award the contract for demand generation of family planning using interventions to change shared attitudes and behaviours to PSI in November 2017. However, due to changes in internal processes , including within Procurement and Commercial Department (PCD) the contract was only signed on 16th August 2018. Delays were caused by new and additional requirements, such as the need for PSI to sign the General Data Protection Regulation (GDPR) and get their safeguarding policy reviewed. These delays had the following effects on the project:
- The inception phase will be from September 2018 to March 2019. As this covers the Christmas break when schools will be closed, the number of additional users has had to be revised down.
- Upcoming elections, the start of the rainy season (in October) and Christmas may further delay the inception phase.
- PSI has changed Programme Directors as the person proposed during the tender process was no longer available.

The workplan for the inception phase was approved within two weeks of the inception phase as outlined in the contract.

Due to the delays in signing the contract, the programme team considered implementing an alternative project that would contribute to the 16,000 additional users of family planning by March 2020. One of the options was to have a delegated cooperation agreement with a bilateral partner implementing a similar project[9]. Another was to sign an accountable grant with a private sector supplier that could deliver results quickly. These options were discarded because of the high transaction cost to the programme team of ensuring programme management compliance.
[9] Vault number: 13286068

Whilst not currently an indicator in the Logframe, the second part of the demand-side component (£2m) was allocated to the UN Joint Programme ‘Action for Girls and Young Women in Mozambique’ (known locally as ‘Rapariga Biz’), currently supported by Sweden. Rapariga Biz shows potential to make a substantive impact and generate valuable evidence on what works to improve women and girl’s reproductive health and rights in Mozambique, through a comprehensive set of interventions that seek to reduce high levels of unintended pregnancy in two of the poorest and most populous provinces in Mozambique (Nampula and Zambezia). Activities include increasing rates of school enrolment and retention, social and behaviour change communications, community engagement and using a participatory approach to give voice to vulnerable women and girls. The programme is delivered in close partnership with four Government Ministries, with the objective of strengthening services for sustainable and transformative change. To strengthen the evidence base, and support the successful delivery of this programme, an additional £1m was reallocated from the programme coordination and innovation component bringing the total to £3m for Rapariga Biz until December 2019.

Supporting an established programme offers the additional advantage of contributing to greater coherence in the family planning sector. Additional investment will strengthen the evidence base to understand which interventions are most cost-effective, improve coordination between the sectors, support more sustainable and transformative results through complimentary interventions that engage men and boys and scaling-up livelihoods/skills activities. Additional funding will also ensure the programme reaches the most vulnerable groups, including by strengthening work on disability inclusion across programme interventions. To channel funding to the programme, a delegated cooperation agreement with Sweden was explored, but in February 2018, was declared not feasible by the Swedish CooperationThis created unexpected delays to programme implementation, which were planned to start in June 2018. As a result, DFID has been working with the UN to establish a bilateral agreement between DFID/UN, which aligns as much as possible with Swedish funding to ensure complementarity, harmonisation, and avoid double-reporting. Programming is due to commence in October 2018, when the Logframe will be updated to reflect this new agreement and new milestones.
Lessons identified this year, and recommendations for the year ahead linked to this output
Escalate issues rapidly as possible to ensure quick resolution and to support the programme to deliver to agreed timeframes.

Recommendation
Now that both the supply and demand-side components are active, the programme team need to ensure they share lessons and communicate with each other to resolve issues. For example, the demand side relies on the provision of contraceptives from the supply-side through the National Health Service. This implies that the UN Joint Programme needs to be aware of any gaps in contraceptives that the demand side projects are facing. In practice, this means ensuring supply-side interventions deliver in the same communities as the demand-side; and having a plan in place to ensure PSI and Rapariga Biz work complements each other (from a public/private perspective), but does not duplicate.

Output Title	Strengthen the sector’s capacity to respond to emergencies
Output number per LF		6	Output Score	B
Risk:		High	Impact weighting (%):	5%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
7.1 MoH’s ability to prevent and respond to outbreaks is strengthened	WHO responds to the cholera outbreak	(i) Achieved with DFID support.
7.2 WHO has the capacity to respond to emergencies	(ii) WHO strengthens its capacity to respond to emergencies	(ii)Not achieved. The programme manager was recruited in November 2018 and other long-term staff are still in the process of being recruited.

7.1 Achieved. In December 2017, WHO received £400,000 from DFID to support the MoH response to the cholera outbreak in Nampula province.[10] Results from this support contributed to the cholera response in Cabo Delgado and Nampula. The outbreak was declared over only in May 2018 after 2,317 cases and 5 deaths. WHO also supported a pilot exploring how to respond to road traffic accidents. Lessons from this influenced the approach to be scaled up by the Government. Effects of this support included regular distribution of situational reports on the outbreak.
[10] Vault number: 22519248

7.2 Not achieved. DFID then extended the scope and size (£2 million) of this support in August 2018, to include: Advocating for dedicated budget lines in the sector for preparedness and response interventions, setting up a public health emergency operations centre, scaling up the use of digital to improve the national surveillance system to detect and respond to outbreaks and strengthening the laboratory capacity to detect outbreaks. To ensure that all these interventions would be implemented in timely manner, DFID support would also be used to recruit additional staff for WHO including a programme manager. Delays with the centralised WHO recruitment process has meant that the programme has been run without dedicated staff.

Lessons identified this year, and recommendations for the year ahead linked to this output
Recommendation
Raise concerns with WHO about the delays in contracting staff and request measures to accelerate programme implementation.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The programme’s theory of change took into account the rapidly changing external context. This is now manifesting as a liquidity crisis on the Government’s part and increased fragmentation of support on the donor side. The supply side and demand side components now being implemented by the UN and PSI respectively were both designed to be flexible. For example, the UN programme allows for a different set of interventions to be implemented in each province or over time depending on need as long as the programme outputs do not change significantly. In practice this has allowed DFID to respond to timely requests from the Government such as: a contribution of $100,000 for the Malaria National Survey on the prevalence and Incident of Malaria in the Population and printing 300,000 child health cards[11] while the Government mobilised funds for the 1.2 million health cards needed.
[11] These are used to the children’s health status cards kept by their mothers that record their medical history. Eg. any vaccines they have had.

However, a number of assumptionsfrom the theory of change are no longer in place:
- Salaries for health workers will continue to be paid. There is evidence that salaries for existing health workers are irregular: whether it is a lab technician or a community health worker. As a result, newly trained maternal and child health nurses are staying at home or working on a voluntary basis because the sector currently cannot pay for them.
- There will be minimum standards of health services in health centres. As a result of the liquidity crisis there are ad-hoc reports of shortages ranging from fuel for ambulances, allowances for supervision visits reporting forms. Health care facilities are unable to respond to arising needs because they do not have resources to do so.
- There is political will to base practice on evidence of what works. As a consequence of the external crisis, decision makers in the Ministry are not prioritising issues or basing decisions on evidence.

The implication of these is that the programme’s interventions may not lead to the intended outcome or the results anticipated,So far the UN has been able to ensure the sector continues to follow most interventions in the proposal but an important questions remains around the sustainability of the results they have achieved given the human resources issues raised above. DFID will be discussing this with other partners in the sector and escalating it beyond sector level when appropriate to find a solution.

Another assumption of the programme was that the Steering Committee would look beyond DFID’s funding to the RMNCH Investment Case. Significant inflow of funds will be coming in from the GFF over the next five years. This coupled with significant in-kind and financial contributions from other global funds (Global Fund to fight AIDS, TB and Malaria and the GAVI Vaccine Alliance) means that the theory of change needs to flex to take these funds into account. DFID also need to consider how to leverage these larger funds to continue to strengthen systems and service delivery. This has not happened despite advocacy by the UN and DFID with the Ministry of Health. Current discussions to review the dialogue structure to include the GFF provide an opportunity to address this.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Below is an explanation of how each component is performing:

UN Joint Programme – Largely on track although interventions such as delivery of WASH in health centres are taking longer than initially anticipated. To address this, the DFID and UNICEF WASH and Health teams will be meeting to discuss how to get this activity on track as outlined in recommendation 4 above.

Demand side
- To accelerate implementation of activities, PSI changed target provinces (Nampula and Gaza) where they are already established. The programme has been extended until 2021 for the full contract to be implemented.
- For Rapariga Biz, programme implementation will commence in October 2018. The programme team has recommended that the UN contract external Technical Assistance to support the implementation of the learning component on an ongoing basis.

Emergency Preparedness
The programme team requested that WHO recruit additional staff to help them implement and manage the programme effectively. Delays in recruiting staff have meant that most activities are off-track. To remediate this, DFID will be putting WHO on a three month improvement plan, after which the component may close if there are no improvements to the programme.

Explain major changes to the logframe in the past year

The only significant change to the logframe was the addition of emergency preparedness as outcome 7. Agreements with suppliers of the demand side components were signed recently, so the inception phases were not included. There were amendments to each of the milestones in the UN Joint Programme to reflect developments that were expected this year. The weighting of the outputs for the Joint Programme also increased as it took up most of the programme team’s time.

Describe any planned changes to the logframe as a result of this review (1/2 page)
The current logframe focuses largely on the UN Joint Programme (Supply-Side). The following revisions are planned to take account of progress in signing new contracts on the demand-side component, which are currently in the inception phase:
- Reduce the number of outputs for the UN Joint Programme to 3 and the weighting of this component.
- Output 4 will focus on the demand side having an indicator for the PSI programme and another for the Rapariga Biz programme.
- Review the indicators for Emergency Preparedness to focus on the different interventions WHO will undertake to support disaster prevention and response in the health sector.

Recommendations
- Assess whether the theory of change needs to be reworked and/or we take up the human resources issue at the highest levels and work with other partners to find a solution.
- WHO Programme to be put on a three month performance improvement plan after which a decision needed to be made with Management on whether the programme should continue.
- Evolve the theory of change to consider how the programme needs to flex to leverage results from other big funding channels

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
Component	Comments
RMCH UN Joint Programme	Cost drivers: Procurement of medical equipment and ambulances took up 36%, followed by the supply of medicines and contraceptives (21%) and support for community health activities (9%). / The UN has spent 89% ($13,382,000) of the total funds disbursed to date. It is expected that there will be larger execution of funds in the second half of this year as the programme has spent an additional £2.6 million from next year’s budget to prepare for next year.
PSI - Demand Side	Cost drivers: The programme is still at inception.
Programme Management	Technical Assistance to the Ministry of Health was the main cost driver.
WHO Support for Emergency Preparedness	Cost drivers: the consultant to write the proposal took up 24%, followed by trainings (23%) and General Operating Costs (12%). / Execution has been satisfactory in the first phase of the project with 95% of planned budget.

Assessment of VfM for each of the Components

UN Joint Programme
In light of the fact that the UN’s standard operating procedures and systems do not lend themselves to DFID’s VfM approach, the programme team asked the Commercial Advisor for support in discussing VfM with the UN submitted revised VfM indicators that do not include effectiveness. The revised indicators need to be further improved by including metrics, reflect the range of interventions supported by DFID and capture provincial variations whenever possible. An additional measure to be considered is the effect of the external environment on the programme in terms of loss of qualified staff, stockouts of medicines or inconsistent payments for recurrent spending (salaries, fuel etc).

Economy: The programme takes advantage of economies of scale and secures the lowest available price where it can. The UN has Long Term Agreements to provide services and goods allowing them to negotiate price/volume where possible. These were used in the acquisition of maternal and neonatal equipment as well as ambulances. Trainings for maternal and child health nurses and CHW took place at the same time reducing overheads (maximum of 16%).
Efficiency: beside the efficiencies brought through the central purchase of equipment, further efficiencies in WASH will be achieved through market pricing, reliability of suppliers for undertaking work efficiently and knowledge of the Mozambican context.
Equity: The training of maternal and child health nurses and CHW will take place at Provincial and local level ensuring retention and allocation of the nurses within the Provinces and serving the most remote areas. Similarly, the CHW trainings are based on a needs assessment to ensure CHW cover populations that may not receive any other health interventions including people living with disabilities. At the moment the programme is not adequately capturing how these excluded groups are benefitting from interventions.
WHO Support for Emergency Preparedness
Who was expected to submit VFM indicators to be approved by DFID as part of the first quarterly progress update in September 2018. It is likely that WHO will need support to draft VfM indicators to monitor whether the programme is making good use of funds.

Assessment of whether the programme continues to represent value for money
The Programme Team assesses that this programme is good value for money. The UN Joint Programme is addressing inequality in accessing health services, reaching the poorest in remote areas. The UN also ensure that most commodities and medicines are procured cost-effectively and capture how they are distributed throughout the system, carrying out spot checks on a regular basis. These data need to be recorded systematically with metrics as part of the programme’s VfM. Inefficiencies in the system are still not being captured nor are provincial variations in the cost of delivering interventions. Taking in account that the UN Joint Programme constitutes 64% of the overall business case, it will be important for the business case to track value for money of this component better.

It is too early to assess if the demand side components represent good VfM. We expect that they will because they will be responding to need (for family planning information and services) of vulnerable groups (women and girls, adolescents); and working to strengthen Government systems and processes in order to achieve transformative and sustainable change. Each programme in the business case will have their own VfM metrics.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
The programme has been designed to strengthen systems and build capacity of the sector for service delivery and decision-making – there are strong signs that the UN programme is achieving this. In so doing, this will ensure better use of other resources coming into the sector. In the immediate future this will include adapting to the significant increase in resources from the GFF (at least $25 million a year). The programme has enabled continued delivery of basic health services in rural Mozambique at a time when the sector is facing challenges associated with the fiscal crisis. The focus of the programme on rural and remote areas ensures that the poor are benefitting from health care services. The flexible and adaptable approach of the programme ensures that it is able to respond to the context.

The UN through the Joint Programme are also providing technical support to the Government for better decision-making and prioritisation, which are needed in an increasingly resource constrained environment. What is lacking are metrics to capture the value for money of the programme and its adaptable approach. Early signs of sustainability include greater coverage of services through more nurses and CHW. However, the irregularity with which CHW subsidies are paid and lack of funding for MCH nurses’ salaries once they graduate, risks undermining this sustainability. It is therefore necessary to monitor this.

The demand side will complement the supply side by reaching adolescents who are currently excluded from accessing reproductive health information and services. This is also the age- group that is contributing the most to maternal mortality and early pregnancy.

Emergency Preparedness will reduce the effect of outbreaks and disasters on the poor and vulnerable over the long term. The potential of this programme to strengthen health systems and prevent constant disruption of service delivery should make it good VfM.

Recommendation
DFID to support the UN to improve their VfM indicators for the Joint and Emergency Preparedness programmes including capturing how under-served groups like people living with disability are benefitting from interventions.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Moderate (but will recommend to management team that we amend this to high given human resources risk).

Overview of programme risk
Despite the overall medium risk rating for the business case, the rating for the operating environment continues to be high. The fiscal crisis, fragmentation of donor support and reduced engagement from the MoH in policy dialogue all contribute to this. Three of the 13 risks are now about the external context, four are delivery risks, and three are operational. The programme team and UN discuss the risk register every six months, with ad-hoc discussions when relevant. However, given the resource constrained environment these discussions should take place at least once every quarter. The UN does have regular discussions with the MoH on how to minimise these risks. The UN is still learning how to use the risk register as a management tool – with risks mentioned in the narrative report that are not in the risk register. The programme team’s use of the risk register in quarterly discussions with the UN should improve this.

Given the nature of the business case and its target group (adolescents and young women) it should be assumed that there are significant safeguarding risks. These are currently being assessed through an enhanced due diligence process. The programme team have set out a process to undertake enhanced due diligence of all the UN agencies. UNFPA will be assessed by mid- December, UNICEF by April and WHO later next year.

The UN Joint Programme (supply-side) and WHO both do not have explicit safeguarding risks in their programme risk register. However, all agencies have safeguarding policies in place and are aware of the safeguarding issues in their programmes. The programme team will therefore have a discussion with the UN to ensure that the programme’s risk registers are updated to reflect these policies.

PSI has a good safeguarding policy in place with a Code of Conduct outlining expected behaviours and unacceptable behaviours. This was assessed as part of the contract negotiation process. This shows a proactive approach to safeguarding with indicators to assess risk, examples of what this means in practice and an outline of steps to be taken should a risk materialise.

Discussions have also taken place between DFID and UN Rapariga Biz partners on safeguarding policies and measures to protect and prevent exploitation and abuse from occurring, and to ensure there are clear lines of reporting of any abuse.  In addition, a meeting between UN partners and MUVA has taken place to share learning on safeguarding approaches. As part of DFID’s support to the UN, funding in this programme will go towards strengthen psychosocial services and systems, to ensure support is available to young girls and women who wish to report, or are victims of abuse and harm.  Safeguarding has also been added in the programme’s risk register, with accompanying mitigating actions.

Recommendations on risk
- Include better safe-guarding risks with the UN Supply-Side contract ensuring they consider all the areas where there are vulnerabilities in the system.
- Discuss risks more regularly (at a minimum on a quarterly basis) with the UN and use the risk register as a management tool.
- Update the risk register with the issues mentioned in the programme management section of the mid-year report (page 17) submitted by the UN.

Update on partnership principles
UK policy is that no financial aid is provided directly to the Government of Mozambique and therefore partnership principles do not apply.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

Figure 1: The fund flow diagram for the UN Joint Programme in the business case

At the time the business case was approved, Ministers had decided that no funds could be channelled directly to Government as a result of undisclosed loans from Government. Funds would therefore be channelled from DFID to UNFPA who would use a part and allocated the rest to ach of the other two agencies in the programme. Each of the UN agencies would pay contractors or service providers for serviced delivery.

The fund flow for the other programmes was not outlined as these had not been contracted yet.
Figure 2: The current fund flow for the business case

UN Joint programme -
The current fund flow demonstrates that the majority of DFID funding is still channelled by the UN to contractors for the procurement of medicines, equipment and commodities. However, some of this funding is now being channelled to the Government at central and national level who pay contractors or deliver services themselves. This fund flow applies to WHO and UNFPA for the emergency preparedness and Rapariga Biz programmes respectively.

PSI channels its funding to contractors or service providers for the procurement equipment for example. The Consortium (PSI and Nweti) also deliver most services themselves.

This assessment is focused on the main components that have been implemented from September 2017 to August 2018.

Table 1: Comparison between the budget and expenditure for the programme in the assessed period
Component	Budget (£)	Spend (£)	Balance (£)	% Spend

RMCH UN Joint Programme – Resource	6,192,400	4,325,200	1,867,250	70%
RMCH UN Joint Programme – Capital	1,150,000	1,150,000	0	100%
Programme Management and Coordination	99,270	99,270	0	100%
Support Emergency Preparedness	401,090	382,280	18,800	95%
Total	7,842,790	5,956,740	1,886,051	76%

UN Joint Programme
DFID has disbursed £7.3 million and 75% (£5.475,000) had been executed by September 2019. An additional £1,334,700 should be spent by October 2018.

PSI – Family Planning Demand Side Support
The Family Planning Demand side component is behind schedule. Although Minister’s approved the supplier selected through the tendering process in November 2017, PSI only signed the contract in August 2018 due to changes in procedures within Procurement and Commercial Department. This component is therefore off-track. It has been extended until August 2021 for PSI to have the 36 months needed for implementation of the programme. The inception phase began in September 2018. No payment has been made because disbursements are expected to be quarterly in arrears starting from November 2018.

Programme Management and Coordination
Programme management and coordination has focused on two consultancies:
A study on the retention and attraction of health workers. DFID disbursed £50,900. The consultancy ended in February 2018 with the Attraction and Retention Strategy approved by the Minister of Health. This consultancy has enabled DFID to maintain our influence in the sector by getting involved in such a strategic area. The report recommended the introduction of performance based financing instead of paying allowances to retain staff. It also recommended that staff experience and place of work be taken into account within salaries, to encourage staff to work in under-served rural areas. The health donors are now discussing 10 of the recommendations from the Strategy with Government, in order to start the scoping work needed to introduce performance based financing into the sector.

Contracting a Senior Financial Management Consultant to support the MoH to respond to the findings of the Global Fund to fight AIDS, TB and Malaria‘s programmatic audit undertaken in April 2017. The consultancy was carried out from November 2018 until August 2019 with a budget of £48,400. It helped address the Secretary of State’s concern that not enough was being done to respond to the GFATM audit findings. The consultant supported the MoH to put financial management controls in place and have a more systematic approach to monitoring expenditures in the HIV & AIDS, TB and malaria programmes. The Global Fund is now paying for this consultancy.

WHO Support for Strengthening Public Health Emergency Preparedness and Response in Mozambique
The first phase of WHO support was implemented in three months (January – March 2019) with a total budget of £401,100. £382,280 (95%) of this was spent. The second phase began in August 2018.

Performance of partnership (s)

DFID and the Government
Within the UN Joint Programme, DFID and the Government have met every six months to discuss progress and agree priorities for the next six months. In both meetings the MoH has had requests for additional activities they would like the MoH to support. This has happened even though the UN was involved in the sector’s planning meetings in June at central and sub-national level. The date for these meetings is often agreed at the last minute due to constant itinerary changes on the part of Government. This meant that the MoH only received the 2017 report and plan for 2018 a day before the meeting.

The UN’s added value has been evident as they have managed to continue working closely with the Government, at a time when the MoH is less engaged in strategic dialogue. The UN’s technical support is valued at sub-national level where their challenge of how programmes are delivered is appreciated by Government officials.

DFID and the main delivery partners
The relationship with the UN Agencies has improved. The UN have been responsive to DFID feedback on the reports. The six-month meetings provide an opportunity to discuss programme implementation and the strategic direction of the programme. UNFPA are still understaffed although the existing team have been very responsive. WHO has struggled to be involvement in the six monthly meetings the field visits due to staff turnover. They are now in the process of recruiting additional staff.

DFID ensures that Sweden is included in the main strategic discussions with the UN on Rapariga Biz. The programme team also participated in the programme’s Steering Committee in June with the Ministry of Youth where DFID’s involvement in the programme was formally approved.

DFID and other bilateral donors
The head of office and programme team have been working to improve donor coordination in the sector. The new troika system tested this year was not always effective at responding to issues. The GFF has also not yet reduced the fragmentation in the sector, as expected. This is partly because the World Bank has focused on getting the mechanism functioning. At the same time it has been difficult to get the MoH to play a stronger role in leading the dialogue with partners. DFID have called for principles to guide how partners behave in order to reduce the fragmentation that currently exists. We will also continue to advocate for the GFF to play a more strategic role in aligning partners better. This is integral to the success of this programme as both the UN Joint Programme and GFF support the RMCH Investment Case.

The country development diagnostic and ongoing discussions in the office have highlighted the importance of investing in the demographic transition. Despite large investments in the social sectors the Government is struggling to provide sufficient services to a rapidly (3.5%) growing population, the third highest in Africa. Furthermore, the structure of this population is young, with almost half (46%) below the age of 16 years. A decision was therefore made in June to develop a five year demography business case, to be approved in the first quarter of 2019. This will continue the RMCH agenda as poor child health and low access to contraceptives are both drivers of high fertility. It will also imply closer collaboration with the World Bank and UNFPA who are leading this agenda. We have recruited a democracy advisor to support the influencing and coordination agenda. There will tbe a two year overlap between this business case and the new one. For example, the programme funded post still fits within the programme management and coordination component of the current business case.

Delivery Partners
All partners have submitted delivery risk maps. It would be a good time to review the delivery risk map with the UN in the mid-year discussion of the Joint Programme at the end of November. This will allow the programme team to assess if risks to downstream partners have changed.

Asset monitoring and control
DFID agreed asset management procedures with all programmes. This includes regular asset monitoring and control throughout the life of the project. Until now only the UN Joint Programme have purchased assets and provided an asset register in their six month reports.

The UN Joint Programme has purchased and distributed 32 ambulances and emergency medical obstetric equipment for the Ministry of Health. Two asset spot-checks were carried out to date: at the Central Medical Warehouse in Maputo in May 2018 when the ambulances and medical equipment were officially handed over to the government, and as part of the project monitoring visit to Zambezia province in November 2018. In the latter the programme team confirmed the delivery and use of medical equipment at district and health facility level. Programme team have been getting reassurances from the MoH that the ambulances will be maintained well, however, it will be important to ensure that the budget reflects this and DFID and the UN will continue to monitor if this is the case. A more systematic plan for next year will consist of 4 spot checks and three field visits to each of the programmes.

Recommendation
- UN to send the annual report and workplan to the Government at least a week before the Coordination meeting between the National Directors, UN agencies and DFID.
- Programme team to develop a systematic plan for spot checks and field visits next year.
- Programme team to discuss with management whether to extend the entire business case to August 2021 to align with the extension of the PSI Programme.

Date of last narrative financial report(s)	Mid-Year Progress Report – 31 October 2018 / Financial Report – 01 October 2018
Date of last audited annual statement (s)	WHO Certified Financial Statement – 07th November 2018 / UNFPA Certified Financial Statement – 15th November 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

UN Joint Programme
The SRO and Project Officer have been on two field visits this year, in June and November 2017 respectively. The June visit took place in the Southern province of Inhambane where the programme team visited three districts to see a training school for maternal and child health nurses and community health workers at work. In November the field visit to Zambezia included a rural hospital, a district hospital, the provincial training school and the Provincial Warehouse. The programme team also talked to beneficiaries to hear about the effect of the programme in their lives and any recommendations they would like to make. Both visits concluded with debriefs with Provincial Health Directors.

The UN provides six-monthly reports and quarterly briefs to the programme team. The latter can consist of an informal meeting or e-mail updating the programme staff about developments in the implementation of the programme. The six monthly reports are discussed with DFID and followed by a meeting with the National Directors of Planning and Cooperation and Public Health at the Ministry of Health.

The Rapariga Biz programme has also been visited by the Social Development Adviser and Project Officer in December 2017 to better understand programme activities and inform discussions over whether to provide additional investment in the programme. The programme team had discussions with the mentors and the girls benefitting from the programme, visited economic empowerment training underway, and visited a health facility. Since then, the Head of Office and Team Leader and have also undertaken field visits to the programme in June and July 2018 respectively.

The Head of Office also visited the PSI project on the 8th November to see how the focus group discussions are being carried out in Gaza province. This activity is part of the programme’s inception phase.

The UN Joint Programme was designed to have oversight of the entire RMNCH Investment Case. Without this it becomes difficult to see the added value of the programme and whether it is on track to contribute to the outcomes. The interdependencies of interventions in the sector- some of which are not funded by the UK, means that this oversight is essential for outputs to translate to outcomes. Otherwise, the programme will only contribute to outputs without making a shift in maternal mortality or the contraceptive prevalence throughout the country for example.

Evidence
 The Programme has contributed to the Malaria National Survey on the prevalence and Incident of Malaria in the Population. Results from this will be disseminated by the end of the year.

No evaluation of the business case is planned. However, an external independent review of whether the interventions will result in the desired outcomes and how they can collaborate better would help the business case have a bigger impact.

Recommendation
To organise a consultancy in the first quarter of the year to review the programme, capture how the adaptive nature of the programme is functioning and explore how to get better coordination between the different components.

Learning
The UN Joint programme was designed to respond to arising needs in the sector. The programme’s ability to flex to the needs at the MoH as a result of the fiscal crisis has validated this approach. It would be good to capture how this adaptive approach is working to share across the office and to implement in future programmes.

The TA funds have enabled DFID to respond to timely requests from the MoH or partners that we support centrally such as the GFATM. This is contributing to one of the objectives of the BC which is to support the UK aid footprint in Mozambique.

Recommendation
Ensure that lessons from the different components of the programme are being shared among the different suppliers.

Progress on recommendations from previous reviews
Out of a total of 11 recommendations made in last year’s annual review, six were not achieved, four were achieved and one is ongoing. Progress faced several challenges associated with the broader context of fragmentation among partners, working with another sector (WASH) which makes decision-making take longer and delays in contracting suppliers for the demand side. Annex I below has a more detailed update on the recommendations.

Annex I: Update on the recommendations from the previous annual review

Recommendations from Previous AR	Update
Set up a Governance Structure for the RMNCH Investment Case that oversees the different funding streams for RMNCH including DFID’s. Ideally this should be agreed within the next 3 months.	Not achieved: Despite advocacy by the UN and DFID with the Ministry of Health and other partners including the World Bank, this hasn’t happened yet.
DFID to explore with the WHO how to strengthen disaster preparedness and response to disease outbreaks in the health sector.	Achieved. The first phase was from January- March 2018 and the second phase since July 2018.
Get buy in to the updated risk matrix from the MoH to monitor how the fiscal crisis is affecting the programme	Achieved: The UN revised the risk matrix to include the impact of the fiscal crisis. This is updated every six months.
Support the MoH to define WASH standards that should exist in different kinds of health facilities.	Achieved. Standards have been defined by the Ministries of Health and Public Works.
WASH and Health programme teams agree a work plan for joint technical meetings and collaboration to provide water and sanitation services in primary care facilities.	Not achieved. Due to delays in agreeing the standards to be used for the work, this hasn’t yet happened. This recommendation will be implemented in the next year.
Programme team to set up the delegated cooperation arrangement with Sweden looking at programme compliance and gaps in programming that DFID can help address.	Not achieved: Programme team were unable to set up a delegated cooperation arrangement with Sweden because it would invalidate their existing agreement with the UN Joint Programme. Instead, DFID signed an agreement with UNFPA in August 2018.
DFID to support UNFPA to convene partners working in family planning	In progress: UNFPA is working more closely with the World Bank on demography. An “friends of family planning” group will be meeting informally at DFID’s request.
DFID to ensure strong links between the Demand for Family Planning (OJEU) component and the innovation and coordination component through MoU agreements if possible, and if not by informal coordination mechanisms.	Not achieved. Delays with the approval of the demand side component have made it difficult to implement this. The programme team will implement this recommendation in the next year.
Develop provincial level risk matrices with each Provincial Health Directorate	Not achieved. This is not realistic given that the some interventions are national while others are specific to a province.
Review the overall risk rating for the programme in light of the external environment and reduced MoH engagement with the programme.	Achieved: The overall risk remained the same but DFID continues to monitor the impact of the external environment and reduced MoH engagement in policy dialogue.
DFID Health and Governance teams to agree an effective way to get beneficiary feedback to verify the performance of the programme.	Not achieved: The Governance programme is still undergoing a tendering process. Programme team ensure that they hear from beneficiaries during field visits.