Type of Review: Annual Review

Project Title: Nigeria: State Accountability and Voice Initiative (SAVI)

Date started: 2008	Date review undertaken: December 2013 – January 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
SAVI was originally designed as a £21.5 million programme covering 5 states (with initial operations in 5), operating over 6 years (2008-2014). A business case was approved in June 2013 to expand the programme to cover a total of 10 states and to extend implementation until mid-2015, for which additional funding of £7.4 million was provided. SAVI currently operates in 8 states: Kano, Kaduna, Jigawa, Lagos, Enugu, Zamfara, Katsina and Yobe. Due to insecurity, the Yobe programme is currently managed semi-remotely by a small team based in Jigawa. Inception phase work commenced in October 2013 in two additional states: Anambra and Niger.

What are the expected results?
SAVI was designed as part of suite of interlinked State Level Programmes (SLPs) which began work in 2008. SAVI aims to support the work of the other SLPs by strengthening the capacity of Nigerian civil society, media and State Houses of Assembly to engage in policy advocacy and demand better performance from government. The expected impact of the programme is ‘enhanced efficiency and effectiveness of selected state level governments’ use of public resources.’ The expected outcome is ‘to improve the capability of state houses of assembly, civil society, media and citizens to ask for better performance from government by building their collective credibility, confidence and commitment…’ / The following results are expected at output level: / civil society demonstrates a replicable and sustainable approach to issue-based policy advocacy and monitoring. / civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes. / more open and inclusive systems of communication and improved understanding between citizens, CS, media, SHoA and government. / improved systems of transparency, public engagement and financial oversight in State Houses of Assembly. / other development partners take a more sustainable and replicable approach to strengthening voice and accountability. / SAVI works to bring about these results by building the capacity of coalitions of civil society organisations, the media and State Houses of Assembly, and strengthening connections between these actors to enhance their collective influence. It has developed a distinctive approach and way of working that avoids the provision of direct grants to partner organisations, and instead engages them in ongoing processes of training, mentoring and facilitation. Programme activities are flexible and adapted on the basis of local conditions and political economy analysis. SAVI aims to bring about improved policies and governance by demonstrating the potential of its partners to demand change on selected issues, and by encouraging broader replication of its approach by other actors (further discussion of SAVI’s approach and Theory of Change is provided in the accompanying narrative report).

What is the context in which UK support is provided?
More than 100 million Nigerians (64% of Nigeria’s 158 million people[1]) live in poverty. Nigeria has a quarter of Africa’s extreme poor, 10% of the world’s children out of school, 10% of child and maternal deaths and 25% of global malarial cases. Nigeria’s human development indicators are worse than comparable lower middle-income countries[2]. In northern Nigeria, poverty rates are 77% and the current context is one of poor service delivery and little progress towards the Millennium Development Goals. / Poor governance is a major challenge and contributes to these poor development statistics. Thirty years of military rule and dependence on oil revenues has weakened the social contract in which government is accountable and responsive to citizens. Although oil provides Nigeria with disposable income, public resources are often mismanaged and corruption remains widespread. / Within Nigeria’s federal system, state and local government are responsible for delivery of core public services and spend around 50% of the total budget. Effective spending at state level is essential for service delivery and poverty reduction. However, the various mechanisms for Nigerian citizens to hold government to account are very weak at state level (and even more so at local government level). The state legislature is seen as a ‘rubber stamp’ for the Governor. Civil society and the media still lack both the capacity and the resources they need to truly engage with government and advocate for change. All are only weakly accountable to the people themselves. These factors contribute to a generally weak state of governance with limited ability of citizens to claim rights. The result is poor service delivery and little progress towards the MDGs.
[1] See UN Population Division’s World Population Prospects: 2010 revision and Nigerian Living Standard Survey (NLSS), NBS & World Bank, 2006.
[2] All figures are from the “Gender in Nigeria Report 2012”, British Council, May 2012.

## Section A: Detailed Output Scoring

Output 1: Civil society demonstrates a replicable and sustainable approach to issue-based policy advocacy and monitoring
Output 1 score and performance description: A (output met expectation)
Output 1 covers the results of SAVI’s work in supporting coalitions of civil society organisations (Advocacy Partnerships) to engage in policy advocacy and monitoring at state level on specific issues of their concern. / Progress against expected results: / The output is measured according to three indicators. The main results are summarised below, with more detailed state-by-state scoring reported in the annex to the ARIES form. / Indicator 1.1 measures the strength of civil society partnerships in terms of their internal capacity, external relations and skills in policy advocacy and monitoring. The indicator is based on a self-assessment tool completed by the Advocacy Partnerships (Partnership Capacity Assessment). On a five-point scale the average PCA score for all output 1 advocacy partnerships rose to 3.3 in the original five SLP states (Enugu, Jigawa, Kaduna, Kano, Lagos) by the end of 2013, and to 1.5 in the 3 new ZKY states (Zamfara, Katsina and Yobe). This slightly exceeds the SLP target of 3.2 and meets the ZKY target of 1.5. / Improvements for this indicator have been most pronounced in Jigawa and Kano. Rapid increases in capacity for output 1 Advocacy Partnerships have also been noted in Yobe. / Indicator 1.2 measures the level of independence of the Advocacy Partnerships from SAVI using the same PCA tool as for indicator 1.1. The average score across the APs for this indicator at the end of 2013 was 3.4 (5 SLP states) and 1.3 (3 ZKY states) out of 5.0. This slightly exceeds the SLP target of 3.3 but just falls short of the ZKY target of 1.4. / Improvements for this indicator have been most evident in Jigawa and Enugu with slow progress reported in Kaduna and Lagos. / Indicator 1.3 records cases of replication where civil society partnerships that are not directly supported by SAVI have adopted aspects of the approach used by SAVI supported partners. SAVI reports 37 replication cases so far against a target of 15. / Observations of the annual review team / Field visits for this annual review confirmed that the many of the Advocacy Partnerships in the existing SLP states are demonstrating greater capacity and effectiveness in engaging in policy advocacy. There has been impressive progress in organisational development, building capacity in policy research and advocacy, and brokering connections with the media, State Houses of Assembly and the executive. In the original 5 SLP states many of the Advocacy Partnerships are working increasingly independently of SAVI determining their own priorities and work plans with limited support from SAVI. Examples of the policy advocacy results achieved by Output 1 Advocacy Partnerships are provided in the box below. In the ZKY States SAVI has made good progress in facilitating the formation of Advocacy Partnerships, but these remain at an early stage of development, and the emphasis of SAVI’s work is on organisational development, basic capacity building and identification of priority issues for advocacy. Experience from the SLP states indicates that it takes around 3-5 years to bring Advocacy Partnerships to a level where they can act as effective change agents. / Examples of policy advocacy results achieved by Output 1 Advocacy Partnerships during 2013 / In Enugu the SAVI has worked closely with Inclusive Education Partnership has worked closely with government in the preparation of an inclusive education policy. The policy has now been approved and includes commitments by government to ensure access by people with disabilities to 450 schools under renovation and construction. / In Jigawa the State Ministry of Health has invited the Maternal and Newborn Child Health Advocacy Partnership to participate in five of its working committees. / In Kaduna the Gender Working Group AP has participated in consultation on the Kaduna State Development Plan. Advocacy Partnerships have also been engaged to contribute to the development of service charters for two pilot MDAs. / In Kano the Gender and Social Inclusion AP has been invited by the Ministry of Health and Education to provide input into the development of State long term and sector plans. / In Lagos the Climate Change Advocacy Partnership provided input into a three year climate change mitigation and adaptation plan developed by the Ministry of Environment. / In Yobe the State Government has committed fund the rehabilitation of the General Hospital in Damagun following advocacy from SAVI supported civil society partnerships. / For further details see annex 2 to the narrative report on outcome 4 case studies / Following last year’s data quality assessment, the Annual Review team continues to have confidence in the use of Partnership Capacity Assessments (PCAs) as a valid tool to measure progress in this output (indicators 1.1 and 1.2). SAVI’s close and trusting relationships with the Advocacy Partnerships makes self-assessment a valid monitoring tool. / The review team noted numerous cases of replication where the approach taken up by SAVI is being replicated by other civil society partnerships (indicator 1.3). Documented evidence of replication is provided in ‘replication diaries’ in the state M&E frameworks. The review team found that this evidence to be mainly limited to the listing of organisations engaging in advocacy work without adequate reporting of how these have been exposed to or influenced by SAVI’s work. The review team have gained a qualitative sense that replication is occurring at the expected level, but do not have sufficient documented evidence to verify the number of replication cases claimed under indicator 1.3. / The review team is well satisfied with results under output 1, and considers that SAVI has developed a highly effective model for strengthening Advocacy Partnerships that is already demonstrating results. The priority for the remaining 18 months of the SAVI programme under this output should be to consolidate the gains already made, bring the Advocacy Partnerships in the new states to a higher level of capacity, and develop forms of support that are more adapted to the needs of more mature partnerships. The review team is concerned that the quality and relevance of capacity building support to Advocacy Partnerships has not been externally assessed or peer reviewed. A review of training and capacity building activities is required to enable SAVI to identify means to enhance the quality of its support. There is also a need to develop more specialist training and mentoring focussed on particular policy issues in addition to the general advocacy training that it already provides. / Recommendations: / R1) Conduct a review of training and other forms of capacity building support offered to members of Advocacy Partnerships focussing on the overall strategy for capacity building, training methods, the relevance of the training content and applicability of the training to the practical and policy issues of concern to the Advocacy Partnerships. External experts should be engaged to conduct this review. / R2) Fully document existing training packages and approaches before programme closure, and make these available online to civil society in Nigeria and abroad. This should refer to specific training modules as well as SAVI’s broader approach to capacity building, mentoring and hands-on learning. / R3) Introduce systematic quality controls for training activities, including closer communication between SAVI and trainers, a trainer’s report and the use of trainee evaluation forms. Introduce a questionnaire sent to trainees six months after the completion of training to assess retention and use of skills. / R4) Develop and deploy 2-3 more specialist training modules focussed on policy advocacy for specific subject areas (e.g. maternal and child health, inclusive education, people with disabilities). These should be developed in collaboration with other DFID State Level Programmes (e.g. Paths2 and ESSPIN). These modules should be designed in a way that ensures that they can be delivered by local trainers, and can be used and replicated after programme closure. / R5) Introduce a structured programme for the more regular mentoring of Advocacy Partnerships in state by specialists recruited in Nigeria with sectoral expertise and policy advocacy. / R6) Strengthen the monitoring of indicator 1.3 through the use of more complete replication diaries recording evidence on how civil society partnerships that are not supported by SAVI have adopted elements of SAVI’s approach, including documentation of specific events and processes that indicate influence by SAVI. / R7) Include in next year’s Annual Review or Project Completion Review an online or telephone questionnaire sent to organisations that SAVI claims are replicating the approach demonstrated by SAVI and its supported partners. This will provide objective evidence to verify indicator 1.3 and to understand where replication has proven to be most effective. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes.
Output 2 score and performance description: A+ (output moderately exceeded expectation)
Output 2 covers the results of SAVI’s work in supporting coalitions of civil society organisations (Advocacy Partnerships) to engage in government budget and planning processes. Following the Mid Term Review recommendations, this output has been reorganised to ensure that the budget and planning advocacy partnerships work more in support of issue based, output 1 Advocacy Partnerships. / Progress against expected results: / Indicator 2.1 measures the strength of output 2 Advocacy Partnerships in terms of their internal capacity, external relations and skills in policy advocacy and monitoring. The indicator is based on the same Partnership Capacity Assessment tool used for output 1. On a five-point scale the average PCA score for all output 2 APs was 3.2 (5 SLP states) and 1.7 (3 ZKY states) at the end of 2013. This exceeded the targets of 3.1 and 1.4, respectively. / PCA data indicates that the strongest gains in the capacity of output 2 partnerships over the past year have been in Enugu, Jigawa, Kano and Yobe with slow progress in Lagos, Zamfara and Katsina and regression in Kaduna. The situation in Kaduna relates to the reforming of the Know Your Budget partnership, which now appears to in a stronger position to support other Advocacy Partnerships in the state. / Indicator 2.2 measures the level of independence of the Advocacy Partnerships from SAVI. The average score across output 2 APs for this indicator at the end of 2013 was 3.4 (5 SLP states) and 2.7 (3 ZKY states) out of 5.0, against targets of 3.3 and 1.3, respectively. / State level PCA data indicates that progress for this indicator over the past year has been most rapid in Lagos, Kaduna, Jigawa, Zamfara and Yobe, / Indicator 2.3 records cases of replication where civil society partnerships that are not directly supported by SAVI have adopted aspects of the output 2 approach used by SAVI supported partners. SAVI reports 39 replication cases so far against a target of 30. / Observations of the annual review team / The observations recorded by the annual review team for output 1 also apply to output 2. Generally, the review team has confidence in the PCA scores, which reflect the team’s observations on the ground, but are not satisfied with the level of detail for evidence provided in support of indicator 2.3. / The annual review team notes with satisfaction that many of the weaknesses identified under output 2 at the time of the Mid Term Review appear to have been addressed. As recommended by the MTR, output 2 Advocacy Partnerships are now working more in support of issue based Advocacy Partnerships under output 1. The weakest performing output 2 Advocacy Partnerships in Enugu and Kaduna have been reformed and appear to have better prospects for effective working. There has also been a noticeable strengthening of SAVI’s relationship with SPARC, which has led to a stepping up in joint support for output 2 Advocacy Partnerships and the use of output 2 Advocacy Partnerships in the activities of SPARC. Output 2 Advocacy Partnerships have had notable success where they have engaged with direct observation of the execution of public contracts, for example the work of the Project Monitoring Partnership in Jigawa, which has brought attention to shortcomings in infrastructure projects and resulted in significant savings of public funds. / Examples of policy advocacy results achieved by Output 2 Advocacy Partnerships during 2013 / In Enugu an stakeholders' public dialogue on the budget took place in 2013 following pressure from civil society groups supported by SAVI. / In Jigawa the SAVI supported Project Monitoring Partnership (PMP) has mentored other CSOs to participate in consultations on the budget process. The Advocacy Partnership has enjoyed continued success in project monitoring, including obtaining commitments from state government to restart a windmill borehole programme, the realign a road that had not been built to specification and improve fertiliser distribution in Hadeija. / In Kano the Budget Tracking Group has had some success in pushing for the more timely release of the Accountant General’s report. / In Yobe the Budget Tracking Partnership (established with SAVI support) is closely involved in budget process, and formally receives copies of Call Circulars. The group identified the poor quality of construction of a motor park, which has resulted in the contractor being required to conduct remedial works. / For further details see annex 2 to the narrative report on outcome 4 case studies / Recommendations: / R8) The proposed review of the quality of SAVI’s capacity building activities should include an assessment of the relevance and usefulness of training in budget tracking (see recommendation R1). SAVI should focus more on sector specific budget training for the more mature Advocacy Partnerships. / R9) The model developed by the Project Monitoring Partnership in Jigawa should be encouraged and extended to more other states where alignment of interest exists. This should include further efforts to share experiences and lesson learning between states, and to make available required technical expertise on monitoring of construction standards and budget adherence. / R10) Strengthen the monitoring of indicator 2.3 following the same proposals as for recommendations 6 and 7 / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: high / Revised since last Annual Review? N

Output 3: More open and inclusive systems of communication and improved understanding between citizens, CS, media, SHoA and government
Output 3 score and performance description: A (Output met expectation)
Output 3 measures the extent of improved understanding and communication between citizens, civil society, the media, State Houses of Assembly and Government, which is considered to be an essential enabling condition for effective advocacy. / Progress against expected results: / Indicator 3.1 measures the cumulative number of partnerships using SAVI approaches that are supported by leadership in civil society, the media, State Houses of Assembly and government. According to SAVI’s logframe, this should be measured by SAVI partners using a self-assessment tool (extension to the PCA), but in practice some partners have been unable to use this tool and SAVI has completed scores through interviews. SAVI reports that 10 partnerships and platforms now receive a level of leadership support that is strong enough to be viewed as ‘institutionalising’ (just short of the target of 12). On lower levels of leadership support (permissive, facilitative and promotional) all targets were exceeded (66 against 50, 46 against 35 and 30 against 25 respectively). / Indicator 3.2 measures the cumulative number of partnerships and platforms using SAVI approaches (including State Houses of Assembly and directly supported media houses) that are progressively including the voice of women and other socially excluded groups in the context of their work. This is now measured through use of a supplementary PCA tool, but some states have failed to assess progress correctly. Progress against this indicator appears to be somewhat behind target. SAVI reports that only 8 partnerships and platforms in 2013 had ‘institutionalised’ the voice of women and other socially excluded groups, against a target of 15. 20 partnerships out of a target of 25 were promoting the voice of women and other socially excluded groups; 27 from a target of 36 were providing ‘facilitating support’; and 44 from a target of 46 were providing ‘permissive support’ for gender and social inclusion. / Indicator 3.3 measures the extent of public understanding of the expected roles and responsibilities of civil society, the media, state houses of assembly, government and citizens in improving voice and accountability. This is based on scoring by SAVI partners and limited use of citizen surveys. SAVI reports that 76% of partners and 60% of citizens in the 5 SLP states have an acceptable level of understanding, against targets of 63% and 40% respectively. While in the 3 ZKY states, 43% of partners and 27% of citizens are reported to have an acceptable level of understanding, against targets of 42% and 28% respectively. / Indicator 3.4 measures the strength of SAVI supported media partners’ internal capacity, external relations and programing skills in support of local partners’ achievement of their objectives under all five outputs. Baselines were established in 2012 using a media OCA tool. On a five-point scale, the average media OCA score for all SAVI-supported media partners under output 3.4 was 3.7 (5 SLP states) and 2.5 (3 ZKY states) at the end of 2013. This just falls short of the SLP target of 3.8 but exceeds the ZKY target of 2.3. / Observations of the annual review team / The annual review team is concerned about the quality of data for indicators 3.1, 3.2 and 3.3. For indicators 3.1 and 3.2 not all states have followed the approved methodology, and reports from many states lack narrative sections and supporting evidence to justify the scores provided. There are wide variations between states in the methodology used to assess 3.3 including structured questionnaires for SAVI partners, interviews with SAVI partners, small field based surveys, feedback from media partners and assessment of the quality of contributions to phone in programmes. Given the lack of methodological consistency, the Annual Review team has based its rating for output 3 on indicator 3.4 (capacity of SAVI supported media partners) and the review team’s qualitative assessment of progress in strengthening communication and understanding between citizens, civil society, the media and State Houses of Assembly. Against these measures progress appears to match expectations (rating ‘A’). / In spite of these concerns with data quality, the annual review team is generally satisfied with progress under output 3. In line with the recommendations of the Mid-term Review, SAVI has substantially increased its engagement with the media, and is following a more purposeful approach to build media capacity, and use the potential of the media to bring citizens into debates around governance. SAVI supported radio phone-in programmes, such as ‘Nigeria go better’ in Enugu and ‘Akasa Afaifai’ in Kano have attracted large audiences and very active participation by politicians and members of the public. SAVI notes that several state owned media houses are taking a more informed and critical view of governance processes in their states (e.g. Zamfara and Yobe). / Under output 3 SAVI has invested in supporting media houses to develop 5 year strategic plans and operational plans. The results of this activity have been rather mixed, and while many media houses express appreciation for this support (e.g. Freedom Radio, Kano), others appear to show limited commitment and capacity to implement the resulting plans (e.g. Jigawa Broadcasting Corporation). The Annual Review team considers that the Strategic Plans provide a useful means for Media Houses and SAVI to develop a broader understanding of the constraints and opportunities in-order to identify areas for joint working. However, the operational plans appear to relate more business management and marketing, where SAVI has less expertise. SAVI’s comparative advantage in media work relates more closely to training journalists on advocacy issues, working with media houses to strengthen coverage of governance issues, promoting higher standards in editorial policy, and promoting innovative and interactive programming on governance issues. SAVI’s engagement in these areas has brought impressive results, and can be strengthened further over the remaining duration of the programme. / Another important achievement by SAVI under output 3 has been to strengthen connections and communications between civil society partnerships, the media and State Houses of Assembly. This has occurred as a result of informal connections brokered by SAVI, and also through the formation of tripartite platforms bringing together these three groups (e.g. the high level tripartite platform in Kano). Several State Houses of Assembly (e.g. Kano and Lagos) have established civil society and media liaison desks. As a result of these initiatives communications between civil society, the media and State Houses of Assembly has become more regular and productive, and less affected by mistrust and institutional barriers. / Recommendations / R11) Focus media development activities training journalists on advocacy issues, working with media houses to strengthen coverage of governance issues, promoting higher standards in editorial policy, and promoting innovative and interactive programming on governance issues. SAVI should continue to work with media houses on Organisational Capacity Assessments and strategic planning tools to address the weaknesses identified in the OCAs. SAVI should not be directly engaged in operational/business planning with media houses (except for jointly implemented activities), but should be ready to help media houses to source advice in business development and marketing from suitable providers. / R12) Undertake remedial measures to correct deficiencies in the monitoring of indicators 3.1, 3.2 and 3.3. This requires SAVI Abuja to work with state teams to ensure that agreed assessment frameworks are used, and the development of a standard approach to assess civic awareness of governance roles under indicator 3.3. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 4: Improved systems of transparency, public engagement and financial oversight in state houses of assembly
Output 4 score and performance description: A+ (Output moderately exceeded expectation) / This output measures the performance of State Houses of Assembly as institutions of accountability. It is assessed using five indicators, four of which are derived from an annual Organisational Capacity Assessment (OCA). / Indicator 4.1 measures the level and quality of systems for recruitment and retention of house support staff and aides. The average OCA score for this indicator in 2013 was 3.0 (5 SLP states) and 2.7 (3 ZKY states) against targets of 2.6 and 1.6 respectively. There are important variations between states with the greatest progress reported in Lagos, Kaduna, Zamfara and Yobe over the past year. / Indicator 4.2 measures the level of quality of systems for induction and monitoring of compliance with House rules and procedures. The average OCA score for this indicator in 2013 was 4.1 (5 SLP states) and 3.0 (3 ZKY states) against targets of 2.7 and 2.3 respectively. All states recorded substantial increases in this indicator over the past year with the greatest advances in Jigawa, Kaduna and Kano. / Indicator 4.3 measures the level and quality of systems for public access to information and processes in the House and representation of public interests by members. The average OCA score for this indicator in 2013 was 2.8 (5 SLP states) and 2.3 (3 ZKY states) against targets of 2.6 and 1.7 respectively. The greatest increases in this indicator over the past year were recorded in Jigawa, Kano and Zamfara. / Indicator 4.4 measures the level and quality of systems for scrutinising public financial documents in the House. The average OCA score for this indicator in 2013 was 3.1 (5 SLP states) and 2.2 (3 ZKY states) against targets of 2.6 and 1.8 respectively. The greatest improvements in this indicator over the past year were recorded in Enugu, Jigawa and Zamfara. / Indicator 4.5 is a new indicator measuring the cumulative number of house committees and state houses improving the quality of their systems based on approaches initially demonstrated with SAVI support. As of late 2013 SAVI reports improvements in 48 committees and 24 state houses, against targets of 45 and 20 respectively. / Observations of the annual review team / SAVI has made good progress on output 4 over the past year, and has responded to the recommendation of the last annual review to align SAVI support more closely to the findings of OCAs and SHoA strategic plans, and to focus more on strengthening constituency relations and financial oversight roles of SHoAs (indicators 4.3 and 4.4). There has also been significant progress in strengthening House rules and compliance (indicator 4.2). All eight states now have legislation approving the establishment of a House Service Commission; seven states have secured budgets and established necessary physical and institutional structures; five Commissions are currently operational; and four out of the five Houses in SLP States now have operational Legislative Budget and Research Offices (LBROs) or their equivalent. In terms of budget allocations and releases for house development, Katsina, Kaduna, Kano and Lagos are now self-accounting; Zamfara, Yobe, Enugu have secured annual budget allocations and enjoyed releases this year. All eight states now have House ‘development plans’ based on SAVI-supported organisational capacity assessments (OCAs). / This progress has been driven by several factors including: (1) a favourable point in the state electoral cycle, (2) the constitutional review process (which has prompted State Houses of Assembly to update standing rules and push for financial autonomy), (3) improved collaboration with SPARC in supporting the public financial management function of State Houses of Assembly, and (4) SAVI’s role in building stronger connections between State Houses of Assembly, civil society and the media (see output 3). SAVI’s increasing experience with working with State Houses of Assembly is also an important factor, and this has enabled rapid progress to be achieved in Yobe and Zamfara where SAVI has only recently begun operations. / There are important variations between states in terms of the commitment of State Houses of Assembly to work with SAVI. This can be observed in the varying quality and content of SHoA strategic plans, which have been developed on the basis of SAVI sponsored Organisational Capacity Assessments. For example, in Yobe the Strategic Plan is highly developed, and fully costed indicating the respective commitments of the State House of Assembly and SAVI. However, in Kaduna the Strategic Plan provides only a broad identification of priorities and is not linked to a workplan or budget. / The Annual Review team noted that relations between SAVI and the State Houses of Assembly vary greatly between states depending on political conditions and personal relationships between SAVI staff and key individuals in the house (Speaker and Clerk). This is a reflection of the higher political risks under output 4 compared to other outputs, and the dependence of SAVI on enabling political conditions to achieve progress. SAVI enjoys very good access to the State Houses of Assembly in Yobe, Zamfara, Jigawa, Lagos and Enugu, but the relationship has become problematic in Kaduna and Kano. In Kano a major constraint has been the assassination of two House members in the past year, which has made access to the House more difficult. In Kaduna SAVI has encountered mistrust from the House (which has been wary of SAVI’s intentions and perceived foreign backing) and its work has been disrupted by high level political changes in the House. These problems are not indicated in the OCA scores for Kano and Kaduna, which show a positive trend between 2012 and 2013. This may indicate that change has occurred without involvement from SAVI, or may point to data quality issues with the OCA self-assessment tool, which may not provide reliable information in in these cases where SAVI has a difficult relationship with State Houses of Assembly. A more accurate picture may be provided by the Governance Index measure for the level of functionality of State Houses of Assembly (see section B part 1.6), which shows a very small increase in Kano and a regression in scores between 2012 and 2013. This indicates that there is an urgent need for SAVI to refocus efforts on these states and improve working relationships with their State Houses of Assembly. / SAVI is supporting output 4 through its new ‘federal unit’ that has engaged national level actors (mainly the National Assembly and national media) to support state level processes. Key areas of work included State House of Assembly autonomy, promoting key fiscal legislation in states, strengthening civic education and engagement of citizens in open public debate.
Recommendations: / R13) Conduct an urgent review of working relationships with the State Houses of Assembly in Kano and Kaduna, and identify measures to strengthen SAVI’s engagement, including providing backstopping support from other SAVI offices, requests to DFID for higher level political engagement (care must be taken where political perceptions in a House is that donor support is undermining the integrity of local political processes), and a plan of action with close monitoring of quarterly targets. This review will need to be informed by careful assessment of the political economy and personal factors that have disrupted working relationships. Verify whether the OCA scores provide an accurate assessment of changes in these states and whether self- assessment is an appropriate monitoring tool in situations where SAVI has a difficult relationship with State Houses of Assembly. / R14) Begin a forward planning process for engagement with State Houses of Assembly in the run up to the 2015 elections. Using political economy analysis identify opportunities and risks for SAVI engagement over this period, and prioritise support on the basis of where progress is likely to be possible as elections approach. This may require a switch in emphasis between sub-outputs and between supporting elected members and legislative support staff. / R15) From mid-2014 develop ‘transition plans including supporting the various Houses in preparing the Legislative support staff required induction process for new Members’ with the State Houses of Assembly to manage the likely change of administration and leadership in their Houses following the 2015 elections. / Impact Weighting (%): 30% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 5: Other development partners take a more sustainable and replicable approach to strengthening voice and accountability
Output 5 score and performance description: A+ (Output moderately exceeded expectation)
Progress against expected results: / Output 5 measures uptake of elements of SAVI’s approach by other development partners and is assessed according to two indicators: / Indicator 5.1 measures the cumulative number of other development partners (individuals) accessing and taking-up relevant and useful lessons learnt by SAVI and its local partners. SAVI reports that in late 2013 there were 68 organisations taking-up relevant and useful lessons, against a target of 50. / Indicator 5.2 measures the cumulative number of firm commitments by other development partners (organisations) to replicate key aspects of SAVI and its local partners’ approaches. SAVI reports that in late 2013 there were 50 such instances of firm commitments (of various degrees ranging between practical application and organisational policy) to replicate, against a target of 15. / Observations of the annual review team / There are continued weaknesses in the documentation of replication events by SAVI, and the recommendation of the 2012 review to strengthen reporting and evidence on replication has not been adequately implemented. Most states simply record a listing of replication events without providing details on contacts between SAVI and its external partners and evidence of which particular aspects of SAVI’s approach have been taken up. The 2012 Annual Review indicated that the output 5 indicators should only be admissible when backed by a replication diary, which is not yet the case. Consequently it is difficult to rate this output according to the evidence provided by SAVI. SAVI intends to address these weaknesses through the staff recruitment (3 results and communications specialists have recently be recruited). / In spite of these reporting weakness, the Annual Review mission is satisfied that the replication of SAVI’s approach is occurring according to, or above expectations, and therefore recommends a rating of ‘A+’ for this output. The mission encountered numerous instances where SAVI’s approach appears to have influenced other development projects. These are mainly DFID funded programmes, although SAVI claims that some non-DFID partners have also adopted elements of SAVI’s approach (e.g. HERFON, Save the Children and UNICEF). The Annual Review team notes a clear improvement in working relationships between SAVI and other DFID State Level Programmes, and greater appreciation by other DFID partners of SAVI’s approach and contribution. This Annual Review did not encounter any cases of dysfunctional relationships between SAVI and other SLPs, which had been the case at the time of the MTR. All of the problematic relationships noted in the MTR (e.g. between SAVI and ESSPIN in Enugu and between SAVI and SPARC in Kano) appear to have much improved. SAVI’s efforts to demonstrate results and communicate its approach appear to paying dividends. However, there are still instances where the different working methods and approaches of SAVI and its external partners are potentially problematic. This applies in particular to situations where other DFID programmes are considering providing grants to CSOs for advocacy work (e.g. M4D in Kano). Such situations will need to be carefully managed to ensure that SAVI’s relations with its CSO partners are not undermined by other programmes providing large scale funding. / Over the past year SAVI (through its UK team) has made significant progress in strengthening external communications at an international level, and has participated actively in the Civil Society Learning Forum (a network of empowerment and accountability programmes) and DFID governance advisors meetings. This is a welcome development, which should help to ensure that lessons learned from SAVI can be applied elsewhere. / SAVI has mainly relied on its partner organisations to communicate its approach to the Nigerian audience. In addition, it pursues direct contacts with other development programmes to explain and advocate its way of working. This approach has merits and is consistent with SAVI’s behind the scenes approach. However, the Annual Review team considers that SAVI is missing an opportunity to provide its own communications materials geared to needs of demand side actors in Nigeria more broadly. There is a large community of civil society, parliamentarians and journalists in Nigeria who would benefit from exposure to SAVI’s experiences and the lessons the programme has learned on effective strategies for advocacy. SAVI is beginning to fill this gap through the SAVI website (about to go on line) and participation in the SPGN website. However, more remains to be done to ensure that SAVI’s approach becomes better known in Nigeria and that its ideas will be sustained beyond the programme duration. / Recommendations: / R16) Fully implement the recommendation from the 2012 annual review that replication events should be fully documented, logged and analysed. Replication diaries should include at a minimum: (1) a record of contacts between SAVI and other organisations, (2) reports of the reaction and receptiveness of other organisations to SAVI approaches, including verbal commitments to adopt elements of SAVI’s approach, (3) evidence on how the working practices of other organisations have changed following exposure to SAVI. / R17) Strengthen communication efforts geared towards a Nigerian audience. This should be strategic, targeted and selective, and should work through key influencers, as well as through direct communication. The focus should be the communication of stories of change (outcome 4 case studies), explaining approaches to advocacy work using various media (in particular online video and social media), and making available SAVI’s training resources online. / Impact Weighting (%): 10% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money

1. Progress and results
Has the logframe been updated since last review? Yes / At DFID’s request there have been some changes to the 2013 and 2015 targets in the logframe. These reflect the contractual delays (Contract Amendment Number 4) in securing the programme expansion, which resulted in an 8 month delay to scale up in Zamfara, Katsina and Yobe and delayed start-up in Anambra and Niger. In addition, targets for output 1 and 2 for Enugu and Kaduna were lowered for 2013 on DFID advice to reflect the failure to achieve 2012 targets in these states and lowered expectations of future progress. Targets for output 5 have been raised in response to earlier overachievement of targets. IMEP has not been involved in the process of reviewing targets. / Other minor changes to logframe wording include: / Outcome level. Indicator 4 disaggregation (b) – reworded to clarify meaning of ‘indirect attribution’. / Output 3. Indicator 4 – reworded to reflect what is being measured in practice: ‘capacity of media partners’ rather than ‘quality of media coverage’. / Output 5. Indicators 1 and 2 – reworded to differentiate between the process of influencing ‘individuals’ and ‘organisations’, and disaggregating the process into measurable stages of progress. / Output 5. Indicator 3 – inclusion of a new indicator to measure the depth of learning by other programmes from SAVI’s approach. / 1.2 Overall Output Score and Description: A+ (outputs moderately exceeded expectation) / See separate excel calculation sheet. / 1.3 Direct feedback from beneficiaries / The annual review mission carried out visits to four states (Kano, Jigawa, Zamfara and Kaduna) and covered the Yobe programme while visiting Jigawa. This enabled the team to conduct numerous interviews with programme beneficiaries in Advocacy Partnerships, the media and State Houses of Assembly. These interviews demonstrated that SAVI is held in high regard by programme beneficiaries, who show a high level of interest and commitment to working with SAVI.
1.4 Summary of overall progress / SAVI has made good progress over the past year and is increasingly achieving results. Its theory of change has proven to be valid. By working with a range of actors in civil society, the media and State Houses of Assembly, SAVI has demonstrated a viable approach to strengthen demand for more accountable governance that is contributing to changes in policy and implementation. SAVI has recorded a total of 75 examples across 8 states where it claims that its approach has influenced changes in policy and implementation (see comments and caveats in section 1.6 below on this outcome indicator). Around 22 of the changes have occurred through replication, where elements of SAVI’s approach have been adopted by other organisations. / Over the past year SAVI has moved into full implementation in three new states: Zamfara, Katsina and Yobe. The scale up of activities in these states has been 8 months behind schedule as a result of contractual delays. However, there have already been significant results in Zamfara, and in particular in Yobe, which is very encouraging given the high level of insecurity in the state. In Anambra and Niger SAVI is currently engaged in inception work (not covered by this review), which has started behind schedule as a result of contractual delays. / Progress under each output is reviewed in detail Section A. In most cases the civil society advocacy partnerships supported by SAVI under outputs 1 and 2 appear to have matured and strengthened over the past year in the original 5 states, and good progress has been recorded in forming new partnerships in Zamfara, Katsina and Yobe. SAVI has made good progress in implementing the MTR recommendation to strengthen its engagement with the media under output 3, and there are numerous examples of improved and interactive radio coverage of governance questions. SAVI has also achieved notable results in strengthening connections between civil society, the media and State House of Assembly under output 3. Under output 4 there has been significant progress in improving administration of State Houses of Assembly, strengthening constituency relations and the role of the State House of Assembly in scrutinising public finances. Under output 5 there is increasing evidence that SAVI’s communication programme is influencing other development programmes, and SAVI’s approach is spreading through replication.
1.5 Key challenges / Insecurity. The past year has witnessed continued insecurity in Northern Nigeria associated with attacks by Boko Haram. Over the past year attacks have become more geographically concentrated in Yobe and Borno states. However, there is still a high level of threat across Northern Nigeria. / SAVI has managed to continue operations in spite of insecurity. Compared to 2012, SAVI has experienced significantly less insecurity related disruption in 2013 as measured by the number of office closures, rescheduling of activities, threat messages, and levels of attendance at SAVI meetings. However, there continue to be major security related challenges. In 2013 two members of the Kano State House of Assembly were assassinated, which has made access to the State House of Assembly difficult, and dissuaded members from attending public meetings. / In 2012 SAVI took the decision to withdraw staff from Yobe state, and to manage Yobe operations remotely from Jigawa. In spite of the challenges of remote working, the Yobe programme has shown significant progress and has benefitted from good relations with the media and State House of Assembly. The programme operates by convening key workshops in locations out of state, and travelling into the state as conditions permit. / SAVI has generally managed its response to the security challenge well, and has put sensible precautions in place, most importantly the employment of local staff, maintenance of a low public profile, lack of identification on offices and vehicles and improvements to office security. However, it must be recognised that there remains a significant level of threat and a high risk of further programme disruption. The security challenge is also not restricted to Northern Nigeria, incidents of armed robbery and car jacking have increased in Southern Nigeria over the past year (Anambra is a particular concern). In the run up to the 2015 elections there is an increasing risk of political violence and related programme disruption. / Expansion. SAVI has generally managed its expansion well, and initial progress in Zamfara and Yobe has been very encouraging. There has been a slower start in Katsina due to recruitment delays in response to 2 key Programme Staff resignations, and the situation in this state should be carefully watched over the coming year. SAVI has succeeded in appointing capable and politically aware staff in the new states, and has been able to draw on lessons learned from the original SLP states to ensure efficient and rapid start up. / SAVI has generally managed to maintain good progress in the five original states during the expansion phase. However, the Annual Review team is concerned about faltering progress in a few cases, notably work with the State Houses of Assembly in Kaduna and Kano. In Kaduna, SAVI’s work has been adversely affected by the loss of two critical staff including a highly effective SPO in the past year (their replacement took 3-3.5 months). SAVI should have done more to fill the gap either through backstopping from other states and more rapid recruitment. Human resource gaps in Kaduna appear to be an exception to SAVI’s generally strong staff management, and is probably explained partly by the pressure on SAVI’s management brought by expansion requirements.
1.6 Annual Outcome Assessment / SAVI has made good progress against its outcome indicators, with most of the scores having moderately exceeded expectation. An overall rating of A+ appears justified at outcome level. / Outcome indicator 1 measures the level of functionality of State Houses of Assembly as agents of voice and accountability. The scores are derived from SAVI’s annual Governance Index updates. Scores of 3.3 (5 SLP states) and 2.3 (3 ZKY states) out of 5.0, against targets of 3.2 and 2.4 respectively, were achieved in 2013. This is an increase from the 2012 scores of 2.9 and 2.2 respectively, but this year’s score for ZKY states just falls short of the 2013 target. The strongest gains since 2012 have been in Enugu, Jigawa and Zamfara. There has been a slight regression of scores in Kano and only a small increase in Kaduna (see explanation of the situation in these states under output 4 in part A). / Outcome indicator 2 measures the level of functionality of civil society as agents of voice and accountability as measured by SAVI’s governance index. Scores for 2013 were 3.5 (5 SLP states) and 2.2 (3 ZKY states) out of 5.0, against targets of 3.1 and 1.9 respectively. This is an increase from the 2012 scores of 3.0 and 1.6 respectively. The strongest increases have been in Enugu, Jigawa, Katsina and Yobe. / Outcome indicator 3 measures the level of functionality of the media as agents of voice and accountability, again measured by the SAVI governance index. Scores for late 2013 were 3.5 (5 SLP states) and 2.8 (3 ZKY states) out of 5.0, against targets of 3.2 and 2.9 respectively. Since the baseline scores for this indicator were only established in mid-2013, trend data must be treated with caution. However, there appears to have been a significant improvement in scores over the past 6 months in Enugu and Kano. / Outcome indicator 4 measures the cumulative number of demonstrable changes in policy and implementation by state government in response to public demand where there is evidence of attribution to SAVI's approach. At the end of 2013 SAVI claimed it had achieved 75 demonstrable changes against a target of 35. 40 of these changes were reported to reflect gender and social inclusion concerns (against a target of 18). / Observations of the annual review team / The Annual Review team notes the improvements SAVI has put in place for the measurement of the Governance Index following the recommendations of IMEP’s data quality review in 2012. Notably, the governance index scores are now compiled through a process of scoring by experts that is facilitated by independent consultants rather than SAVI staff. This annual review has not been able to verify the 2013 Governance Index scores in detail. In general, they appear to reflect patterns observed in the field. However, there are a few scores which appear out of line. The Governance Index records a strongly positive trend in Katsina for the level of functionality of civil society, which is at odds with the negative trend measured by output 1 indicators. In addition, there appears to have been a regression in the level of functionality of the media in Zamfara, which contradicts the strongly positive trend observed under output indicator 3.4. Differences between output and outcome scores may be expected because the latter captures a broad set of actors in the state (and the functionality of institutions) whereas the former consider only SAVI partners and their own capacity. However, given the limited size of the media and civil society in Zamfara and Katsina, the differences appear puzzling and may raise data quality issues. / The Annual Review team considers that SAVI is increasingly demonstrating results as captured by outcome indicator 4. Many of the case studies describe impressive changes in policy and implementation where evidence of SAVI’s contribution appears convincing (see examples under VFM effectiveness below). However, the overall quality of documentation supporting the 75 case studies is not satisfactory. The excel based evidence sheets are cumbersome and repetitive, and do not provide a straightforward narrative. Many reports fail to provide an adequate description of the change observed and do not provide sufficient information on SAVI’s contribution. Many of the reports describe public consultation processes, which do not constitute a change in policy or implementation, but are valuable in their own right and may be a precursor to improved policy. Very limited information on the estimated costs and benefits, and the sustainability of the observed changes is provided. In some cases there is a tendency to over-claim attribution to SAVI when many actors were involved. / A complete analysis of the outcome 4 case study evidence is provided in annex 2 of the narrative report accompanying the ARIES form. The general finding is that SAVI should have been committing greater resources and giving greater priority to evidence gathering and documentation for this vital indicator. The case studies are a crucial source of evidence of outcomes that need to be fully developed in order for the programme to be able to demonstrate credibly the effectiveness of its approach. It is not too late to rectify this weakness, but SAVI needs to give immediate attention to the problem. There are indications that action is already being taken to devote more staff resources to case study evidence gathering and presentation in Abuja and in the UK. / Recommendations: / R18) Investigate apparent discrepancies between output and outcome scores, notably for the functionality of civil society in Katsina, the functionality of State Houses of Assembly in Kaduna and Kano, and the functionality of the media in Zamfara. / R19) Fully implement the recommendation of the 2012 Annual Review to strengthen the documentation of case studies supporting outcome indicator 4. Conduct an urgent quality review of the existing results evidence sheets. Develop a simple narrative format for the presentation of the case studies. This should include the following elements: (1) a clear description of the change, including a categorisation scheme for upstream and downstream changes in the policy process (the scheme used in this annex could be taken as a starting point), (2) a record of key events (with dates) leading to the change, including meetings, site visits, surveys and consultations, publications and media communications, contacts with government, policy and budget decisions, judicial decisions, issuance of tenders, enforcement actions etc., (3) an assessment (using a ratings scale and written justification) on the extent to which the change can be attributed to SAVI and SAVI’s partners, (4) where possible, an assessment of the benefits arising from the change and their sustainability, (5) where possible, an estimation of costs to SAVI, SAVI’s partners, government and other actors, record of actions taken by SAVI, its partners and other actors in support of the change, (6) an assessment of lessons learned from the change episode.

2. Costs and Timescale
2.1 Is the project on-track against financial forecasts: Yes / The approved DFID budget for SAVI is £28.9 million, of which £16.7 million (58%) had been spent by the end of year 4 of implementation (July 2013). This is an appropriate level of expenditure with 2 years of the programme remaining given the recent scale-up. Between August 2012 and July 2013 the programme recorded a total expenditure of £4.66 million against a projected budget of £4.92 million. This implies that SAVI realised a 95% utilisation rate in the year under review. / 2.2 Key cost drivers / Since inception SAVI has expended £6.2million on long-term technical assistance, £1.4million on short-term technical assistance, and £8.1million on other expenses. Technical assistance is therefore a major cost driver, representing 48% of the total expenditure to date. This proportion has increased since inception and first year of implementation (July 2010), up from 39% to 50%. However, SAVI has ensured economy throughout by limiting use of short term international TA wherever possible and continuing to reduce the unit costs for long and short term TA (see section 5.1 on VFM economy measures). / Amongst ‘other expenses’, the main cost elements are programme activities (£3.4million since inception), office operations (£2.1million), living costs/daily allowances (£1.9million) and travel (£0.43million). / Since inception total security costs have amounted to £180,000. Additional security costs over the past 12 months are estimated at £49,000, compared to £125,000 in 2012. / 2.3 Is the project on-track against original timescale: Yes / The project should deliver its expected results in the original five states over the original six-year time frame (2008-2014). With the extension and expansion of the programme, the targets for these states have been substantially revised, and so the original expected results are now purely historical.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Data from the Citizen’s Perception Survey has been made available by IMEP for use in SAVI’s impact indicator 2. This will provide a further source of evidence on governance conditions and trends in the states where SAVI is working. Further evidence at impact level will be provided by the next sub-national Open Budget Index survey that will be administered in all 36 States in 2014 with DFID support. / SAVI has made progress in implementing the recommendations of the data quality review conducted by IMEP in 2012, notably in relation to strengthening the methodology for the compilation of the Governance Index. However, improvements are still required for the documentation of evidence of replication (see output indicators 1.3, 2.3, 5.1 and 5.2 in Part A) and for demonstrable changes in policy and implementation (see outcome indicator 4 in section 1.6 above) / 3.2 Where an evaluation is planned what progress has been made? / A final evaluation of SAVI (project completion review) is likely to be combined with the 2014 Annual Review.

4. Risk
4.1 Output Risk Rating: medium to high / 4.2 Assessment of the risk level / SAVI’s own risk assessment of 2013 appears to be broadly accurate and is reproduced below. The Annual Review team would like to highlight the following points: / Security risks are judged to be high, particularly in the north of Nigeria, but also in Lagos, Enugu and Anambra, where instances of kidnapping and car jacking have become more frequent. Violence associated with Boko Haram in Northern Nigeria disrupted SAVI’s operations in several Northern states in early 2012, but since then the impact has been much reduced. Boko Haram attacks have become increasingly contained to Yobe, Borno and Adamawa states, but a significant threat remains across Northern Nigeria. If attacks again become more widespread across Northern Nigeria then this would cause further programme disruption and could jeopardise SAVI’s ability to continue operating in affected Northern States. / Political risks are expected to increase over the next 2 years. The approach of the 2015 elections can be expected to generate increased social tension and political violence. This may particularly affect SAVI’s ability to work with State Houses of Assembly. / The institutional risks surrounding SAVI’s expansion into 2 more new states is judged to be medium to high. SAVI is not only expanding into potentially insecure new states, but will possibly be engaging in new sectors where it has limited experience. There is a significant risk that the demands of managing expansion could reduce attention given to maintaining quality and progress in existing states. This risk appears to have been realised in 2013 in Kaduna where the programme suffered from abovenoted human resource gaps (see section 1.5) that SAVI would probably have been able to address more quickly if it had not been so engaged in expansion.sh / SAVI’s risk assessment for 2013 (ratings the same as for 2012 except where indicated) / Risks Likelihood Impact Mitigation strategies / 3=high 1=low 3=high 1=low / POLITICAL / Increased insecurity 3 Rating increased from 2 to 3 in 2013 Programme: SAVI will enforce recently updated security procedures (general security architecture for the programme) by hiring a full time (cost-shared) security manager. Additional security requirements are necessary given recent spread of Boko Haram attacks (Defensive Driving, Hostile Environment Awareness Training and upgrading of security structures in SAVI offices). / DFID: State Representatives, Advisers and DFID Risk Management team to proactively address potential security risks and mitigation response. Ensure partners understand the potential delay or termination if security risk threaten programme. / Inadequate autonomy of state houses of assembly Likelihood reduced from 3 to 2 in 2013 2 Programme: Engagement with National Assembly, Conference of Speakers, Association of Clerks of state houses, and Nigerian Governors Forum to advocate for the adoption of required Amendments to the Constitution previously blocked by the then incumbent Governors. The passage of the Constitutional Amendments is still facing considerable political “push back from sitting Governors and NASS members” and may result in poor / inadequate changes. / DFID: Leverage opportunities through policy and programme dialogue to lobby for required changes. / Political volatility Likelihood reduced from 3 to 2 in 2013 2 Programme: Adaptation of advocacy strategies, identifying opportunities to influence policy under the prevailing circumstances, while also implementing above-proposed management /mitigation measures against rising insecurity, greater sensitivity in the selection of issues. Potential opportunities might arise in the lead up to the elections, linking civic education with political commitments of candidates for elected posts. / DFID: Maintaining close working relations programmes on political analysis and high level engagement with political office holders and security personnel as appropriate / BENEFICIARIES / Intimidation of individuals and groups supporting reform. 2 2 Programme: The provision of a self-assessment of the House (OCA) and resulting change plan endorsed by the Legislature has provide “political cover” to individuals and minorities in the House in order to take forward the endorsed reform agenda and those supporting its implementation. Retribution levied on journalists for reporting more evidenced based reporting needs to be protected with the use of publicly available sources, help and guidance is expected from the Nigerian Guild of Editors. Where appropriate both formal and informal contacts will be required to establish confidence-building measures through existing contacts at State Level. / DFID: Leverage opportunities through policy and programme dialogue to lobby for required changes and support for reform. Political engagement as required. / INSTITUTIONAL / Lack of SLP Co-ordination 1 3 Programme: Persistence with SPARC, identifying common areas of engagement. Targeted results communications with DFID (and IMEP) to advocate for consistent approach to/policy on V&A intervention through SLPs, to extend learning for replication and damage limitation of unsustainable approaches. / DFID: Ensure structures for SLP co-ordination at state and national level are functional and able to coordinate activity and/or synergy. / Impact not sustained beyond the programme lifetime 1 3 Programme: The “Theory of Change” and approach of SAVI with its engagement with partners emphasise diminishing dependency on SAVI resources and an exit strategy is agreed with partners from day one. / DFID Validate approach in independent Annual Reviews with low profile field reviews undertaken by DFID State Representatives. Schedule and allocate resources for post-programme impact evaluation. / Fraud or corruption on the Programme 1 3 Programme: Ensure good quality financial management control systems in place. Monthly monitoring of financial implementation against activities. Whistle-blower policy in action. / DFID: Regular financial audits and reviews. / OVERALL 1.75 2.5
Risk of funds not being used as intended / This risk is low as SAVI does not provide sub-grants to its partners and manages all of its funds itself according to DFID’s accounting and audit standards (as noted in the independent Audit Report and Management letter for the period April 2012 to March 2013). / 4.4 Climate and Environment Risk / Environmental screening was completed as part of the original programme proposal. There is no evidence to suggest that the proposed programme will have a negative impact on environment and climate change. In Lagos State SAVI partners are engaged in advocacy work on climate change risks, which focuses on promoting climate change adaptation and flood control.

5. Value for Money
5.1 Performance on VfM measures / SAVI has prepared a detailed report on VFM measures to accompany this review using the methodology developed in IMEP’s 2012 Annual Review. Since 2012 SAVI has been able to provide expenditure data (including TA costs) by sub-output by state, which has enabled more in depth VFM analysis. SAVI has a Value for Money strategy that outlines the framework for the programme to generate evidence and data for the basis of responding to the developing DFID Nigeria VFM framework. The SAVI VFM strategy builds on the work and recommendation of a DFID Nigeria commissioned study - ‘Better Assessing VFM in DFID Nigeria Governance and Conflict Programming’ conducted by ITAD in October 2012 - which aimed to set out how value for money can best be monitored and measured in DFID Nigeria governance and conflict programming. / Economy (cost of inputs) / SAVI continues to make valuable efforts to achieve more economy during the year in review by making use of systems and processes put in place in 2012 for competitive and economical procurement. SAVI has made progress in reducing unit costs for technical assistance, and switching from reducing the use of relatively expensive short-term international TA (see table below). The GEMS3 Annual Review conducted in June 2013 undertook a comparative analysis of average TA costs between SLPs, and found that SAVI achieved the lowest TA costs (see table below). / SAVI - Average Daily TA costs/ £s / Inception Year 1 / ends (July 2010) Year 2 / ends (July 2011) Year 3 / ends (July 2012) Year 4 / ends (July 2013) Average / Long Term TA 171 142 149 149 141 147 / Short term TA (national) 490 277 151 241 292 271 / Short term TA (international) 483 504 546 598 600 545 / % of STTA days in total TA 7% 9% 5% 6% 6% / % of international TA in STTA days 62% 37% 31% 35% 28% / Source: SAVI 2013 Value for Money Analysis: Annual Report of Progress Against VFM Strategy / Efficiency (cost of outputs) / SAVI has calculated VFM efficiency scores which reflect the change in output scores associated with a unit of expenditure. VFM efficiency scores by sub-output by state for 2013 are shown in the annex. Meaningful comparisons can be made between states and over time (but not between outputs or sub-outputs). / Based on an average of 2013 VFM efficiency scores across the 5 outputs (rescaled to give each output equal weight), the states achieving the greatest spending efficiency appear to be Yobe, Jigawa and Enugu. Lowest spending efficiency occurred in Katsina, Kaduna and Lagos. Low VFM efficiency in Lagos is likely to be a function of higher unit costs. In Katsina it may be too early to make a valid judgement on VFM efficiency. The VFM score for Kaduna is a cause for concern that reflects challenges in SAVI’s relationships with partners and staff shortages in the office. / On average there has been slightly greater VFM efficiency in the ZKY states (average 5.1) compared to the SLP states (average 4.9), which may indicate that SAVI has been able to make use of its previous experience to bring about efficiency gains in the new states. SAVI reports that if the SLP states are compared with the ZKY states for equivalent time periods (i.e. counting years since inception) then the VFM efficiency in the ZKY states appears to be significantly greater than the SLP states. / Comparative VFM efficiency across the SAVI states / . State Average VFM efficiency score across 5 outputs (2012-2013) / Enugu 282 / Jigawa 368 / Kaduna 179 / Kano 201 / Lagos 164 / Zamfara 271 / Katsina 139 / Yobe 278 / Average 235 / Adapted from SAVI 2013 Value for Money Analysis: Annual Report of Progress Against VFM Strategy, page 31 / There have also be noticeable improvements in VFM efficiency over time as indicated in the table below: / State 2011 Average 2012 Average 2013 Average / Change in score and/or count VFM efficiency ratio Change in score and/or count VFM efficiency ratio Change in score and/or count VFM efficiency ratio / Output 1 0.4 31.8 0.3 44.9 0.6 155.0 / Output 2 0.1 9.0 0.5 82.8 0.5 209.0 / Output 3 0.2 21.2 1.3 53.8 0.4 108.6 / Output 4 1.7 30.0 0.4 39.1 0.8 297.4 / Output 5 0.4 26.8 0.3 120.0 0.6 380.6 / Adapted from SAVI 2013 Value for Money Analysis: Annual Report of Progress Against VFM Strategy, page 33 / Effectiveness (cost of outcomes) / Two methods can be used to measure VFM at effectiveness level: (1) comparison of changes in the Governance Index scores against spending over time and across states, and (2) use of data on costs and benefits from the evidence case studies of demonstrable changes in policy and implementation. / The VFM effectiveness scores based on changes in the Governance Index are shown in the table below. This indicates greatest overall effectiveness in 2013 in Enugu, Yobe and Jigawa, and lowest overall effectiveness in Katsina, Kaduna and Kano. The low score for Katsina may be explained by the very early stage of programme implementation. The low scores in Kaduna and Kano should be a cause for concern given weaker performance observed at output level in these states. / VFM Effectiveness ratios based on changes in the Governance Index for 2013 / State Impact 1 (Governance general) Outcome 1 (SHoA) Outcome 2 (CS) Outcome 3 (Media) Weighted Average / Change in GI score VFM effectiveness ratio Change in GI score VFM effectiveness ratio Change in GI score VFM effectiveness ratio Change in GI score VFM effectiveness ratio Change in GI score VFM effective-ness ratio Rank / Enugu 0.6 149 1.1 828 0.8 602 0.6 602 0.72 413 1 / Jigawa 0.8 207 0.6 470 1.3 1019 0.0 0 0.72 352 3 / Kaduna 0.1 24 0.2 145 0.2 145 0.1 96 0.13 76 7 / Kano 0.1 26 -0.2 -156 0.0 0 0.9 933 0.17 142 6 / Lagos 0.1 22 0.5 336 0.2 135 0.8 718 0.30 209 4 / Zamfara 0.4 139 0.7 740 0.3 317 -0.3 -423 0.32 175 5 / Katsina -1.0 -427 -0.6 -776 0.8 1035 0.4 690 -0.40 -55 8 / Yobe 0.9 284 0.3 286 0.7 668 0.4 509 0.68 386 2 / Source: SAVI 2013 Value for Money Analysis: Annual Report of Progress Against VFM Strategy, page 45 / The case study evidence supporting outcome indicator 4 provides some information on the costs and benefits of demonstrable changes in policy and implementation where there is evidence of attribution to SAVI. Several examples of changes occurring in 2013 are shown in the table below, and indicate a high rate of return to SAVI’s investment. The review team is relatively confident that these examples provide a robust demonstration of VFM effectiveness (attribution to SAVI and impact are both clearly demonstrated). There are many other case study examples collected by SAVI that appear promising, but are undermined by weaknesses in presentation and the evidence base (see accompanying narrative report annex 2). If SAVI can implement the recommendations to strengthen the case study evidence, then it likely that a stronger case for VFM effectiveness will be demonstrated. It is vital that SAVI responds to this challenge. / Selected case study evidence demonstrating VFM effectiveness / Case study Evidence of value of outcomes Evidence of cost to SAVI and partners / Enugu: Inclusive education policy drafting / SAVI has worked closely with Inclusive Education Advocacy Partnership for 3 years building capacity and has been able to facilitate the group’s participation in the drafting of the Inclusive Education policy. / Refs: annex 2, case study 8; SAVI ref EN-CS8 Approval of new policy. Commitment to ensure PWD access for 450 schools under renovation and construction. These contracts are valued at NGN 1.8 billion. Cost of supporting the Inclusive Education Advocacy Partnership / NGN 6.5 million from SAVI / NGN 2 million from ESSPIN / Enugu: 2013 Budget Proposal Defence / SAVI has worked with civil society and media groups who participated in the budget discussions and advocated successfully for changes to the budget in favour of pro-poor expenditure. / Refs: annex 2, case study 10; SAVI ref EN-CS New Increased budget allocation to agriculture of NGN 63 million. Reduction in allocation to Ministry of Information of NGN 73 million. Participation of civil society partners estimated at the equivalent of NGN 2 million of analysts’ time. / Jigawa: Completion of female hostel at State College of Education / SAVI’s work with the media resulted in the issue of the lack of female accommodation being discussed on a radio programme. The State Government later committed to complete the hostel. / Refs: annex 2, case study 24; SAVI ref JG-CS 14 Over 5 million NGN was released from the state budget for the completion of the hostel. 260 female students are now accommodated No estimate provided by SAVI / Jigawa: Completion of work on 25 abandoned wind-powered boreholes / The SAVI supported Project Monitoring Partnership mentored the Meyitti Allah Cattle Breeders Association who pushed for the completion of the boreholes. / Refs: annex 2, case study 27; SAVI ref JG-CS 17 Estimated value of boreholes = NGN 125mn NGN 150,000 – cost to SAVI of various workshops with Project Monitoring Partnership / Kano: Review of Women Empowerment Fund Disbursement / The SAVI supported Gender and Social Inclusion Advocacy Partnership drew attention to fraud in the administration of payments. Following a discussion on a radio programme new procedures have been put in place to replace cash payments with bank payments. / Refs: annex 2, case study 50; SAVI ref KN-CS 12 Estimated avoided fraud = NGN 40 million No estimate provided by SAVI / Katsina: Release of funds for College of Health Sciences. / Funding has reportedly been unblocked as a result of advocacy work by the SAVI supported Godiya Health and Education initiative and discussion on radio, which was supported through SAVI’s Public Policy Dialogue. / Refs: annex 2, case study 50; SAVI ref KT-CS 2 Release of NGN 148 million for the college. It cost SAVI N600,000 to air 5 episodes of the radio programme. / Yobe: Remedial works for construction of motor park / The SAVI supported Budget Tracking Group drew attention to substandard consruction, resulting in the State Government ordering the contractor to carry out remedial works / Refs: annex 2, case study 68; SAVI ref YB-CS 3 Contractor required to undertake remedial works. Value of improvement estimated at NGN 15 million No estimate provided by SAVI / Yobe: Increase in health budget / The SAVI supported Advocacy Partnership Better Health for All successfully lobbied for an increase in the health budget / Refs: annex 2, case study 71; SAVI ref YB-CS 6 Increase in health budget from 8% to 10.7% of the state budget. No estimate provided by SAVI / For further details see narrative report, annex 2. / 5.2 Commercial Improvement and Value for Money / SAVI appears to be recruiting technical assistance at rates that are competitive within the industry. / SAVI procures most of its supplies through a procurement contract with Crown Agents Nigeria, and reports no major challenges with this arrangement. The Procurement Plan and Detailed Item Specification was adhered to (with the exception of a 2 month delay in the procurement of vehicles for Anambra and Niger). SAVI worked with Crown Agents Nigeria to identify cost savings for several purchases, for example the decision to purchase lower cost KIA Sportage vehicles (see SAVI VFM Annual Report for further examples). / 5.3 Role of project partners / For each output SAVI’s contribution has often been matched by a financial or in-kind contribution of the project partner. This makes it possible to deliver outputs at lower cost, thereby increasing value for money on efficiency grounds. SAVI still faces challenges to measure the value of partners’ contributions, which makes it difficult in a number of cases to assess the scale of these leverage effects. However, in a few cases these contributions are referred to in the case studies of demonstrable changes in policy and implementation. / 5.4 Does the project still represent Value for Money : Yes / The Annual Review finds that SAVI is continuing to offer Value for Money. SAVI’s LTTA and STTA rates compare favourably with similar DFID projects. SAVI also demonstrated strong evidence on Economy and Efficiency. There is clear evidence of value for money at cost effectiveness level, but the quality of documentary evidence needs to be further improved. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / None for this type of project.
7. Conclusions and Actions
SAVI has made good progress over the past year, and is increasingly demonstrating the value of its approach and ability to deliver results. SAVI is has made progress in implementing the Mid Term Review and 2012 Annual Review recommendations. The expansion process has been well managed and is already leading to good results in Yobe and Zamfara. The main challenges for SAVI for the remaining 18 months relate to the need to consolidate progress and to maintain focus and quality while undergoing expansion. This will depend in particular on (1) strengthening technical skills and organisational capacity of partners, (2) consolidating progress in the new states, (3) refocussing on challenging states (Kaduna and Kano), (4) enhancing communications to a Nigerian audience, and (5) reviewing training materials and strengthening case study evidence. Specific recommendations are provided under the output headings in section A above and in section 1.6 under outcomes. If these measures can be put in place there are good prospects for sustaining many of the capacities that have been built by SAVI. / The Annual Review mission is concerned that the start-up of full implementation in Niger and Anambra in the final phases of the programme is too late to enable SAVI to create conditions for sustainability and will detract attention from consolidating gains in other states. Expansion to Niger and Anambra is only justified if DFID can ensure rapid follow-on support using an approach and set of partners similar to SAVI. Any interruption in programming in the new states (even for a matter of months) would rapidly erode any progress that SAVI is likely to achieve in Niger and Anambra over the remaining life of the programme. / In view of the good results demonstrated by SAVI and the effectiveness of its approach, the Annual Review team supports the proposal to begin preparations for a follow on programme in 2014. Lessons for a successor programme are provided in the accompanying narrative report.

8. Review Process
This review was carried out by the Independent Monitoring and Evaluation Project (IMEP), and was led by Gareth Williams with support from Victor Adetula and Emmanuel Adegbe. This ensures continuity as the same consultants have led SAVI reviews since early 2011. The National Planning Commission sent an observer (Yusuf Isa Kachako), who participated fully in the mission. / This review draws on documentary evidence and interviews conducted in Abuja and the states over a two and a half week period. The annual review mission carried out visits to Kano, Jigawa, Zamfara and Kaduna, including interviews with SAVI staff and partners selected by IMEP. The team interviewed SAVI staff covering Yobe state from Jigawa, and a few project partners who travelled from Yobe to meet the review mission in Jigawa. Extensive meetings were held with the SAVI core team in Abuja, and interviews were held with SAVI State Team Leaders from Lagos, Enugu and Katsina who travelled to Abuja. A small number of additional telephone interviews were held with SAVI partners in Kano and Kaduna, who the team were unable to meet during fieldwork.

Annex – Indicators used in ARIES scoring

Output indicators

Indicator	Data source/ methodology	Target for late 2013 / SLP states	Achieved late 2013 SLP states	Target for late 2013 / ZKY states	Achieved late 2013 ZKY states	State level figures / Achieved late 2013 / (2012 score in brackets below) / (VFM efficiency score based on change in scores between 2012-2013 in italics)[3]
						En	Jg	Kd	Kn	Lg	Zm	Kt	Yo
1.1 Level of strength of civil society partnerships in terms of their internal capacity, external relations and skills in policy advocacy and monitoring.	Partnership Capacity Assessments (PCA) for each Advocacy Partnership (AP). Scores reflect a self-assessment by the APs, assessment by SAVI of the APs or joint assessment. 18 sub-indicators feed into output indicator 1.1, and 5 sub-indicators into output indicator 1.2. Each question requires a rating on a 5 point scale (5=best) on the basis of narrative descriptions for each level.	3.2	3.3	1.5	1.5	2.5 / (2.0) / (71)	3.8 / (2.7) / (169)	2.5 / (2.3) / (24)	3.6 / (2.5) / (162)	3.9 / (3.1) / (58)	1.6 / (1.0) / (76)	1.0 / (1.5) / (-119)	1.8 / (1.0) / (172)
1.2 Level of independence / dependence of civil society partnerships on SAVI support.		3.3	3.3	1.4	1.3	3.1 / (2.3) / (139)	4.1 / (2.7) / (224)	3.0 / (2.9) / (15)	3.9 / (3.4) / (87)	2.7 / (2.9) / (-22)	1.2 / (1.0) / (39)	1.0 / (1.0) / (0)	1.6 / (1.0) / (145)
1.3 Cumulative number of civil society partnerships emerging in other sub-sectors, sectors and states which have based key aspects of their approach on that of SAVI-supported partnerships.	Indicator based on replication diaries and case studies prepared by SAVI state teams.	All states / 15	All states / 37			6 / (1) / (375)	7 / (2) / (395)	7 / (4) / (293)	8 / (3) / (477)	6 / (1) / (458)	1 / (0) / (121)	0 / (0) / (0)	3 / (0) / (361)
[3] The VFM efficiency score is the score/count in 2013 minus the score/count in 2012, divided by the number of calendar quarters between the two points in time when these two evaluations were made, divided by the maximum score/count possible for indicator in question, divided by the total amount spent (in millions) on that indicator (sub-output) during the period in question.

Indicator	Data source/ methodology	Target for late 2013 / SLP states	Achieved late 2013 / SLP states	Target for late 2013 / ZKY states	Achieved late 2013 / ZKY states	State level figures / Achieved late 2013 / (2012 score in brackets below) / (VFM efficiency score based on change in scores between 2012-2013 in italics)
						En	Jg	Kd	Kn	Lg	Zm	Kt	Yo
2.1 Level of strength of civil society partnerships in terms of their internal capacity, external relations and skills in facilitating public involvement in government budget and planning processes.	Partnership Capacity Assessments (PCA) for each Advocacy Partnership (AP). Scores reflect a self-assessment by the APs, assessment by SAVI of the APs or joint assessment. 18 sub-indicators feed into output indicator 1.1, and 5 sub-indicators into output indicator 1.2. Each question requires a rating on a 5 point scale (5=best) on the basis of narrative descriptions for each level.	3.1	3.2	1.4	1.7	3.2 / (1.3) / (412)	4.1 / (2.8) / (203)	2.0 / (2.5) / (-42)	3.8 / (3.0) / (240)	3.1 / (2.9) / (49)	1.8 / (1.0) / (126)	1.1 / (1.0) / (28)	2.1 / (1.0) / (461)
2.2 Level of independence / dependence of civil society partnerships on SAVI support.		3.3	3.4	1.3	2.7	2.9 / (2.8) / (29)	3.8 / (3.2) / (173)	2.6 / (2.0) / (160)	4.0 / (3.6) / (86)	3.5 / (2.9) / (179)	3.2 / (1.0) / (689)	1.0 / (1.0) / (0)	3.8 / (1.0) / (1175)
2.3 Cumulative number of issue-based civil society partnerships supported by these budget and planning process partnerships through replication of key aspects of their approaches to facilitating public involvement.	Indicator based on replication diaries and case studies prepared by SAVI state teams.	All states / 30	All states / 39			6 / (3) / (121)	6 / (2) / (190)	9 / (5) / (181)	8 / (4) / (195)	7 / (2) / (224)	0 / (0) / (0)	0 / (0) / (0)	3 / (0) / (138)

Indicator	Data source/ methodology	Target for late 2013 / All states	Achieved as of late 2013
			Average all states	En	Jg	Kd	Kn	Lg	Zm		Kt	Yo
3.1 Cumulative number of partnerships supported by SAVI (for demonstration) and by local partners (for replication) under all five outputs progressively supported by the leadership in civil society, the media, state houses of assembly and government	Counts of number of partnerships linked to SAVI that are supported by elements of the leadership of civil society, media, government and SHoA at different levels ranging from: (1) permissive support, (2) facilitative support, (3) promotional support, and (4) institutional support. Qualifying partnerships include directly supported partnerships (APs, V&A platforms, media platforms) etc, as well as other partnerships who have replicated SAVI methods. The data source is a supplement to PCA questionnaire and SAVI state team analysis.	Permissive
		50	66	11	7	7	9	7	6		9	10
		Facilitative
		35	46	11	6	1	8	5	3		4	8
		Promotional
		25	30	10	6	0	6	4	1		0	3
		Institutional
		12	10	6	2	0	1	0	0		0	1
3.2 Cumulative number of partnerships supported by SAVI (for demonstration) and by local partners (for replication) under all five Outputs progressively including the voice of women and other socially excluded groups	Counts of number of partnerships linked to SAVI that include the voice of women and other socially excluded groups at different levels ranging from: (1) permissive support, (2) facilitative support, (3) promotional support, and (4) institutional support. Qualifying partnerships include directly supported partnerships (APs, V&A platforms, media platforms) etc, as well as other partnerships who have replicated SAVI methods. The data source is the gender and social inclusion supplement to PCA questionnaire and SAVI state team analysis	Permissive
		45	44	7	8	7	6	9	0		2	5
		Facilitative
		35	27	1	4	6	6	6	0		2	2
		Promotional
		25	20	1	1	6	5	5	0	2			0
		Institutional
		15	8	0	0	6	2	0	0	0			0

3.3 Extent of public understanding of the expected roles and responsibilities of civil society, the media, state houses of assembly, government and citizens in improving voice and accountability	SAVI state teams estimate the percentage of (a) local partners, and (b) state citizens, with an acceptable level of understanding of 'the expected roles and responsibilities of civil society, the media, state houses of assembly, government and citizens in improving voice and accountability'. This is based on their own definition of what is an acceptable level for their own needs, and is calculated through survey or scoring methods (methodology varies by state).	Target for late 2013 / SLP states	Achieved late 2013 / SLP states	Target for late 2013 / ZKY states	Achieved late 2013 / ZKY states		State level figures / Achieved late 2013 / For indicator 3.4 / (2012 score in brackets below) / (VFM efficiency score based on change in scores between 2012-2013 in italics)
							En	Jg	Kd	Kn	Lg	Zm	Kt	Yo
		Local partners
		63	76	42	43	76		83	85	66	70	30	40	58
		State citizens
		40	60	28	27	60		79	15	86	59	10	40	32
3.4 Level of strength of SAVI supported media partners in terms of their internal capacity, external relations and programming skills in support of local partners achievement of their objectives under all five Outputs.	The measure is based on an Organisational Capacity Assessment (OCA) specifically designed for the media with 19 sub-indicators grouped into three categories: internal capacity, external relations and programme skills.	3.8	3.7	2.3	2.5	4.1 / (3.9) / (40)		3.6 / (3.6) / (0)	3.5 / (3.5) / (0)	3.6 / (3.0) / (171)	3.8 / (3.4) / (110)	2.8 / (2.0) / (314)	2.3 / (2.2) / (39)	2.4 / (1.9) / (198)

Indicator	Data source/ methodology	Target for late 2013 / SLP states	Achieved late 2013 / SLP states	Target for late 2013 / ZKY states	Achieved late 2013 / ZKY states	(State level figures / Achieved late 2013 / For indicator 3.4 / (2012 score in brackets below) / (VFM efficiency score based on change in scores between 2012-2013 in italics)
						En	Jg	Kd	Kn	Lg	Zm	Kt	Yo
4.1 Level of quality of systems for recruitment and retention of house support staff and aides.	Organisational Capacity Assessment (OCA). This can be undertaken by SAVI staff, as a self- assessment by SHoA or completed jointly. The OCA includes ratings against 25 sub indicators on a five point narrative scale (5=best). Groups of these sub-indicators are then averaged to generate output indicators 4.1-4.4	2.6	3.0	1.6	2.7	2.8 / (2.7) / (21)	2.8 / (2.3) / (129)	2.8 / (2.0) / (181)	2.8 / (3.3) / (-121)	4.0 / (3.0) / (333)	3.0 / (1.0) / (1179)	2.8 / (2.5) / (176)	2.3 / (1.0) / (783)
4.2 Level of quality of systems for induction and monitoring of compliance with house rules & procedures		2.7	4.1	2.3	3.0	4.3 / (3.3) / (167)	4.5 / (2.0) / (811)	4.3 / (2.0) / (607)	4.3 / (2.7) / (521)	3.3 / (3.3) / (0)	3.3 / (2.0) / (766)	3.5 / (3.7) / (-119)	2.3 / (1.7) / (362)
4.3 Level of quality of systems for public access to information and processes in the house and representation of public interests by members		2.6	2.8	1.7	2.3	3.0 / (2.3) / (123)	3.0 / (2.2) / (257)	2.6 / (2.3) / (99)	2.6 / (1.6) / (327)	3.0 / (2.7) / (100)	2.6 / (1.0) / (943)	2.4 / (2.0) / (237)	2.0 / (1.8) / (36)
4.4 Level of quality of systems for scrutinizing public financial documents in the house		2.6	3.1	1.8	2.2	2.9 / (1.6) / (135)	4.0 / (2.4) / (505)	3.1 / (2.0) / (356)	2.4 / (2.0) / (85)	2.9 / (2.6) / (81)	2.5 / (1.0) / (882)	1.8 / (2.3) / (-261)	2.4 / (1.9) / (301)
4.5 Cumulative number of house committees and state houses improving the quality of their systems based on approaches initially demonstrated with SAVI support by (a) house committees, and (b) State Houses of Assembly	This is a new replication indicator established since the MTR. It is constructed on the basis of judgements made by the SAVI state teams on the total number of House Committees (within the 5 states) and the total number of State Houses (across Nigeria) that are actively improving their systems based on approaches originally demonstrated with SAVI's support.	All states / target	All states / achieved
		Committees
		45	48			8 / (4)	9 / (5)	4 / (6)	10 / (7)	8 / (4)	4 / (2)	2 / (0)	3 / (0)
		Houses
		20	28			5 / (2)	4 / (3)	2 / (2)	2 / (1)	10 / (6)	2 / (1)	2 / (1)	1 / (0)

Indicator	Data source/ methodology	Target for late 2013 / All / states	Achieved late 2013 / All / states	State level figures / Achieved late 2013 / (2012 score in brackets below) / (VFM efficiency score based on change in scores between 2012-2013 in italics)
				En	Jg	Kd	Kn	Lg	Zm	Kt	Yo
5.1 Cumulative number of other development partners (individuals) accessing and taking-up relevant and useful lessons learnt by SAVI and its local partners.	Indicator based on replication diaries and case studies prepared by SAVI state teams.	50	68	10 / (3) / (980)	18 / (10) / (1447)	12 / (8) / (573)	13 / (8) / (184)	9 / (8) / (49)	2 / (2) / (0)	3 / (1) / (706)	1 / (1) / (0)
5.2 Cumulative number of firm commitments by other development partners (organisations) to replicate key aspects of SAVI and its local partners approaches.	SAVI results/replication diaries maintained by State Team Leaders	15	50	6 / (1) / (541)	4 / (0) / (464)	6 / (4) / (222)	8 / (5) / (338)	6 / (2) / (370)	2 / (1) / (156)	2 / (0) / (309)	1 / (0) / (156)

Outcome indicators

Indicator	Data source/ methodology	Target for late 2013 / SLP states	Achieved late 2013 SLP states	Target for late 2013 / ZKY states	Achieved late 2013 ZKY states	State level score / Achieved late 2013 / (2012 score in brackets below, mid 2013 baseline for indicator 3) / (VFM effectiveness score based on change in scores between 2012-2013 in italics)[4]
						En	Jg	Kd	Kn	Lg	Zm	Kt	Yo
1. Level of functionality of state houses of assembly as agents of voice and accountability.	Governance baseline (2010 and 2012 update) derived from focus groups scores on 35 questions on a 5 point narrative scale (5=best).	3.2	3.3	2.4	2.3	4.0 / (2.9) / (828)	3.2 / (2.6) / (470)	3.1 / (2.9) / (145)	2.8 / (3.0) / (-156)	3.5 / (3.0) / (336)	2.2 / (1.5) / (740)	2.2 / (2.8) / (-776)	2.5 / (2.2) / (286)
2. Level of functionality of civil society as agents of voice and accountability.		3.1	3.5	1.9	2.2	3.3 / (2.5) / (602)	4.1 / (2.8) / (1019)	3.3 / (3.1) / (145)	3.5 / (3.5) / (0)	3.1 / (2.9) / (135)	1.9 / (1.6) / (317)	2.5 / (1.7) / (1035)	2.2 / (1.5) / (668)
3. Level of functionality of the media as agents of voice and accountability.	New indicator scored using an extension of the governance baseline methodology.	3.2	3.5	2.9	2.8	3.5 / (2.9)	3.4 / (3.4)	3.4 / (3.3)	3.7 / (2.8)	3.3 / (2.5)	2.3 / (2.6)	3.1 / (2.7)	2.9 / (2.5)
4. Cumulative number of demonstrable changes in policy and implementation by state government in response to public demand where there is evidence of attribution to SAVI's approach.	SAVI State Teams, Case study evidence	Total / All states
		35	75	Cost per result £‘000s		8 / (5) / (145)	18 / (6) / (60)	9 / (6) / (130)	14 / (7) / (82)	11 / (5) / (124)	2 / (0) / (158)	2 / (0) / (144)	11 / (0) / (30)
		No. reflecting the voice of women and other socially excluded groups
		18	39			4 / (3)	12 / (3)	6 / (4)	8 / (4)	5 / (2)	0 / (0)	1 / (0)	3 / (0)
		No. that are not directly attributable to SAVI support (result from replication of the approach by partners and others
		10	22			2 / (1)	10 / (1)	2 / (1)	4 / (2)	3 / (1)	0 / (0)	0 / (0)	1 / (0)
		No. are outside of focal states
		5	4			0 / (0)	1 / (0)	0 / (0)	0 / (0)	3 / (0)	0 / (0)	0 / (0)	0 / (0)
[4] The VFM effectiveness score is the score/count in 2013 minus the score/count in 2012, divided by the number of calendar quarters between the two points in time when these two evaluations were made, divided by the maximum score/count possible for indicator in question, divided by the total amount spent (in millions) on that indicator (sub-output) during the period in question.