The Independent Monitoring and Evaluation Project for the State Level Programmes (IMEP)

2013 Annual Review SPARC

Client: UK Department for International Development (DFID)
Abuja and UK,

31 January, 2014

Funded by UKaid from the Department for International Development

Ken Robson
Jeremy Cant
Chikaodili Anene
Mukthar Tanko

Abuja and UK,

31 January 2014

Table of Acronyms
Abbreviation	Full Meaning
AR	Annual Review
CGS	Conditional Grants Scheme
DFID	Department for International Development
ESSPIN	Education Sector Support Programme in Nigeria
ExCo	Executive Committee (of State Government)
FCT	Federal Capital Territory
FGN	Federal Government of Nigeria
G&SI	Gender and Social Inclusion
GEMS	Growth and Employment in States Programme
HMG	Her Majesty’s Government (UK)
HoS	Head of Service
HR	Human Resources
HRM	Human Resource Management
IFMIS	Integrated Financial Management Information System
IMEP	Independent Monitoring and Evaluation Programme
LGA	Local Government Area
MDAs	Ministries, Departments and Agencies
MDG	Millennium Development Goal
MDGs CGS	Millennium Development Goals Conditional Grant Scheme
M&E	Monitoring and Evaluation
MoBP	Ministry of Budget and Planning
MoH	Ministry of Health
MTSS	Medium-Term Sector Strategy
NGF	Nigeria Governors Forum
NGO	Non-Governmental Organisation
OHCS	Office of the Head of the Civil Service
P&S	Policy and Strategy
PATHS2	Partnership for Transforming Health Systems Phase 2
PDG & STL	Programme Development Group & State Team Leaders (SPARC)
PEA	Political Economy Analysis
PEFA	Public Expenditure and Financial Accountability
PFM	Public Financial Management
PSM	Public Service Management
PSR	Public Sector Reform
SAVI	State Accountability and Voice Initiative Programme
SDP	State Development Plan
SEAT	State Evaluation and Assessment Tool
SHoA	State House of Assembly
SLP	State Level Programme
SPARC	State Partnership for Accountability, Responsiveness and Capability
SPoA	State Plan of Action
SPRM	State Peer Review Mechanism
SSAR	State Self Assessment Report
TA	Technical Assistance
ToC	Theory of Change
ToR	Terms of Reference
VFM	Value for Money
WB	World Bank

Executive Summary

Main findings

Performance assessment

This Annual Review scores progress and the achievement in delivering the expected 2013 milestones as an ‘A+, outputs moderately exceeded expectation’.

All Outputs exceeded the expected standard:

- Output 1: Policy and strategy development, monitoring and evaluation improved - A+ (output moderately exceeded expectation)
- Output 2: State public financial management improved - A+ (output moderately exceeded expectation)
- Output 3: State civil service performance improved – A+ (output moderately exceeded expectation)
- Output 4: Federal support to state governance improved – A+ (output moderately exceeded expectation).

Performance by state also varies but not all met the expected standard:

	Overall Outputs score
Met/exceeded standard		Failed standard
Anambra	A++	Jigawa	C
Enugu	A++	Yobe	C
Lagos	A++	Zamfara	C
Niger	A+	Kano	C
Kaduna	A+
Katsina	A

Kano’s poor performance rating is expected; DFID have already agreed a 17 Point Action Plan with the State Government to help get the SPARC programme back ‘on track’. Jigawa’s performance is surprising given its long standing reputation as a committed, reforming State.

Theory of change and evidence base

There is a strong evidence base at the Output level. The evidence base at the Outcome level needs to be better collated, presented and strengthened. The evidence for the Intermediate Impact needs to be captured in cooperation with the sector programmes, ESSPIN and PATHS2.

Value for money

The SPARC programme, with total expenditure to date of £42 million, represents value for money for DFID. Performance varies across the 10 states as illustrated below.

Good value	Fair value	Poor value

Anambra	Kaduna	Kano
Enugu	Katsina
Lagos	Jigawa
Niger	Yobe
	Zamfara

Sustainability

Within SPARC, there is no agreed working definition of ‘sustainable’. However, there are positive signs of probable sustainability when defined in terms of repeated processes, with evident signs of improved quality, and these include:

- Medium Term Sector Strategies where there is evidence that the MTSS process is ‘taking root’
- Budget documentation and budget execution rates.

 But it is too early to confirm that any SPARC supported system or process is sustainable.

Recommendations and next steps

State performance:

1. The dip in Jigawa’s performance needs closer investigation and remedial measures agreed and implemented taken to get the State (back on track).
2. Kano’s progress with implementing the 17 Point Action Plan will be reviewed in May 2014 and based on progress achieved DFID will need to decide on SPARC’s future engagement in the State.

Theory of change and evidence:

1. SPARC and DFID should agree the key questions in the ToC that need to be answered and for SPARC to commission the necessary research and analysis.
2. SPARC, in conjunction with state level programmes in the education and health sectors, should carry out more research and analysis in an attempt to identify causal connections between improvements in governance and movements in indicators measuring education and health sector outcomes.
3. SPARC should continue to identify impact-type case studies, as a proxy for measures of effectiveness in improving governance, and should look to extend these into the Planning and Strategy and Public Sector Management work streams.

Value for money:

1. To demonstrate continued value for money, SPARC should ensure that programme resources are allocated to states and work streams in a way that provides the best opportunity for achieving reform objectives. This should be a combination of a top-down strategic approach and a bottom-up workplan-based approach. SPARC has agreed to document their resource allocation approach for 2014-15.
2. In terms of assessing programme effectiveness, SPARC should identify and adopt performance indicators that measure the impact of programme ouputs, rather than the cost of achieving those outputs. SPARC should also liaise with other SLPs in an attempt to assess SPARC’s contribution to achieving overall programme objectives.

Sustainability:

1. Prepare a working definition of ‘sustainability’ in relation the main programme components
2. Assess how far along the sustainability ‘spectrum’ can SPARC progress by the end of the programme; set specific targets (to the extent not already defined in logframe) and schedule and fund interventions to help ensure these sustainability targets are met or visible progress made so that a successor reform programme can complete the task
3. Consider the implications, if any, of introducing sustainability into the ToC and the implications for gathering an evidence base.

In considering the implications for the ToC, the first issue to consider is where in the intervention logic should sustainability be considered, either at Outcome or Intermediate Impact or Impact levels. Then, depending on the agreed criteria for measuring sustainability decide on (a) the indicator(s) to be used for monitoring (b) the target(s) to be achieved and (c) the internal SPARC process(es) that need to be introduced to help move towards sustainability (for example, in terms of achieving replication, improving quality and increasing own financing) and the type of evidence that will need to be collected (linked to the indicator(s)) in order to demonstrate success.

# Chapter 1

1	Introduction

## 1.1 Background
The Department for International Development’s (DFID’s) State Partnership, Accountability, Responsiveness and Capability (SPARC) programme started in 2007 and worked in 5 states: Enugu, Jigawa, Kaduna, Kano, and Lagos. In 2012, the programme was extended to 5 more states and the overall funding increased from £45.9 million to £60.4 million with an extended completion date from June 2014 to June 2015. These additional states are Anambra, Katsina, Niger, Yobe and Zamfara.

The intended impact of SPARC is that Nigeria’s own resources are used efficiently and effectively to achieve the Millennium Development Goals (MDGs). The programme’s outcome is the enhanced efficiency and effectiveness of selected state governments’ use of public resources. To help deliver these results, SPARC has 4 outputs:

- Output 1: Policy and strategy development, monitoring and evaluation improved.
- Output 2: State public financial management improved.
- Output 3: State civil service performance improved.
- Output 4: Federal support to state governance improved.

The 2012 Annual Review (AR), the first AR for the extended programme, was completed in January 2013. It was categorised as a ‘light touch’ review, in that only Lagos and Enugu states were visited and beneficiary stakeholders met. It assessed progress as ‘A+, moderately exceeded expectation.’

## 1.2 Approach
This 2013 AR was planned as a more detailed assessment of programme performance. The main objectives of the AR were as follows:

- To independently assess progress against the results in the SPARC logframe
- To contribute to the consideration of a potential next phase for the programme and its potential scope and modality.
In fulfilling these two objectives, the AR Team was required to focus on the following issues:

- Relevance and theory of change – extent of the evidence base for the Theory of Change, effectiveness of approach and lessons learned for possible future phase
- Performance and effectiveness - progress on the scaling up to 10 states under SPARC's Consolidation and Expansion Strategy, sustainability issues for the enlarged programme, results achieved against all indicators across ten states, synergies and working with other SLPs, assumptions between outputs and outcomes and managing risks
- Sustainability and future planning – sustainable results delivered, prospects for sustainability, political economy considerations, design issues for a possible successor programme
- Value for Money (VfM) – performance to date, evidence of VfM achieved, analysis of costs versus results, comparison with comparable programmes, options for delivering greater VfM

The AR Team, mobilised by DFID’s Independent Monitoring and Evaluation Project (IMEP) comprised the following members: Chika Anene (IMEP) Mukhtar Tanko (National Planning Commission), Jeremy Cant and Ken Robson (both freelance consultants). The fieldwork in Nigeria was completed between 25 November and 13 December 2013. Prior to starting work in Abuja, the AR Team agreed an Approach Paper with DFID and with the SPARC technical assistance team which set out how the Team proposed to address the requirements in the ToRs.

The approach to the AR consisted of an extensive document review (see Annex A for documents consulted) complemented by a series of meetings with DFID, beneficiary stakeholders both at the federal and state levels, members of the SPARC technical assistance team and representatives from the other State Level Programmes, namely ESSPIN, PATHS 2 and SAVI. Annex B details the list of people met. To cover the breadth of the programme during the 3 weeks of the review, the Team’s efforts were prioritised as follows:

More detailed analysis of performance with the Federal organisations through meetings with the Nigeria Governors’ Forum and the MDG Conditional Grant Scheme Office in Abuja. A similar approach was followed in the visits to the 3 states of Jigawa, Kano and Zamfara. In each of these states, the SPARC technical assistance teams provided briefings of progress to date which the Team was able to validate with its meetings with senior state government officials. In all 3 states, the Team, as a minimum, met with the Ministry of Budget and Economic Planning, the Ministry of Finance and the Office of the Head of the Civil Service. A list of the people met and their respective MDA is included at Annex B.

Whilst not able to visit Yobe, for security reasons, the Team did meet with the SPARC State Programme Manager for Yobe in Gusau, Zamfara as well as 3 representatives from the state government: The Permanent Secretary for the Ministry of Health, the Accountant General and the Director Planning, Ministry of Budget and Economic Planning.

In addition, the Team met with the respective SPARC State Level Programme Managers for Enugu, Lagos and Niger whilst in Abuja and discussed progress to date issues arising and the needs for continued governance reform beyond the life of SPARC.

Finally, the AR Team’s consideration of SPARC performance in Anambra, Kaduna and Katsina was informed by the routine progress reports made available by the SPARC technical assistance team. In terms of the VfM assessment, additional data was provided by SPARC to enable the Team to draw conclusions on VfM performance in these 3 states.

At the end of the fieldwork, the AR Team presented its initial findings and recommendations arising from the review both to DFID and to the SPARC technical assistance team.

## 1.3 Structure of this report
Following this introduction this AR report is structured as follows:

- Theory of change
- Progress to date and scoring
- Value for money
- Sustainability
- Implementation features
- Governance reform post SPARC.

In addition, there are several annexes. Furthermore, this report needs to be read in conjunction with the complementary DFID ARIES report which provides additional information, particularly in relation to progress to date and scorings by Output.

## 1.4 Acknowledgements
The AR Team is grateful for the courtesy and time afforded to them by the large number of senior officials from the state governments with whom the Team met. In addition, the contributions and insights from the SPARC technical assistance team, and the success in arranging the logistics for such an extensive visit to the North, are very much appreciated.

# Chapter 2

# 2 Theory of Change

## 2.1 Updated Theory of Change
SPARC’s Theory of Change (ToC) is articulated in two documents: the Business Case (BC) for the scale up of the programme[1] completed in 2012 supplemented by a further elaboration produced by SPARC[2] in 2013. During the Review, the SPARC Team compiled a list of the evidence presently available to support the ToC at each of the following ‘transitions’ in the logical framework:
[1] Scale Up of the State Partnership for Accountability, Responsiveness and Capability (SPARC) Programme Business Case DFID Nigeria October 2012
[2] Theory of Change, SPARC report, April 2013

- Transition 1: Inputs to Outputs where programme assisted activities are expected to result in better systems and procedures for planning, financial management and human resources management
- Transition 2: Outputs to Outcome where these better systems and procedures are expected to result in more efficient and effective management of public resources
- Transition3: Outcome to Impact[3] where more efficient and effective resource management is expected to result in the improved provision of basic services.
  [3] In completing this analysis, the SPARC Team introduced an ‘Intermediate Impact’ level referring to the improved delivery of basic services which strengthens the ToC

This analysis is presented at Annex C for reference.

## Strength of the evidence base
From this analysis, it is apparent that there is a wealth of evidence for Transition 1 where the inputs of the SPARC team have resulted in improvements in the content and use of the key business processes. However, as the analysis moves higher up the logical framework to Transitions 2 and 3, the evidence, as currently presented, is less substantial and, consequently, tends to be less persuasive. But there are different issues at play when considering the evidence base for each of these transitions.

For Transition 2, it is likely that there is plenty of available evidence to demonstrate that the adoption of better systems is resulting in improved resource management. But it is not altogether clear that the most pertinent questions have been articulated in the updated ToC copied at Annex C. What are the most relevant questions to answer in order to confirm that better systems result in better resource management? The key questions are listed but are located across both Transitions 2 and 3.

It is problematic on how best to measure the Outcome objective because of the difficulty of identifying where measuring ‘resource management’ ends and where measuring ‘service delivery’ starts. However, recognising this division may be not so clear cut, for the purpose of gathering the evidence base in support of the ToC, the main questions identified by SPARC seem to be these:

- Are state government policies and strategies more financially viable and aligned to budgets?
- Does the improved quality of policies and strategies result in better targeting?
- Do state governments exercise better fiscal and budget discipline?
- Does improved fiscal and budget discipline lead to the better allocation of resources?
- Does better organisation and management of civil servants result in greater productivity?

For Transition 3, the issue here is about generating the evidence that improved resource management results in the greater delivery of basic services. The key question to be addressed with convincing evidence is the one that SPARC highlights, namely “improved government effectiveness (in relation to improved resource management) leads to improved service delivery.” Typically, the evidence to demonstrate this result is compiled from a range of techniques such as public expenditure reviews, public expenditure tracking surveys and the use of citizens’ scorecards and public satisfaction surveys. So SPARC will need to work with the ‘service delivery’ programmes, such as ESSPIN and PATHS 2, to gather the necessary evidence. For example, recently PATHS 2 have completed health spending reviews in each of ‘their’ states and the information should be ‘mined’ by SPARC to assess whether there are demonstrable/ attributable links between the systems reforms in the ‘central’ MDAs facilitated by SPARC, through their adoption in the ‘spending’ MDAs facilitated by ESSPIN and PATHS 2 through to more citizens receiving higher quality services.

The likely, first question to be asked in relation to the achievement of the Intermediate impact is ‘has SPARC’s support resulted in the improved delivery of basic serices within a selected state?’ The approach to answering this question might be to select one state, with a realistic budget and already into a second generation of MTSS’s. Then to identify the budget releases/spending on a particular service (such as primary health care) and the associated service standards achieved with that level of increased spending. Calculating a spend per unit of service delivered, ideally compared with a baseline in the same state or a counterfactual in another state, may provide some indication, however tentative, that better planning linked to more realistic budgets and budget releases, results in improved services.

In addition, there are two key assumptions in the ToC which require further substantiation and more detailed elaboration informed by the programme’s experience to date. Firstly, the ToC predicates a technical approach to governance reform built on the 3 pillars of (1) policy and strategy (2) public financial management and (3) civil service performance. There is evidence emerging from SPARC’s work in Kaduna that goes some way to answering this question in a positive light. However, more evidence needs to be documented for the ToC to become persuasive. Secondly, the ToC states that governance reform is not only a technical process but is part of a broader political process brings its own issues and challenges to the nature, scope and pace of reform. The evidence to substantiate the first assumption needs to be presented. There is plenty of evidence to substantiate the second assumption as illustrated by the current events in Kano as well as the experiences in Lagos and Enugu.

## Recommendations
SPARC and DFID to agree the key questions in the ToC that need to be answered. SPARC to commission the necessary research and analysis.

SPARC, in conjunction with state level programmes in the education and health sectors, should carry out more research and analysis in an attempt to identify causal connections between improvements in governance and movements in indicators measuring education and health sector outcomes.

SPARC should continue to identify impact-type case studies, as a proxy for measures of effectiveness in improving governance, and should look to extend these into the Planning and Strategy and Public Sector Management work streams.

# Chapter 3

## 3 Progress to date and scoring
## 3.1 Summary
This Annual Review scores progress and the achievement in delivering the expected 2013 milestones as an ‘A+, outputs moderately exceeded expectation’ which continues the performance standard achieved at the 2012 Annual Review. The results for each Output are as follows:

- Output 1: Policy and strategy development, monitoring and evaluation improved - A+ (output moderately exceeded expectation)
- Output 2: State public financial management improved - A+ (output moderately exceeded expectation)
- Output 3: State civil service performance improved – A+ (output moderately exceeded expectation)
- Output 4: Federal support to state governance improved – A+ (output moderately exceeded expectation).

The detailed analysis supporting these scores is presented in the ARIES report[4].
[4] In Section A, pages 4-9

## 3.2 State performance assessments
During the visits to states[5], and through discussions with state government officials and SPARC teams, the AR team gained the sense that performance in the states varied and these differences could be classified as follows[6]:
[5] Jigawa, Kano and Zamfara with Yobe officials meeting AR Team in Jigawa
[6] Anambra and Katsina are excluded; these states were not visited and no SPARC representatives met

1. States operating in forward gear, making positive progress: Enugu, Lagos, Niger, Yobe and Zamfara
2. States in neutral gear, losing momentum: Jigawa
3. States in reverse gear, going backwards: Kano.

The subsequent detailed analysis of individual performance, presented in the ARIES report, largely confirmed this typology. The analysis of individual state performance reveals the following spectrum of results:

State	Overall Outputs score

Anambra	A++
Enugu	A++
Lagos	A++
Niger	A+
Kaduna	A+
Katsina	A
Jigawa	C
Yobe	C
Zamfara	C
Kano	C

The only ‘discrepancy’ is in the results for Yobe and Zamfara where the analysis reveals that progress is not as impressive as the AR Team’s first impressions. It is probably fair to say that the early, positive impression was influenced by the very persuasive statements made by state government officials about the importance of the SPARC programme in their state and their interest in, and commitment to, governance reforms. The poor performance of Yobe and Zamfara is more likely to be due to operational constraints, such as the security situation, and where each state is in the early stages of reform, rather than any fundamental concern about commitment and engagement with the programme.

This same explanation does not apply to Jigawa and Kano. Jigawa’s C score is surprising given its reputation and track record as a high performing state. Kano’s score is expected given the long running difficulties experienced by SPARC in obtaining the high level engagement from the Governor and the Commissioners. DFID have discussed with the Kano State Government how best to get the SPARC programme on track. A 17 Point Action Plan for implementation by May 2014 by the Kano State Government has been agreed. Performance in implementing this Action Plan will determine the nature and extent of SPARC’s continued involvement in the State. Since the fundamental reason for the poor performance of Kano is due to the lack of engagement by the Executive stemming, from the absence of the Governor’s proactive support, it seem unlikely that the programme will get back ‘on track’, despite both DFID’s and SPARC’s best endeavours. This period leading up to the national elections in 2015 is highly likely to crowd out the possibility of any meaningful political re-engagement with SPARC.

Jigawa’s situation needs more detailed analysis by DFID and SPARC to better understand the factors behind this poor performance. It is evidently not caused by the lack of support from the Governor. In all likelihood there will be a range of reasons; the factors may be related more to the content of work plans, the availability of the ‘right technical assistance at the right time’ and perhaps just a dip in the energy levels of the middle managers who have to carry the major share of the extra work to drive through the changes.

Individual state performance summaries are included at Annex D.

## 3.3 SPARC’s approach to progress monitoring and reporting
The SPARC programme has developed a comprehensive, logical and transparent system for monitoring and reporting progress. The system is based on a categorisation of progress using a traffic light system of ‘green, amber/green, amber and red’ (referred to as
RAG). This system is applied to the performance of each state and measures progress towards state specific milestones for each of the indicators[7] (for Outcome as well as for Outputs) for which milestones have been set. Progress using the RAG system is reported quarterly and the measurement is evidenced against cross referenced sources that are available on the SPARC website. Then there is a formula that is applied to ‘translate’ the RAG assessment into the ARIES scores of A++, A+, A, B or C.
[7] Several of the indicators are multi dimensional in that they contain more than one characteristic that is measurable

As part of this AR, this scoring methodology was validated using a two stage sampling approach:

1. The wording of the Output indicators in the programme logframe was checked against the wording of the Output indicators in the state logframes for those states visited during the AR in order to ensure consistency
2. For each of the states visited, for Outputs 1, 2 and 3, indicators assessed as Green or Amber/Green were validated through discussions with Government officials and the supporting documentary evidence checked on the SPARC website.

The conclusions from this validation exercise are as follows:

- The scoring methodology is being applied in a rigorous way with several internal checks and balances to ensure that the scoring is accurate
- SPARC STMs are fully familiar with the assessment methodology
- Consequently, SPARC’s reporting is accurate and credible.

# Chapter 4

## 4 Value for Money
## 4.1 Introduction
The assessment of value for money in the SPARC programme focused on three aspects:

- Validation of the data contained in SPARC’s Value for Money Working Paper, produced in November 2013;
- Review of allocative efficiency – whether SPARC has allocated resources to states and work streams that offer the best opportunity for reform;
- Assessment of programme value for money – whether the total amount invested by DFID Nigeria in the SPARC programme represents value for money.

## 4.2 SPARC approach to achieving and measuring value for money
On economy, SPARC has identified the key cost drivers in programme administration and is taking appropriate action to manage costs, while maintaining the quality of outputs. Economy savings totalling £3.7 million have been made to date and this total has been achieved through several measures: reduced office accommodation costs (£212,000), better use of human resources (£287,000), increased role of full-time technical staff in supporting capacity development (£2,445,936) and using Nigerian consultants instead of bringing in expatriates (£668,702).

On efficiency, SPARC has identified alternative ways of delivering consultant inputs (the key cost driver). This has involved using more national consultants, with a corresponding increase in central quality assurance, and remote support (largely driven by security constraints). Appropriate indicators, primarily focused on the average cost of key deliverables, have been developed to track overall programme performance on efficiency.

Effectiveness is closely related to the achievement of the overall programme goal: Nigeria’s own resources are used efficiently and effectively to achieve the MDGs. Of three indicators at this level, only one is related to governance performance and this is measured by reference to citizens’ perceptions. The other two indicators are concerned with progress in achieving the MDGs and on improvements in education and health sector outcomes, such as the number of children enrolled and levels of child mortality. SPARC have not fully engaged in measuring effectiveness at this level.

Several of SPARC’s effectiveness indicators, as set out in their VFM Working Paper of November 2013, are focused on the cost of delivering specific outputs and these ‘cost of production’ type measures are more an assessment of efficiency. SPARC have recognised the need to develop VFM measures in regard to the measurement and assessment of outcomes. These effectiveness indicators could be designed to assess the impact of programme outputs; for example, the extent to which MTSS priorities and resource allocations are reflected in state annual budgets.

Where SPARC has had success is in identifying ‘one-off’ cases of financial impact. These are set out in the ARIES report and to date total £202 million, a return of almost five to one from SPARC expenditure (as at October 2013) of £42 million. Most of the case studies flow from specific identifiable improvements in public financial management (for example, consolidating dormant bank accounts and returning funds to the Treasury).

## 4.3 Allocative efficiency

Analysis of budget allocations to individual states for 2013-14 shows that the pre-defined funding envelopes developed in 2012, with the identification of the state typologies, have broadly been respected. However, there have been adjustments to reflect circumstances in individual states. Three states (Anambra, Enugu and Yobe) received significantly in excess of their defined budget, reflecting the level of political commitment and opportunity. By contrast, the Federal component received significantly less, reflecting the current operating difficulties. The SPARC management team advised that, going forward, more emphasis will be placed on levels of commitment, traction, and opportunity in determining annual budgets.
Within states, the indicative logframe weightings for allocating resources to each work stream represent an overall balance of effort rather than a fixed resource allocation figure. SPARC management makes work stream resource allocation decisions based on:

- Priorities identified in collaboration with state governments, in line with state governance reform plans and the SPARC theory of change;
- An understanding of the political economy and related opportunities or constraints for governance reform;
- The relative balance of expertise (and its associated cost) required to successfully deliver work plans.

Analysis of budget allocations to each work stream, for each state, for the duration of the programme showed that there has been a consistent tendency to allocate less than the amount indicated by the logframe weighting to the PFM work stream. This has been balanced by higher allocations to the P&S and PSM work streams. Beyond this, there is no consistent pattern – the balance of support between work streams differs each year for each state and, as such, appears to reflect the best opportunity to make progress.

## 4.4 Assessment of overall programme value for money
The AR team carried out an assessment of value for money at overall programme level. For each of the ten states, plus the Federal component, this took the form of a baseline analysis, comparing current performance with a baseline (generally referenced by the SEAT and PEFA self-assessments carried out in 2008-09 and 2011-12) and taking into account the relative financial investment by SPARC. These assessments are incorporated in the State summaries, attached at Annex D, and in more detailed working papers held by IMEP.

This analysis demonstrated that SPARC investment in four states (Anambra, Enugu, Lagos and Niger) and the Federal component represents good value for money[8] and that investment in a further five states (Kaduna, Katsina, Jigawa, Yobe and Zamfara) represents fair value for money. Only one state, Kano, represents poor value for money. An indicative ‘league table’ of state performance combining the overall achievement scores and this value for money is presented in Table 1 below.
[8] ‘Good value’ represents a situation where achievement is better than could be expected for the financial input; ‘Fair value’ represents a situation where achievement is in line with the financial input; ‘Poor value’ represents a situation where achievement is less than would be expected.

Table 1: Performance ‘league’ table[9]
[9] See Annex D for analysis supporting this table and also the ARIES report
State	Overall Outputs score	VFM assessment

Anambra	A++	Good value
Enugu	A++	Good value
Lagos	A++	Good value
Niger	A+	Good value
Kaduna	A+	Fair value
Katsina	A	Fair value
Jigawa	C	Fair value
Yobe	C	Fair value
Zamfara	C	Fair value
Kano	C	Poor value

Taking account of additional SPARC investment in programme-wide technical activities to support activities in each state, and notwithstanding the disappointing level of performance in Kano State, the review team concluded that the SPARC programme, with total expenditure to date of £42 million, represents value for money for DFID.

## 4.5 Benchmarking SPARC performance with other governance programmes
The design of SPARC, within the context of Nigeria’s Federal and State level system of government, is probably unique. Unlike asset delivery programmes (for example, cash transfer or distribution of mosquito nets) governance programmes in different countries do not revolve around a common set of core activities. In addition, SPARC has the additional challenge of delivering activities in three distinct work streams to ten separate State governments, each of which has different geopolitical contexts. As such, it is highly unlikely that a comparator programme exists to form the basis for a benchmarking exercise.

## 4.6 Recommendations
To demonstrate continued value for money, SPARC should ensure that programme resources are allocated to states and work streams in a way that provides the best opportunity for achieving reform objectives. This should be a combination of a top-down strategic approach and a bottom-up workplan-based approach. SPARC has agreed to document their resource allocation approach for 2014-15.

In terms of assessing programme effectiveness, SPARC should identify and adopt performance indicators that measure the impact of programme ouputs, rather than the cost of achieving those outputs. SPARC should also liaise with other SLPs in an attempt to assess SPARC’s contribution to achieving overall programme objectives.

# Chapter 5

## 5 Sustainability
## 5.1 Definition and understanding
The sustainability of SPARC’s achievements to date is difficult to assess in part due to the iterative, long term nature of the reform processes that SPARC is helping state governments to adopt. For example, putting in place robust, evidence based planning and budgeting is a multi-year programme in any government. The absence of a definition and shared understanding of what ‘sustainability’ means also makes it difficult to draw definite conclusions on the achievements to date. The word ‘sustainability’ is often used together with ‘embed’ and ‘institutionalise’ to describe the situation where previously new activities have become adopted as a matter of routine.

Although there is no agreed working definition within the SPARC programme, there is an appreciation that ‘sustainability’ exhibits a number of characteristics and these are:

- The capability to both replicate a process and to improve on the process both in terms of scope and quality of content
- The ability to maintain the process without external technical assistance; the ability to fund the necessary activities from within ‘own’ resources.

## 5.2 Achievements
Despite the definitional challenges, there are positive signs of probable sustainability within the SPARC programme. In terms of repeated processes, with evident signs of improved quality, and these include:

- Medium Term Sector Strategies – there is evidence that the MTSS process is taking root[10]. In Enugu, 7 sector MTSSs were prepared for 2011-13, updated annually over those three years and revised for 2013-15. The content quality of the 2013-15 MTSSs has improved dramatically from fully meeting only 2.4% of the quality standards to 9%; in the same period the total non compliance in the quality standards reduced from 75% to 42%.
  [10] Medium Term Sector Strategy Development their Content Standards and their Influence on State Budgets SPARC Report April 2013
- Budget documents including the Budget Policy Statements, calendar and call circulars with their content improving year on year (such as the inclusion of sector budget allocations)
- Budget execution rates moving on a positive trajectory to closer to 100% spending against original allocations
- Audited final accounts available within the statutory deadlines.

Performance levels, and the prospects for sustainability, do vary between states and across components. But, as yet, there is no single process that can be judged to be ‘sustainable’ given the outline definition presented above. The MTSS process shows the best prospects. However, it should not be surprising that even after 5 years’ support from SPARC that most of the reform efforts remain ‘work in progress’ given the highly politicised context, widespread capacity constraints and the in-built resistance to change within a public service. DFID’s experience in other countries confirms how difficult governance reform proves to be.

## 5.3 Next steps
In taking the sustainability analysis forward, there are three suggested next steps for the SPARC Team to carry out:

- Prepare a working definition of ‘sustainability’ in relation to the main programme components
- Assess how far along the sustainability ‘spectrum’ can SPARC progress by the end of the programme; set specific targets (to the extent not already defined in logframe) and schedule and fund interventions to help ensure these sustainability targets are met or visible progress made so that a successor reform programme can complete the task
- Consider the implications, if any, of introducing sustainability into the ToC and the implications for gathering an evidence base.

In considering the implications for the ToC, the first issue to consider is where in the intervention logic should sustainability be considered, either at Outcome or Intermediate Impact or Impact levels. Then, depending on the agreed criteria for measuring sustainability decide on (a) the indicator(s) to be used for monitoring, (b) the target(s) to be achieved and (c) the internal SPARC process(es) that need to be introduced to help move towards sustainability (for example, in terms of achieving replication, improving quality and increasing own financing) and the type of evidence that will need to be collected (linked to the indicator(s)) in order to demonstrate success.

# Chapter 6

## 6 Implementation Features
## 6.1 Introduction
There are two features that run through all of SPARC’s work: (1) its engagement with other DFID programmes and (2) the constant attention to managing risk, starting with the political risk and in recent years having to monitor and mitigate the security risks. SPARC, as part of the SLP suite of programmes, was designed as the governance programme working in the central MDAs in support of the sectors. The sector programmes, such as ESSPIN and PATHS 2 were designed as governance programmes in their respective MDAs[11]. Over time, this original design concept was modified to shift the emphasis of the sector programmes to service delivery. The political economy of SPARC’s work has been a prominent feature of its implementation approach; perhaps featuring more in this programme than comparable DFID programmes outside Nigeria. The attention to security has become a prominent feature for all of DFID’s programmes and especially for those programmes operating in the northern states.
[11] GEMS, also part of the SLP suite, was designed after SPARC, SAVI, ESSPIN and PATHS

## 6.2 Linkages between SPARC and other SLPs
The original design of the SLPs focused on 5 states[12]. Over time, as the SLP programmes grew and other DFID programmes were introduced, this focus on common states has become diluted as Table 2 below illustrates.
[12] ESSPIN operated in 6th state, Kwara

Table 2: State distribution of SLPs
Pr’gme / State	SPARC	SAVI	ESSPIN	PATHS2	GEMS1	GEMS2	GEMS3	GEMS4
Anambra	X	X			X
Cross River					X	X	X	X
Enugu	X	X	X	X
Jigawa	X	X	X	X
Kaduna	X	X	X	X	X	X	X	X
Kano	X	X	X	X	X	X	X	X
Katsina	X	X
Kwara			X
Lagos	X	X	X	X	X	X	X	X
Niger	X	X
Yobe	X	X
Zamfara	X	X

Where there is a joint presence in a state, there are close working relationships as evidenced by:

- Routine meetings of the respective state team managers (mainly chaired by the SPARC STM), often with the DFID state representative participating, where information is shared about events and work plans
- Joint working, especially between SPARC and SAVI and mainly in relation to SAVI’s work with SHoA
- Adoption by the sector programmes of SPARC’s guidelines and tools such as the preparation of MTSSs and more recently the HRM guidelines[13].
  [13] The experience of ESSPIN in Kano taking SPARC’s HRM guidelines and corporate planning approach into the Ministry of Education and SUBEB is a good example

These working relationships have strengthened over time and most probably in recognition of the mutual value derived from information sharing, deploying complementary skills and optimising the use relevant tools and techniques. Clearly, there are benefits for this synergy to continue and even extended wherever possible.

## 6.3 Risk management
SPARC’s approach to risk management is ‘hard wired’ into its routine management processes. In relation to the security risks, SPARC deploys the necessary technical expertise to regularly monitor the nature and extent of possible threats to its operations and there is a routine risk reporting from the state offices to Abuja with regular updates circulated across the programme. All of this effort is coordinated closely with the wider security monitoring adopted by DFID and its other programmes. SPARC has responded innovatively to help mitigate risks through establishing communities of practice and in facilitating ‘partnering’ between states (such as between Zamfara and Kaduna and between Yobe and Jigawa).

In relation to the technical, operational risks for day-to-day implementation the quarterly progress reporting provides an update of how selected risks are affecting, and are likely to affect, progress with implementing activities in each state. For each state, the quarterly progress reports are prefaced by a brief scan of the political horizon with any critical events being highlighted. Also, informative analytical work is completed to continually update SPARC’s approach in each state such as its work on looking at the politics of the state budgets.

# Chapter 7

## 7 Governance Reform post SPARC
## 7.1 Lessons learned
The experience to date, covering both SPARC and its predecessor programme SLGP, is that:

- Reform is a slow and long process; it is not linear and success ebbs and flows (especially with changes in political leadership)
- Each state is different and presents its own challenges
- Interventions need to be presented as a coherent ‘menu’ which provides flexibility to move ahead on areas which have traction at a particular time and allows for adjustment when progress falters or indeed accelerates
- Donor driven reform does not in itself create the demand for reform; DFID interventions have greater chance of success where they align with the agendas of reform minded Governors.

## 7.2 Possible components
The approach to governance reform is in line with the main building blocks that are included in DFID’s capability, accountability and responsiveness framework and reflect features of governance reform internationally. For the future, the content of a governance programme is likely to contain the same or similar elements. For the recent 5 new states, the reform process has just started and there is still a long way to go. For the original 5 states, new processes are being adopted and replicated year on year but it is probably too early to say with confidence that these reforms are sustainable. So the substance of the basic design remains relevant and appropriate as is the selection of participating states.

During the review, and in the meetings with Government officials in the states visited, the following areas were discussed as priorities for continued and/or new support:

  - More ‘on the job’ skills development, in part to widen the competency base but also to replenish the skills as staff are rotated to other assignments within the civil service
  - Building the evidence base for implementation of SDPs and MTSSs – upgrading systems and skills for monitoring and evaluation
  - IT systems design – providing technical guidance of how best to implement 2nd generation IFMIS and 1st generation HRMIS.

SPARC’s approach to ‘on the job’ skills development was welcomed largely because it is targeted to improving practical skills related to the introduction of new tools and techniques and it does not require long periods away from the place of work. The use of short workshops, with participants drawn from several states, is much appreciated. It provides for a valuable exchange of experiences, especially between SPARC ‘partner’ states. Then, in addition, the availability of guidelines and briefing notes accessible from the SPARC website provides a valuable additional learning resource.

## 7.3 Future design questions
The likely detailed design questions will be around focus and balance. In terms of focus: which states, which MDAs (central or service delivery), and whether to include local governments. In terms of balance: how many states and what should be the emphasis in relation to the breadth and depth of DFID’s engagement?

The selection of states is for DFID to decide. It seems pragmatic to continue with the current states where progress is visible, continues to be made in the next year and where the incoming Governors, post national elections, are reform minded. In looking at the MDAs where the focus should be, then serious consideration needs to be given to shifting the effort more towards the spending agencies and away from the central MDAs such as Finance, Budget and Economic Planning and OHCS. It is in the service delivery MDAs where the demand and pressure for reform is most evident and this is where the major efficiency and effectiveness gains can be achieved. However the design question remains about whether to place the governance reform within a sector specific programme, such as ESSPIN and PATHS 2, or have it located within a complementary intervention such as a SPARC successor. This is the design issue that has been present since the design of the original SLPs back in 2007.

Should the next DFID governance programme include local governments? SLGP included local government explicitly, SPARC has not. Working with and through local governments is necessary and essential in the context of service delivery as ESSPIN and PATHS 2 have recognised as well as M4D. Given the continuing tensions between state and local governments, and that there is still much more reform needed at the state level, the balance of probability is that a new governance programme should not venture into local government. However if such a move gains favour, and some form of piloting gains support, then Lagos State might be the most receptive and potentially rewarding.

In terms of the number of states, SPARC has been successful in scaling up from 5 to 10 states whilst sustaining value for money. However, given the finite resources available to DFID, the question is not so much the number of states but whether to go for breadth of coverage (touching as many states with as much of the governance reform portfolio in the expectation that states will be stimulated to ‘pick up the reform baton’ and run with it) or depth of coverage (drilling down, embedding change and seeing how and whether transformational reform can be achieved, especially when the crucial decisions about the size, structure and performance of the civil service are brought into sharper relief). From a learning perspective, probably depth of coverage would generate the most informative evidence of what can work and why (and the corollary of what can’t work and why). However, breadth of coverage may be needed to address the country’s demand for representation across the geo-political regions and DFID’s focus on targeting the states with greatest need.

In designing a new programme, it will be important to try and articulate what successful governance reform will look like. The current programme starts from the premise that systems and processes are weak, as measured by the PEFA and SEAT tools, and that over time improvements will be made across a broad front. However, there is no explicit statement of the standards to be achieved for given levels of investment. As part of the further consideration of the definition and measurement of ‘sustainability’, a clearer picture should emerge as to what standards can DFID reasonably expect to help selected states achieve over the life of the next governance programme. This should be easier to specify now after so many years of SPARC engagement, combined with the individual states’ experience of designing their own change action plans and monitoring their own performance.

In the current programme design, the ‘politics’ of reform is dealt with as a risk to be monitored and mitigated where possible. It does not feature as an area in which SPARC proactively and extensively intervenes to help bring about change[14]. Given how important the political economy is to the success or failure of reform, the question can be asked “should a successor programme adopt a different approach in this highly politicised environment and more actively engage with the party political leadership structures and processes?“ Deciding to become more involved in the political party structures would require very careful consideration in the context of the inherent challenges and implications for DFID in managing this relationship.
[14] SPARC’s work with the Nigeria Governors’ Forum could be seen as part of a political influencing approach without being involved in or with the formal political party structures
# Annex A
## List of documents reviewed
SPARC

Annual Report for the Period August 2012 to June 2013 July 2013
Quarterly Progress Report (No 14) for the period January to March 2013 April 2013
Quarterly Progress Report (No 15) for the period July to September 2013 October 2013
Updated Quarterly Progress Report (No 15) Annex 1 November 2013
SPARC Self Assessment Aries Form for 2013 AR, November 2013
State Self-Assessment Guidelines Working Draft – for consultation, March 2011
Public Service Management Self Assessment Performance Measurement Framework
Policy and Strategy and Information Management / M&E for State Governance Reform A Performance Measurement Framework for a Self-Assessment Workshop
2009-2012 PEFA/SEAT scores
SPARC Consolidation and Expansion Strategy, May 2012
SPARC planning, monitoring and evaluation systems, October 2013
Theory of Change, April 2013
Logframe RAG criteria, September 2013
The Partnership between SPARC and Zamfara State Government, Working Together to Strengthen Accountability, Responsiveness and Capability, Agreed Approach. January 2013
Work Plan Narratives for the period July 2013 to June 2015, June 2013
Briefing Note: Response to 2012 Annual Review Recommendations
State and Programme Logical Frameworks and Activity Logs For the period July 2013 to June 2015
Knowledge Management Strategic Plan, revised October 2012
Value for Money, November 2013
Value for Money, December 2012
Finance data for AR VFM analysis: 2009/12, 2012/13, 2103/14
Issues leaflets, Lessons leaflets, Partner results leaflets, Results leaflets, Voices leaflets

DFID

Scale Up of the State Partnership for Accountability, Responsiveness and Capability (SPARC) Programme Business Case October 2012
SPARC AR 2012, February 2013
Zamfara State Engagement Strategy – 2013/15
DFID Nigeria Programme Overview
Nigeria Operational Plan: Current Project Portfolio

State Governments

Enugu State Government Public Service Management Self Assessment Report, April 2012
Jigawa State Government Public Service Management Self Assessment Report, April 2012
Kaduna State Government Public Service Management Self Assessment Report
Kano State Government Public Service Management Self Assessment Report
Katsina State Government Public Service Management Self Assessment Report
Lagos State Government Public Service Management Self Assessment Report, March 2012
Yobe State Government Public Service Management Self Assessment Report
Zamfara State Government Public Service Management Self Assessment Report
Jigawa State Government Performance Evaluation Report on Jigawa State Comprehensive Development Framework, September, 2013
Synthesis Report of the 2nd Joint Annual Performance Review of the Jigawa State Governance Change Programme, August 2009 to July 2011
Plus a selection of state development plans, budget documents and HRM reports prepared by individual states with SPARC’s assistance

Other

PEFA Public Financial Management Performance Measurement Framework, June 2005
The Independent Monitoring and Evaluation Project for the State Level Programmes (IMEP)

A Common Framework for Value for Money Analysis in State Level Programmes, October, 2013
Accelerating Progress, Sustaining Results, The MDGs to 2015 and Beyond, UNDP September 2013
Selection of World Bank Project Appraisal Documents relating to PFM

# Annex B

## List of people met

Organisation	Name		Designation		Contact
Nigerian Governors’ Forum, Abuja	Mr. Asishana Okauru		Director General		08035981617 / aokauru@yahoo.com
	Titilola Akindeinde		Policy Adviser		08105253025 / Takindeinde@ymail.com
	Myani Bukar		Knowledge Management Adviser		08028853632 / bukaru@gmail.com
	Lot Shittu		Executive Director (Strategy & Research)		08077361336 / Lotshittu@hotmail.com
	Juliet C. Eleje		Technical Assistant to DG		07032884713 / julieteleje@gmail.com
MDGS – CGS	Dr. I.J. Falegan		Technical Adviser to Senior Special Adviser to President (SSAP) on MDG		08035752157 / faleganji@yahoo.com
	Dr. S.F. Brisibe		Head, CGS-OSSAP-MDG		08033131614
World Bank	Jariya Hoffman		Senior Economist		08140439769 / Jhoffman@worldbank.org
PATHS 2	Dr. Steve Harris		Deputy Program Manager		07063650184 / s.harris@paths2.org
	Benson Obonyo		Deputy National Programme Manager - Technical		08135385045 / b.ochonyo@paths2.org
Kano State
Ministry of Planning and Budget	Shuaibu Musa		Permanent Secretary, Planning and Budget		08061619060
	Baballe Ammani		Director Statistics		08055581420
	Taiyes Na’abba		Director Budget		08037133685
	Ali Sani Fane		Deputy Director		08059867985
Office of Head of Service	Umar Muhammed Jalo		Permanent Secretary, Special Duties		08033491565
Ministry of Finance	Muhammed Auwal Naiya		Permanent secretary		08035907251 / Auwalnaiya@yahoo.com
	Basiru M. Lawan		Director Final Accounts		08035860606 / Bashirla73@yahoo.com
	Ibrahim A.M. Kura		Director Treasury		08033492538 / imkura@yahoo.com
Ministry of Environment	Muhammad Badawi		Permanent secretary		08097899999
	Lawal Habib Ibrahim		Director Admin		08065525517
	Hashim S. Minjibar		Director Planning, Research and statistics		08035191667
SERVICOM	Kabiru M. Gwangwazo		State Coordinator		08034511721 / kgwangwazo@yahoo.com
	Hamisu Sule Garko		Head of Administration		08092184438, 08023666812 / Garkohamisusule@yahoo.com
Jigawa State
Ministry of Budget and Economic Planning		Abdulaziz Abdulhamid	Special Adviser to Governor		08060316805
		Sani Ahmed Jaliun	Acting Accountant General		07038228767
		Adamu Muhammed G.	Permanent Secretary, Budget and Planning		08036832233
		Aminu S/Hatsi Kudai	Director Budget		08065282818 / aminukudai@gmail.com
		Aminu Adamu Ringui	Director MDGs		07033852606 / Aminuring@yahoo.com
Office of Head of Service		Mustapha Aminu Dutse, mni	Head of Civil Service		08034520867 / Mustapha1960@yahoo.com
		Na’Annabi Ahmed	Permanent Secretary, / Establishment		08036077332
Ministry of Finance		Habibah isa-Dutse	Permanent Secretary		08036423794 / hidutse@yahoo.com
		Sani Ahmed Jahun	Acting Accountant General		07038228767
		Abdu Umar Adan	Director Account and Finance		08037808771
		Tanko Muhammad	Director, Debt Management		08105696920
		Muhammad Haruna	Deputy Director Finance and Accounts		08036227048
Yobe State
Yobe government Officials		Muhammad B. Ibrahim	Ministry of Budget and Planning		08039368007 / Gadaka22@yahoo.com
		Adamu Idi Danchuwa	Accountant General		08065034224
		Smaila Babale	Director, Service welfare (Office of Head of Service)		07065641618
		Lawan Gajerima	Permanent Secretary, State Ministry of Healthy		08036070703
Zamfara State
Ministry of Budget and Economic Planning		Kabiru Mohammed	Permanent Secretary		08062242525 / Malkabs@yahoo.co.uk
		Hamza Salihu	Director of Budget		08036309922
		Dalhatu Musa	Director of Economic Planning		08034762059 / Dalhatumusa64@yahoo.com
		Kabiru Samaila	Deputy Director Planning		0703155496
Office of Head of Service		Muhammad Bello Umar, mni	Head of Service		08037874179
		Ahmad Gusau	Chairman Civil service Commission		08065690925
		Hamza Salihu	Director of Budget		08036309922
		Yakubu Mohmmed Tsafe	Secretary ExCo		08065662272
		Joseph U. Tsafe	Director Labour		08108770636
		Ismaila Muhammad Aminu	Executive Secretary		08030684995 / Iaminu4@gmail.com
Ministry of Finance		Mohammed M. Abubakar	Director, computer Services		08032094843 / baukabis@yahoo.com
		Sirrajo Hassan	Director Main Accounts		08035251123
		Sani Muhammad Nakwada	Director Debt Management		08025503888 / Muhammadsani44@yahoo.com
Board of Internal Revenue		Ibrahim Abdulwasir	Director, Board of Internal Revenue		08036003544
		Shehu Dandare Gummi	Director Assessment		08060600393
State Ministry of Health		Dr. Lawal U. Bungundu	Permanent Secretary		08062222876
		Bello A. Anka	Director, Planning, Research and Statistics		08036141576
		Ahmad Rufai Halilu	HMIS Officer		08034576300
DFID
		Tia Raappanna		Governance Adviser
		Okey Eze		Programme Manager
		Zaynab Lukat		State Representative, Jigawa & Yobe

SPARC
		Mark Walker		National Programme Manager
		Joe Abbah		Fmr National Programme Manager
		Chris Perry		M&E Manager
		Ursula Blackshaw		PSM Stream Leader
		Alan Griffiths		Finance Manager
		Steve Hallan		PFM Stream Leader
		Tim Donaldson		Knowledge Management
		Hadiza Elayo		Federal Programme Manager
		Ben Arikpo		Lagos State Team Manager
		Ifeanyi Peters Ugwuoke		Niger State Team Manager
		Sam Onyia		Enugu State Team Manager
		Yusuf Jajire		Yobe State Team Manager
		Auwalu Yusuf and Team		Jigawa State Team Manager
		Hadjira Shibkau and Team		Zamfara State Team Manager

# Annex C
## SPARC’s updated Theory of Change: Programme Intervention Logic and Relationship to TOC

Political Engagement
DFID and SLPs
Technical Approach
### Table 1: Programme Intervention Logic: Assumptions and Evidence
Output - Improvements
Assumptions	Evidence
State governments apply improved policy and strategy making methods.	State specific MTSS guidelines have been adopted in Anambra, Kano, Niger, Yobe and Zamfara, whilst previously adopted MTSS guidelines have been formally issued to the majority of MDAs by the central planning agency in Enugu, Jigawa, Kaduna and Lagos. All guidelines are consistent with good practice standards. / State policy guides have been prepared and are in use in Anambra, Jigawa, Kaduna, Kano, Katsina and Yobe. / New strategy and policy making processes are being promoted by the central planning agency in Enugu and Lagos and are consistent with good practice standards. / Relevant SEAT/PEFA scores show improvement.
State governments apply improved methods for assuring fiscal and budget discipline.	Budget call circulars which include aggregate and sector budget allocations based on fiscal/revenue forecasts have been prepared in Anambra, Enugu, Jigawa, Kaduna, Lagos, Niger, Yobe and Zamfara. / Budget manual has been prepared and formally adopted in Anambra and Enugu and budget documentation meets 6 out 9 PEFA standards in Kaduna. / The Budget Classification and Chart of Accounts (BC&COA) have been reviewed in Jigawa, Kaduna, Kano, Katsina, Lagos and successfully updated in Kaduna, Katsina and Lagos. / A cash forecasting model has been developed and is in use in Jigawa, Kano, Lagos and Niger whilst training on cash planning/profiling in selected sectors has been provided in Enugu, Kaduna and Yobe. / Yobe State House of Assembly have demanded access to and participation in YOSERA III and MTSSs. Katsina State House of Assembly demanded the release of accounts, following which the Auditor General published accounts for 2008, 2009 and 2010. / Relevant PEFA scores show improvement.
State governments apply approaches to reorganization and civil service performance improvement.	Mandates have been revised and updated for selected MDAs in Anambra, Enugu, Jigawa, Kano and Lagos whilst mandates have been mapped across government in Niger, Yobe and Zamfara. / The majority of targeted MDAs have completed the first phase of corporate planning in Enugu, Jigawa, Kano, Katsina, and Lagos. Corporate planning is underway in targeted MDAs in Yobe and Zamfara. A system and guidelines for expanding corporate planning across government is being used in 5 additional MDAs in Kaduna. / Service charters have been developed for targeted MDAs in Enugu, Jigawa, Kaduna, Kano and Lagos. / The capacity of a relevant unit to support MDAs in the preparation of service charters has been developed in Enugu, Jigawa, Kaduna, Kano, and Lagos. / Relevant SEAT/PEFA scores show improvement.
State governments engage in national performance improvement initiatives.	Piloting of the SPRM is complete in two out of the four pilot states. The remaining two are in the third and fourth (of six) stages of the process. / Four new states outside the pilot states have commenced the SPRM process. / All 36 States and the FCT have continued to apply for the State level CGS grant which has consistently been reviewed and adjusted - making the process stronger each year. / The LG CGS is fully operational. The LGAs currently in the scheme stand at 511 with the addition of 250 LGAs in 2013 to the already existing 113 which commenced in 2011 and an additional 148 in 2012.

Improvements - Outcome
Assumptions	Evidence
State govt policies and strategies are financially feasible and are aligned to budgets.	State development plans have been formally approved and subsequently updated in Enugu, Kano, Jigawa, Kaduna and Lagos, awaiting final approval in Yobe and under development in Katsina and Zamfara. Approved SDPs meet the required level of compliance with policy content standards. / 2014-2016 MTSSs have been prepared and are being finalized for all targeted priority sectors in Enugu, Jigawa, Kaduna, Kano, Lagos, Niger, Yobe and Zamfara. Where assessed, draft MTSSs meet the required level of compliance with strategy standards.
State governments exercise better fiscal and budget discipline.	Variances in expenditure outturns against original budget have been demonstrated by Enugu, Lagos and Niger based on 2012 outturn information. Both Enugu and Niger have demonstrated sustained reductions in expenditure variances since 2009 and 2010 respectively. Outturn data for 2012 is not yet available for other states to provide sufficient evidence, however Yobe and Jigawa have both demonstrated variance reductions since 2010 and 2011 respectively. This evidence is based on the PEFA based assessment of expenditure outturn against original budget. / 2014 budgets have reduced in absolute terms compared to 2013 budgets in Jigawa, Yobe, Zamfara, and Lagos. Niger and Zamfara reconsidered initial 2013 budget proposals, approving reduced budgets more in line with historic trends and revenue forecasts. / Anambra and Zamfara have demonstrated improvements in budget discipline through improved budget documentation and processes, including the introduction of ceilings in their 2013 budget call circulars.
State governments make organizational changes and demand better performance of civil servants.	Mandates have been agreed and published in Enugu, Jigawa, Kaduna, Kano, Lagos and Niger. Some reorganisation to rationalise mandates has taken place in Enugu, Jigawa, and Kano. In Kaduna and Lagos, mandate review guidelines have been adopted and circulated. In Lagos the deputy governor led a subcommittee to conduct a second review of mandates. / In Jigawa and Lagos, reorganisation of priority MDAs based on corporate planning is underway. Kaduna BPSR has been given responsibility for rolling out corporate planning, currently in 10 MDAs covering of the 12 sectors in the state, and Lagos has also taken the decision to roll out corporate planning under the direction of OoT. Yobe has begun to implement first stage CP decisions. / Jigawa and Kaduna have agreed, and Enugu and Kano are currently considering modern HRM policies and/or improvement plans at ExCo level. Lagos is furthest advanced, with a suite of HRM policies agreed, along with a detailed HRM improvement strategy which has already been piloted in six MDAs. / ‘SERVICOM’ units/teams have been established and Service Charters have been developed in Enugu, Jigawa, Kaduna, Kano, and Lagos in addition, Lagos has introduced Performance Agreements for Commissioners, and Kaduna has agreed to adopt a new employee performance management guideline.
State governments implement SPRM programme of action (SPoA) and continue to meet CGS conditions.	Implementation of the SPoA in Anambra has led to the documentation of ANIDS; Budget Process and Management Manual developed, with Planning and Budgeting Calendar revised and updated; MTSS Guide with clearly defined results frameworks and KPIs developed and disseminated etc. Ekiti has made efforts with restructuring the Civil Service, Budget linkages to MTSS have been improved and plans are on the way to scale up SPRM to Local Government level. / In 2012 the state CGS criteria was improved by allocating scores to the Governance criteria indicators for the first time since its inclusion in 2011. / In 2013, the state CGS criteria was further strengthened by requesting that states provide detailed operational plans and budgets and show evidence of counterpart funds in state government annual budgets. Scores where increased for evidence of institutional capacity to account for CGS funds, a governance framework for the application of projects under the governance section was developed and gender issues included as evaluation criteria.

Outcome - Intermediate Impact
Assumptions	Evidence
Improved government effectiveness leads to improved service delivery.	Growing academic evidence links stronger institutions and improvements in service delivery, including: / World Bank: Making Services Work for Poor People 2003. / World Bank: Strengthening World Bank Group Engagement on Governance and Anticorruption 2007. / Differences in efficacy of public spending on health and education can largely be explained by the quality of governance (Rajkumar & Swaroop: Public Spending and Outcomes: Does Governance Matter. World Bank 2007. / Government effectiveness is positively associated with per capita incomes, adult literacy and reduced infant mortality (Kaufmann, Kraay and Mastuzzi Governance Matters 3: Governance indicators for 1996 to 2002. World Bank 2003). / Public administration reform is intensely political and needs local leadership rather than being donor-driven (Schacter, M: Public Sector Reform in developing Countries: Issues, Lessons and Future Directions [CIDA 2000]). / More successful public sector reform initiatives depend on readiness, innovation and flexibility and are integrated with wider reforms (Robinson, M:The Politics of Successful Governance Reforms: Lessons for Design and Implementation (2007: Commonwealth and Comparative Politics 45:4). / SPARC will be assessing the evidence base for this assumption as part of the 2014 Evaluation Study.
Improved quality of policies and strategies lead to better targeting and service delivery.	Brumby, J: An Investigation into the Impact of the Medium Term Expenditure Framework. on Budgetary Outcomes. World Bank and related publications, 2010 onwards.
Improved fiscal and budget discipline leads to better allocation and utilization of resources.	Earle, L et al: Assessing the Evidence of the Impact of Governance on Development Outcomes and Already Reduction (Emerging Issues Research Service GSRDC) 2010.
Better organization and management of civil servants leads to improved service delivery.	World Bank: Making Services Work for Poor People (2003) cites growing evidence that stronger institutions are linked to improved service delivery. / World Bank CPIA evaluations concluded that civil service reforms led to some improvements in the quality of public administration in only 42% of countries assessed. However World Bank Public Sector Reform: What Works and Why 2008 records that institutional reforms are not easily assessed using empirics. / CPIA criteria themselves may reflect a generic 'neoliberal and administrative modernisation' bias (The limits of Institutional Reform in Development: M. Andrews Cambridge University Press 2013.)
Other DFID programmes contribute to improved sector performance.	IMEP may be able to provide evidence to assess whether or not this assumption is holding from its reviews of the other programmes, alongside the comparator states study it has completed as part of the SLP suite evaluation. / ESSPIN Composite Survey 2013, to be repeated 2014 and 2015.

Intermediate Impact - Impact
Assumptions	Evidence
Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC.	Growing academic evidence confirms that challenges in government stem from a combination of patronage politics and weak systems, including: / Earle, L et al: Assessing the Evidence of the Impact of Governance on Development Outcomes and Poverty Reduction (Emerging Issues Research Service GSDRC 2010)) / Aigbokhan, B: Growth, Inequality and Poverty in Nigeria 2008. / SPARC is planning to document its experience of transitions between administrations, which gives some indication of the likelihood that political will be sustained through a transition period after the end of SPARC.
State governments continue to prioritize the MDGs in the allocation and use of public resources.	Although it is difficult to track expenditure against MDGs explicitly it is possible to use health and education expenditures as a proxy and to show that the majority of states are increasing or maintaining sufficient[15] shares of expenditure in these sectors. / Across the ten SPARC states, 2011 expenditures show that three states (Jigawa, Katsina and Niger) allocated more than 30% to health and education, whilst two allocated less than 20% (Anambra and Lagos). Looking at the totals across all ten states over 2004-2011, expenditure has varied between 16-24%. / Jigawa has shown a very substantial increase in health and education expenditure - rising from a low of 8% in 2006 to 41% in 2011. In other states, health and education expenditure has increased more modestly. For example, between 2006 and 2011, expenditure rose steadily from 21% to 25% in Kaduna (with a high of 35% in 2010), from 18% to 23% in Kano, from 22% to 32% in Katsina (with a high of 42% in 2007), from 14% to 19% in Lagos and from 17% to 22% in Yobe. / Some states have decreased expenditure on health and education. For example, between 2006 and 2011, expenditure fell from 17% to 16% in Anambra (with a low of 10% in 2012), and from 33% to 20% in Enugu. Niger has demonstrated volatility in health and education spending, varying between 24-31% over 2006-2011 before falling sharply to 7% in 2012. / Ideally, this would be assessed through a combination of PEFA performance and Public Expenditure Tracking Surveys (PETS) (although that would necessarily be carried out by sector programmes, rather than SPARC.)
Levels and fluctuations in oil revenues do not unduly undermine fiscal stability.	Information to assess whether or not this assumption is holding may be available from the Federal Ministry of Finance.
SAVI achieves sustainable improvements in state government inclusivity and responsiveness to citizens’ rights and demands.	SAVI should be able to provide evidence to assess whether or not this assumption is holding, including through the SAVI Governance Index.
[15] In recent years, there have been a number of declarations proclaiming that countries will strive to achieve internationally agreed upon sectoral budget targets. The Abuja declaration committed African leaders to a 15% budget target for health expenditure and the Dakar declaration set a 20% budget goal for education; making a total of 35%.

# Annex D
# State performance summaries
# Introduction
This annex provides summaries of the performance of each state and the analysis is structured as follows:

- ARIES scoring (by Outcome, by individual Output and for all Outputs) for 2012, where available
- ARIES scoring for 2013
- Value for money assessment: good value, fair value and poor value
- Spending and value for money achievements that informed the assessment
- Observations on performance in the state to highlight notable features.

The methodology note indicates those states visited and those not visited. Where no visit took place, the note indicates also but where the SPARC State Programme Manager was interviewed. These summaries, especially for the explanation of the scoring and the value for money assessment, need to be read in conjunction with the ARIES report. Each state, in the heading, includes a notation of ‘A’, ‘B’ or ‘C’ which indicates its classification in the SPARC typology for engaging with the 10 states.

## Indicative ranking of states
This table provides a snapshot of the comparative performance of each state, with those states listed at the top being the better performers.

Performance ‘league’ table

State	Overall Outputs score	VFM assessment

Anambra	A++	Good value
Enugu	A++	Good value
Lagos	A++	Good value
Niger	A+	Good value
Kaduna	A+	Fair value
Katsina	A	Fair value
Jigawa	C	Fair value
Yobe	C	Fair value
Zamfara	C	Fair value
Kano	C	Poor value

## Anambra ( C)
Performance assessment summary
	2012 AR	2013 AR
Outcome	N/ass’d	A++
Output 1	N/ass’d	A+
Output 2	N/ass’d	A++
Output 3	N/ass’d	A++
Output overall	N/ass’d	A++
Value for money	N/ass’d	Good value

AR methodology

Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC, Logframe Update as at November 2013

Value for money performance
Work stream and funding	Main VFM achievements compared to baseline (2011)

P&S: £149,326	Agreed Intervention Approach signed by Governor in February 2013 and provides guide for work plans. Integrated Development Strategy documented, but not published. Framework for SDP agreed with MoEPB. MTSS guideline ‘domesticated’ and 24 service managers trained in its use. Pilot MTSS being prepared for Agriculture sector.

PFM: £166,621	Draft multi-year fiscal forecasts include the 2014 Budget Policy Statement, 2014-16 Economic and Fiscal Update, and Fiscal Strategy Paper. 2014 BCC includes sector budget allocations based on forecasts from the Revenue Model. Final draft IGR Improvement Strategy developed. Revised budget performance reporting templates developed, but not yet piloted. Draft Procurement Manual prepared and validated by AnSG. On the downside, government refused to pilot cash forecasting and expenditure variance for 2012 high (though down 25% on 2011).

PSM: £135,728	Mandates of three central MDAs clarified and documented. PSM analytical report produced, with description of MDAs, and will provide basis for future mandate clarification and workforce audit. Concept of corporate planning introduced – ‘roadmap’ developed and corporate planning processes introduced in two MDAs. Following stakeholder consultation, HRM policy/Principles Concept Paper adopted by AnSG.

Total: £451,675	Given the limited expenditure by SPARC, the achievements made in Anambra State represent good value for money.

Observations on performance

Strong performance across all components / High level political engagement committee established to help guide SPARC implementation, chaired by Chief of Staff/Honourable Commissioner, Ministry of Economic Planning and Budgeting / Agreed Intervention Approach formally adopted by State Government to help formalise the SPARC role in the state and Government’s reciprocal obligations / For SPARC implementation, Anambra ‘partnered’ with Enugu with SPARC Enugu STM managing the Anambra engagement / Guides have been produced for SDP and MTSSs but as yet no products emerged – though conclusion of Agriculture MTSS is imminent / Budget documentation improving: call circular and Budget Manual now adopted / Procurement Manual validated by State Government / The existing OHoS and MEPB mandates have been revised, updated and adopted by the State Government / Process for moving into corporate planning at early stage of design.

## Enugu (B)
Performance assessment summary

	2012 AR	2013 AR
Outcome	B	A++
Output 1	A++	A++
Output 2	C	A++
Output 3	A	A
Output overall	A	A++
Value for money	N/Ass’d	Good value

AR methodology

(a) Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC, Logframe Update as at November 2013 / (b) Meeting with SPARC STM for Enugu in Abuja

Value for money performance

Work stream and funding	Main VFM achievements compared to baseline (2008)

P&S: £873,339	The 2012-15 SDP, approved by ExCo, meets 75% of content standards and is being updated for 2014-16. The 2012 MTSSs met 42% of content standards, compared with 16% in 2010. This was the best improvement across the five original states. All six MTSSs cover three years and incorporate outputs and KPIs. Five of the six were considered to be financially feasible (within ceilings) and were developed with public involvement. Three of the six are consistent with national policy. Linkage of the 2012 MTSSs to the 2013 Budget were considerably better than those of the 2012 MTSSs to the 2011 Budget – two had variances of less than 1%. Seven 2014-16 MTTSs have been approved and they meet more than 30% of content standards (the specified milestone). There are high level KPIs and targets for all the sectors in the Medium Term Development Plan, though baseline data exists for less than 15% of KPIs. MTSSs also contain high level KPIs, baselines, and targets. The Central Planning Agency has provided training and support to sectors on annual performance reviews. On political commitment to governance reform, two high level discussions have been held.

PFM: £1,450,922	Expenditure variance improved to 17.9% in 2010 and to a significantly better 5.5% overspend in 2011, before dropping back to a 14.0% underspend in 2012. Major progress has been made in credible and realistic budget preparation, execution and control: there is a fiscal forecasting model and key budgeting instruments (MTEF, Fiscal Strategy Paper, Budget Policy Statement, budget profiling, cash management frameworks) have been introduced into the budgeting system. Revised budget manual and calendar, and draft final accounts manual, led to early approval of 2013 budget and timely completion of 2012 accounts. An MDA-wide assets registration and reporting template is being piloted and should help safeguard assets (and result in additional funds from asset disposals). Staff have been trained in debt management, procurement, and audit procedures.

PSM: £985,596	Mandates documented for all ministries and clarified in respect of planning functions. Training provided on corporate planning processes and service charter development. First phase of corporate planning in OHoS completed and new structure recommended. Modern HRM policy, covering over 50% of content standards, and Action Plan presented to EnSG. Workforce planning ‘approach paper’ prepared, which should inform establishment and workforce planning (currently behind schedule) in OHoS. Service Charters, with performance standards, developed for seven pilot MDAs and SERVICOM has provided significant support to MDAs.

Total: £3,943,399 (including Inception activities)	For the level of SPARC resources invested in Enugu State, the achievement, particularly in the PFM work stream, represents good value for money.

Observations on performance

A strong performer; a notable, positive shift in gear from last year’s assessment. / Good access to Governor and Commissioners through six monthly KPI review meeting for DFID’s SLPs / Monthly meeting between SPARC and Secretary to State Government to review progress with SPARC interventions and to resolve any issues / Well established infrastructure in place for coordination between DFID programmes and for overall engagement of, and supervision by, state government (via the mechanism of the State Steering Committee) / Joint working with SAVI on Citizens’ Guide to the Budget and support to the Legislative Budget Research Office / Enugu State Statistical Act passed to help strengthen data management in support of evidence base for measuring the results of the Enugu State Vision 4:2020 Medium Term Implementation Plan / For the first time, in preparing the 2014 Budget used a Budget Policy Statement approved by ExCo / Government proceeding with the implementation of second generation IFMIS but SPARC not clear over the detailed specifications and implementation plan / Efforts in corporate planning and restructuring have started in OHoS but not yet rolled out to other MDAs / HRM Improvement Action Plan awaiting agreement by ExCo of new state HRM policy

## Jigawa (A)
Performance assessment summary

	2012 AR	2013 AR
Outcome	C	A++[16]
Output 1	A+	B
Output 2	N/ass’d	C
Output 3	C	A
Output overall	N/ass’d	C
Value for money	N/ass’d	Fair value
[16] Based only on one measured indicator (out of a possible 3)

AR methodology
(a) Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC, Logframe Update as at November 2013 / (b) Meeting with SPARC STM and team in Kano and Dutse / (c) Meetings with State Government officials / (d) Meeting with DFID State Government representative

Value for money performance

Work stream and funding	Main VFM achievements compared to baseline (2008)

P&S: £1,607,151	Comprehensive Development Framework (CDF) reviewed and Results Framework developed. CDF is more robust, containing sharper sector targets. Performance Report produced and validated for all KPIs and targets. CDF fully consistent with 6 of 7 policy content standards. MTSSs ‘rolled over’ for 2014-16 in five priority sectors and new MTSS developed for Commerce. Four MTSSs meet expected policy and content standards. Linkage of MTSSs to budget is variable. Guidelines relating to development of policy, strategy, and M&E provided to 75% of MDAs and include reference to 75% of process standards. The CDF has comprehensive KPIs and data definitions for all nine sectors. Sector performance reviews have been carried out.

PFM: £1,730,033	Expenditure variance was 3.6% (overspend) in 2011 and 9.0% (underspend) in 2012 – expenditure was up 22.9% against a budget increase of 39.7%. BC and CoA reviewed (in line with Federal Directive). Extent of budget documentation improved slightly (4 of 9 on PEFA dimension). Cash forecasting model developed and IGR Improvement Strategy being completed. New revenue forecasting tool provides a good link between forecast and budget ceilings. Pay and pensions systems computerised and ‘ghost’ workers removed from payroll. Monthly expenditure reports being produced, though with some delay. Draft debt policy produced. Procurement law and guidelines reviewed and over 140 officials trained. Compliance with procurement procedures assessed at 78% and savings being made. Functional review of AG Office and AG committed to recommendations.

PSM: £1,421,265	Organisation mandates documented and final report submitted to ExCo. / Corporate plan implementation (functional and structural change) underway – 50% of MDAs have completed first phase. Action plan to modernise Registry in OHoS. HRM Policy and Strategy developed and agreed with members of PSM Core Group representing OHoS. MoF workforce plan (including establishment level) developed and undergoing QA and similar work underway in MoBEP. Support and guidance established for developing Service Charters and Draft Charter developed for BEP.

Total: £5,353,744 (including Inception activities)	Steady progress has been made over the duration of the SPARC programme, though early momentum appears to have been lost. Overall, reflecting relatively high level of support, value for money considered to be fair.

Observations on performance

Jigawa’s reputation as a well performing state is not substantiated by these results. The reasons for the poor performance, especially in relation to PFM, are not immediately evident. A variety of factors could be at play: as a perceived successful past performer, the milestones may be too challenging; SPARC’s inputs may not have met Jigawa’s needs at a particular time; enthusiasm and energy for driving through a large reform agenda may have lessened and that reaching a ‘plateau’ rather than a ‘peak’ in reform achievements has become the implicit standard to be achieved / Good access by DFID, through its State Representative, to the Governor who remains supportive of the SPARC engagement and especially the work on MTSSs (currently operating in 6 sectors) / Gender and social inclusion mainstreaming making progress with drawing up of an implementation Plan under energetic leadership of Honourable Commissioner, Ministry for Women Affairs and Social Development / Close coordination and several examples of joint working between SPARC and other DFID programmes, including GEMS, SAVI and PATHS 2 / HRM reform taking place (mandates, corporate planning and some workforce planning) being completed in following MDAs: Budget and Economic Planning, Finance, Agriculture, Commerce and Local Government

## Kaduna (B)
Performance assessment summary

	2012 AR	2013 AR
Outcome	A+	C
Output 1	C	B
Output 2	A++	A++
Output 3	A++	A++
Output overall	A++	A+
Value for money	N/Ass’d	Fair value

AR methodology

Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC, Logframe Update as at November 2013

Value for money performance

Work stream and funding	Main VFM achievements compared to baseline (2008)

P&S: £966,169	A financially feasible SDP has finally been developed, with a variance of 14% between revenue figures in the plan and forecasts from the revenue model. MTSS guidelines have been reviewed. Three priority sectors are preparing 2014-16 MTSSs, aligning strategic goals with SDP objectives. The 2012 MTSSs met 52% of content standards. Only the Education MTSS has a strong link to the budget. A comprehensive results framework with relevant KPIs has been developed and integrated into the SDP. Baseline data is available for 26% of these KPIs. Annual Performance Review guidelines have been reviewed and circulated to MDAs. A Policy Guide has been circulated to ExCo and SHoA members.

PFM: £877,239	Expenditure variance (underspend) for 2012 was 41.0%, up from 30.8% in 2011, the result of unrealistically high revenue budget and an inability to spend up to the level of cash available. Revised parameters have been entered into the revenue model and medium term revenue projections updated. Revenue projections, based on the model, have been prepared for each MDA and attached as ceilings to the 2014-16 BCC. Annual budget documentation is consistent with six out of nine PEFA standards. BC and CoA have been updated to reflect the Federal directive. Health sector has profiled its approved 2013 budget using an agreed template. More than 50% of debt management staff formally trained in new software. A robust accounting, recording and reporting system is in place, providing consistency and timely accounts, and which is capable of producing in-year budget reports. The 2012 audited accounts were published on 31 May 2013 and audit reports are considered to be of good quality. An electronic tax administration system is being introduced.

PSM: £1,158,642	Mandates of all MDAs have been documented. A guideline to support the review of mandates prepared and adopted by KdSG. Corporate planning is taking place in 10 ministries in five sectors. State-wide G&SI sensitive HRM Improvement Plan and workforce strategy has been developed and agreed. More than 75% of MDAs have been sensitised on the plan. An individual performance measurement tool, produced by SPARC, has been adopted. SPARC has developed draft HRD templates and used them to train HRD managers. Key central MDAs of MoEP, OHoS and MoF have HRM unit with ‘schedule’ staff. More than 20% of other MDAs are trained and better able to operate HRD system. Service Charters developed and being piloted in three MDAs. An ICT centre has been established and is leading the drive for e-governance across MDAs with impressive efficiency improvements (processing property registration reduced from 130 days to 7 days).

Total: £3,531,688 (including Inception activities)	With the lowest level of support from SPARC for original states, the achievements in Kaduna State represent fair value for money. Traction appears to have been greatest in the PSM work stream.

Observations on performance

New SDP drafted (2014-18) and awaiting Governor’s approval / Updated 2024-16 MTSSs being prepared for Agriculture, Education and Health / Mandates of all MDAs mapped; corporate planning being adopted in 5 of 12 sectors / Establishment and workforce plans completed and agreed in OHoS (including PSO?, BEMST ? and Bureau of Public Sector Reform (BPSR) ) and MoEP / Role of BPSR as focal point for reform oversight / Good coordination of DFID SLPs’ activities with role of DFID State Representative / State Government proactive in engaging with civil society on planning and budget issues, including publishing details of contracts awarded

## Kano (B)
Performance assessment summary

	2012 AR	2013 AR
Outcome	C	A
Output 1	C	B
Output 2	A	B
Output 3	C	C
Output overall	C	C
Value for money	N/ass’d	Poor value

AR methodology

(a) Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC, Logframe Update as at November 2013
(b) Meeting with SPARC Team in Kano
(c) Meetings with State Government Officials in Kano

Value for money performance

Work stream and funding	Main VFM achievements compared to baseline (2008)

P&S: £1,638,983	Generic policy and strategy development guidelines and MTSS guide developed, ‘domesticated’ and submitted to KnSG early-mid 2013. SPARC assisted SDP scrapped and new KnSDP approved by ExCo in May 2013. The plan does not contain a structured results framework for sectors, though the health and education sectors have policy targets that are measurable. 2013-15 Education Sector MTSS (which will be rolled over to 20914-16) contains a comprehensive results framework with KPIs. MTSSs being developed in three other sectors. Annual Sector Performance Review Guidelines have been developed and approved in June 2013. Service Performance Review Committees established for Environment and Agriculture sectors and reviews scheduled for early 2014. Action Plan for improving M&E produced in September 2013 and draft improved templates developed for collection and collation of data. Attempts to hold high level sensitisation meetings with KnSG officials have failed. A meeting with the State Reform Steering Committee was held in October 2013 and sensitised the committee on SPARC’s governance reform support to KnSG. DFID have given KnSG a list of action points and targets that will be revisited in May 2014.

PFM: £1,470,578	Expenditure variance for 2010 was 17.4% (underspend). No data available yet for 2011 and 2012. Given the huge budget increase in 2012 (81% higher than 2011), the variance for 2012 will likely be very high. The 2013 budget was prepared using an appropriate technical approach, but was rejected in favour of significantly higher revenue/expenditures. The BC and CoA have been restructured to comply with the Federal Government IPSAS directive. A reviewed and updated revenue projection model has been used to develop medium term revenue projections and these have informed the Economic and Fiscal Update/Fiscal Strategy Paper. The 2014 Budget Call Circular, issued in September 2013, reflects these revenue estimates, but does not contain resource allocations to sectors. Budget profiling training, using a cash forecasting model, was delivered in August 2013 and MDAs have been requested to develop cash plans for Q4 2013 using the model. Draft Debt Management Policy and Procedures Manual developed and will be submitted to KnSG for approval by December 2013. Strategy for improving State IGR also expected to be completed by December 2013. Development of database of informal sector businesses has identified potential additional taxpayers. Draft framework for a Treasury Manual submitted to KnSG and Accountant General has given approval for a Treasury Manual to be developed. Bank reconciliation software installed and training provided to enhance bank reconciliations at MDA level.

PSM: £1,068,205	Mandates of 54 MDAs mapped in 2010 and exercise to clarify and resolve overlaps for four central MDAs successfully completed in December 2012. Organisational reviews have recommended changes to functions and structures, but no formal realignment of functions has taken place. SPARC focus has shifted from central to other key MDAs (where interest has been shown). Corporate planning awareness briefings have been conducted for KBIR, Office of Auditor General, and MoF Internal Audit unit. Establishment and workforce plans are expected to be completed for KBIR by December 2013. Draft G&SI sensitive HRM policy developed and submitted to OHoS in May 2013, with no response. Service Charter Development Task Team set up in September 2012 (ahead of KnSG’s creation of SERVICOM Kano in October 2012). Service charters for two MDAs validated in March 2013. Joint SAVI-SPARC capacity building training provided to KnSHoA members on budget realism in March 2013.

Total: £4,933,699 (including Inception activities)	There is little commitment to governance reforms. Given the four year programme period, and almost £5 million support from SPARC, progress has been slow and results largely confined to production of plans and guidelines, without much evidence of implementation by KnSG. Overall, the assessment is of poor value for money.

Observations on performance

Poorest performing state in the SPARC programme; lack of interest from the Governor has resulted in non engagement, previous work being abandoned, and SPARC’s inputs described as ‘pockets of intervention’. / There is a sense that the SPARC team is seeking opportunities to ‘push at open doors’ such the support to the Internal Board of Revenue but these are tactical rather than forming part of a coherent programme moving ahead on all fronts / DFID have ‘negotiated’ a 17 Point Plan of Action with the Commissioner Economic Planning to endeavour to get the programme ‘back on track’ by May 2014. But OHCS was not aware of this agreement; majority of the 17 Points fall within the remit of the OHCS to action / In meetings with officials, it was difficult to gather any sense of how SPARC’s engagement is fitting in to a state wide, state owned programme of governance reform; there is no reform rhetoric and no articulation of a direction and intended set of results / Being in Kano during this review was redolent of the time of DFID’s predecessor programme, SLGP, was operating in the state and faced difficulties in gaining traction; tendency of the TA inputs to be supply driven

## Katsina (C)
Performance assessment summary

	2012 AR	2013 AR
Outcome	B	A+
Output 1	A++	A++
Output 2	A+	C
Output 3	A	A
Output overall	A+	A
Value for money	N/ass’d	Fair value

AR methodology

Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC, Logframe Update as at November 2013

Value for money performance
Work stream and funding	Main VFM achievements compared to baseline (2011)

P&S: £302,718	Agreed Intervention Approach signed by Governor in January 2013. Training provided on medium term planning and sector strategies and a schedule has been agreed for developing an SDP. An MTSS has been developed for Education Sector, but work discontinued in the health sector. Support provided to four sectors on development of KPIs.
PFM: £307,004	A new BC and CoA has been produced and validated, and officials trained in its use. A draft 2014 BCC template has been developed and some components adopted in the 2014 budget process. Budget documentation does not yet meet PEFA standards. Expenditure variance was very high in 2011 and 2012 data not available.

PSM: £226,084	With SAVI, two day workshop held for SHoA on budget realism, which it is hoped will lead to demand for better reporting of budget performance. Members directed the Auditor General to finalise and submit audit reports (those for 2009 to 2011 published in June 2013). A Corporate Improvement Plan has been developed, based on Functional and Performance Review of MoFBEP. An HRM Improvement Plan has been developed in conjunction with OHoS. A policy paper on corporate planning and a concept note on workforce planning have been submitted to government.

Total: £835,806	Compared to the other new states in the SPARC programme, progress has been slow and hindered by a lack of interest in some areas and low technical capacity. Overall value for money is assessed as just about fair.

Observations on performance

Intervention Approach, for SPARC’s engagement, agreed by State Government / SDP process started; MTSS also started in Education / Budget documentation improving but not yet to required standard; PFM work stream does not seem to have the same support as in other states / Workshop held in collaboration with SAVI on Budget Process and Budget Realism for members of State House of Assembly / Governor has approved the establishment of HR department at the OHoS to champion HR issues in the state / Corporate planning process started / Although performing well against milestones, sense that the pace of change, and interest in reform, lower than in other states with several of SPARC’s tools not being taken up (such as cash forecasting and revenue modelling).

## Lagos (A)
Performance assessment summary

	2012 AR	2013 AR
Outcome	A++	A
Output 1	A++	A+
Output 2	A+	A++
Output 3	A++	A++
Output overall	A++	A++
Value for money	N/ass’d	Good value

AR methodology

(a) Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC, Logframe Update as at November 2013 / (b) Meeting with SPARC STM for Lagos in Abuja

Value for money performance

Work stream and funding	Main VFM achievements compared to baseline (2008)

P&S: £1,679,046	Lagos SDP, meeting over 30% of content standards, approved and draft implementation programme, with KPIs, produced. Most MDAs have medium term plans containing governance reform objectives. Planning and M&E units established across MDAs. MTSS processes meet more than three policy standards. Policy guidelines and revenue envelopes provided to MDAs and MDAs mandated to link MTSSs to annual budget. Three priority sector MTSSs meet over 30% of content standards. Sector strategies comprise SMART policy outcomes and outputs and targets, with budget ceilings. Strategies cover three year rolling period and provide for incorporating performance review. However, technical quality needs to be improved and strategies better linked to budget. KPI MIS exists within MoEPB and compendium of MTSS-level KPIs developed. MoEPB supporting performance reporting and report template revised to reflect lessons learned. Capacity to implement strategic planning demonstrated in construction sector and traffic management. Development of strategies reflects public consultation.

PFM: £2,392,834	Expenditure variance was 17.4% (underspend) in 2012 and revenue performance was 89%, the best in 12 years. Marked improvement in adherence to budget calendar – 2013 budget signed off on 1 January. 2014 budget planning adhered to BC and BCC in virtually all sectors. Revenue envelopes communicated to MDAs and within 15% of projections from revenue model. Review of BC and CoA completed and documented – awaiting configuration on State ORACLE system. STO prepares monthly/quarterly cash forecasts on a more regular basis, using cash forecasting model. IGR strategy submitted to government. Further training provided for procurement officials. Work in progress on automatic daily bank reconciliation. Improvements to budget report formats accepted by MoEPB, though yet to be tested. OAG re-organised into six directorates and using improved audit procedures and techniques. Audited financial statements published on OAG website.

PSM: £1,995,546	Revised mandates, signed off by each MDA and Governor, recently presented to ExCo. Three central HRM MDAs have agreed action plan to clarify and agree functions, including state-wide HR roles and responsibilities. Corporate planning pilots on-going in four central MDAs – recommendations for re-organising functions and draft model job descriptions tabled. Suite of HR policies accepted in principle and aligned, where possible, with recently revised civil service rules. Draft HR operating guidelines being finalised. LSG has agreed an HR Unit structure with defined HR duty posts tailored to fit an MDA. Options being considered for externally accredited HR training. State-wide training and development policy awaiting ExCo ratification. Workforce audit and planning exercise initiated in December 2012 and seen as crucial to MDA effectiveness – exercise identified high level skill and capability gaps. Service charters launched in 14 pilot MDAs in July 2012 and impact assessment by Office of transformation found that half of pilot MDAs recorded 50% improvement over baseline scores. Draft performance agreements (Governor/Commissioner) currently on hold.

Total: £6,640,904 (including Inception activities)	Steady progress has been made in each work stream and aspects of strategic planning and PFM are now relatively strong compared to the baseline position. Overall, good value for money has been achieved from SPARC’s investment in Lagos State.

Observations on performance

Consistent strong performer across all SPARC components with good quality products; successes to date provide a good resource which SPARC is helping to publicise nationwide / July 2013 approval of Lagos State Development Plan (2013-2025) / Important focal point for managing reform in the state through the Office of Transformation located in the Governor’s Office / Good progress with putting in place many of the building blocks for effective HRM; for example, comprehensive analysis of work force completed, including a staff audit across all MDAs, parastatals and LGAs, with key skill gaps identified / Service improvement plans, linked to Service Charters are being implemented and are showing positive results / One of the few states where SPARC supports Office of the State Auditor General / Effective role of the DFID State Coordinator / Close interaction/communication between SPARC and DFID programmes in the state; publication of ‘DFID@Work in Lagos’ / Participation of SPARC in World Bank design missions in the state / Delays in ExCo’s consideration/approval of HRM initiatives/ recommendations such as corporate plans, restructuring, setting up HR Units and training / Continuing difficulties with the operation of Oracle based IFMIS, particularly relating to the uploading of the Budget Calendar and revised Chart of Accounts / Weak capacity of the Office of Transformation

## Niger (C)
Performance assessment summary

	2012 AR	2013 AR
Outcome	N/ass’d	A+
Output 1	N/ass’d	A++
Output 2	N/ass’d	A++
Output 3	N/ass’d	A
Output overall	N/ass’d	A+
Value for money	N/ass’d	Good value

AR methodology

(a) Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC, Logframe Update as at November 2013 / (b) Meeting with SPARC STM for Niger in Abuja

Value for money performance
Work stream and funding	Main VFM achievements compared to baseline (2011)

P&S: £272,614	The State has a draft medium term development plan and the SPARC supported State Planning Commission has produced guidelines to meet the content standards. MTSS guidelines have been adapted to state systems and are being piloted in three priority sectors. The Agriculture MTSS is consistent with 90% of content standards. Results based management is being introduced: training has been provided on M&E and work is on-going to improve data availability for reviewing performance and evidence-based planning. Results frameworks have been developed for three sectors and incorporated into draft MTSSs.

PFM: £253,088	Successes achieved are mainly in budget process improvements. The 2013 expenditure budget was 12% lower than in 2012 and the variance in 2012 (though still high) was significantly lower than in 2011. 2014 BCC improved – revenue envelopes determined from the medium term fiscal forecast and guidance given to MDAs in preparing the budget. An IGR strategy discussion paper has been submitted to government, along with recommendations for improving procurement processes. Bank accounts have been reviewed and unconsolidated holdings of £44 million identified. A framework for in-year reporting is being finalised and a ‘roadmap’ developed for upgrading BC and CoA.

PSM: £222,114	Mandate mapping of central agencies and those in economic sector completed. Mandates also documented for 57 of 58 MDAs in Social and Regional sectors. Key HRM policies identified and prioritised. However, no progress made on corporate planning or employee performance management.

Total: £747,816	Within Niger State there has been a successful launch of the programme and completion of inception activities in record time. For the level of expenditure, and time elapsed, good value has been achieved.

Observations on performance

Strong performance across all components / Work on MTSSs is progressing (Agriculture complete; Health and Education finished with UNDP funding and technical support from SPARC / Medium Term Development Plan results framework finalised / New Chart of Accounts adopted; progress made in planning for the IPSAS introduction

## Yobe (B)
Performance assessment summary

	2012 AR	2013 AR
Outcome	N/ass’d	C
Output 1	N/ass’d	B
Output 2	N/ass’d	C
Output 3	N/ass’d	A
Output overall	N/ass’d	C
Value for money	N/ass’d	Fair value

AR methodology

(a) Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC , Logframe Update as at November 2013 / (b) Meeting with SPARC STM for Yobe in Dutse, Jigawa / (c) Meeting with Yobe State Government officials in Dutse / (d) Meeting with DFID State Coordinator

Value for money performance
Work stream and funding	Main VFM achievements compared to baseline (2011)

P&S: £256,731	Yobe State Socio-Economic Reform Agenda (YOSERA) updated and reviewed by SPARC. Capacity of core MTSS teams improved. Draft Health sector MTSS, based on guidelines and reflecting budget ceilings, being finalised with stakeholders. YSG has established an M&E Department in MoBP and a comprehensive results framework has been developed for YOSERA3, containing high level KPIs for each sector.

PFM: £239,462	Fiscal Strategy Paper, containing economic and fiscal analysis, informs budget planning and is the key element in the MTBF. BCC contains sector allocations based on forecasts from revenue model. Significant improvement in budget documents in 2014 (meeting 8 of 9 criteria). Simple cash forecasting model developed and MoH budget profiled. BC and CoA being reviewed to comply with IPSAS criteria. Final accounts now submitted for audit on time. On the downside, the 2013 budget was unrealistic (politically influenced) and the Fiscal Responsibility Act has been held up in SHoA.

PSM: £343,385	Mandate mapping carried out in 24 Ministries and results, analysed by PSM Core Group, to provide foundation for structural review. First stage of corporate planning (vision and mission statements, strategic and medium term objectives, and KPIs) completed for three central MDAs. Sensitisation on HR issues has commenced, though work on HRM Policy and Action Plan deferred. Enlightenment training, in conjunction with SAVI, provided for SHoA members.

Total: £839,578	The results achieved represent fair value for money, especially given the security constraints.

Observations on performance

Similar to Zamfara, the performance results fail to reflect the enthusiasm and commitment to reform that the State Government officials expressed. / Yobe is one of 3 northen states operating under a State of Emergency, since May 2013. The security situation is making it very difficult to carry out normal business; the mobile phone network gets closed down, curfews are imposed, roadblocks make travelling more time consuming within Damaturi and travel outside the state capital is high risk due to the threat of armed attack. / Mandate mapping of all MDAs completed; awaiting ExCo approval of the rationalisation plan / Ministry of Finance has started corporate planning process with definition of its medium term objectives prior to moving into next stage of completing the functional review of the Ministry / PFM ‘sensitisation’ event for State House of Assembly together with SAVI / The reasons for governance reform taking place, albeit slowly, in a conflict affected state is worthy of further study. There is literature on the challenges facing post conflict and fragile states; there is unlikely to be any analysis of the experience that Yobe is acquiring.

## Zamfara (category C)
Performance assessment summary
	2012 AR	2013 AR

Outcome	N/ass’d	C
Output 1	C?	A
Output 2	C?	C
Output 3	C?	C
Output overall	?	C
Value for money	N/ass’d	Fair value

AR methodology / (a) Review of SPARC reports, including: Annual Report 2013, Quarterly Progress Report, July to September 2013, VFM reports and analyses produced by SPARC, Logframe Update as at November 2013 / (b) Meeting with SPARC Team in Gusau / (c) Meeting with State Government officials in Gusau

Value for money performance

Work stream and funding	Main VFM achievements compared to baseline (2011)

P&S: £298,866	Sensitisation on importance of SDP conducted and State has developed a draft Concept Paper, quality assured by SPARC PDG. Draft plan now targeted for March 2014. MTSS guidebook has been prepared for 2014-16 cycle and being used in preparing MTSSs. Draft Health MTSS meets 65% of content standards, though will now only be finalised in time for 2015-17 budget cycle.

PFM: £378,118	A draft Fiscal Responsibility Act has been prepared. The 2013 budget is 9% lower than that of 2012 and multi-year budgeting is in place, though expenditure variances are not available for 2011 or 2012. A BCC was issued for the 2014 budget, with ceilings for MDAs. There was a revenue forecast for the first time for the 2014-16 budget cycle. A basic cash forecasting model is being developed and a draft report on budget monitoring and report format has been prepared. A draft IGR strategy discussion paper has also been prepared, though revenue administration remains very weak. TA Debt Management Office has been set up and is identifying dormant bank accounts. The Auditor General has agreed to work with SPARC on improving audit reporting.

PSM: £361,641	Mandates, structures and staffing have been documented for 25% of MDAs. A Corporate Improvement Plan has been developed to guide reorganisation of MoBEP. SPARC is represented on the Governance Reform and Policy Committee. A government-wide HRM Improvement Plan has been developed, but not yet agreed. Capture and analysis of HR data has identified ‘ghost’ workers and 3,000 redundant positions have been rationalised, with a saving of £4 million.

Total: £1,038,625	Zamfara State has received the highest amount of funding of the five new states and while there is considerable commitment to reform, and much work in progress, overall value for money at this stage can only be assessed as fair.

Observations on performance

The performance results fail to do justice to the amount of energy, enthusiasm and commitment to governance reform exhibited during meetings with officials / State Government is funding reform activities such as the recent visit of 10 officials for training at RIPA in London. / There is a close working relationship during budget preparation and approval between State House of Assembly (SHoA) members and Ministry of Budget and Economic Planning (MoBEP) / Budget issues issued on call in programme on local radio. 2013 Budget on the MoBEP web site / Good coordination and linking with other DFID programmes; joint initiative with SAVI in budget familiarisation training to SHoA members / Effective role of the DFID state coordinator and engaging with SPARC SPM and issues / OHCS, a key player in the reform programme, is championing the use of the SPARC HRM approaches and guidelines. Mention was made of a staff rationalisation study which identified posts surplus to operational requirements (namely those individuals appointed through political patronage); however the study’s recommendations not actioned by ExCo due to lack of political will / Increasing internally generated revenues viewed as an opportunity to increase flexibility in the budget but the Internal Revenue Board has low capacity. The realistic prospects of generating significant additional revenues are low especially where enforcement is politicised / Ministry of Local government is keen to be more closely involved with SPARC supported activities; officials are invited to attend workshops when possible but no push by SPARC to commit resources specifically to the local government ‘sector’ / Ministry of Finance starting to think about the acquisition of a second generation IFMIS but with limited understanding of how best to embark on this process and how to avoid the purchase of the incorrect hardware and software (such as Oracle or SAP)

Vincent House
Quay Place
92-93 Edward St.
Birmingham B1 2RA
United Kingdom
T +44 (0)845 313 7455
F +44 (0)845 313 7454

www.uk.ecorys.com