Business case and intervention summary: emergency humanitarian response

Title: Emergency Response to South Sudan Crisis

Intervention summary

What support will the UK provide?
The UK will provide an initial allocation of £39.5 million over the next six months to address emergency needs of those affected by crisis in South Sudan both in South Sudan and the region. £17.5 million will be disbursed in the current financial year, with the remaining £22M disbursed in FY 14/15 before end June 2014. / The response will aim to meet the priority needs of affected populations in a timely fashion, with a particular emphasis on the needs of vulnerable groups including women and girls. Throughout the response we will work with HMG and other partners to maintain principled humanitarian access and ensure the protection of civilians. / This figure is an initial allocation. The situation is evolving rapidly – needs are likely to increase and displacement is likely to continue for some time to come. The initial emergency response plan had a likely caseload of 400,000 IDPs and a worst case scenario of 800,000. The latest planning figures put the likely caseload at 1 million IDPs and 260,00 refugees by June. A further submission will be made shortly to request additional funding for humanitarian action in South Sudan, building on the latest assessment of needs as set out in the Crisis Response Plan (launched on 4 February). / On 23rd December 2013 the Secretary of State approved an envelope of up to £20 million for rapid response to the unfolding crisis. The submission stated that as access improved and needs became more apparent we would define the nature of our response, set priorities and submit a business case for this initial tranche of funding. This business case includes both assistance inside South Sudan and to neighbouring countries to address refugee needs: 22.5 million for assistance inside South Sudan and a further £17 million to meet refugee needs in the region. / The total amount includes the £12.5 million announced by the Secretary of State for International Development in December, as well as contingency funding for both the response inside South Sudan and the region, to be assigned based on emerging needs. It is broken down as follows: / In South Sudan / Recipient Organisation Funding Results / Rapid Response Facility – supporting Concern Worldwide, the International Medical Corps, the International Rescue Committee, Oxfam GB and World Vision £6M 150,000 people have access to clean water and sanitation facilities. This will include providing water purification tablets and building separate latrines for men and women in new camps / 50,000 people get basic shelter from tarpaulins and shelter kits / 50,000 people have access to essential items such as cooking utensils, blankets and mosquito nets / emergency medical response units can provide trauma care, primary and secondary health care, nutrition advice and help prevent disease among 100,000 people in Pochalla, Akobo, Malakal and Awerial / better sanitation facilities and lights are installed in emergency camps to keep people safe / vulnerable girls and women are protected by creating ‘safe spaces’ for them to get medical and psychological care / International Committee of the Red Cross (ICRC) £3M Medical supplies and skilled medical staff to enable emergency medical treatment to thousands of people and clean water to nearly 15,000 people. / International Organisation for Migration (IOM) £1M Tents for up to 11,400 people who have fled their homes. As well as protection against the elements, up to 1,906 family-sized tents will also provide women, girls and young children with some privacy. / World Food Programme – emergency logistics appeal and UN Humanitarian air service £2.5M To airlift aid workers and humanitarian supplies to those in need across the country, including through the UN’s Humanitarian Air Service. / Pipeline projects including food security and livelihoods support through WFP and FAO and 5 strategic secondments to meet critical skills gaps in the UN system. £5M 6,800 people reached with emergency food supplies over next 2-3 months. / Livelihoods support for affected groups. / 5 strategic secondments to fill critical capacity gaps across the humanitarian system, with a focus on protection and camp management. / Contingency £4.5M Additional funding to respond to emerging needs as the situation evolves / Surge staffing £0.5[1]M Additional staff to DFID South Sudan to assist with the response / To refugees from South Sudan in neighbouring countries: / Country Recipient Organisation Funding Results / Ethiopia WFP £2.2M 6 months of food rations for 30,000 refugees / Ethiopia UNHCR £1.8M 25,000 provided with temporary shelters; adequate clean water for 25,000 refugees; 25,000 with access to family latrine; 600 malnourished children reached with supplementary feeding / Kenya WFP £1.5M 6 months of food rations for 20,300 refugees / Kenya UNHCR £1M Temporary shelters constructed for 20,000 people / Latrines constructed for 11,200 people / 3000 children in primary education / 20,000 with access to clean water / Uganda WFP £1M 6 months of food rations for 18,000 refugees / Uganda UNHCR £4M 60,000 people with access to primaty healthcare; 60,000 people provided with temporary shelter and basic household items; 60,000 with access to adequate clean water / Uganda UNICEF £1M Improved water and sanitation facilities for 60,000 people; nutritional surveillance and treatment; immunisation of 21,000 children; safe spaces available to 12,900 children / Sudan and regional contingency Contingency £4.5M Refugees have only just started to arrive in Sudan, and Government access restrictions have slowed a UNHCR-led multisectoral response. Full needs assessments have therefore not been carried out and exact needs are not yet known. We propose to keep £4.5 million in contingency funding to respond in Sudan and top up responses across the region if necessary. / This funding is in addition to some £60 million in funding provided in 2013 to meet humanitarian need in South Sudan in a ‘normal’, non-crisis year, some of which has been redirected to support response in early 2014. This included a £19 million contribution to the Common Humanitarian Fund for 2014 which has been reoriented to address critical gaps in the crisis response plan.
[1] Staffing costs currently budgeted at £345,343 for three Kampala-based additional members of staff - 1x Humanitarian Adviser (6 months), 1x Humanitarian Affairs Officer (6 months) and 1x Humanitarian Affairs Officer (3 months). The slightly higher budget line above for any contingencies but any additional funds will be redirected to the programme.

Why is UK support required?
The current crisis in South Sudan has dramatically increased humanitarian need in a country where one third of the population were already in need of emergency assistance. The level of need across the country and in refugee populations in the region is extremely high and growing steadily. Widespread violence and human rights abuses against civilians, coupled with extremely limited humanitarian access and response capacity mean that the situation is critical. The UK should respond quickly and flexibly to meet urgent priority needs, ensure access is maintained and support refugees in the region. / As of 19th January 2014, OCHA estimates that over half a million people have fled their homes since 15 December 2013, including 494,000 people displaced inside South Sudan and 86,100 in neighbouring countries. Given the security situation and extremely constrained access within South Sudan, only around 50% of affected people can currently be reached with assistance. The US$1.27 billion UN interagency Crisis Response Plan (CRP) launched on 4 February is based on estimates that by June 2014 there will be 7m at risk across the country including 1 million people internally displaced, 236,000 refugees in South Sudan, and 260,000 South Sudanese seeking refuge in the region. / The graphic below shows the situation by January 19th 2014: / Our estimates as of 24th January are that there are now some 17,500 refugees in Sudan, 11,262 in Kenya and 60,000 in Uganda. Ethiopia is planning for a total caseload of 60,000. / Even before the current crisis, extreme poverty, food insecurity and fragility, inter-communal violence and the pressures of returning South Sudanese from the North mean that more than a quarter of the population of South Sudan (some 4.3 million people in 2013) required humanitarian assistance, of which 3.3 million were targeted with humanitarian response. In 2013 DFID provided over £40M in humanitarian assistance across key sectors including food security and livelihoods, water and sanitation, health, nutrition, non-food items and emergency shelter, and protection. It also included a £19m allocation to the CHF which was disbursed in late December to enable timely prepositioning for the 2014 rainy season. Following the onset of the crisis in mid-December this was re orientated to meet immediate needs of affected populations. / On 15 December 2013, heavy fighting between different elements of the SPLA broke out in Juba. Fighting has since spread across much of the country, and has been especially intense in Jonglei, Unity and Upper Nile States. There are widespread reports of severe abuses against civilians, including of people being targeted based on ethnicity. Critical humanitarian concerns are the ongoing risk of violence to civilians (especially where there is no UN/INGO visibility) and associated spikes in people requiring medical attention. In addition, given the pre-existing chronic underlying vulnerability in South Sudan and limited basic service provision (mostly delivered through NGOs), there is concern around the coping capacity and resilience of communities, particularly as planting seasons are being disrupted and flooding during the rainy season is likely to result in secondary and repeated displacement of affected populations. UNMISS was overwhelmed by the large influx of IDPs into their compounds; the water and sanitation situation among the displaced is poor due to immense overcrowding and there is an increased risk of disease outbreaks. The situation continues to evolve and there are a number of possible scenarios.. / Following the Cessation of Hostilities agreement, DFID South Sudan, FCO and MOD have worked up a range of detailed scenarios covering the evolution of the situation over the rest of 2014. DFID South Sudan analysis suggests that the most likely immediate humanitarian scenario will be increased internal displacement, and continued abuses against civilians, as a result of ongoing conflict and inter and intra communal clashes. In addition to this it is highly likely we will see continued destruction of civilian property, and ongoing looting of humanitarian assets, particularly in areas where hostilities continue. Effects on pastoralist migrations, agriculture/crop production, livelihoods and markets are likely to be significant in the short to medium term, with millions acutely affected across the country in the longer term if time critical preparedness (e.g. for the rainy season, planting season) is not carried out. There is a high risk of epidemic and disease spread (among cattle herds) further impacting the lives and livelihoods of the most vulnerable. / The December Emergency Response Plan estimated that $166 million (£100 million) is needed to meet the most immediate unmet needs over the first three months of 2014. But this figure is currently being revised upwards (appeal to be published next week) based on a new projected caseload which estimates that there will be 7.2 million people at risk by June 2014, including 1 million IDPs and 200,000 refugees in neighbouring countries. The proposal to contribute at least £22.5 million to meet humanitarian need in South Sudan over the next six months, added to the £19 million CHF contribution at the end of 2013 and DFID’s shares of CERF and ECHO commitments (see analysis in Appraisal Case), means that the UK will cover 18% of estimated immediate needs inside South Sudan over the next three months (pre-revision – percentage will be far lower once new estimates published). Our proposed £17 million contribution to regional refugee needs puts us at around 30% of UNHCR and WFP’s requirements to meet needs in neighboring countries. / The cost of the operation is likely to increase the longer we wait. Pre-positioning relief supplies (to the extent that security allows) ahead of the rains in June – when roads become impassable in some areas - is critical for mitigating the need for more costly and inefficient air delivery later. And providing seeds and tools where there is sufficient safety for farmers to plant is also required in the coming months. / Given the likely budget constraints faced by ECHO, who face significant cutbacks to their 2014 budget, and the speed with which the crisis is worsening, it is right that we should contribute substantially towards appeals. The current and projected levels of humanitarian need in South Sudan mean that the UK should quickly and flexibly provide funding to meet priority needs and respond as the situation evolves.

What are the expected results?
The expected results of each sub-grant are listed in the section above. The objectives of the programme are to save lives, reduce suffering and maintain the dignity of those affected by the crisis, respond to gaps in the response wherever possible, with a particular emphasis on the needs of vulnerable groups, including women and girls. The programme will also aim to maintain principled humanitarian access and ensure the protection of civilians, as well as supporting a well-coordinated and effective overall response which integrates preparedness activities. Overall with the support proposed indicative results include: / In South Sudan / Almost 165,000 people with access to clean water / 6,800 reached with emergency food supplies over the next three months / 57,500 people with basic shelter / 50,000 people with essential household items / 100,000 people with access to healthcare, including reproductive health / 5 strategic three-month secondments to fill critical capacity gaps in the humanitarian system, in priority areas including camp management and protection / Improved sanitation in IDP sites / Protection for vulnerable girls and women and medical and psycho-social treatment for those affected by sexual violence / To South Sudanese refugees in the region / In Ethiopia: / Food for 30,000 people for six months / 25,000 provided with temporary shelters; / adequate clean water for 25,000 refugees; / 25,000 with access to family latrine; / 600 malnourished children reached with supplementary feedinPrimary healthcare, including reproductive health, available to affected population / In Kenya: / Food for 20,300 people for six months. / Temporary shelter and clean water for 20,000. / 3000 children in primary education. / Primary healthcare, including reproductive health, available to affected population / In Uganda: / Food for 18,000 people for six months / 60,000 people with access to primary healthcare; / 60,000 people provided with temporary shelter and basic household items; / 60,000 with access to adequate clean water / Nutritional surveillance and treatment; / Immunisation of up to 21,000 children; / Safe spaces available to 12,900 vulnerable children and young people / In Sudan: Total caseloads not yet specified. Contingency funding to meet food, shelter, WASH and protection needs as these are identified. / The situation is rapidly evolving, and there are a broad range of possible scenarios. The proposed programme therefore also contains £4.5 million in contingency funding to respond to new needs and priorities inside South Sudan in the short term, and a further unallocated £4.5 million is reserved to meet emerging refugee needs in Sudan and across the region as necessary. As above, the South Sudan team will reassess needs in March and submit to Directors with an assessment of whether an uplift is needed in the current six month programme, and an estimate of the scale of our response until the end of 2014.

Strategic case

A. Context and need for DFID intervention / As set out in the intervention summary above, the crisis which began on 15th December 2013 has led to a significant increase in humanitarian need in a country with a lack of basic services, chronic underlying vulnerabilities and where one third of the population were already in need of humanitarian assistance. Widespread violence, including human rights violations and targeted killing of civilians, has led to massive population movement. OCHA estimates that by June 2014 there will be approximately 7.2 million at risk across South Sudan including one million internally displaced people inside South Sudan and a further 20,000 south Sudanese seeking refuge in the region. A rapid and flexible response is needed to meet basic needs and protect affected populations. The intervention summary above and appraisal case below set out why UK assistance is needed, our proposed response and why this is appropriate given the context. / A significant DFID intervention is consistent with the leading role we play in the political process (as a member of the Norway, UK, US, Troika) and our development engagement in the country – the UK is the second largest bilateral aid donor after the US. / The visit of Assistant Secretary General for Human Rights, Ivan Šimonović, on 14-17 January underlined the seriousness of the situation in South Sudan. In a public statement on 17 January he referred to reports received of mass atrocities committed by both sides, including enforced disappearances, sexual violence, widespread destruction of property and the use of children in the conflict. He also highlighted concerns about the inter-ethnic dimension of the conflict. / It remains to be seen whether the Cessation of Hostilities agreement signed in Addis Ababa on 23 January will lead to reduced conflict. Commitment to the agreement is fragile and control over armed groups by leaders is weak. Fighting continues in many parts of the country. Updated scenario planning is ongoing across HMG. Under all realistic scenarios, humanitarian needs will increase over coming months. Under the worst case of increased and entrenched conflict, the increase will be substantial. / The relief effort is providing a life-line for thousands affected by the fighting, but only half of those displaced have received humanitarian assistance. IDP camps and settlements are overcrowded and lacking in basic services. This has led, in some cases, to outbreaks of disease, including diarrhoea and measles, and fatalities. / Insecurity will limit the pre-positioning of food and other relief supplies before the rains in June, which render broad swathes of the country inaccessible by road. This will increase the need for expensive air drops. / Humanitarian access is constrained by several factors. Many conflict-affected areas are remote, posing logistical challenges. Aid agencies must frequently withdraw staff in response to a rapidly changing security environment. Armed groups have been looting relief supplies in some areas. As of 20 January, the UN estimated that enough food to feed up to 306,000 people for one month had been taken from warehouses. / Obstruction of aid efforts by authorities is increasing, fuelled by tension between the government and the UN. In a press conference on 21 January President Salva Kiir criticised UNMISS and its leadership, accusing them of bias in favour of his opponent Riek Machar. On 23 January, over one hundred aid workers were prevented by local authorities from boarding UN helicopters to evacuate Yirol, in Lakes State. The deadlock lasted two days, but has raised serious concerns among the humanitarian community.
B. Impact and outcome expected / The impact of the UK’s humanitarian response to the South Sudan crisis will be to save lives, reduce suffering and maintain the dignity of those affected by the crisis, and build resilience in South Sudan and the region. The priority outcomes are: / Respond wherever possible to gaps in emergency protection and assistance needs inside South Sudan, particularly for the most vulnerable, including women and girls / Provide funding to agencies who are able to respond in accessible areas in critical sectors, including food assistance and integrated livelihoods support to meet immediate needs. / Strengthen protection of civilians and principled humanitarian access / Provide funding to partners who undertake protection monitoring and engage with armed actors over responsibilities, protection of civilians and need for safe and unhindered humanitarian access. / Work closely with other parts of HMG to press for protection of civilians / Enhance coordination and emergency preparedness / Support pipelines and prepositioning of critical commodities (e.g. food, WASH, shelter, health); staff/ equipment necessary to implement any response; / Establish and clarify rapid and flexible financing mechanisms accessible to a range of partners when necessary. / Support coordination and other aid-enablers (e.g. logistics, security) / Support the resumption of livelihoods activities of affected populations through time critical preparedness activities where possible. / Provide support to neighbouring countries - Kenya, Ethiopia, Uganda, Sudan - to help address urgent needs associated with refugee outflow / Support key pipelines and response activities through UNHCR, WFP and partners. / These outcomes form the basis of DFID South Sudan’s humanitarian response strategy.

Appraisal case

A. Proposal that addresses the needs of the strategic case / The option is to intervene through activation of the Rapid Response Facility as well as through contributions to UN and Red Cross appeals in South Sudan and the region. / The situation has deteriorated rapidly and continues to develop. The estimated likely scenario – 1 million IDPs and 200,000 refugees by June 2014 – is worse than the worst case scenario of 800,000 IDPs envisaged in late December and early January, against which our initial response envelope of £20 million was allocated. / HMG have developed and are planning for a range of possible scenarios, each with a different humanitarian impact. The most likely scenario sees the number of IDPs continuing to grow, reaching 750,000 – 1.5 million by the end of 2014, as well as more than 150,000 refugees. Access is likely to remain constrained with roughly half of affected people not reached with humanitarian assistance. This is explained in more detail in the submission covering this business case. / It is therefore imperative that we provide flexible funding to those partners best able to access affected populations and meet priority needs as quickly as possible. The option proposed is that inside South Sudan we fund a range of experienced partners specialising in different areas of the response to meet the range of needs identified in the HCT’s emergency response plan. This includes investing in strengthening the logistics base so that affected populations can be reached with necessary goods and personnel, and funding organisations to respond with medical care, water and sanitation, protection interventions, temporary shelter and food for those affected. It also includes using our advocacy channels to push for the protection of civilians and sustained/ improved humanitarian access. / In neighbouring countries receiving South Sudanese refugees as a result of the crisis we will fund trusted partners - WFP and UNHCR – to provide shelter and basic services, including protection, to refugees in Ethiopia, Kenya, Sudan and Uganda. / Burdenshare / The UN interagency crisis response plan is based on a planning figure of US$1.27billion (£820million) needed before June. Inside South Sudan we are proposing a contribution of £22.5 million in addition to £19 million in previously disbursed funding to South Sudan’s Common Humanitarian Fund which has been reprioritised in line with the emergency response plan. This initial contribution equates to a DFID burden share over the first six months of 2014 of 5%. If we include DFID-attributable shares of planned ECHO and CERF contributions, this rises to 5.8%. / This initial burden share is appropriate given the engagement of the UK in South Sudan, financing difficulties faced by other major donors, notably ECHO whose 2014 budget is likely to be cut significantly, and the need for rapid and flexible funding to address urgent needs and save lives. The next submission will recommend additional funding and an engagement strategy to encourage additional support from other donors for the response. / In neighbouring countries we plan to meet approximately 30% of UNHCR’s emergency appeal, and through WFP to feed more than 68,300 refugees over the next 6 months out of a revised likely caseload of 200,000 by June (34%). These contributions are high, but not so high that we will crowd out other donors, particularly given the high caseloads of refugees from other countries and underfunded needs DFID’s ability to fund rapidly and flexibly means that we are in a position to respond to this crisis and meet immediate needs in a timely fashion, which constraints on some other donors makes difficult. Given the likely cuts to ECHO’s budget, and the need to construct new camps in some areas to accommodate refugees, it is right that we should contribute significantly to meeting the emergency appeals. We will continue to encourage donor partners to commit significant resources to tackling this crisis. / The discrepancy in burdenshare between the response inside South Sudan and assistance to neighbouring countries comes because: / The lack of humanitarian donors in many neighbouring countries mean that a burdenshare of around 25% for humanitarian activities is normal in the region, and the current crisis – and need for prepositioning and flexibility – justify a slightly higher burdenshare / In Kenya, for example, high levels of initial investment are needed to construct new camps and put heavy infrastructure in place / Because of some other partners’ current financial situation DFID is well-placed to contribute early, lowering overall costs / The counterfactual – not intervening to support emergency response in South Sudan – would leave humanitarian actors struggling to respond to urgent and growing needs and would lead to widespread morbidity and mortality in affected populations. The UK’s humanitarian assistance is driven by need alone, and the number of people affected by this crisis, the widespread violence against civilians and the speed with which the crisis is growing and developing makes South Sudan one of the world’s most acute crises. Early, substantial and flexible intervention is necessary in this case. / Theory of change / Inputs Process Outputs Outcome Impact / £39.5 million of which: / -£22.5 million to meet needs inside South Sudan / -£17 million to meet the needs of South Sudanese refugees who have fled to neighbouring countries Responding to priorities set out in the HCT’s emergency response plan and in coordination with other donors, support provided through UN agencies, NGOs and the Red cross to address the most immediate needs in South Sudan and neighbouring countries. 165,000 people with clean water and sanitation facilities. / Basic shelter for 50,000 people / Essential household items for 50,000 people / Medical treatment/ facilities for 100,000 people / Better sanitation facilities in camps / Safe spaces for vulnerable women and girls / Tents for up to 11,400 people / Increased logistical capacity and functioning UN Humanitarian Air Service / Emergency food supplies to 6,800people / Capacity to respond to new needs as they emerge / -In Uganda, 18,000 people provided with food for 6 months / -in Ethiopia, 30,000 people provided with food for 6 months / -In Kenya, 20,300 people provided with food for 6 months / -In Sudan, refugee needs met as these become apparent Appropriate aid reaches those in need speedily: / Respond wherever possible to gaps in emergency protection and assistance needs, particularly for the most vulnerable women and girls / Strengthen protection of civilians and principled humanitarian access / Enhance coordination and emergency preparedness in case the situation deteriorates further / Provide support to neighbouring countries - Kenya, Ethiopia, Uganda, Sudan - to help address urgent needs associated with refugee outflow The impact of the UK’s humanitarian response to the South Sudan crisis will be to save lives, reduce suffering and maintain the dignity of those affected by the crisis in South Sudan and the region / Staff input: / 5 full time staff in London and the region + proportion of 4 regional HA’s time+ a CHASE OT deployment of one Humanitarian Advisor for 6 months, one Humanitarian Affairs Officer for 6 months and one Humanitarian Affairs Officer for 3 months National governments: / UN agencies: / NGOs: / ICRC/IFRC: / Assumptions: humanitarian access; sustained minimum cooperation of Government of South Sudan and governments of refugee-hosting countries; sustained support from other donors; adequate human resource capacity of humanitarian agencies and NGOs;
B. Strength of the evidence base / Evidence rating / Strong / The response proposed is a traditional response to a complex crisis, seeking to meet basic needs of and increase protection for crisis-affected populations inside South Sudan and in neighbouring countries. Partners will respond using tried and tested methods which have been used both in South Sudan and in other crisis contexts to reduce morbidity and mortality in affected populations and improve protection of civilians. We are intervening in a complex environment with constrained access and widespread population movements and a shifting security situation. Therefore we may expect delays in implementation or shifts of focus. Over the course of the response, if appropriate, we will aim to link emergency interventions to DFID’s longer term resilience and development efforts in South Sudan. / Likely impact on climate change and environment / Overall the intervention will have a limited impact on climate and environment. Risks from increased air and road traffic and from camp construction are justified given the level of need, but careful management of both activities can mitigate these impacts. UNHCR, for example, dedicates significant programme resources to environmental protection. / Risks and impacts (negatives) Opportunities (positives) / Support to increased logistical capacity will increase air and road traffic and therefore carbon emissions / Construction of new camps, if necessary, will have a significant environmental impact. These must be managed carefully. Support to improved management (including improved sanitation) of IDP and refugee sites will reduce their environmental impact
C. Costs and benefits / Costs / The overall cost of the proposed support is £39.5 million over 6 months (February – July 2014), which includes £22.5 million for needs inside South Sudan and £17 million for refugee needs in neighbouring countries. / Benefits / As in the results section above, this funding will save lives, reduce suffering and maintain the dignity of those affected by the crisis in South Sudan and the region. Specifically in will achieve results including: / In South Sudan / Almost 165,000 people with access to clean water / 6,800 reached with emergency food supplies over the next three months / 57,500 people with basic shelter / 50,000 people with essential household items / 100,000 people with healthcare / 5 strategic three-month secondments to fill critical capacity gaps in the humanitarian system, in priority areas including camp management and protection / Improved sanitation in IDP sites / Protection for vulnerable girls and women and medical and psycho-social treatment for those affected by sexual violence / To South Sudanese refugees in the region / In Ethiopia: Food for 30,000 people for six months / In Kenya: Food for 20,300 people for six months. Temporary shelter and clean water for 20,000. 3000 children in primary education. / In Uganda: Food for 18,000 people for six months / In Sudan: Total caseloads not yet specified. Contingency funding to meet food, shelter, WASH and protection needs as these are identified. / It will also help us to leverage other donor support, and increase our influence on the humanitarian and wider system to ensure that access is maintained and civilians receive adequate physical protection.
D. Value for money assessment for the intervention / All value for money assessments in DFID’s humanitarian responses include the three key components of the humanitarian value for money triangle: cost, quality/appropriateness and speed/timeliness. All agencies will report to DFID on these three through the various reporting stages set out in the Humanitarian Funding Guidelines. DFID has also assessed value for money of funding partners in this Business Case through: / RRF activation: value for money has been assured by the RRF application process, whereby prospective partners had to demonstrate a history of proven value for money provision. Additionally post action reviews will be conducted by DFID to ensure ongoing reassurance, and partners who have clearly failed to deliver will be removed from the RRF. / Contribution to appeals (UN, Red Cross): value for money of contributing to international appeals has been assured through the Multilateral Aid Review (MAR). The MAR examined more than 40 multilaterals receiving funds from DFID against a set of criteria. The MAR drew on a range of evidence including: survey data; other studies of effectiveness; external evaluations; reporting by the multilaterals; visits by DFID staff; consultation with developing country partners; and submissions to the review from UK civil society and the organisations themselves. The MAR provides DFID with the evidence needed to take decisions on how to deliver funding through multilaterals to make the greatest possible impact on poverty. DFID is developing core funding Business Cases with agencies that will serve as institutional strategies and include analysis that can be drawn on when completing country specific business cases: / IOM – the MAR highlighted that IOM has historically been a key UK partner on migration management that gives it flexibility. The same flexibility has allowed IOM to often contribute effectively to the international response to humanitarian emergencies. The MAR reported that IOM has low overhead rates and has controlled costs by reducing back office and staff costs and their budget structure and expenditure is transparent. / UNHCR - the MAR highlighted the expertise that UNHCR has in providing assistance to displaced persons, although experience in supporting air operations is more limited. Given this relative inexperience there is a compelling case for DFID to provide additional capacity support. / WFP – the MAR acknowledged WFP as the only agency capable of delivering emergency food assistance at scale in difficult and often dangerous environments. WFP is a critical humanitarian partner for the UK, with more assistance delivered through them than any other agency. / ICRC - the MAR gave the ICRC a very strong rating for their value for money. The MAR said ICRC manages limited resources effectively and allocates aid according to agreed schedules. Its built up reserves allow it to pre-fund operations before donor funds have been made available. It has strong systems for financial accountability and the ability to change the focus of project activities to ensure that they are always appropriate to the context.

Commercial case

Direct procurement

A. Procurement and commercial requirements for intervention / Direct procurement is not part of the response and therefore information for this section is not required.
B. How does the intervention use competition to drive commercial advantage for DFID? / not applicable for this response.
C. How do we expect the market place will respond? / not applicable for this response.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Not applicable.
E. What is the intended procurement process to support contract award? / not applicable for this response.
F. How will contract and supplier performance be managed? / not applicable for this response.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / Indirect procurement will account for the full amount of £39.5 million. / Funds are dispersed to NGOs via accountable grants, with funds based on proposals they submit and assessed via an IRS (this is applicable to RRF and non-RRF funding applications). / Funds are dispersed to multilaterals (including Red Cross) via memorandums of understanding established and agreed with each agency.
B. Value for money through procurement / Please see section D in the appraisal case above.

Financial case

What are the costs, how are they profiled and how will you ensure accurate forecasting? / The costs are as follows, and funding will be disbursed according to the schedule below: / Disbursed To be disbursed by 31/03/14 To be disbursed by 31/07/14 / Rapid response facility £6M / ICRC £3M / IOM £1M / WFP (UNHAS + logs) £2.5M / Pipeline projects including support to WFP EMOP and strategic secondments £5M / Surge staffing costs £0.5M / Contingency £4.5M SS total: £22.5M / Ethiopia: WFP and HCR £4M / Kenya: WFP and HCR £2.5M / Uganda: WFP, UNICEF and HCR £6M / Sudan: UNHCR and WFP + regional contingency £4.5M Regional total: £17M / Totals £17.5M £22M £39.5M / The timing of each disbursement will be agreed with each organisation as the MOU or grant agreement is drawn up. The priority is for NGOs and agencies to begin/ scale up their response as soon as possible. Both WFP and UNHCR will accept a funding commitment as soon as the business case is approved, begin spending on that basis immediately, and accept payment at the start of FY 14/15.
B. Funding the proposal / All funding can be managed from within Africa Division’s resources.
C. Payment of funds / See section A of the indirect procurement section in the commercial case above.
D. Assessment of financial risk and fraud / RRF activation: financial risk and fraud was assessed by the RRF application process, whereby prospective partners had to demonstrate a history of proven financial management. RRF members are fully accountable for funds provided to them by DFID and money fraudulently used can be recovered by DFID. Additionally post action reviews will be conducted by DFID to ensure ongoing reassurance, and partners who have clearly failed to deliver will be removed from the RRF. / Contribution to appeals (UN, Red Cross): financial risk and fraud of contributing to international appeals has been assured through the Multilateral Aid Review (MAR).
E. How will expenditure be monitored, reported, and accounted for? / Accountability and monitoring requirements will be agreed by each recipient of UK funding through their MOU or grant agreement. / Requirements vary slightly between implementing partners. Funding to the ICRC, for example, is governed by a central DFID agreement which stipulates that receipt of ICRC’s annual report for the country appeal funded when this is ordinarily published will be sufficient in terms of accountability. For funding to specific agencies and NGOs we ordinarily require a mid-term and final report on progress against objectives, and the Humanitarian Advisor will require regular informal updates from implementing partners and expect to be informed of any delays in implementation or emerging challenges or blockages. The RRF will provide a report at the 3 and 6 week point as well as at the end of the intervention, and the South Sudan HA will hold a weekly informal meeting with RRF partners to get feedback on progress and identify and emerging issues. / Regional refugee responses in neighbouring countries will be monitored by the Humanitarian Adviser/ Programme Manager in each country, and accounted for centrally by UNHCR and WFP in their regional reports. A single point of contact will be identified with responsibility for coordinating and collating, monitoring and reporting for the refugee response, including inputs into PCRs and regular updates to the South Sudan HA, to ensure that DFID has a solid understanding of overall progress with the response and emerging issues.

Management case

A. Management arrangements for implementing the intervention / The proposed intervention is more complex than South Sudan’s standard humanitarian programme, involving a greater number of more complex grant agreements which will require careful monitoring and close working with partners. Added to this is the security challenge – all staff are currently evacuated from Juba, with the Humanitarian Adviser due to return next week. Movement outside of Juba and therefore direct monitoring of projects by DFID staff will likely be constrained for some time to come. / Because of the additional programme management and humanitarian advisory requirements, DFID South Sudan has brought in additional capacity across both disciplines. Currently there is an information manager in Nairobi through CHASE OT, and two additional humanitarian advisors deployed to the response team from other parts of the organisation. Stabilisation Unit are deploying one Humanitarian Adviser and one Humanitarian Affairs officer for six months, and one additional Humanitarian Affairs Officer for three months, to be based in Nairobi or Kampala at a cost of £345,343. This will be covered by the programme budget. / Monitoring and reporting requirements for each grant are set out in the section above. The South Sudan Team will be responsible for monitoring all projects within South Sudan and assessing progress against outputs 1-3 of the logframe. Regional Humanitarian Advisers, through a designated lead, are responsible for monitoring refugee responses in their respective countries and for monitoring progress against output 4 of the logframe. DFID South Sudan and the regional offices will agree detailed roles and responsibilities for management and reporting, including to monitor risks and identify emerging issues, to ensure that staff in South Sudan and neighbouring countries have clear responsibilities and that the division of labour enables them to implement and monitor the programme in a coherent and coordinated way to a high standard. / Contingency funding will be allocated over the course of the programme as needs emerge, and will be released on the basis of a submission from the Humanitarian Team Leader to South Sudan’s Head of Office where the total sum of the grant is within her delegated authority. The Humanitarian Advisor will report regularly on progress to the head of office, flagging any risks and blockages as early as possible. Allocation of the regional contingency fund will be approved by South Sudan’s Head of Office by a short submission from the relevant regional HA, cleared through the agreed regional focal point.
Risks of intervention and how these will be managed / Risk Likelihood Mitigation / Worsening insecurity and constraints on humanitarian access means that affected populations cannot be reached by implementing partners, or assistance is manipulated for political and military gains. Medium - High DFID SS continue to work with the HC to strengthen leadership, and distinction of humanitarian interventions / DFID funding to logistics cluster and UNHAS will improve access to remote areas / HMG will work with other donors to ensure the UN integrated Mission respects humanitarian space and does not worsen the access situation / Working with trusted partners with a long history in South Sudan who are best placed to negotiate and maintain access. / Lack of other donor financial support reduces implementing partner capacity to respond to needs Medium Sustained advocacy in the South Sudan donor group and at HQ level to maintain support for this crisis. / Lack of consistent humanitarian donor presence in South Sudan undermines coordination efforts and monitoring/evaluation of humanitarian interventions. Low-Medium Plans in place for HA to return to Juba. / Government of South Sudan, Anti-government forces or regional Governments place restrictions on the operation of humanitarian partners Medium-High Sustained diplomatic engagement/lobbying for facilitation of international staff operations / Situation worsens or changes prompting further mass population movement and a change in needs Medium-high Ongoing diplomatic efforts to maintain humanitarian access. Funding to large, flexible organisations with the ability to scale up or down and change area of focus. Contingency funding retained to respond to new needs as these arise. / Rainy season prepositioning strategy undermined high Continued lobbying for access during dry season, and respect for humanitarian personnel and assets. / In extremis, use of MCDA for to support humanitarian activities. / DFID South Sudan not adequately staffed to manage complex programme and multiple grant agreements Low HA and Team Leader will monitor progress carefully. If additional resources are needed, HA to request draw-down of a roving Humanitarian advisor and/ or short term programme management support from CHASE. / Implementing partners lack the human resources to adequately manage funds and deliver results Medium Working with trusted partners who we judge to have the necessary expertise, and well-managed HR systems. / DFID South Sudan to consider strategic secondments into implementing agencies to address skills gaps. / HA will request regular feedback from implementing partners so that problems can be identified early and appropriate action taken. / Overall response poorly coordinated leading to overlap and/or gaps Low-medium Work closely with OCHA and through the HCT to ensure coordination systems continue to function adequately. / Advocacy at the New York level possible if OCHA need additional support or resourcing. / Ongoing advocacy at country level to ensure strong HC leadership. Continue advocacy at NY level if required. / Funds or assets are misappropriated High All partners deemed to have adequate financial oversight and management mechanisms in place. Any mismanagement or losses will be reported by partners, and cases forwarded to DFID’s fraud unit for action. / Effective implementation f MCDA for the protection of humanitarian assets Medium-High Working with FCO to ensure sufficient UNMISS capacity to respond to requests for MCDA if required / Humanitarian intervention does harm, worsens conflict or poses significant protection risk and increases dependency on humanitarian aid Medium Working with trusted and experiences partners who routinely consider these issues when planning interventions.
C. Conditions that apply (for financial aid only) / Not applicable
D. How will progress and results be monitored, measured and evaluated? / Reporting requirements for all DFID implementing partners are set out in the Humanitarian Funding Guidelines. The RRF has separate, but specific requirements.
E. Logframe / Quest document number 4345129