Annual Review

Title: Financial Sector Deepening Zambia (FSDZ)
Programme Value £ (full life): 22,950,000		Review Date: November 2018 (for 12 month period to end March 2018)
Programme Code: 203000	Start Date: May 2013	End Date: March 2021

Summary of Programme Performance

Year	28/02/2014	28/11/2014	27/11/2015	30/11/2016	20/07/2017	15/12/2018
Programme Score	B	A	A	A	A	A
Risk Rating	Medium	Low	Medium	Minor	Minor	Moderate

DevTracker Link to Business Case & Addendum	https://ec.vault.dfid.gov.uk/OTCS/cs.exe?func=ll&objaction=overview&objid=4320471 / https://ec.vault.dfid.gov.uk/OTCS/cs.exe?func=ll&objaction=overview&objid=30266711
DevTracker Link to Log frame:	https://ec.vault.dfid.gov.uk/OTCS/cs.exe?func=ll&objaction=overview&objid=14778608

A. Summary and Overview (1-2 pages)

Description of programme
Under Financial Sector Deepening Zambia (FSDZ) DFID has allocated up to £22.950 million to support increased access to financial services by Poor[1] people in Zambia. Financial exclusion in Zambia remains high. Nationally, it has reduced from 62% in 2009 to 41% in 2016, (FinScope 2015) but this masks a number of variations. In rural areas 50% of adults still have no access to any financial service, whether formal or informal. Financial exclusion is higher for women (43%) than men (39%), and for those working in the informal sector than formal wage earners.
[1] Men and Women whose household income is less than $2.50 per day

The Government of Zambia has shown commitment to expanding financial inclusion and with extensive support from FSDZ has recently launched the National Financial Inclusion Strategy and established a new Financial Inclusion Unit in the Ministry of Finance to deliver on this strategy. The aim is to have an overall increase in financial inclusion (formal and informal) from 59% to 80% and an increase in formal financial inclusion from 38% to 70% by 2022.

As a market facilitator, FSDZ’s interventions are designed to enable innovative and inclusive finance solutions in the market to address the mismatch between supply and demand of financial services, as well as helping improve market supporting functions and rules. FSDZ works with a wide array of financial service providers, regulators, civil society organizations, government agencies, market infrastructure actors, consumers and other stakeholders to spur their engagement in inclusive finance.

The outcome of the programme is a “Financial sector capable of delivering a wide range of financial services to more people and businesses in Zambia”. This annual review covers the 12 month period through to end March 2018. By end March 2018, FSDZ aimed to provide:

- 300,000 additional people with access to finance (of which 65% to be women)
- 50,000 smallholder farmers with access to agricultural finance (of which 50% to be women)
- 12,000 additional MSMEs with finance from banks and financial service providers (FSPs)

FSDZ was established as a consultant-led model until April 2016, where the status was changed to a local non-profit company led by an independent board made up of mostly Zambian financial sector specialists, policy-makers and private sector entrepreneurs. FSDZ’s support for innovations in financial education of poor households, geographic outreach, micro-insurance, rural, agri and SME financing and policy advice on gender and on financial inclusion generally is well acknowledged by financial service providers and stakeholders in Zambia.

Summary supporting narrative for the overall score in this review (1/2 page)
The Financial Sector Deepening Zambia Programme has scored an A overall for the period to March 2018. The programme is doing valuable work some of which is not captured in the logframe relevant to the review period. FSDZ has played an instrumental role in making the financial sector environment more conducive for poor people and small businesses in Zambia. In its second year as an independent Zambian entity, FSDZ now enjoys an influential position in the policy forums of the government and has successfully nurtured innovation and provided valuable capacity building support to organizations. Numerous innovations, pilots and capacity building activities have started demonstrating results. Some good results and projects include:

- Over 31,000 poor people including 70% women received financial education through FSDZ supported activities in the year including innovative pilots such as Digital Financial Education. A successful pilot was tested through Zazu using mobile based financial education applications.
- Over one million small farmers have subscribed to private sector-provided Weather Index Insurance covering germination under the government-led Farmer Input Support Programme (FISP). This is an excellent example of an FSDZ pilot now taken to scale and transformational in a manner not envisaged when milestones were originally set. Additional pilots addressing farmers’ vulnerability to extreme weather and other risks are being tested.
- Savings Groups continue to grow across the country. These are now acknowledged as formal entry points for financial inclusion in the country.
- FSDZ supported research and knowledge products have been instrumental in refining the financial sector architecture in country. Over 191 organizations including policy makers, regulators, think tanks, financial service providers and other pro-poor service providers have benefitted so far.
- Financial sector infrastructure has improved with FSDZ support. A collateral registry is now operational in the country supporting SME access to loans. Similarly, the National Payment switch despite its initial delays has now received a satisfactory compliance audit report funded by FSDZ.
- Capacity of a local educational organization has been built to provide an SME Relationship Banking Diploma without any external consultancy support
- Access to microfinance loans has been made easier and faster through a digitization project with Agora Microfinance: 4,972 clients (61.4% female and 38.6% male) have gained access to loans in 1 month, when ordinarily the lending process would have taken 3.5 months.

However, there have been challenges in the year of review particularly in relation to the progress of partner organisations, and progress will need to accelerate in order to meet the ambitious targets set in the FSDZ Five Year Strategy through to March 2020:

- FSDZ has built enduring multi-year relationships with certain organisations, but progress has been mixed. Despite many successes, some partnerships have been less successful, for example improvements in the the Credit Reference Bureau are still pending action by the Bank of Zambia; the national payment switch has been delayed by two years.
- Existing banks are taking more time to upgrade their systems and strategies to improve the share of SME financing in their portfolio, even while new players are entering the market.
- Farmers who have subscribed to Weather Index Insurance are still waiting for their claims to be paid out (funds have been released by the insurer but have not yet been paid out by government – payments are expected to be made around the end of the year 2018).
- Savings Groups have grown in the country but the pace has slowed and this year FSDZ missed the logframe target.
- Reporting and mapping of activities to outputs continued to be challenging, particularly for example in relation to delivering innovation and designing models that have wider application across the region – some of FSDZ’s most important and innovative work is not captured adequately.
- FSDZ’s five year strategy is rightly ambitious. But it risks FSDZ support being spread too thinly across many areas.

Output No.	Output Description	Impact Weight (%)	Output Performance
1	More and Better Industry Data and Public Information on the Financial Sector is available and used by stakeholders.	10%	Outputs moderately exceeded expectation (A+)
2	Improved Policy and Regulatory Environment for the delivery of financial services	20%	Outputs met expectation (A)
3	Adequate Infrastructure and Support Services in place to support financial sector development.	20%	Outputs met expectation (A)
4	Improved Capacity of Financial Service Providers to deliver products that are accessible, affordable, and appropriate to poor women and men	30%	Outputs moderately did not meet expectation (B)
5	Improved Capacity of Financial Service Providers to deliver products that are accessible, affordable, and appropriate to MSME and smallholder farmers	20%	Outputs moderately did not meet expectation (B)

	ANNUAL OUTPUT SCORE	Outputs met expectation (A)

Recommendations for the year ahead (1/2 page)

- For the period to March 2018, the logframe for the programme is outdated and requires review for future activity. Outputs are not always clear, milestones are not current. In many cases, quality aspects of change due to FSDZ interventions are not captured. (DFID & FSDZ by January 2019)
- An additional output should be added to the logframe to measure the strength of FSDZ as an independent entity. The output indicators may include strength of corporate governance (Board’s role/oversight) annual board performance evaluation, management structures/compliance (internal/external audits), financial management (% of forecasts being met), adopting a cost centre approach, and Value for Money. (DFID & FSDZ by January 2019)
- FSDZ should engage with the government to ensure the Farmer Input Support Programme (FISP) claims are disbursed to the beneficiaries. In addition, we found that not all FISP beneficiaries under the Government-led programme are yet aware of their insurance claims and the amounts they are entitled to. FSDZ should engage the relevant department to encourage clearer communication to farmers and grievance redressal mechanisms are in place. (FSDZ January 2019)
- Reporting formats should be updated to have clear read across to the logframe outputs (some activities feed into multiple outputs/milestones in the current logframe) (FSDZ and DFID January 2019)
- Independent third party arrangements should be built into the programme monitoring regime to validate/ quality assure the results. (FSDZ March 2019)
- An independent assessment should be prioritised to assess the learning outcomes of the saving groups. Findings from the review should be used to improve the quality of groups (FSDZ June 19)
- FSDZ should build on the success of the Zazu financial education pilot and consider how it could be scaled up on a commercially sustainable basis. (FSDZ March 2019)
- FSDZ should strengthen the means by which lessons from its technical support to market players are made available to other Financial Service Providers in the market (FSDZ June-19).
- DFID should put in place a risk-based field monitoring strategy to monitor the activities in the field and obtain first hand beneficiary feedback. (DFID January 2019)
- Quarterly Reporting should be provided on Value for Money indicators and risks, in addition to results. (FSDZ January 2019 – i.e. for reporting on 2018-19 Quarter 3)
- Regular donor Coordination arrangements should put in place for DFID and other funders to review progress of FSDZ, discuss challenges and financial performance together (DFID & SIDA; March 2019 )
- DFID should carry out the next Annual Review (for 2018-19) at an earlier point in the year to ensure that findings are timely and recommendations are in place for the remaining year – this should be done after the FSDZ Annual Report is received (DFID June 2019)

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	More and Better Industry Data and Public Information on the Financial Sector is available and used by stakeholders.
Output number per LF		1	Output Score	A+
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Indicator 1.1 / Number of financial sector stakeholders using new industry data and public information products	28	191
Indicator 1.2 / Number of Target Beneficiaries Receiving Financial Education	150,000 / 75,000 (Women)	195,023 / (136,738)

Key Points
FSDZ has established a strong position as research and knowledge hub for the Financial Sector in Zambia. The valuable research products, evidence and data sets developed by FSDZ have been extensively used by Commercial Banks, Bank of Zambia, Ministry of Finance, mobile money firms and off-grid energy companies. These products are highly valued by market users including both state and non-state stakeholders and instrumental in policy formulation and product development. The output also captures poor people with an increased level of financial literacy.

This output has scored an A+ (output moderately exceeded expectations). FSDZ continued to overachieve on both indicators since last year. The 2018 milestones for both the indicators were met last year but the logframe target was not revised.

Output indicator 1.1
This indicator was exceeded by over 400%, with additional 155 organisations using FSDZ’s information products in the last year. This brings the cumulative number of organizations to 191. The overachievement is attributed to using an information web portal which is accessed more widely compared to FSDZ’s own website.

FSDZ has partnered with the “Data First Unit”[2] at the University of Cape Town to archive its historic data, and other research products for public access. The FinScope datasets (2005, 2009 and 2015), Financial Diaries data and the geospatial data (2015 and 2017) and other valuable reports are now available on the Data First portal. The portal tracks usage and downloads statistics. In some cases, and consistent with the M4P model, FSDZ also measures progress made by “copy cats” which are not FSDZ direct partners but adopt or implement FSDZ innovation or practices. FSDZ observes market systems to establish if there are any causal links between them and non-partners.
[2] https://www.datafirst.uct.ac.za/dataportal/index.php/catalog/central/about

Output indicator 1.2
The milestone for this year was already achieved at the time of the last annual review. During the period under review, FSDZ reached an additional 31,000 men and women with Financial Education interventions bringing the total number of beneficiaries to 191,023 including 70% women (136,738). If we take the incremental increase[3] expected during the year under review, it was expected that FSDZ will reach additional 30,000 beneficiaries - using this approach, FSDZ have reached additional 35,000 beneficiaries[4].
[3] Difference between millstones 2017/18 & 2016/17 (150,000-120,000)
[4] Difference between progress 2017/18 & 2016/17 (195,046-160,023)

FSDZ responds to financial education needs of people through a number of initiatives including financial education of members of saving groups, education to farmers about insurance products, working with educational institutes on incorporating Financial Education in curricula, and large scale campaigns through Insurance Week and Financial Literacy week. Savings groups are the major contributor to this indicator. FSDZ also partnered with “Zazu Africa[5]” to pilot USSD[6] based financial education modules in English and local languages for poor people. The contents covered both basic financial literacy and information about different financial products available in the market. 6,185 people subscribed to this service, of which 75% demonstrated increased knowledge on financial matters and financial products including insurance, loans, and mobile wallets.
[5] Fintech established to support digital finance
[6] USSD (Unstructured Supplementary Service Data) is a Global System for Mobile(GSM) communication technology that is used to send text between a mobile phone and an application program in the network

Lessons identified this year, and recommendations for the year ahead linked to this output
- The overachievement against indicator 1.1 is attributed to an improvement in dissemination and outreach strategy. However, the effectiveness of the use of the information products can be further validated. FSDZ should consider how to capture the effectiveness of knowledge products in contributing to improving the policy framework and service delivery of financial inclusion in Zambia (FSDZ, by January 2019).
- The attribution of copy-cats is more relevant at the outcome level. At output level, only those activities should be contributing where FSDZ have a direct control and monitoring system in place. This should be added to the indicator methodology note. (FSDZ, by March 2019/ end Q4).
- The 2017/18 milestone for indicator 1.2 was overachieved last year. Combining financial education with other support like formation of Saving Groups is an effective method for capacity building. However, in many cases, it is observed that the “Master Trainers” continue their engagement with the group after the first year. This raises two sustainability issues: either there are still gaps in learning and the group is unable to operate on its own; and/or there are no incentives[7] for the master trainer to build the local capacity and nominate someone from within the community. An independent assessment should be prioritised to assess the learning outcomes of the saving groups, and the value for money of the Master Trainer approach compared to others. (FSDZ, by June 2019/ end Q1).
  [7] Master Trainers are provided a decent sum of money to attend the monthly meeting of the group.
- FSDZ should build on the success of the Zazu pilot and consider how it could be scaled up on a commercially sustainable basis. (FSDZ, March 2019 – this is currently underway).

Output Title	Improved Policy and Regulatory Environment for the delivery of financial services
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of organizations demonstrating improved effectiveness in advocating for financial sector reform	4	4 / Benefiting organisations: Insurance Association of Zambia (IAZ), Technical Advisory Group (TAG), Bankers Association of Zambia, Zambia Credit Ratings Bureau.
Improved capacity of Policy makers to formulate and implement effective financial sector policies and regulations	25% improvement in capacity using FSDZ’s capacity assessment tool (this tool assesses organisations on their use of evidence, timely implementation and communication of new policies, and feedback on their policies and regulations from other stakeholders).	Bank of Zambia supported to Launch the National Financial Inclusion Strategy. / ZICTA, Financial Intelligence Centre (FIC), Zambia Competition and Consumer Protection Commission (CCPC) supported to update the 5-year Payment Systems Vision and Strategy / Pension and Insurance Association supported to draft and enforce Microinsurance. principles

Key Points
FSDZ is using its expertise to build capacity in key organisations to improve their delivery on financial inclusion. Following the development of advocacy and policy and regulatory assessment toolkits, it is now able to measure the impacts of its activities quantitatively. These toolkits measure advocacy capacity as well as policy making and regulatory capacity.

This output has scored an A (Outputs meet expectation). The 2018 milestone for the first indicator was met last year and no formal assessment was undertaken to measure the improved capacity under the second indicator. However, some strategic policy and regulatory milestones were achieved with FSDZ’s support.

Output indicator 2.1
FSDZ continued to work with the same four organizations as last year. This year, the Technical Advisory Group (TAG)[8] began to implement its five-year strategy. FSDZ supported all the technical meetings held during the year and facilitated institutionalization planning for the TAG. One of the major strategic achievements was the agreement to institutionalize the TAG by transforming the group into a registered network or association during the next fiscal year. FSDZ assisted the TAG to draft the 10 Microinsurance principles that should promote sound and good business practices in product design and delivery of Microinsurance products in Zambia. The planned enforcement of these principles is primarily through industry self-regulation by the Insurance Association of Zambia, and complementary through Microinsurance regulatory provisions from the Pension and Insurance Authority (PIA). After endorsement by the private sector, there is now indication from the PIA that they would enforce these principles. FSDZ also supported the implementation of the Insurance Week for 2017 and monitored activities in all 10 provinces. The Insurance Week is aimed at increasing consumer education on insurance. Work from the TAG and FSDZ has resulted in a commitment from the Government to take the long-awaited Insurance Bill to Parliament by February 2019.
[8] Technical Group with representation from Private Sector (insurance Providers), Public Sector (Ministries , Regulator, Pension and Insurance Authority) & Sector Associations (Insurance, Brokers, Pension, MFIs, Funders and Development agencies etc.)

FSDZ facilitated collaborations between regulators whose work impacts Digital Financial Services, with the market regulator which is the Bank of Zambia. Recommendations were provided for the regulatory road maps, particularly how the Bank of Zambia can work with three other regulators which have key roles. These included the Financial Intelligence Commission (FIC) which handles AML/CFT and identity; the Competition and Consumer Protection Commission (CCPC) which handles consumer protection; and the Zambia Information and Communications Technology Authority (ZICTA) which handles Information Technology and telephony including cell phone operations market regulation. At the request of Government regulators, a multi-regulator consultant was invited, coming twice in the year to engage regulators and market players. Meetings with all regulators as well as with each regulator were held. This provided BOZ, ZICTA, CCPC including FIC with an opportunity to raise matters of interest and clarification with the consultant. These organisations also agreed on a multi-regulator consulting agreement and meetings as well as MOUs.

Output indicator 2.2
FSDZ is yet to assess the capacity of Bank of Zambia (BoZ), Zambia Information and Communications Technology Authority (ZICTA) and Ministry of Finance (NFIS work) with regards to effective implementation of policies and regulations. An assessment for Bank of Zambia (BoZ) is expected in this FY (2018-19).

FSDZ has been supporting the Ministry of Finance to implement the National Financial Inclusion Strategy (NFIS). The NFIS was launched in November 2017 with significant FSDZ engagement and provision of background support including design sessions. FSDZ is actively participating in five NFIS working groups and is designing the monitoring and results management system. FSDZ is the only organisation on the NFIS coordinating committee which is not a government body.

In addition, the 5-year Payment Systems Vision and Strategy was updated in a consultative process facilitated by FSDZ involving commercial banks, ZICTA, Financial Intelligence Centre (FIC), Zambia Competition and Consumer Protection Commission (CCPC) and other financial institutions. In addition, through Technical Advisory FSDZ continued to support the Pension and Insurance Association (PIA). FSDZ facilitated engagement meetings with the PIA concerning the Microinsurance principles. Ten Microinsurance principles were drafted and are being considered for enforcement by the PIA, along with a certification process for those meeting the standards.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Output 2.1 is unclear and difficult to measure – a clearer description should be provided. (FSDZ, by January 2019).
- Capacity assessments need to be carried out annually in order to assess progress made, alongside beneficiary feedback from the organisations that have received TA or capacity building. (FSDZ, before next DFID Annual Review – June 2019).

Output Title	Adequate Infrastructure and Support Services in place to support financial sector development.
Output number per LF		3	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 3.1 Number of new or improved support service offerings to stakeholders	15	10 (target not met)
Output indicator 3.2 Number of financial infrastructure functions recording progress during the year	4	4 (100%): target met / ZIBFS (Level 5) / Credit Reference Bureau (Level 3) / Collateral Registry (Level 5) / National Switch (Level 3)

Provide supporting narrative for the score

Key Points
The output covers FSDZ’s technical support to create an enabling environment where efficient and effective market infrastructure and support services[9] are in place to advance the delivery of financial services to its clients.
[9] A support service is defined as any service delivered by a support service provider to a FSP, such as business advisory services or staff training and human resource development services.

This output has scored an A (Outputs meet expectation). For milestone 3.1, to maximise impact and ensure fully engaged partnerships FSDZ focussed their work on 10 organizations, but has broadened the scope of their work within these – for example, on coordination for a Zambia Electronic Clearing House, which involve a number of the banks. It has also contributed to major achievements in the sector in terms of infrastructure development and services offered such as the placement of new cell phone towers, progress towards biometric identity, and cybersecurity and credit systems management. Each is potentially critical in terms of developing a new financial sector architecture that delivers for the poorest at a cost that Government and the private sector can make sustainable. The milestone for indicator 3.2 was met with all four organizations being supported by FSDZ demonstrating considerable progress and scoring high on the assessment tool developed by FSDZ.

Output indicator 3.1
FSDZ is supporting 10[10] organizations operating in Rural Agricultural Finance, SME Sector, and Inclusive Insurance. FSDZ provide advisory support in various forms to the recipient organizations so that they can play a more effective role in creating an enabling financial sector environment in Zambia. For example, next year TAG is hosting the first Sub-Saharan Africa International Microfinance conference within its service offer agenda. Other such examples of ‘support services’ include signing a contractual arrangement with Catholic Diocese of Ndola (CDN) to form and build the capacity of Savings Groups and build the capacity of a local institute to impart diploma level courses for the SME sector. A major achievement during the year was the operationalization of the Collateral Registry which is addressing the issue of access to finance for many businesses which were finding it hard to secure loans from the banks. Additionally, over time, the registry will significantly reduce the commercial disputes arising from the same collateral being pledged by different finance providers.
[10] Rural Agri Finance- Catholic Diocese of Ndola , Catholic Relief Services, MFinance & Microsave; SME- Relationship banking; Inclusive Insurance- African Life, Professional Insurance Corporation Zambia, FINCA, Entrepreneurs Financial Centre; Microinsurance Acceleration Facility – Proflife, Madison,

Output indicator 3.2
FSDZ continued supporting the same four organizations. All of them have shown significant progress during the last year and their score progressed upwards on “Financial Infrastructure Assessment Matrix[11]”.
[11] FSDZ developed a scoring system to benchmark and assess the scale of improvements to financial infrastructure across 8 levels. See Programme Annual Review 2016 for details on the matrix.

See progress below;
Zambia Institute of Banking and Financial Services (moved from Level 3 to Level 5) FSDZ successfully handed over the Executive Diploma in “SME Relationship Management” programme to Zambia Institute of Banking and Financial Services (ZIBFS). Four master trainers from Zambia are now certified to deliver the trainings independently without the support of international consultants. All training manuals/material have been handed over to ZIBFS and will be available for use by the trainers and participants in the next programme.

Credit Reference Bureau (Level 3 - No change since 2016) FSDZ completed a review of the credit bureau and recommended improvements to the Bank of Zambia as regulator, though action by the regulator has been delayed. FSDZ consulted with officials in the FIC, the Ministry of Home Affairs, and the Attorney General to support introduction of the planned Government national biometric identity rollout.

Collateral Registry (moved from Level 4 to Level 5) A significant milestone met this year is the operationalisation of the Collateral Registry in Zambia. The collateral registry will improve businesses access to finance by making a broader range of assets eligible as collateral. Since, the launch in November 2017, 222 financial institutions have registered for the registry, a total of 8,695 financial statements have been registered, and the total number of moveable assets registered is 14,344. FSDZ working closely with International Finance Corporation (IFC) provided significant technical support in registry public education, worked with FSPs and the judiciary on the methods of use of collateral and rules governing its pledging, realization, and repossession of assets.

National Payment Switch; (moved from Level 1 to Level 2) Mixed progress is made on National Financial Switch project for Zambia to interlink the various institutions and players in the payment area to ensure that the payments are cleared at a central place and transmitted to other parties as quickly as possible. FSDZ funded a “software audit” of NFS conducted by “Volante of Kenya” to give Payment Card Industry Data Security Standard (PCI DSS)[12] compliance. FSDZ is working with Bank of Zambia (BOZ) on the formation of an autonomous Payment Association of Zambia. Mobile money operators have been engaged and are working out a framework of operation. A concept paper was developed and shared with BoZ and key stakeholders. The Zambia Electronic Clearing House Limited is targeting to have a fully functional National Payment Switch by the end of 2018.
[12] The PCI Standard is mandated by the card brands and administered by the Payment Card Industry Security Standards Council. The standard was created to increase controls around cardholder data to reduce credit card fraud

FSDZ also provided consultation and information support to the Ministry of Transport and Communications and to Zambia Information and Communications Technology Authority (ZICTA) for expansion and improvement of cell phone coverage throughout Zambia. FSDZ is monitoring the rollout of cell phone towers and biometrics identity. This year, the following financial infrastructure will be added to the scoring system: 1) cell phone towers; 2) biometrics ID and 3) payments systems.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Building the capacity of ZIBFS to deliver the trainings independently is a success. However, there is still need for ZIBFS to hire more local trainers to deliver the course. Feedback should be obtained on the quality of training and the impact on improving the banking services. (FSDZ, by March 2019).
- The National Financial Switch is over two years late in go-live status and there are still some outstanding issues. FSDZ should continue its engagement with the Bank of Zambia to speed-up the process on putting the critical infrastructure in place. (FSDZ, ongoing, by end of 2019).
- FSDZ should more clearly define the type of support services being provided to recipient organizations e.g. training, TA, advice, commissioning research, or other services. (FSDZ, by January 2019).
- Although progress has clearly been made with the four organisations under 3.2, the output indicator simply measures the number of organisations, not their capacity. This also does not reflect the materiality of the interventions, nor recognise the relatively limited number of organisation that have the capacity and desire to act as partners for FSDZ. This should be revised in the logframe. (FSDZ, by January 2019).
- A significant challenge in this output is to clearly identify and explain the support service and how FSDZ’s role on establishing/enhancing these support services. The same activity may still be contributing to other outputs. The logframe should be revised to clearly define the support services. (FSDZ, by January 2019).

Output Title	Improved Capacity of Financial Service Providers to deliver products that are accessible, affordable, and appropriate to poor women and men
Output number per LF		4	Output Score	B
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 4.1 Number of financial service providers (FSPs) with increased capacity to reach poor women, men and microenterprises with financial services	20	20 (target met last year)
Output indicator 4.2 Number of sustainable community based financial institutions providing financial services to poor men and women	7500	5,737 (76%): Target not met

Key Points
The output covers FSDZ support to Financial Service Providers to enhance their capacity for delivering a range of financial services including Microfinance, Insurance, Agri-finance and etc. to poor people and also supporting informal saving groups to enhance culture of savings and credit amongst poor women and men.

This output has scored an overall “B” (outputs moderately did not meet expectation). The milestone for indicator 4.1 was met at the time of last annual review. However, the logframe target was not updated. FSDZ continued to work with the same organizations. The milestone for indicator 4.2 was not met substantially.

Output Indicator 4.1
During the year, FSDZ signed contracts with Barclays Life, Madison Life and Sanlam Life insurance to support Microinsurance product development and implementation activities such as product awareness creation. All the three partners launched the products in March 2018. FSD Zambia provided both technical and financial support to the partners for continued support towards capacity building. In addition, work under Digital Financial Services (DFS) with Zoona, Airtel Money, MTN Money, and Zamtel Money on market development, options for investment and products and resolution of challenges with the urban kiosks’ placement have been important capacity development areas. Work with AB Bank and with Agora Microfinance on how to access rural clients and women as well as digitisation have been important areas for their growth.

Output Indicator 4.2
The informal saving groups continued to be instrumental in supporting the culture of savings, access to informal loans and earning interest income. The Saving Groups (SGs) are nationally recognized as the valid entry point for financial inclusion for the underserved. The size and influence of SGs as a vehicle for women’s empowerment and expansion of microenterprises, particularly in rural areas, is increasingly being recognized, given that SG members are over 80% female.

During the year, 823 new Saving Groups were formed bringing the total number to 5,737 with FSDZ supported interventions. The progress has been significantly lower than last year, when 2000 new groups were successfully created. The target for this year was missed by almost 50%. The target was previously revised upwards due to the ‘J curve’ acceleration in progress, though the pace of savings group creation has since slowed, in part due to accessing harder to reach communities. One challenge was due to the high dropout rates of Master Trainers. Another factor explaining the slower progress may be the incentive structure of Master Trainers to create more groups, compared to working with the same groups over multiple years – there seems to be limited ‘graduation’ of savings groups.

FSDZ support is not only aimed at increasing scale, but also enhancing the quality of these groups and making the market shift from NGO engagement to private sector creation and support. The transition involves NGO-private blends such as the private service provider (PSP) and village agent models. By the end of March 2018, a cumulative total of 141 PSPs and 96 village agents had been certified and trained respectively to mobilize and train groups across the country. Research this year shows that in villages, PSPs and village agents are the most trusted persons involved in financial learning, advice, and services.

FSDZ has also collaborated with MFinance to design and pilot a mobile savings platform. The product is being piloted among SGs in Kasama, Kafue and Chongwe. MFinance will continue refining the product by incorporating feedback from the SGs during the pilot. 50 transactions were recorded on the mobile platform. Initial reports indicate that members are attracted to the platform due to increased security of funds and efficiency during transactions.

Lessons identified this year, and recommendations for the year ahead linked to this output
- Potential challenges with savings groups include the safety of cash deposits, record of contributions and withdrawals. FSDZ should explore options for cash safety (such as formal banking or mobile money) and most importantly digitisation of transaction history in some way to avoid loss of important data and to build credit history for members.
- FSDZ should explore how the savings groups and especially their credit history can be documented and shared with the microfinance industry to help them to access long term formal financing. (FSDZ, by June 2019).
- The master trainers should be bound to build the capacity of the group within one year. The incentive structure should be revised to support the creation of new groups, compared to continued engagement with the same group over many years. (FSDZ, by June 2019).
- Business and entrepreneurial support services could also be provided where there is demand. (FSDZ, by June 2019).
- The current monitoring system only tracks names of group members to identify duplicates across different groups. FSDZ should engage with other FSDs to explore more robust ways of identifying duplication. (FSDZ, by March 2019).

Output Title	Improved Capacity of Financial Service Providers to deliver products that are accessible, affordable, and appropriate to MSME and smallholder farmers
Output number per LF		5	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 5.1 Number of FSPs with increased capacity to reach MSMEs with financial services	15	13 (same as last year)
Output indicator 5.2 Number of financial service providers with increased capacity to reach smallholder farmers with financial services	10	10 (100%) – target met

Key Points
The indicator captures FSDZ’s capacity building support aimed to enhance institutional and human resource capacity, develop and implement strategies for increased outreach to SMEs[13] and Smallholder Farmers[14], strengthen governance and internal controls functions.
[13] Businesses employing between 6 and 50 staff
[14] Farmers who cultivate less than 5 acres of land

This output has scored an overall “B” (outputs moderately did not meet expectation). The milestone for indicator 5.1 was not met. FSDZ continued to support the same 13 organizations[15] since 2015. However under indicator 5.2, FSDZ provided technical support/advice to 4 new organizations to improve their capacity and outreach to small holder farmers.
[15] SME - Investrust, MFinance, MFZ, Focus, AB Bank; Industry training: FINCA, Stanbic, Cavmont, Zanaco, FNB, EFC, NATSAVE and DFS - Zoona

Output Indicator 5.1 The milestone for this year was not met. FSDZ continued providing technical support to the same 13 organizations. However, this hides the fact that there are only a limited number of organisations in Zambia (18 banks for example) and not all will have the capability and desire to participate with FSDZ. Also, the indicator does not yet capture progress made within the organisations. A significant milestone achieved this year is the institutionalisation of Executive Diploma in “SME Relationship Management” programme to Zambia Institute of Banking and Financial Services (ZIBFS) through certifying Zambian “Master Trainers” to deliver the trainings in future without any external technical support. All training manuals and materials were handed over to ZIBFS and are available for use by the trainers and participants in the next programme (note that this activity also contributed to Output 3).

Progress made with other partners remained mixed. Zanaco[16] embarked on several projects to re-engineer its business processes across all departments of the bank, though the Live Labs project was terminated due to significant delays on the part of the banks taking part. MFinance[17] plans to transition into a Micro Small and Medium Enterprise (MSME) bank in the first quarter of 2019. FSDZ supported MFinance to revise its MSME Banking strategy which was approved by MFinance Board. FSDZ also undertook a detailed diagnostic of all Investrust Bank systems, processes and procedures in its MSME Banking Department, as well as the current MSME Banking strategy.
[16] Zambia National Commercial Bank, commonly referred to by the name "Zanaco", is a commercial bank in Zambia
[17] MFinance is a financial services company in Zambia operating in the micro-finance segment of the market

Output Indicator 5.2 FSDZ embarked on various activities supporting outreach of Financial Service Providers (FSPs) to smallholder farmers. This included process engineering for issuance of microfinance loans to rural population through supporting digitisation of loan processes by Agora Microfinance Bank. The pilot is successful and Agora Microfinance Bank have fully digitised two of its branches. The bank teams working in the field are now equipped with Digital Tablets which allow them to issue loans and receive payments in the field with biometric verification and issuance of receipt. This process benefitted over 4,972 clients in less than a month, reducing the overall cost of financing for the Agora MF bank and saving of travel cost to visit the bank branch by the client.

FSDZ also partnered with Alliance Ginneries (an agriculture inputs company) to provide ’nano-Loans’[18] at zero interest to poor farmers during the hungry season[19]. This helps them meet their daily consumption needs and mitigate the risk of short selling of crops or engaging in other jobs and ignoring their fields. Approximately 1200 farmers benefitted from this support and the loan recovery rate was 95%. Alliance Ginneries confirmed that they will again offer this facility to farmers using the loan amounts returned plus their own contribution. This represents an important innovation that has much wider application.
[18] These are loans of up to 200 Kwacha (US$20)
[19] December to March (Period between planting and harvesting)

Supporting agri-insurance has been a huge success this year and included the first public private partnership where Ministry of Agriculture partnered with Mayfair Insurance[20] to embed “Weather Index Insurance” [21] into the national Farmer’s Input Support Programme (FISP)[22]. The FISP Weather Index Insurance (FISP WII) provided insurance cover for inputs (seeds, fertilizer) to over 1 million farmers with their contribution of 100 Zambian Kwacha[23] against the risks of drought, dry spells, and excessive rainfall during the germination season. Payout is a maximum of K1,700 (i.e. the value of the input subsidy).
[20] Private sector Insurance Provider contracted by Government through an open competitive procurement process.
[21] Weather index insurance pays indemnities based not on actual losses experienced by the policyholder but rather on realizations of a weather index that is highly correlated with actual losses
[22] Partial subsidy of agriculture inputs (seeds and urea) targeting one million smallholder farmers
[23] Equivalent $10 only

During the last season, due to confirmation of bad weather at 627 sites across the country, claims of 60 million Kwacha are now due to over 400,000 small farmers. The Insurance provider, Mayfair, has already transferred the funds to the government . though the disbursements have not yet been made, posing a risk to the scheme’s credibility. The Ministry is now planning to disburse the funds to the beneficiaries together with the next distribution of FISP subsidies and e-vouchers, by the end of 2018. This is a good example of a pilot supported by FSDZ now scaled up at the national level with further targeted technical support to Mayfair for design of the insurance product, though FSDZ needs to work with Mayfair and the Ministry to ensure claims are paid out and improve the scheme’s efficiency and effectiveness in the second year. We are aware this is already beingactively pursued.

FSDZ under its Microinsurance Accelerator facility also tested another innovative product - “Chilala weather Index Insurance” - to cover farmers from maize seed germination failure due to bad weather (no or excessive rains). Every year, farmers lose their crops due to weather conditions and are forced to borrow funds to buy seeds. In partnership with the seed company Dekalb and Focus General Insurance, the product was launched to target 100,000 farmers. In addition to support for design, FSDZ supported product awareness and training campaigns to merchandizers. At the end of the season, approximately 9,000 farmers accessed the insurance through purchases of Dekalb seed. The review team visited one site and met the farmers. It was noticed that, while the scheme has potential, further support for information dissemination is needed, as very few farmers who have bought the same seeds were actually aware of the insurance product. The seed bag is comparatively low priced compared to other available brands. Thus, increased sale of these bags cannot be attributed to the provision of the insurance product at this stage.

Lessons identified this year, and recommendations for the year ahead linked to this output
- FSDZ must ensure that lessons from all its capacity building support is made available to other Financial Service Providers in the market. In both cases of Alliance Ginneries and Chilala Insurance, the evidence of demonstration effect was not clear and the support could be argued as focusing on selected players only – in line with the M4P approach, expansion should be encouraged through the demonstration effect. (FSDZ, by March 2019).
- FSDZ should continue to engage with the government to ensure the claims are disbursed to the beneficiaries, and to advocate for payments to be made directly by the insurer to claimants in future. (FSDZ, ongoing - by January 2019).
- Some FISP beneficiaries are unaware of their insurance claims and the amounts they are entitled to. FSDZ should continue engaging with the Ministry of Agriculture and the insurer (Mayfair) to encourage a communication plan is in place to consistently inform farmers about the scheme. (FSDZ, by March 2019 – during this agricultural season).
- Grievance Redressal Mechanisms should be encouraged to address any inclusion/ exclusion errors.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)
The Theory of Change of the Programme still remains valid. The project supports financial sector development in Zambia and assumes that it will deliver a range of financial services which are affordable and accessible to poor people and businesses, hence improving their income and/ or a reduction in their vulnerability. The programme adopts a “Market Systems Development” approach and is aiming to tackle market failures at different levels. For example, the research products are helping to identify valid entry points for financial sector players and also informing regulators and associations to create a more conducive financial environment. The capacity building support is being provided at different levels ranging from financial literacy of the poor to supporting infrastructure development, product development and business process engineering through innovative digital tools to improve the service delivery. The theory of change also supports testing product innovations through pilots which can then be replicated by other players in the market thus creating a competitive environment which favours both coverage of unserved population and affordability.

Overall, FSDZ is doing a commendable job as described in the earlier sections and delivering in line with the theory of change. It is also very clearly working in a way to gain support from wider stakeholders and potential funders, and is helping to put in place the building blocks for a broader transformation of the finance and investment sector in Zambia, which should have much wider benefits across Zambia and possibly the region. However, whilst doing so there are risks that it may have spread itself thinly by working on many different interventions, which has led to organisational and resourcing challenges. We note that since the period of review, FSDZ’s new strategy does attempt to reduce the number of focus areas, for example by combining SME with rural finance.

There have been some shifts from the original Theory of Change, but these were mainly at activities level. For example, the shift from a consultancy led model to a locally established Special Purpose Vehicle (SPV) has been largely successful, provides greater local ownership and gives FSDZ the opportunity to be sustainable beyond funding from DFID. Similarly, learnings from challenges on expanding informal finance mechanisms have helped FSDZ to move from a pure NGO led model to using NGO-private blends such as the private service provider (PSP) model.

FSDZ has now developed its next five year strategy aiming to reach additional 336,000 people by end of 2022. In line with views from FSDZ’s own Programme Investment Committee (PIC), it is recommended that FSDZ should continually challenge itself to ensure that it is strategic and not spreading itself too thinly, while recognising the external drivers for this, including government and donor demands.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)
The intended impact of the programme is “Sustainable improvements in the livelihood of poor people. This is measured through “number of poor people experiencing an expansion in their income opportunities or a reduction in vulnerability”. Against the impact target of 138,000 people benefiting from an increase in income opportunities or a reduction in vulnerability, 1.24m beneficiaries were recorded. Against the outcome target of 50,000 smallholder farmers, the progress reported was over 1.13 million. These achievements are largely attributed to Weather Index Insurance (explained at output 5.2 above), which added 1.1m beneficiaries in addition to the outcome and impact targets. The insurance company has already disbursed the insurance amount to the government, but the funds are yet to be disbursed to the farmers. It could not be determined by the review mission whether beneficiaries we met were fully aware of their entitlement and/or if they are experiencing any change in their vulnerability. Excluding the claimed beneficiaries from weather index insurance, all outcome targets would still have been achieved, while the impact target would have been narrowly missed (128,000 against the target of 138,000).

The outcome of FSDZ programme is “financial sector capable of delivering a wide range of financial services to more people and businesses in Zambia”. Achievement of this outcome is broadly on-track.

Outcome Indicator(s)	Milestones	Progress
Outcome indicator 1 Number of poor people and microenterprises accessing a new financial service	300,000 / (65% women)	292,782 / (54% women)
Outcome indicator 2 Number of smallholder farmers accessing a new financial service	50,000 / (50% women)	1,113,020 / (25% women)
Outcome indicator 3 Number of MSMEs accessing a new financial service	12,000	20,000

FSDZ has played an instrumental role in making the financial sector environment more conducive for poor people and small businesses in Zambia. FSDZ now enjoys an influential position on the policy forums of the government and has successfully nurtured innovation. Pilot projects supported by FSDZ have been taken to scale by other players in the sector, including the government. Expanding and strengthening savings groups, which are generally formed at grass roots level with the majority of members being poor women, have been instrumental in building a culture of savings and using loans for income generating activities (outcome indicator 1). Although in percentage terms, the progress on outreach of women is low at 25% compared to 50%, FSDZ has nonetheless reached significantly more number of women than the target implied in terms of actual numbers of beneficiaries i.e. 278,300 compared to 25,000.

FSDZ continued providing technical support for design and implementation of various financial instruments for small holder farmers. The decision of including insurance support into a large scale programme is a strong example of a successful pilot being institutionalised by the government, notwithstanding some of the delivery challenges that have somewhat inevitably come with that (outcome indicator 2). Finally, fast processing of loans through digitisation of loan process will help business access the capital when needed the most (outcome indicator 3).

Explain major changes to the logframe in the past year (1/2 page)
No major changes to logframe during the year, though FSDZ updated their projections to demonstrate increased reach. The outcome, impact and one output indicators have since been revised prior to signing the new accountable grant, and all targets revised upwards.

A number of issues with the current output indicators were raised by DFID and discussed with the FSDZ Monitoring and Evaluation team, including duplication and relevance to FSDZ’s current activities. The team agreed to review the output indicators and will discuss proposed changes with DFID , as well as commissioning external quality assurance of results this is still ongoing and should be prioritised

Describe any planned changes to the logframe as a result of this review (1/2 page)
The logframe of the programme is outdated and requires review. The mapping of activities to outputs is complex - in some areas where FSDZ uses its influencing support, the attribution of results is not clear, though we recognise that this is typically hard to achieve. Similarly, in many cases, more than one activity is contributing to the same output, and some activities contribute to more than one output. Some of the milestones are on a cumulative basis and were achieved in previous years; however FSDZ continues to provide support in these areas to enhance the quality of interventions, which is not captured in the logframe. Perhaps most importantly, for a programme that aspires to, and does, deliver genuine innovation and delivery models that have wider application across the region, the logframe does not recognise these benefits in a way that appropriately incentivises the type of innovation that can deliver more transformational change whilst simultaneously risking failure of certain interventions.

A thorough review of the logframe including revision at all levels is critically important and should be done as soon as possible (January 2019).

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

FSDZ’s value for money approach is aligned with DFID’s approach on measuring the progress against the ‘4Es[24]’. Overall, the progress has been mixed during the period under review. Overall value for money looks positive given outperformance against output milestones whilst underspending against budgets and delivery costs per beneficiary look good when compared to regional comparators. On the other hand, headline administrative costs rose slightly to 24% from 23% last year. This included some one-off costs related to SPV set up and an office move, as well as forex losses – once these are excluded, the headline administrative costs were 20%, but still requires improvement to deliver the target level of 18%. Similarly, the average cost per beneficiary[25] also increased from £7.90 to £10.40. To a large extent, this is a function of FSDZ entering harder to reach areas with geographically dispersed populations, but close monitoring is needed. Below is a summary of progress against each indicator:
[24] Economy, Efficiency, Effectiveness and Equity
[25] Cost per beneficiary from savings groups supported by CDN is used since this is the only intervention where comparative data for previous years is available.

Economy
Ratio of national to international consultants
This shows a positive trend which should lead to savings, assuming local consultancy is lower cost than international consultants. By the end of March 2018, national consultants supported FSDZ in selected skills areas such as small social research measurement events under Monitoring and Communicating Results (MCR), Informal Finance and SME Executive Diploma training. In Rural Agri Finance (RAF) pilot initiatives and the SME Executive Diploma training, internationals led in service provision. However, during the period under review international and national consultants collaborated to handover the SME Executive diploma training to the Zambia Institute of Bankers and Financial Services (ZIBFS). Going forward, the ratios will move further in favour of national consultants.

Recommendation: the ratio would be more meaningful if it included a comparison of fee rates and duration of inputs between international and national consultants (FSDZ, by March 2019 - the revised VfM indicator for the current year does include a fee rate target.)

Technical Assistance	March 2016	March 2017	March 2018
National Technical Assistance	10	26	17
International Technical Assistance	12	23	11
Ratio	1/1.2	1.1/1	1.7/1.0

Cost savings
In the period under review limited cost savings were tracked, albeit in a period during which the SPV setup was still driving variable costs. Going forward FSDZ should look to make and report on more substantive cost savings – for example, the programme is now sharing its offices with another organisation, which will generate specific cost savings in the next review period. There may also be scope to drive further efficiencies in consultancy spend and network operations through innovation in operating models. Attracting new funders will also help drive greater synergies across the organisation.

Programme management (administrative) costs to total costs
The target for this indicator is 18%. FSDZ continued to exceed the target in the review period with management costs as a proportion of total expenditure 1 percentage point higher than last year at 24%, albeit still lower than under the previous supplier-led model. This is partly influenced by the in-year underspend on variable intervention costs (see Section F) while many administrative costs are relatively fixed. Excluding ‘one-off’ expenditures, such as costs associated with the office move and IT and forex losses, the management costs for FSDZ were around 20%. This also excludes the matched costs provided by project partners for which some degree of administrative costs is related – including this would potentially drive the ratio lower.
Recommendation: FSDZ should identify further opportunities to reduce administrative costs down in future years in line with agreed targets (18% in 2018/19, moving to 16% in the next year) which in part will be delivered through greater spending on direct interventions. (FSDZ, ongoing, by March 2019). As an example of recent progress, FSDZ is now sharing its office space with another partner which will reduce overhead costs in the current year.

Efficiency

Average cost per beneficiary
This indicator measures the efficiency of FSDZ’s support to savings groups. The Rural and Household component comprised 36% of FSDZ’s programme spend over the reporting period, with savings groups accounting for the majority of this. The average cost per beneficiary of the Savings Group is £10.4 which compares favourably to the regional average of £14 per beneficiary. The average cost per beneficiary for a pilot of Nano-Credit to farmers implemented through Alliance Ginneries is £3 (25% of the actual credit received by the farmer[26]). Although this is a pilot project, the cost would clearly need to decline in order for the pilot to be sustainable.
[26] Nano Credit ZMK200= £13.3

Partner leverage ratio
This ratio is a good indication of whether FSDZ’s private sector partners are convinced by the business case of the proposed activities and are willing to ‘buy-in’ with their own finances. This indicator also demonstrates the probability of sustainability of the activity beyond FSDZ role. Last year 7 out of 11 partners contributed more than 50 percent of total project costs, enabling FSDZ funds to go further.

Percentage of partnerships resulting in sustainable practice change
This indicator captures the market change which is driven by FSDZ interventions. For example, the government decision to include the Weather Index Insurance as part of the Farmer Input Support Package covering over one million farmers. Similarly, a significant market transition took place with the national level recognition of savings groups (SGs) as the valid entry point for financial inclusion for the underserved. In addition, there was a market move to shift from purely NGO-led growth to private actor generation and support of SGs. The size and influence of savings groups as a vehicle for women’s empowerment and expansion of microenterprises, particularly in rural areas, is increasingly being recognised, given that the 600,000 plus SG members are over 80% female.

Effectiveness

Number of actual people utilizing financial services vs planned
This indicator measures the actual results of the programme against the expected milestones across impact and outcomes indicators. Across the board FSDZ has achieved higher results than expected and thereby delivered greater value for money than forecast.

A cumulative total of 1,405,802 poor people, microenterprises and smallholder farmers accessed a new financial service. This figure represents an addition of outreach results from outcome indicators 1 and 2. The end of year results indicates that 98% (292,782) was achieved against March 2018 milestone of 300,000 poor men and women outreach for Outcome Indicator 1. For Outcome Indicator 2: Smallholder farmers access a new financial service; results show achievement of 1,113,020 which is over and above the March 2018 milestone of 50,000 – though this is due to the inclusion of farmers benefiting from weather index insurance (see ‘Theory of Change and Progress Towards Outcomes’ section).

Estimated economic returns on specific project activities
This indicator is currently being compiled to determine FSDZ outreach and the benefit compared to the investment in the savings group intervention. Recommendation: to compile estimates ahead of the next Annual Review (FSDZ, by June 2019).

Equity
Percentage of beneficiaries that are female
FSDZ has a target of 65% of beneficiaries being female. Overall, FSDZ has so far supported 1,239,539 people including 30% women (384,031) experiencing a reduction in poverty and/or vulnerability. The huge disparity between the target and progress achieved is due to the results from the weather index insurance scheme, where the farmers are predominantly men. If we exclude the beneficiaries of the insurance intervention, then the percentage is higher at 54% (last year 51%) but still below the 65% target.

Percentage of beneficiaries that are below $2.5/day as measured by PPI
No surveys were conducted during the period under review to measure the progress against this target. However, a Monitoring Impact Survey (MIS) conducted in January 2017 indicated that most respondents (70%) were from extremely poor to poor households, and 20% from near-poor households.
Percentage of beneficiaries in least connected/ poorest states
No date is available for this indicator. Recommendation: FSDZ should aim to provide a geographical breakdown of beneficiaries (FSDZ, by June 2019 - for the next Annual Review).

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

FSDZ’s objectives are in line with DFID’s Economic Development Strategy and, by unlocking constraints to Zambia’s long-term prosperity, forms an important part of DFID’s and the UK Government’s overall portfolio in Zambia. FSDZ’s work on policy, regulation and relationships also provides a broader basis for increasing investment further up the value chain for SMEs and growing businesses. Facilitating financial inclusion is also a primary means of using technology and digital innovation to deliver enhanced services and leverage strengths of the UK offer, so fits squarely with HMG interests in Zambia. Finally, DFID Zambia’s risk appetite for innovation is high, given the positive operating environment and the potential to trial new approaches that have broader application across the region, and FSDZ fits strongly within that ambition.

Based on the above analysis of progress against value for money indicators, the programme overall represents strong value for money. Despite underspending against forecasts, and showing weaker performance against specific KPIs, overall it has over-delivered in the majority of outputs. It has performed well against the impact, outcome and output milestones. FSDZ has now transitioned into a Special Purpose Vehicle and enjoys an influential position at government policy forums. The policy environment of the financial sector in Zambia is conducive for structural changes. The government has shown its commitment through launch of the National Financial Inclusion Strategy and incorporating weather index insurance and/or recognising Savings groups as an entry point for financial inclusion. There is still a wide scope for innovations to support financial inclusion in the country, and much progress to be made, thus the review recommends that FSDZ should continue. However, as this Annual Review recommends, there is scope for the programme to improve its VfM and to better demonstrate the results it is achieving.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Moderate

Overview of programme risk
The overall assessment of programme risk is moderate. The risk matrix for the programme is reviewed monthly through Programme Boards, and at least quarterly with FSDZ. This covers all identified risks at a given point in time, and tracks their status and trend.

The current risks to the FSDZ programme are set out in the table below:

Risk Description	Risk Category	Mitigation Strategy	Residual Risk
Financial sustainability / As DFID funding is expected to decline, there is a risk that additional funding from other sources is not sufficient to compensate.	Operational	Incentivise FSDZ to mobilise new funds through matched funding; attracting new funds part of CEO's responsibilities in job description; DFID to assist in facilitating contacts of potential new funding partners.	Major
Corporate governance and DFID oversight / FSDZ corporate governance is not effective (for example policies and procedures are not followed), while DFID does not strike the right balance in terms of engagement on FSDZ day to day management.	Operational	Additional corporate governance requirements added to new accountable grant, for example on communication with DFID and financing partners. DFID to attend Board meetings as a member and review whether necessary to join as a Director. DFID to ensure that day to day management is proportionate.	Moderate
Policy environment and partner support / Deterioration in the Zambian policy/regulatory environment (e.g. reserve requirements further crowd out SME lending; partners such as Bank of Zambia, Ministry of Finance, and the Pensions and Insurance Authority cease to be supportive of financial inclusion).	Delivery	Develop relationships with policymakers; programme objectives include policy influencing, support and capacity building.	Moderate
Macroeconomy / Significant deterioration in the global environment or the Zambian macroeconomy (e.g. a combination of low copper prices, fiscal deficits, and a weakened kwacha raise interest rates and further crowd out SME and other lending). Low GBP exchange rate reduces programme purchasing power as well as international staff and contractor remuneration.	Context	Limited scope for mitigation on economic risks. Salaries moved to local currency (kwacha) to manage exchange rate risks. Weekly brief on latest economy developments. Engaged with key government stakeholders to ensure FSDZ’s interests are taken into account.	Major
Personnel / Risk of key leadership personnel at FSDZ leaving, causing lack of direction if capable deputies not in place).	Delivery	Start CEO contract negotiations early. FSDZ CEO training a capable deputy/ acting CEO as contingency for eventual departure.	Moderate
M&E / FSDZ M&E team lacks capacity to report and verify results and progress timely and credibly.	Operational	FSDZ to contract independent QA of results. Change in M&E team leader.	Moderate
Misuse of funds / Funds not being used as intended – including fraud, corruption and reputational damage. This includes the risk of funds given to subcontracted/ downstream organisations. When government adopts a model that has been piloted by FSDZ, it creates an element of reputational risk even though not DFID funds.	Reputational	FSDZ has a finance and procurement manual which contains measures to prevent fraud. Due diligence was carried out on FSDZ and on downstream partners. A spot check was held end 2017 and one is scheduled for Dec 2018. We update FSDZ on perceived fraud risks; CEO and management have read DFID guidance, and have attended partner events hosted by DFID on awareness and mitigation of fraud risks.	Major
Safeguarding / Risk of improper/ inappropriate conduct or abuse either within FSDZ or with downstream partners.	Safeguarding	FSDZ successfully took part in the pilot scheme on compliance with DFID safeguarding guidance, with interim measures being rolled out while full DFID guidance is developed. A new FSDZ safeguarding policy is in place.	Minor
Innovation risk / FSDZ is encouraged to innovate and trial new approaches that can have transformational and wider applications. Risk that pilot projects and new approaches fail due to testing unproven concepts.	Delivery	Project plans set out risks of new pilot projects. Adaptive approach to start small and regularly review success. / Deploy appropriate expertise and properly test innovations prior to application.	Major

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues
FSDZ is governed by an Independent Board. DFID attends the Board meeting in Observer capacity. The SPV status remains relatively new and the Board are continuing to evolve their capacity and make performance more efficient. A Programme Investment committee is also in place to review and approve the costed work plans – this is a model common across all FSDs. Both the Board and PIC meets on quarterly basis. The Swedish International Development Agency (SIDA) is also co-funding FSDZ. Their support is for a discrete component to improve financial capabilities for Women, youths and children.

Quality and timeliness of narrative reporting and audited financial statements
FSDZ prepares monthly quarterly progress and finance reports. The Quarterly Reports are shared with DFID and the Board for approval. The quarterly finance report provides an analysis of   FSDZ’s performance during the quarter as compared to the cash flow forecast and budgets. It includes variances but FSDZ does not give advance warning for the expected variances. In addition, the report provides an overall summary figure for SIDA’s contribution with no detailed expenditures.

FSDZ is audited on an annual basis by a firm appointed by the Audit Committee. In July 2018, KPMG issued an unqualified opinion on the FSDZ annual financial statements for the year ending 31st March 2018. This is the second Annual Audit conducted by KPMG and they are reappointed to conduct the external audit for the third year as well. The audit reports are unqualified and present a true picture of funds disbursed by DFID during the period covered under the audit.

Quality of financial management
FSDZ has a Finance policy and procedure manual that was approved by the Board and DFID. FSDZ maintains an Approved Delegated Authority Matrix also approved by the Board and DFID. The Delegated Authority Matrix includes limits which are used to determine who is authorised to approve the various financial transactions at FSDZ. A review of internal controls was undertaken by Deloitte. The scope of assignment covered the effectiveness of compliance and controls in procurement, fixed assets and property management, cash and bank management and Human Resource and Payroll. Some small issues were noticed on the financial management e.g. periodic bank reconciliations were missing, discrepancy in petty cash balances. Action has been taken on these areas.

FSDZ prepares cash flow forecasts monthly and quarterly. Quarterly forecasts are reviewed by the Chief Operating Officer and Executive Director after which they are approved by the Board and DFID. The forecast highlights the proposed spend for every pillar for the subsequent quarter. DFID disburses funds based on the bases on quarterly forecast.

There was a large underspend during the review period. The original forecast agreed at the start of the year was £ 4.1million. However, FSDZ continued to underperform on financial management throughout the year and managed to meet only 82% of their initial forecast – underspending by £739,228. In some quarters was in excess of 20%. This demonstrates a need to improve planning and financial forecasting, but also reflects slow and unpredictable implementation by downstream partners, many of whom have relatively complex decision-making governance, are unused to operating with partners such as FSDZ and may require many months to make key decisions – more awareness and engagement can improve this.

2017-18 Budget	Actual	Underspend	% Variance
£4,113,607	£3,374,379	£739,228	18%

Procurement
FSDZ has a Procurement Manual which promotes openness, transparency and value for money in the procurement process. For instance, it includes guidance on: thresholds for procurement; competitive bidding; delegation; evaluation methodologies; contracting; prequalification; complaints handling; disposal; record keeping; roles and responsibilities; and payment procedures.  The Deloitte review noted that in some cases the procurement system was not updated e.g. information about the purchase orders was missing.

Monitoring of assets
FSDZ maintains a register of all its fixed assets, periodically updated (normally on a monthly basis) to reflect any additions. All the company’s assets are tagged. Computers and other   valuable items are allocated to specific staffs that are personally responsible for these assets. The Programme team recently conducted an Assets spot check and found assets management in full compliance with DFID’s relevant guidance.

Recommendations:
- The Board should take ownership of the Value for Money framework and should question/ challenge the management based around key KPIs such as administrative costs.
- Following best practice, the external auditor should be changed after every two or maximum three years.
- The PIC should review the progress against the workplan during the previous quarter. In addition, they should also question the variance (where applicable).
- The logframe should include an indicator which measure FSDZ performance in meeting its financial forecasts.
- FSDZ should provide a detailed explanation on any variances against the actual vs forecast.

Date of last narrative financial report(s)	2nd October 2018
Date of last audited annual statement (s)	24 June 2017

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
FSDZ has developed and implemented a monitoring system. This however needs to be further strengthened to ensure that all activities are adequately captured in the logframe targets. Some independent quality assurance of FSDZ’s results and M&E approach would also be valuable, particularly in light of the approach to including recent weather insurance results.
The Board of FSDZ provides the overall strategic direction and oversight to the organization. The management is responsible for the day to day activities. The monitoring and results measurement team have a framework in place to measure progress. The Programme Investment Committee (a subcommittee of the Board, which DFID chairs) reviews the quarterly results and progress reports.

A detailed methodology note covering all indicators and milestones in the logframe was shared with the review team. DFID receives detailed quarterly progress report, have frequent meetings with FSDZ staff and conducts field visits to verify the progress and discuss challenges/issues.

DFID’s Annual Review was led by a Private Sector Development Adviser from Pakistan office with support of the in-country Lead Advisor and programme team. The process was undertaken in October/November 2018 through: a desk review of documents; a field visit to Chibombo, including meeting with range of implementing partners including Mayfair Insurance, Saving Groups, Zazu, Alliance Ginneries, and others.

Evidence (1/2 page)
One of the objectives of FSDZ is to establish itself as information/knowledge touch point for the industry and to generate, promote and disseminate evidence. FSDZ has planned a number of activities to promote the international best practices, data collection and analysis and conduct and disseminate research work. In the year under review, FSDZ published several research pieces including an analysis of Microinsurance landscape in Zambia which provides insights on the evolution and status of Zambia’s Microinsurance market, gaps and opportunities available. This supported the technical advisory group to draft the ten Microinsurance principles. As mentioned earlier, the evidence created by FSDZ pilots have helped both the government and private sector to develop products and improve service delivery. Inclusion of weather index insurance in Government led programming is a strong example, FSDZ also published the annual report on the state of financial inclusion in Zambia using the MAP diagnostic[27]. The report comprises a comprehensive country context, demand-side, supply-side and regulatory analysis.
[27] http://www.fsdzambia.org/wp-content/uploads/2018/02/MAP-Zambia-Summary-report-final.pdf

Learning (1/2 page)
The programme is employing a range of learning processes. For example, in the area of research, learning was to bridge the gap between research and practice on ground especially when they are led by external actors. FSDZ worked closely with research teams from Financial Sector Deepening Africa (FSDA) and Innovations for Poverty Action (IPA), among others, to provide practical input into the studies that they are planning to carry out. FSDZ has also explored better use of existing data and monitoring efforts, resulting in market presentations and uptake of learning about savings groups and gender and age aspects of financial inclusion. At the same time, to avoid duplication, FSDZ is working closely with other partners and establishing coordination mechanisms to share knowledge and experiences.

Progress on recommendations from previous reviews (1/2 page)
Progress on last year’s Annual Review recommendations is set out in the table below. Recommendations that are outstanding need to be prioritised. Progress on meeting these recommendations are discussed with FSDZ at monthly and quarterly meetings with DFID.

Section	Recommendation	Progress Update
Output 1	FSDZ should consider revising the targets upwards for the final year.	No progress. Logframe targets not revised. Wider logframe review with FSDZ and DFID in December 2018.
	FSDZ to start assessing the quality of research outputs for future assessments.	Some progress. FSDZ has facilitated quality research by analysing Finscope data and a 'Age, gender and financial inclusion in Zambia' technical report. Independent QA for research products a work in progress.
	FSDZ to start assessing the quality of financial education outputs for future assessments (by Q3 of 2017).	Some progress. An FSDZ funded study on Zambia and other countries found that financial education must be part of other interventions on financial inclusion. RCT embedded in the Luapula project to measure financial education impacts.
Output 2	FSDZ should apply the toolkits to measure advocacy capacity and policy/ regulatory capacity in all organisations supported by FSDZ (ongoing; by end 2017).	Some progress. TORs for the policy and advocacy outcome capacity assessment drafted; to be implemented in quarter 4 (start of 2019).
Output 3	Review the progress of the Zambia Institute of Banking and Financial Services (ZIBFS) in delivering the SME Executive Diploma course (ongoing; by end of 2017).	Some progress. MRM has developed TORs for the assessment and a consultant has been selected.
	Carry out a detailed assessment of the course’s impacts and value for money, including whether it leads to changes in banks’ lending practices (ongoing; by end of 2017).	Complete. An assessment study conducted.
Output 4	The large amount of cash held, particularly towards the end of the savings period, increases the risk and impact of theft. FSDZ should continue to work with FSPs to assess whether solutions can be developed to address this risk (by end 2017).	Some progress. FSDZ supported Mfinance to pilot a digital financial platform for savings groups. Informal-formal links with banks being explored in Copperbelt province. These are on-going; results will be shared.
	Banks’ reputation of being unfriendly and untrustworthy will need to be overcome – the Catholic Diocese of Ndola (CDN) in Copperbelt are looking at linking a commercial bank with savings groups to improve understanding (ongoing; by March 2018).	Some progress. In partnership with FSD Uganda, FSDZ undertook a longitudinal study to understand the relationships of saving groups with banks. Findings are being integrated into savings group projects in the Copperbelt as well as the new Luapula project.
	The knowledge of financial product availability is low - FSDZ should do an assessment of the various low cost savings accounts and disseminate this, both to share the information and stimulate competition (by March 2018).	Some progress. Assessment of savings accounts not yet carried out - planned for 2019. However, FSDZ is providing technical support to Mfinance on designing low-cost savings products (findings will inform the market assessment). Additionally, Financial Literacy Week and World Savings Day provide information on some savings products on the market.
	Consider trialling the mobile phone app for savings group record keeping in Zambia, depending on experience in Kenya. DFID Zambia should also establish a link with digital team in London on this (by end 2017).	Some progress. FSD Kenya ended this study - initial results have not yet been shared. FSDZ is supporting Mfinance to design a mobile savings platform that could be used for savings groups.
	FSDZ to look at the implications for members who have more than one savings group, as this seems to be fairly common (Q3 2017).	No progress. Savings Groups Mapping and Replication Qualitative study planned for 2019.
	Most members the review met are involved in trading and small scale agriculture, with low returns. How these returns stack up against the high interest rates should be assessed in due course (by end 2017).	No progress. Savings Groups Mapping and Replication Qualitative study planned for 2019.
Output 5	Assess if the appropriate level of seniority is attending Executive Diploma in SME Relationship Management, and ensure a successful handover for ZIBFS to take over the running of the course (by Q3 2017).	Complete. An assessment was conducted. Details of attendance and appreciation were included, as well as assessment of ZIBFS readiness.
Output 6 (relates to setup of SPV)	The Board and DFID should discuss and agree on how to improve the current governance model. This would ideally be done through a working agreement, or a review of terms of reference. (to be discussed at August 2017 Board and Investment Committee meetings).	Complete. Articles of Association extensively revised and approved by the Board, PIC and AGM (members). Charter was finalised in November 2018.
	FSDZ and DFID should consider adjusting or removing the Output 6 indicators to take into account the stage of development of the SPV, including a focus on seeking out new funders (by Q3 2017).	Complete. Indicators removed.
	The members of the company (DFID and SIDA) should strengthen their roles to ensure they provide timely input into key decisions regarding governance, finances and changes in strategy (ongoing; from Q3 2017).	Complete. Changes in the new grant from DFID and more regular engagement. Sida semi-annual meetings.
	FSDZ’s CEO and finance team should ensure that outstanding operating manuals are finalised, and take steps to improve their quarterly forecasting and reporting, with urgency (from Q3 2017).	Complete. All operational manuals completed and approved by the Board. Financial reporting revised and agreed with DFID.