## Logframe
PROJECT NAME | United Nations Relief and Works Agency (UNRWA): funding basic services and protection for Palestine refugees 2011-15
IMPACT | Impact Indicator 1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015 | NOTES:
Long, healthy and dignified lives for Palestine refugees | Infant mortality rate | Planned | 22.0 2010 | Data available every 5 yrs | Data available every 5 yrs | 22 | Education data is one year behind other data, due to the school year.
Achieved
|  | Source |  |  |  |  | All results except for impact indicator 2 are total UNRWA results, not the DFID attribution. DFID's attribution rate is approximately 9% based on our contribution to the General Fund, though year on year figures can vary.
5 yearly UNRWA Survey, next due in 2015
| Impact Indicator 2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of registered refugees who receive social assistance from UNRWA (note: this number is influenced by UNRWA's level of funding) | Planned | Gaza 8.5% Jordan 2.6% Lebanon 11.6% Syria 7.2% West Bank 4.3% 2008 | Gaza 8.5% Jordan 2.6% Lebanon 11.6% Syria 7.2% West Bank 4.3% | Gaza 8.5% Jordan 2.6% Lebanon 11.6% Syria 7.2% West Bank 4.3% | Gaza 8.5% Jordan 2.6% Lebanon 11.6% Syria 7.2% West Bank 4.3%
|  | Achieved |  | Gaza 9% Jordan 1.9% Lebanon 3% Syria N/A West Bank 5.3% | Gaza 9% Jordan 1.8% Lebanon 3.1% Syria N/A West Bank 4.3%
Source
UNRWA Relief and Refugee Information Systems, reported in annual harmonised donor reporting matrix
OUTCOME | Outcome Indicator 1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions
Basic services are sustainably provided and human rights are protected for Palestine refugees | Percentage of children under 3 years who are underweight (new cases). NOTE: Data for 2012 only represents clinics with e-health and in 2010 there was a change in the growth monitoring methodology and the definition of underweight. The scope is that now children are monitored up to five years instead of three years and underweight, stunting, waiting, obesity and head circumference is also monitored. | Planned | Male: 1.6%. Female 1.7% 2010 Male 1.1%. Female 1.3% 2011 | Male 1%. Female 1% | Male 1%. Female 1% 2013 | Male 1%. Female 1% | UNRWA refugees will need to continue to access UNRWA services. There will be an adequate supply of relevant jobs and/or university places for vocational training graduates to go on to.
|  | Achieved |  | 1.6% male, 1.7% female | 1.6% male, 1.7% female
Source
UNRWA HMIS, reported in annual harmonised donor reporting matrix
| Outcome Indicator 2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| REFORM: Mean score obtained by students in Monitoring Learning Achievement Scores in Arabic and Maths (sex-disaggregated) | Planned | Math 46.4 % (women) Arabic 40.5% (women) 2009 | Data collected biennially. | Math 49.8 % (women) Arabic 44.5% (women) | Data collected biennially
|  | Achieved |  | 2012 data delayed till May 2013 pilot done March 2013 | Provisional data: Maths 35%, Arabic 53%
Source
UNRWA EMIS, reported in donor reporting matrix testing done every two years; next tests 2012/13 then 2014/15
| Outcome Indicator 3 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of graduates employed or continuing their studies among active job seekers (female) | Planned | 87% m (75% f) | 75% (68%) | 75% (68%) | 75% (68%)
| NOTE: Indicator has changed to align with international standards it was "Percentage of graduates working in a job in relation to their training or studying in a relevant field on year later (FEMALE) | Achieved |  | 85% male (70% female) | 78% male (75% female)
Source
Database of graduates, all graduates followed up by phone (over 90% response) reported in donor reporting matrix
| Outcome Indicator 4 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| Survival rate to the end of basic education male (female) | Planned | 89% (94.1%) (school year 2010/2011) | 89% (94%) (school year 2011/12) | 89% (94%) (school year 2012/13) | 91.8% (95.5%) (school year 2013/14)
|  | Achieved |  | 89.8% boys 94.1% girls | 88.8% male (94.7% female)
Source
UNRWA EMIS, reported in annual harmonised donor reporting matrix
| Outcome Indicator 5 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| REFORM: Average daily medical consultations per doctor (across all services). | Planned | 101 2010 104 2011 | 90 | 88 2012 | 93
|  | Achieved |  | 105 | 99
| NOTE: without implementation of eHealth, this figure is not available on a sex-disaggregated basis. NOTE 2: see email from David de Bold 26 April 2013 15.54 for discussion of reasons for higher figure in 2013 | Source |  |  |  |  | RISK RATING
|  | UNRWA HMIS, reported in annual harmonised donor reporting matrix |  |  |  |  | At this level all the risks shown separately in the risk matrix will need to be mitigated against.
| DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumption
Provide high quality educational services | Number of children enrolled in UNRWA basic education schools (% girls) | Planned | 481,145 (2010-11) 49.8% girls | 484,309 (2011-12) 49.9% girls | 487,982 (2012-13) 50% girls | 491,641 (50% girls) | Security is such that children can continue to access schools. The education reforms will improve the quality of education and lead to better outcomes. The education reforms are funded. Funding and material are developed, distributed and available for Agency-wide implementation
| NOTE: Basic education refers to grades 1-9, except in Jordan (grades 1-10) and Lebanon (grades 1-12). | Achieved |  | 490,924 - 245,734 boys, 245,190 girls | 491,641 (50% girls) | 500,689 (50.2% girls)
Source
UNRWA EMIS, reported in annual harmonised donor reporting matrix
| Output Indicator 1.2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of all children identified as having disabilities (or Special Educational Needs) | Planned | 4.1% 2010/11 | 1% | 1.5% UNRWA 2.9% | 1.5% UNRWA 2.9%
|  | Achieved |  | 3.07% 2011/12 | 3.6% | 3.74%
| NOTE: UNRWA redefined indicator along internationally agreed lines | Source
UNRWA EMIS, reported in annual harmonised donor reporting matrix
| Output Indicator 1.3 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| Number of students completing vocational training courses (of which women) | Planned | 2010: 3247 total, 1317 females / 2011: 3724 total (1454 females) | Targets to be adjusted due to Syria | 3632 | 3,458 (1,419 female)
|  | Achieved |  | 3632 | 3,458 (1,419 female) | 5,119 (2,047 female)
Source
UNRWA EMIS, reported in annual harmonised donor reporting matrix
| Output Indicator 1.4 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| REFORM: Pupil teacher ratio/class sizes in basic education | Planned | Gaza 37.5 Jordan 36 Lebanon 30.3 Syria 38.7 West Bank 33.9 2010 | Gaza 37.5 Jordan 36 Lebanon 30.3 Syria 38.7 West Bank 33.9 | Gaza 37.5 Jordan 36 Lebanon 32 Syria 38.7 West Bank 34 | Gaza 38 Jordan 37 Lebanon 34 Syria 38.7 West Bank 35
|  | Achieved |  | Gaza 38.0 Jordan 34.7 Lebanon 30.4 Syria 38.6 West Bank 33.5 | Gaza 38 Jordan 35.1 Lebanon 30.4 Syria 39.3 West Bank 33.5 | Gaza 39 Jordan 37 Lebanon 33. Syria 34 WB 32
| Note: the pupil teacher ratio is being changed as part of the education reform process | Source
UNRWA EMIS, reported in annual harmonised donor reporting matrix
| Output Indicator 1.5 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| REFORM: Number of areas where all teachers have been trained through UNRWA school-based teacher development programme (out of 20 areas) | Planned | 0 | Training course developed | 9 | 14
|  | Achieved |  | Course developed & piloted | 7 | 15
Source
UNRWA EMIS, reported in annual harmonised donor reporting matrix
IMPACT WEIGHTING (%) | Output Indicator 1.6 |  | Baseline 2011 | 2012 | 2013 | Target 2015
50% | REFORM: Percentage of schools using the school-based agency-wide Education Management Information System (EMIS) to report and plan | Planned | 0 but EMIS designed | EMIS designed | Piloted in at least 2 Field Offices | 80%
|  | Achieved |  | EMIS designed and piloting started | Piloted in Gaza and Lebanon | 80%
|  | Source |  |  |  |  | RISK RATING
|  | UNRWA EMIS, reported in annual harmonised donor reporting matrix |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions
Provide high quality health services | Annual number of medical consultations | Planned | 11,125,357 2010 10,669,571 2011 ex Gaza 966,000 | 11917760 | 12334881 | 9371426 | As UNRWA moves to the Family Health Team approach, it is assumed that quality of services will be maintained and that refugees will continue to access these services.
|  | Achieved |  | 9700000 | 9371426 | 9191921
Source
UNRWA HMIS, reported in annual harmonised donor reporting matrix
| Output Indicator 2.2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| Diabetic control rate (of which women) | Planned | No baseline, but there were 114,911 cases | Conduct a baseline study | 30% | 32%
|  | Achieved |  | 32% (24% female) | 42% (sex-disaggregated data not available) | 25.1%
| NOTE: UNRWA did a baseline in 2012 | Source
UNRWA HMIS, reported in annual harmonised donor reporting matrix
| Output Indicator 2.3 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| Number and percentage of pregnant women attending at least 4 ante-natal care visits | Planned | 87% 2011 | 87% | 75,492 (90%) | 75,492 (90%)
|  | Achieved |  | 73,874 (86.5%) | 74,486 (88.8%) | 73,821(90.2)
| NOTE: Indicator was changed - instead of 1 visit, now measure 4 visits | Source
UNRWA HMIS, reported in annual harmonised donor reporting matrix
| Output Indicator 2.4 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of children under 18 months who have received all EPI (Expanded Programme on Immunization) vaccinations according to host country requirements) | Planned | 99% (99,966) | 99% | 99% | 99%
|  | Achieved |  | 99.5% | 99.3% | 99.5%
Source
| NOTE: Only measures as a % of those children UNRWA are in contact with | UNRWA HMIS, reported in annual harmonised donor reporting matrix
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
25% | REFORM: Number of clinics implementing the Family Health Team approach (out of a total of 137 clinics) | Planned | 0 | 20 | 50 | 100
|  | Achieved |  | 33 | 69 | 115
|  | Source |  |  |  |  | RISK RATING
|  | UNRWA HMIS, reported in annual harmonised donor reporting matrix |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions
Protect the vulnerable | Annual number of Palestinian refugees receiving social transfers (food or cash) from UNRWA | Planned | 293718 | 292581 | 291757 | 291757 | UNRWA will receive enough funding to provide social transfers to all families defined as "abject poor" using new Proxy Means Testing model.
|  | Achieved |  | 291,757 (Gaza 106,866; WB 36,129; Jordan: 58,899; Syria: 35,435; Lebanon: 54,428) | 291,757 (Gaza 106,866; WB 36,129; Jordan: 58,899; Syria: 35,435; Lebanon: 54,428) | 290967
Source
UNRWA Relief and Refugee Information Systems, reported in annual harmonised donor reporting matrix
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
15% | REFORM: Percentage of SSN individuals who are abject poor | Planned | 76.1% | 70% | 70% | 45.5%
|  | Achieved |  | 70.7% | 70.4% | 57.58
| NOTE: Indicator changed in 2015 report from "Percentage of refugees identified (or estimated) to be poor who receive a social transfer | Source |  |  |  |  | RISK RATING
|  | UNRWA Relief and Refugee Information Systems, reported in annual harmonised donor reporting matrix |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015 | Assumptions
Ensure protection of human rights | Percentage of new inscriptions meeting UNRWA standards | Planned | 89% 2010 95% 2011 | 97% | 98% (91% UNRWA) | 99% | Funds are available for training. Education staff are willing and capable of attending the training
|  | Achieved |  | 95% | 99% | 91.67%
| (as defined in Agency's Certified Eligibility and Registration Instructions) | Source
UNRWA Relief and registration Information System, reported in annual harmonised donor reporting matrix
| Output Indicator 4.2 |  | Baseline 2012 | Milestone 2013 | Milestone 2014 | Target 2015
| Percentage of education staff who successfully complete the Human Rights and Conflict Resolution training programme (of which women) | Planned | Draft HRCRT Policy adopted | Pilot HRCRT training in GFO & WBFO | 20% | 60%
|  | Achieved |  | Pilot HRCRT training in GFO & WBFO - v successful | 38% (sex disaggregated data not available) | 100%
| NOTE: indicator was changed from absolute no. as UNRWA redefined the indicator | Source
UNRWA EMIS system, reported in annual harmonised donor reporting matrix
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  |  |  | Milestone 2014 | Target 2015
10% | Number of gender-based violence (GBV) survivors detected | Planned |  |  |  | 2360 | RISK RATING
|  | Achieved |  |  | 2360 | 3411 | Low
Source
UNRWA EMIS system, reported in annual harmonised donor reporting matrix
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Results Chain
United Nations Relief and Works Agency (UNRWA): funding basic services and protection for Palestine refugees 2011-15
OUTPUTS |  |  | OUTCOME | IMPACT
1 | Provide high quality educational services | 50% | Basic services are sustainably provided and human rights are protected for Palestine refugees | Long, healthy and dignified lives for Palestine refugees
2 | Provide high quality health services | 25%
3 | Protect the vulnerable | 15%
4 | Ensure protection of human rights | 10%
5 | #REF! | #REF!

## Logframe Summary
United Nations Relief and Works Agency (UNRWA): funding basic services and protection for Palestine refugees 2011-15
Results Chain |  |  | Indicators | Baseline 2012 | Target 2015 | Source
IMPACT | Long, healthy and dignified lives for Palestine refugees |  | Infant mortality rate | 22.0 2010 | 22 | 5 yearly UNRWA Survey, next due in 2015
|  |  | Percentage of registered refugees who receive social assistance from UNRWA (note: this number is influenced by UNRWA's level of funding) | Gaza 8.5% Jordan 2.6% Lebanon 11.6% Syria 7.2% West Bank 4.3% 2008 | Gaza 8.5% Jordan 2.6% Lebanon 11.6% Syria 7.2% West Bank 4.3% | UNRWA Relief and Refugee Information Systems, reported in annual harmonised donor reporting matrix
OUTCOME | Basic services are sustainably provided and human rights are protected for Palestine refugees |  | #REF! | Male: 1.6%. Female 1.7% 2010 Male 1.1%. Female 1.3% 2011 | Male 1%. Female 1% | UNRWA HMIS, reported in annual harmonised donor reporting matrix
|  |  | REFORM: Mean score obtained by students in Monitoring Learning Achievement Scores in Arabic and Maths (sex-disaggregated) | Math 46.4 % (women) Arabic 40.5% (women) 2009 | Data collected biennially | UNRWA EMIS, reported in donor reporting matrix testing done every two years; next tests 2012/13 then 2014/15
|  |  | Percentage of graduates employed or continuing their studies among active job seekers (female) | 87% m (75% f) | 75% (68%) | Database of graduates, all graduates followed up by phone (over 90% response) reported in donor reporting matrix
|  |  | Survival rate to the end of basic education male (female) | 89% (94.1%) (school year 2010/2011) | 91.8% (95.5%) (school year 2013/14) | UNRWA EMIS, reported in annual harmonised donor reporting matrix
|  |  | REFORM: Average daily medical consultations per doctor (across all services). | 101 2010 104 2011 | 93 | UNRWA HMIS, reported in annual harmonised donor reporting matrix
OUTPUTS | Provide high quality educational services | 50% | Number of children enrolled in UNRWA basic education schools (% girls) | 481,145 (2010-11) 49.8% girls | 491,641 (50% girls) | UNRWA EMIS, reported in annual harmonised donor reporting matrix
|  |  | Percentage of all children identified as having disabilities (or Special Educational Needs) | 4.1% 2010/11 | 1.5% UNRWA 2.9% | UNRWA EMIS, reported in annual harmonised donor reporting matrix
|  |  | Number of students completing vocational training courses (of which women) | 2010: 3247 total, 1317 females / 2011: 3724 total (1454 females) | 3,458 (1,419 female) | UNRWA EMIS, reported in annual harmonised donor reporting matrix
|  |  | REFORM: Pupil teacher ratio/class sizes in basic education | Gaza 37.5 Jordan 36 Lebanon 30.3 Syria 38.7 West Bank 33.9 2010 | Gaza 38 Jordan 37 Lebanon 34 Syria 38.7 West Bank 35 | UNRWA EMIS, reported in annual harmonised donor reporting matrix
|  |  | REFORM: Number of areas where all teachers have been trained through UNRWA school-based teacher development programme (out of 20 areas) | 0 | 14 | UNRWA EMIS, reported in annual harmonised donor reporting matrix
|  |  | REFORM: Percentage of schools using the school-based agency-wide Education Management Information System (EMIS) to report and plan | 0 but EMIS designed | 0.8 | UNRWA EMIS, reported in annual harmonised donor reporting matrix
| Provide high quality health services | 25% | Annual number of medical consultations | 11,125,357 2010 10,669,571 2011 ex Gaza 966,000 | 9371426 | UNRWA HMIS, reported in annual harmonised donor reporting matrix
|  |  | Diabetic control rate (of which women) | No baseline, but there were 114,911 cases | 0.32 | UNRWA HMIS, reported in annual harmonised donor reporting matrix
|  |  | Number and percentage of pregnant women attending at least 4 ante-natal care visits | 87% 2011 | 75,492 (90%) | UNRWA HMIS, reported in annual harmonised donor reporting matrix
|  |  | Percentage of children under 18 months who have received all EPI (Expanded Programme on Immunization) vaccinations according to host country requirements) | 99% (99,966) | 0.99 | UNRWA HMIS, reported in annual harmonised donor reporting matrix
| Protect the vulnerable | 15% | Annual number of Palestinian refugees receiving social transfers (food or cash) from UNRWA | 293718 | 291757 | UNRWA Relief and Refugee Information Systems, reported in annual harmonised donor reporting matrix
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | REFORM: Percentage of SSN individuals who are abject poor | 0.761 | 0.455 | UNRWA Relief and Refugee Information Systems, reported in annual harmonised donor reporting matrix
| Ensure protection of human rights | 10% | Percentage of new inscriptions meeting UNRWA standards | 89% 2010 95% 2011 | 0.99 | UNRWA Relief and registration Information System, reported in annual harmonised donor reporting matrix
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | Percentage of education staff who successfully complete the Human Rights and Conflict Resolution training programme (of which women) | Draft HRCRT Policy adopted | 0.6 | UNRWA EMIS system, reported in annual harmonised donor reporting matrix
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!