Type of Review: Annual Review
April 2013 – March 2014

Project Title:
INDONESIA CLIMATE CHANGE TRUST FUND (ICCTF) PROJECT

Date started: 23.03.2010	Date review undertaken: 10.02.2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Introduction and Context
What support is the UK providing?
As of December 2013, the UK has contributed £ 6,200,000 to the Indonesia Climate Change Trust Fund (ICCTF) project, the contribution was in place in 2010. This is in collaboration with Australian Aid (AusAID) who provided US$ 1,4 million, Swedish International Development Agency (SIDA) provided US$ 332,000 and United Nation Development Programme (UNDP) contributed US$ 80,000 at the start of the project.

What are the expected results?
The Indonesian Climate Change Trust Fund will manage funds from international donors and finance climate change mitigation and adaptation projects in Indonesia. In line with the presidential commitment to reduce Greenhouse Gasses (GHG) emissions ICCTF will support the Government of Indonesia (GoI) to provide more effective leadership and management of climate change programs and improve national climate change awareness. Launched by the National Development Planning Agency (Badan Perencanaan Pembangunan Nasional – BAPPENAS) in 2009, the ICCTF is under the interim management of UNDP and expected to become an independent national Trust Fund by the end of 2014. / In close co-operation with BAPPENAS and the line ministries it provides technical assistance to prioritize and select Climate Change projects for potential funding. The project focuses on the following thematic funding windows: / Land Based Mitigation / Energy / Adaptation and Resilience / The planned outputs of ICCTF based on UKCCU’s log frame are: / Priority climate change projects (land based, energy and resilience and adaptation) selected, supported, monitored and evaluated / Functioning policy dialogue and increased awareness of ICCTF nationally and internationally / Capacity of ICCTF governance and related stakeholders (Government of Indonesia and CSOs) developed

What is the context in which UK support is provided?
Indonesia is one of the world´s highest emitters of CO2. In 2005 Indonesia’s estimated GHG emissions of 2.05 gigatons (billion tons) accounted for 4.5 % of global emissions, projected to rise to almost 3.0 gigatons CO2 by 2020. Indonesia needs to accelerate its effort fighting climate change to curb its current high carbon trajectory. / During the G20 meeting in 2009, the President of Indonesia, Susilo Bambang Yudhoyono committed to reducing Indonesia’s CO2 emissions by 26% by 2020 through nationally supported activities and a further 15% (in total 41%) with international support. Consequently in September 2011, the President issued the Presidential Regulation (Peraturan Presiden – PERPRES) No. 61/2011 to enact the National Action Plan to reduce GHG, referred to as RAN-GRK. / Also in the context of ICCTF, the Presidential Decree No. 80/2011 was issued in 2011 to regulate the establishment and management of national trust funds. / A number of international donors have committed to fund Indonesia’s ambitious emission reduction targets. This includes Non-Governmental Organizations (NGOs) and government development agencies such as those from USA, Australia, Germany and others. Reducing Emissions from Deforestation and forest Degradation (REDD+) funded by Norway for example is an ongoing initiative focussing on improving forest and land-use governance proven to be sector which contributes to the majority of GHG emission in Indonesia. / To manage and optimize international assistance, the ICCTF project was initiated in an attempt to establish the first national trust fund for climate change.

Section A: Detailed Output Scoring

Output 1: Priority climate change projects (land based, energy and resilience and adaptation) selected, supported, monitored and evaluated
Score and performance description: / Score : A+ Outputs moderately exceeded expectation / In general the Output 1 has moderately exceeded its expectation against output 1 on selecting proposal, supporting, monitoring and evaluation of on-going projects; and preparing for new small grant projects. / The December 2013 Steering Committee approved a budget of $330,000 for small grant program (SGP). The SGP has been discussed since beginning 2013 but was only launched at end 2013. / Progress against expected Outputs: / Indicator 1.1: / Number of proposals received. Target: / Call for small grant proposals conducted; / At least six proposals received under Small Grant Program for 2014 Achievement 2013: / Call for SGP proposal issued; / 196 proposals received / In addition to this large project implementation, preparatory work for selection of SGP included preparation of guidelines, consultation with relevant stakeholders and drafting the call for proposal documentation which was completed in December 2013. The Call For Proposal was issued in January 2014 with a deadline of 20 February 2014. / Small grant projects are expected to start in March/April 2014 for 6-8 months. / 196 SGP proposals had been received showing the call has met the target by receiving more than six proposals. / All incoming SGP proposals will be presented at the Steering Committee meeting to be held March 2014 for funding approval. / Indicator 1.2: Number and type of activities conducted or supported by ICCTF secretariat for the project selection Target: Two workshops/meetings for project assessment/selection; / 3 trainings for proposal development conducted Achievement 2013: / 2 major workshops/meetings for project assessment/selection; / 4 focus group discussion for proposal development / . / Below is the list of major activities with number of participant between 40-60 people ranging from government officer, CSO, University and other stakeholders. / Table 1. / CAPACITY DEVELOPMENT ON THEMATIC ISSUES AND SELECTION PROCESS OF CLIMATE CHANGE FOR RELATED STAKEHOLDERS / No. Date Program Location Participants Objective / 1 19-21 June 2013 Project Proposal Development and selection Workshop for Adaptation Bandung Line Ministries, CSO and University Introducing Proposal Development Framework and selection for Adaptation / Logical Framework Analysis development / Trial for proposal development / 2 10 June 2013 Socialization of ICCTF project selection tools Bappenas Line ministries and CSO/NGO Introducing ICCTF instrument for assessing and selecting adaptation project / Gain input from Line Ministries / Increased capacity for users and beneficiaries / 3 25 July 2013 FGD on RTRWP optimal from Climate Change Mitigation Perspective to strengthen the proposal development Jakarta Ministry of Forest, ICCTF, GIZ, Bappenas, DNPI, DItjenbun, Greenpeace, APHI, Ministry of Public Work, APKI, Ministry of Agriculture, APKINDO, UNORCID, Tempo Gain information on Implication of RTRWP revision to reduction of GHG Emission / Formulation of RTRWP Optimal for National development and commitment on GHG emission reduction / 4 22 August 2013 FGD on Climate Insurance for Agriculture: Challenge and Opportunity to strengthen the proposal development Bappenas Ministry of Marine Affairs and Fisheries, Ministry of Agriculture, BMKG, JASINDO, Asuransi BUmiputera Muda, IPB, UI, HKTI, WFP, Minstry of Finance Gain information on roadmap of climate insurance for agriculture / Identify related stakeholder development of climate insurance for agriculture / Identify challenge and opportunity for development and improvement climate insurance for agriculture / Identify lesson learned from climate insurance for agriculture as reference for development of climate insurance for fisheries / 5 6 November 2013 FGD on Degraded Peat Land Sustainable Management to strengthen the proposal development Jakarta Ministry of Agriculture, Ministry of Forest, GAPKI, Bappenas, UKP4, GPPI, APHI. Socialization of Degraded Peat Land Map / Formulation of policy/strategy sustainable peat land management in Indonesia / 6 27 November 2013 FGD on Potential and Opportunity of Renewable Energy In the Face of Energy Crisis’ to strengthen the proposal development Jakarta Line Ministries, ICED-USAID, Ministry of finance, local government, university, association of energy and electricity company Socialization on Renewable Energy regulation / Sharing information for related stakeholders on National Energy / As an example, one of the ICCTF activities on proposal development was held in June 2013. The ICCTF secretariat conducted a workshop on adaptation project proposal development, which covered how to develop an adaptation proposal starting from concept note through to the logical framework analysis. / According to Dr Harris Syahbudin from Ministry of Agriculture, the workshop was good as it also provided training on adaptation for line ministries. / During 2013 at least 25 smaller coaching/training/meeting activities also took place for groups ranging from 15-20 participants from specific line ministries focussing on development of proposals and preparation of financial budgets. This involved current partners Ministry of Health, Ministry of Agriculture and Ministry of Forestry and potential partners (Ministry of Marine and Fisheries). / Indicator 1.3: / Number of Climate Change Project selected, monitored and evaluated Target: / 3 climate change project selected, monitored and evaluated; / Each project will have quarterly programmatic monitoring and financial spot check conducted, in total 12 times Achievement 2013: 3 climate change project selected, monitored and evaluated; / 4 programme monitoring and 4 finance spot check for 3 on-going climate change projects was conducted / Three new projects were approved for ICCTF funding support by the Steering Committee in 2012 and commenced implementation in 2013. These projects are working with the Ministry of Health, Ministry of Agriculture and Ministry of Forestry. The projects are expected to be completed in Q3 2014 . Quarterly monitoring and evaluation report were issued. / The ICCTF Secretariat has an improved capacity in project monitoring from operational, technical and financial perspectives by hiring an internal auditor. Field monitoring visits to the project sites in several provinces (Jambi, West Kalimantan, Riau, East Java, Bali and West Sumatra) were conducted quarterly. Spot checks and internal audits for financial assurance were conducted at the project implementers’ (ministries of Health, Agriculture and Forestry) headquarters and project sites in Papua and West Kalimantan. / Some delays in activity implementation were due to administrative and technical reasons, particularly at the Ministry of Health’s project. The ICCTF monitoring evaluation team put a stronger monitoring regime and addressed through adding the time and resources during the coaching/training session. / The ICCTF Secretariat, through its internal auditor (Rasin Ikhwan & Rekan of Alliot Group) has provided an internal audit function to the Project Management Units of each funded project. This has provided recommendations in the areas of 1) control environment; 2) risk assessment, 3) control activities on finance and accounting, procurement, fixed assets; and 4) financial reporting.
Recommendations to Outputs: / Future small grant projects may require a slightly modified M&E approach - different to those of government agencies. So far ICCTF secretariat only has experience working with line ministries. Some of these smaller organisations may also require more rigorous capacity development. . It is recommended that UNDP provide an additional support specific on SGP monitoring and evaluation. Adequate funds and a clear M&E plan should be allocated for these needs / The ICCTF secretariat need to ensure that the SGP implementation period is within the agree timeline - mostly between 6-8 months. It is noted that the SGP period will extend until November 2014, so that ICCTF can make sure December is the last month of payment to NGO/CSO. / Impact Weighting (35%): / Revised since last Annual Review? N / Risk: Medium / Logframe revised since last Annual Review? Y/N / Yes

Output 2: Functioning policy dialogue and increased awareness of ICCTF nationally and internationally
Output 2 score and performance description: / Score: A - Outputs met expectation / The programme met expectation for output 2 of establishing regular dialogues with relevant GOI programs and other stakeholders. ICCTF also met its expectation in communicating and marketing ICCTF in a national and international forum – see Figure 4. / The dialogues encompassed a broader spectrum of climate change and development issues. This included (a) Steering Committee meetings engaging various GOI agencies including those nominated for Majelis Wali Amanat (Board of Trustee) / MWA membership; (b) policy coordination forum (PCF) involving several GOI financing mechanisms (Millenium Corporate Account-Indonesia / MCAI, REDD+ Agency - Fund for Reducing Emissions from Deforestation and forest Degradation in Indonesia / FREDDI, Indonesia Investment Agency, ICCTF); and (c) other dialogues activities i.e Bappenas dialogue on national development planning (Musrenbang) , RANGRK dialogue/ workshop, RANAPI dialogue/ workshop. / One of the Policy Coordination Forum’s key outcomes was agreement between the different financing mechanisms to improve coordination and share of lessons learnt at both policy and technical levels. An immediate and major evidence of this agreement is that ICCTF has learnt from MCAI experience including the development of legal frameworks such as the Peraturan Menteri (Permen) / Ministrial regulation and Keputusan Menteri (Kepmen/ Ministrial Decree. Avenues of potential cooperation with upcoming FREDDI, once it is operational, have also been explored, including possible channelling of FREDDI funds through ICCTF. / Awareness of ICCTF at national and international levels has been increased through ICCTF’s active participation/attendance at major events i.e UNFCCC and 3rd Asia Pacific Climate Change Adaptation Forum . / Progress against expected output: / Indicator 2.1: / Number and type of policy dialogues conducted Target: / 10 national policy dialogues during this year Achievement 2013: 11 formal and informal dialogues conducted / Potential contributions to ICCTF from corporate social responsibility funds were explored during dialogue with private and business sectors however no commitment from these sectors has yet been agreed. / Dialogue with development partners has led to identification of potential contributions from new donors such as Danida and USAID, however no commitment has yet been agreed. A proactive approach of conducting discussion and sharing project successes may help to convince donors of the value of putting their funds into ICCTF. / Table 2. / POLICY DIALOGUE CONDUCTED BY ICCTF / No. Date Program Location Participant Objective / 1 25 April 2013 Steering Committee Meeting Jakarta SC members, TC members, ICCTF secretariat, Observer from GIZ ICCTF progress and Achievement / Allocation remaining Fund / Integration of RAN/RAD GRK / Decision was made for Transition plan and allocation of remaining fund for 2014 activities / 2 7 June 2014 Pre Policy Coordination Forum for Climate Change Meeting 1st Bappenas, Jakarta Bappenas, ICCTF secretariat, PIP MoF, MCAI, REDD+ Task Force Discussion on preparation for PCFCC “ identification and mapping of climate financing in Indonesia” / 3 21 June 2013 Pre Policy Coordination Forum for Climate Change Meeting 2nd Bappenas, Jakarta Bappenas, ICCTF Secretariat ICCTF, GIZ, MCAI, REDD+ Task Force Mapping of climate finance institution in Indonesia / Preparation of PCFCC meeting / 4 15 July 2013 Policy Coordination Forum Meeting Bappenas, Jakarta Lukita Dinarsyah Tuwo, Endah Murniningtyas, Wahyuningsih Darajati, ICCTF, MCAI, FREDDI, PIP, Line Ministries, DNPI, development partners (multilateral & bilateral) Mapping the financing institution for climate change in Indonesia / 5 26 August 2013 SC Meeting Bappenas, Jakarta SC members , Observer: German Embassy/GIZ Update progress ICCTF transition towards National Fund (Legal basis LWA, SOP, Organizational and Capacity Development) / Decision and recommendation was made for: / Legal Basis of MWA and LWA / Operational Basis / Organizational and capacity Development / Fund raising strategy / 6 24 Sept 2014 PCF Meeting follow up Bappenas, Jakarta Bappenas, ICCTF Secretariat, MCAI, REDD+ Task force Mapping on focus area of climate finance in Indonesia / Follow up PCF Meeting / 7 30 Okt 2013 Indonesian Chambers of Commerce (Kadin) Jakarta Rahmat Herutomo, Jakfar Hary Putra, Bjorn Fischer, Shinta Kamdani Socialization on ICCTF roles and track record, and potential collaboration with provate sector / Response from Kadin on the support of climate change-related activity / Confirming the name of the Kadin representative for ICCTF Board of Trustees (MWA-ICCTF) / 8 12 December 2013 SC Meeting Bappenas, Jakarta SC Members, Observers: nominees of MWA members, USAID, DANIDA, German Embassy/GIZ Updates on ICCTF transition / Updates on fund raising strategy / Decisions for legal basis, operational and fund raising / 9 10 January 2014 1st meeting with academicians Bappenas, Jakarta Indonesian Rector Forum (FRI), Rector of Bogor Agricultural Institute (IPB), Rector of University of Indonesia Introducing ICCTF (role, mandate, portfolio) to the academicians / Requesting the academicians to submit the proposed names of representatives for MWA-ICCTF / 10 17 January 2014 2nd meeting with academicians Bappenas, Jakarta Indonesian Rector Forum (FRI), Rector of Bogor Agricultural Institute (IPB), Rector of University of Indonesia Receiving the proposed names of representatives for MWA-ICCTF / Bappenas has conducted the selection process and the names has been announced by Deputy Minister Lukita Dinarsyah Tuwo on Feb. 10, 2014 / 11 17 January 2014 Meeting with Indonesia Business Council for Sustainable Development (IBCSD) Jakarta Tiur Rumondang, Bjorn Fischer, Budi Santosa Exploratory meeting for potential collaboration between ICCTF and IBCSD / Discussing about the participation of ICCTF in Learning by Sharing event on March 7, 2014 / Indicator 2.2: / Number and type of awareness raising activities conducted Target: / 3 major events of awareness raising including: / - Regular quarterly newsletters. / - Participation in COP 2013 and media campaign Achievement 2013: 6 major events of awareness concluded: / -4 newsletters issued / - Participation in COP 2013 in Warsaw. ICCTF present a slide on Indonesia climate finance updates / -3 events related to Climate media campaign and awareness been concluded. / While the ICCTF communication strategy is currently being revised, implementation of relevant activities continues. A number of materials were produced including newsletters on a quarterly basis, video profiles, fact sheets, posters. These were shared and distributed during dialogues and attendance/participation of major events including COP side events in Warsaw December 2013. / A media award was launched in close cooperation with a leading journalist association, about 60-80 journalist participated in the event. Articles on ICCTF and its projects were widely published at local media and TV station (print media, TV trans metro elshinta station) which has helped improve public awareness of ICCTF. The Bappenas Vice Minister gave an opening speech during the media award’s launching and awarding ceremony. / ICCTF also organised a donor and journalist visit to the ICCTF project site in Jabiren, Central Kalimantan in September 2013 / ICCTF Secretariat, Bappenas (Ibu Endah) and journalist from radio KBH68H joined the UNFCCC COP 19 at Warsaw, Poland . Bappenas delivers presentation during the COP 19’s side event titled “Delivering Low-Carbon Development Results through Innovative Financial Mechanisms” / Table 3. / Below is list of outreach and awareness activities conducted by ICCTF during 2013 / No. Date Program Location Participant Objective / 1 18 April 2013 Launching Journalistic Award ICCTF Jakarta Journalist, Bappenas, ICCTF to raise awareness of the Indonesian journalists on the climate change issues / to develop their capacity and skill in covering climate change issues in Indonesia / also to highlight ICCTF activities in light of climate change policies in the country, / 2 26-27 September 2013 Donor and Journalist Visit Jabiren, Central Kalimantan Donors, Journalist To highlight the project development and present lessons learned of the projects to the donors and journalists, / 3 8 November 2013 Awarding ICCTF Media Award Jakarta Journalist, UNDP, ICCTF, Bappenas, GIZ, Encouraging Indonesian journalists to cover climate change issues both from international context and particularly from the perspective of Indonesia’s national interest / to develop the capacity of the media in educating the general public on climate change issues. / ICCTF staff also participate in and presented on the ICCTF project in several climate change conference both national and international / Recommendations to Outputs: / Before an event is held , for example policy dialogue with MCA, REDD+ Agency, MoF-Indonesia Investment Agency on mapping the financing institution for CC in Indonesia, ICCTF needs to prepare a specific outputs that they would like to achieve and to ensure follow up of the actions from the dialogue. In the example of the policy dialogue with MCA, REDD+ Agency and PIP , UKCCU never received any formal updates from UNDP or Bappenas on to what actions been taken and how it impacted the ICCTF work. . / Improving dialogue with the private sector and CSO is important to the future of ICCTF Expanding dialogue and awareness raising activities to unconventional development partners should also be considered in order to explore potential and contributions. These may include countries from the Middle East, ASEAN and other regions. / The policy dialogues and increased awareness activities need to be more strategic and addressing top level policy with the right target of audience, which not only with media but also potential donors nationally and internationally
Impact Weighting (20%): / Revised since last Annual Review? No / Risk: / Medium / Logframe revised since last Annual Review? Y/N / Yes

Output 3: Capacity of ICCTF governance and related stakeholders (Government of Indonesia and CSOs) developed
Output 3 score and performance description: / Score: B - Outputs moderately did not meet expectation / Progress against Output 3 has improved significantly from 2012 however as of February 2014, the National Trust Fund (Lembaga Wali Amanat/LWA) has still not yet been fully established. / A transition plan showing the key milestones and an activity plan was developed and endorsed during the 1st Steering Committee (SC) meeting in April 2013. It was a helpful tools in managing and monitoring the development of ICCTF trust fund, though the plan was not fully completed. / Following intensive preparation, the Ministerial Regulation (Permen) on establishment of ICCTF as a trust fund institution (LWA) was issued on 28 June 2013. This gives the ICCTF a formal and legal status as a national trust fund. A draft Ministerial Decree (Kepmen) on the ICCTF Board of Trustee (MWA) was finalised and membership structure was agreed. Pending formal nomination of a member representing universities, it is aimed that the Minister of Bappenas issued this decree by end February 2014. The SC has begun a dialogue with unconventional partners such as business community (KADIN/Chamber of Commerce), universities and NGO/CSOs who have confirmed their agreement to get involved with the new form of ICCTF (MWA). / At the SC meeting in August 2013 GOI shared their proposition to contribute up to $50 million from 2015 state budget as a multi year’s budget allocation. However further work needs to be done to secure the state budget. / Dialogues with development partners have led to discussion of potential new contributions from USAID and DANIDA. However this funding is not yet confirmed and it is unclear whether there are any deadlines for funding. / Progress against expected output: / Indicator 3.1: / Number and type of capacity development programmes for related stakeholders (GOI and CSO) Target: / 10 capacity development programs conducted during this year Achievement 2013: 19 capacity development programs conducted during this year which are: / 4 thematic workshop for GoI and CSO / NGO were conducted / 6 discussions on TF legal establishment and fundraising development with Bappenas and development partners / 9 national and international conference/training participated by relevant Bappenas and ICCTF officer / As part of its capacity development for related stakeholder, starting July 2013, ICCTF Secretariat conducted monthly thematic discussion/workshop for GoI representative, CSO/NGOs. The first discussion provide discussion on the provincial spatial plan to identify area which are subject to mitigation activities, the second thematic discussion was took place in August 2013 at Bappenas office. The discussion focus on the climate insurance projects to recognize the opportunities and challenges in developing climate insurance for agriculture sector. It is noted from the participant from Ministry of Agriculture that climate insurance project is still new in Indonesia and in fact ICCTF is the first organization who introduce that to line ministries, during this workshop a representative from insurance company and financial institution BNI syariah were participated the workshop. ICCTF also held 6 discussions/workshops on code of conducts (by law) and fund raising development between relevant units of Bappenas and development partners. / As part of capacity development and positioning of ICCTF, Bappenas officers and ICCTF staff participated in several climate conference / training. By participating in these the events, the government officer is expected to expand their network on climate change, increase their knowledge and capability on specific climate change issues and share the ICCTF and Indonesia Climate change financing through a series of presentation. / Indicator 3.2: / Number and type of activities conducted to establish a fully staffed and functioning ICCTF Target: / National Fund Manager appointed; / an institutional set up required for a nationally managed trust fund established (Kepmen/Permen); / data base system (finance, HR, project management) established; / conversion of contract from UNDP to GOI ; - / Review of Fund Raising Strategy and Endorsement of Business Plan Achievement 2013: National Funds Manager appointed; / Permen issued but Kepmen still on process awaiting for final MWA member. Satker (working unit) not yet established as need to wait for Kepmen / Database system established / Conversion of contract from UNDP to GoI / Fundraising strategy still on very early / 1st draft stage which was mainly heavy on private sector engagement and not yet touch the full scheme of ICCTF strategy for fundraising. Business plan just about to start writing thus can not be endorse on 2013. / Following issuance of the LWA Permen (Ministrial regulation on Trust Fund) the MWA Kepmen (Ministerial decree on board of trust fund) has been drafted through a series of consultations with relevant stakeholders including its potential members. It is now pending formal appointment of a member representing universities. The transition/milestone plan anticipated finalisation and signing of the Kepmen in Q4/2013 however this was delayed due to delays in appointment of MWA members. As an effect, the Kepmen now aimed to sign off by end February 2014 or beginning March 2014. / The establishment of the ICCTF Satker (Working Unit) was planned to be in place by Q4/2013 following the signature of the Kepmen however since the Kepmen has been delayed, so is the Satker. In fact now the Satker might only in place by April or May 2014. Database systems for HR and program management have been developed. ERP (financial management system to replace UNDP system) was introduced and has been implemented from mid-2013. A national accounting and audit standard (PSAK 45) applicable for not for profit organisation has also been introduced. / Employment of all staff at Secretariat has been transferred from 1 January 2014 from UNDP to Bappenas. The contracts were signed on 31 December 2013 between staff and National Project Director (NPD) of PREP-ICCTF. A further transfer from NPD to MWA will be arranged after mobilisation of Executive Director (ED). / There is progress on the staff recruitment compare to 2012 however there are still some post which not yet fullfiled. Staff recruitment which aimed to be completed by end 2013 has now continued into 2014 including the Director of Finance (partly funded by GIZ) and Finance Manager. At end January 2014, TOR for Executive Director (ED) position were approved by Vice Minister of Bappenas/Chair of ICCTF SC . ED recruitment process via GOI procurement system commenced and the person is aimed to start by April 2014. Recruitment of other vacant positions will complete in March 2014. / The process to develop a fund raising strategy commenced in late 2013 marked by mobilisation of an adviser partly funded by Germany. Preliminary concepts were presented at the SC meeting held in December 2013. Expected completion is July 2014. / The ICCTF failed to commence the business plan and fundraising strategy, which in the agreed milestone plan should have been endorsed by Q3/2013. In fact, revision of the Business Plan commenced in late 2013 along with the development of fund raising strategy. Final draft will be presented at the 1st SC meeting 2014. / Recommendations: / Regular meetings between ICCTF secretariat and UNDP should be established with relevant units of Bappenas to ensure expeditious and timely achievement of key milestones, namely issuance of legal unit and recruitment and mobilisation of Executive Director (Procurement Unit). / Proactive approach by UNDP and Bappenas to speed up the appointment of MWA member / Dialogues with global funds such as adaptation funds and GCF should be improved. This may include regular liaison with countries/individuals (through their embassies in Jakarta) that are currently holding membership of the board. This is expected to improve opportunities for securing their funding. / The completion of the business plan and fundraising strategy is crucial and requires full support from UNDP and Bappenas. A dedicated UNDP member staff to manage deadline and support completion of business plan and fundraising strategy is needed / Full support from Bappenas senior management and chaired of Steering Committee are important in securing the proposal of 2015 state budget allocation / It appears that during 2013, the UNDP dedicated staff for ICCTF was still not delivered. A full time dedicated staff for ICCTF is urgent given the fact that we cannot postponed the Trust Fund development and the fact that by end 2014 the donor contribution will be finished.
Impact Weighting (45 %): / Revised since last Annual Review? Y/N / No / Risk: High / Logframe revised since last Annual Review? Y/N / Yes

Section B: Results and Value for Money.

1. Progress and results
1.1 Has the log frame been updated since last review? Yes / A new logframe is attached to this review (Annex 1) / 1.2 Overall Output Score and Description: / (A) Outputs met expectation / The current on-going projects were managed, monitored and evaluated properly; the new small grant program has been launched and in-coming proposal is under review. Several policy dialogues and workshops to increase awareness of ICCTF nationally and internationally have been conducted. Bappenas and ICCTF secretariat participated in the climate change national and international meeting/workshop and training as part of capacity building. / The main goal of establishing the ICCTF as an independent national Trust Fund still has not yet been achieved by February 2014. Significant progress has been made over the year however there remains work to be done from the legal and administrative side i.e sigining Kepmen and establishment of Satker (working unit). / Crucially the fund needs to focus on ensuring sustainability following the end of UK funding by developing a credible business plan and fundraising strategy. / 1.3 Direct feedback from beneficiaries / ICCTF beneficiaries are ranging from line ministries where project implemented and the cross cutting line ministries and institution who had a direct and indirect work relationship with ICCTF programme. The annual review managed to have a discussion with one of ICCTF beneficiary which is Ministry of Agriculture / Sustainable Management of Degraded Peatland to Mitigate Green House Gas Emission and Optimize Crop Productivity – Ministry of Agriculture. / An interview with Project Manager shows that the ICCTF programme has met its 2013 target set in the logframe of this project in terms of administration and financial management the project found that ICCTF procedure is quite rigid and sometimes more detailed than line ministry policy and procedures. / In regards to project achievement, it is noted that the project is confident that it will reach its target by August 2014. The goal of the project is to train five provinces in GHG measurement techniques, finalise mapping degraded peatland distribution, and complete sosio-economic surveying in 5 provinces. The project team found that advice and technical support from ICCTF secretariat was well run and enabled them to complete the on-going work on intercrop planting and land treatment and development for policy on sustainable management of degraded peat land.
1.4 Summary of overall progress / Progress in 2013 has improved from the previous year marked by the issuance of Ministrial regulation on the Trust Fund in June. This provides the legal basis for the ICCTF as a nationally managed trust fund. This has subsequently enabled the formulation of two other key documents, Kepmen’s on MWA and Satker which will be issued within the next couple of months. Once issued this documentation will complete the legal establishment process and enable the ICCTF to be legally operational and independent of the current arrangements with UNDP. / Despite that, the fact that there has been no firm indication of new fund contributions from any sources in the immediate future is a major challenge and risk for the future of ICCTF. / Implementation of current projects continues with improved M&E frameworks and mechanism by the ICCTF secretariat, supported by clearly targeted capacity building and development programs for project implementers, other stakeholders and the ICCTF’s staff and governance. / Coordination and liaison with other GOI existing and potential financial mechanisms commenced and will continue to be improved further in the years ahead. / The recommendation from the last Annual Review to increase the amount of senior UNDP staff time dedicated to the project has not materialised. Likewise the expectation that UNDP staff would work at the ICCTF offices twice a week has rarely happened. These recommendations are important to ensuring momentum increases over the last year of the project to complete important actions. The same recommendation is once again made by this Annual Review.
1.5 Key challenges / Coordination / Challenge 1: Coordination between ICCTF secretariat, Bappenas and UNDP in managing the implementation of transition plan and ensuring the establishment of the ICCTF Trust Fund. Given the important of having the Tust Fund before end of 2014 than a Pre-SC and SC meeting is not enough. A regular monthly meeting between ICCTF secretariat, Bappenas and UNDP needs to be set up to address issues and progress updates. / Challenge 2: Coordination amongst Climate Change related institution in Indonesia (REDD+ task force, DNPI, PIP-Min of Finance). Improved coordination is one of the challenging issues highlighted by Policy Coordination Forum supported by ICCTF. As a result ICCTF is working more closely with Millenium Corporate Account-Indonesia(MCA-I) and will be under an integrated Satker. The possibility of the ICCTF to channel funds from MCAI (on climate change related activities) and FREDDI (for land based related sector) has been continuously explored. This is based on ICCTF’s proven experience in managing those activities to date. / Challenge 3: Funding: Identification of international and national donors that are prepared to commit future funds to the ICCTF and confirmation of 2015 state budget funding. / Challenge 4: Determining and articulating the strategic direction (business plan) of ICCTF / 1.6. Annual Outcome Statement / SoP guidance for the Trust fund is in place however the selection of national trustee member (MWA) is still in process which effects the establishment of the Trust Fund. / The project selection mechanism is available and the project managed to implement the pilot project successfully / ICCTF business plan and funding strategy are still under drafted and need to be put into ICCTF priority of work since it actually due to be finished before end 2013.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / The project costs are still within the budget however spending over the lifetime of the project has been slow and there is a possibility of unspent funds in end 2014 with amount appx $ 600K Figure 5). / 2.2 Key cost drivers / According to UNDP an amount of US$1,932,487 will be allocated for 2014 work plan. There is an anticipated remaining balance of US$ 602,636 at end of 2014 which per Cost Sharing Agreement should be refunded to DfID. / Table 4. / Total 2010 2011 2012 2013 2014 Remaining / Project Expenditure Expenditure Expenditure Commitment Expenditure* Scenario** Balance / 11,405,747 2,352,427 3,209,062 840,285 18,996 2,449,854 1,932,487 602,636 / * This is still provisional financial status for 2013, based on CDR 2013 dated 28 Jan 2014. Final expenditure figure will be issued by HQ in April 2014. / ** The 2014 scenario is based on discussion and email from ICCTF Secretariat dated 3 Feb 2014. / 2.3 Is the project on-track against original timescale: N / The original time scale to implement the ICCTF has been extended 3 times (2011, 2012, end of 2012) and is now scheduled for completion by the end of 2014.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Climate Change remains an important subject on international and national levels. / Initiatives such REDD+ are evidence that the support for Climate Change initiatives for Indonesia is available and growing. / Based on the importance of Climate Change, Indonesia’s potential effect on Climate Change and the increasing international support, the original assessment remains that same – that if successfully set up the ICCTF could be an important vehicle to transfer donor funds including international climate finance in a coordinated way into Indonesia´s key Climate Change projects. / 3.2 Set out what plans are in place for an evaluation. / External evaluation was carried out in 2012 and an external review in 2013. No further plans are in place / 3.2 Where an evaluation is planned what progress has been made? / N/A

4. Risk
4.1 Output Risk Rating: / High / 4.2 Assessment of the risk level / Risk 1: Funding beyond December 2014 is not secured / Risk : High / There is a risk on funding availability after December 2014, given there is only 10 months left for ICCTF to secure new funding. The USAID and DANIDA funding discussion is still on-going and might take some time to be finalized and come into agreement. It is important to have the fundraising strategy in place and being implemented to identify and secure new funds. Bappenas has indicated its intention to provide $50m of state budget funding in 2015 but this is still to be confirmed. / Risk 2: Other Trust Funds working in the same area / Risk Level: Medium / The ICCTF Business Plan plan was due to be concluded in Q4/2013 but is still under drafting. This needs to set out clearly set out ICCTF’s position among existing and potential trust funds in Indonesia. ICCTF has initiated a reasonably good synergy with MCAI, which does not operate in the climate change sector but is hosted by Bappenas. Moreover it has learnt a lot from MCAI’s process of establishment. / It has also commenced closer liaison with REDD+ Agency/FREDDI which focuses on REDD+ only. Potential cooperation with upcoming FREDDI may include opportunity for ICCTF to channel funds for land based related sector that has been one of ICCTF’s windows. / Risk 3: Trust Fund not fully established by end of 2014 / Risk Level : Medium / The ICCTF needs to increase momentum in the establishment of the development of Trust Fund. During 2013 there were some activities been delayed and result to the postponed of Trust Fund. It is now essential to ensure that Trust Fund is started to operate within 2014.
Risk of funds not being used as intended / Low / Procurement continues to be managed and administered directly by UNDP, who ensure a good level of control over allocation and spending. / The result from the state auditors of UNDP’s account with unqualified opinion demonstrated good financial management of ICCTF / UNDP will remain responsible to DFID for the proper management of DFID’s grant for ICTTF during the transition to the independent trust fund status for ICCTF and when ICCTF is established as an independent trust fund. / 4.4 Climate and Environment Risk / Any project intervention under ICCTF continues to be based on thorough feasibility studies that include an in-depth assessment of social, environmental and climate risk. Any proposal that bears such risks is excluded from the project pipeline. The pilot projects and the policy dialogues supported by the ICCTF continue to have positive impact on tackling Climate Change.

5. Value for Money –
5.1 Performance on VfM measures / The major focus of the last year has been the transition to Trust Fund status. The value of which is expected later when new donors emerge. / The finalized pilot projects of ICCTF have been successful examples of Climate Change project funding with support by international donors (DFID, AusAID, SIDA, UNDP). / The PT. Pindad (one of ICCTF beneficiary) has committed to energy conservation program and after completion of project with ICCTF they built an energy management team to develop and manage efforts of energy conservation. Now they have been successful in reducing its energy consumption by 12-15%. / 5.2 Commercial Improvement and Value for Money / All sub-contracts were managed directly by UNDP and the ICCTF Secretariat in line with UNDP and Government of Indonesia rules. The allocated funds have been provided directly to the projects through UNDP. / 5.3 Role of project partners / The ICCTF is administered by UNDP as the interim trustee. There is still strong voices that UNDP need to dedicate greater staff time for ICCTF especially during the critical time for the establishment of MWA and Satker. The recommendation from last annual review is to appoint UNDP staff to work at 2/3 days at ICCTF office was not fully implemented. Recently consultant is appointed for ICCTF project management. The consultant needs to be given a full briefing and update on ICCTF from UNDP to ensure they can perform effectively / 5.4 Does the project still represent Value for Money : / Yes, as the target can still be achieved within the planned budget and extended timeline as long as the Transition Plan is kept by UNDP and ICCTF / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
Conclusions: / On-going project and small grant project call for proposal were managed properly by the secretariat ICCTF / The transition plan made progress but was not fully completed mostly due to delays on the legal side: the MWA appointment and development of SATKER. A proactive approach for the MWA appointment need to started in order to established the SATKER and revised the project document between UNDP and BAPPENAS / Business plan and fundraising strategy are important and need to be completed and endorsed by the latest Q2/2014 / Securing the state budget allocation for 2015 should be given top priority and UNDP should provide the best support to have this proposal approved. / UNDP senior engagement during 2013 still low therefore we look forward for a permanent and skilled UNDP staff appointed for ICCTF for 2014

8. Review Process
This review was undertaken by Suriany Ida, Deputy Programme Manager UKCCU during January-February 2014. The review process undertaken was as follows: / 1.Review of 2013 project documentation, logframe discussion and ICCTF report / 2.Interview with ICCTF secretariat / 3. Interview with ICCTF project implementor (Ministry of Agriculture) / 4.Review of UNDP Annual Review – self assessment 2013

ANNEX 1.
REVISE LOGFRAME (v.022014)

PROJECT NAME	SUPPORT FOR THE IMPLEMENTATION AND PREPARATORY ARRANGEMENTS OF THE ICCTF
GOAL	Indicator	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011	Target (Dec. 2013)			Target (Dec. 2014)
To ensure the GoI can provide more effective leadership and management of climate change programming to deliver emissions reduction and poverty reduction outcomes	Development of comprehensive transition plan from interim trustee into the ICCTF	Transition plan doesn't exist.	Implementation of transition plan (deferred to 2013)	Transition plan is fully implemented (deferred to 2013)	Transition plan is fully implemented (i.e SOP of ICCTF finalized and implemented, Ministrial regulation on LWA ICCTF issued, Fund Raising Strategy developed; Ministrial decree on MWA issued)			ICCTF Secretariat and LWA is fully operational
		Source

	Indicator	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011	Target (2013)			Target (2014)
	Existence of a fully functional ICCTF	ICCTF lacks of institutional, legal and organisational arrangements/capacities	N/A	ICCTF has governance, management and administrative capacity required to fully operationalised (deferred to 2013)	National Fund Manager is appointed; ICCTF has governance, management and administrative capacity required to be fully operationalised			National Fund Manager and Satker are fully operational to support ICCTF governance, management and administrative functions
		Source

PURPOSE	Indicator	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011	Target (2013)			Target (2014)		Assumptions
ICCTF efficiently and effectively serves as a National Trust Manager and is fully capacitated to do so	Establishment of ICCTF as Indonesia National Trustee through development of SOP and National Trustee selection Guidance	N/A	N/A (new purpose after AR in March 2011)	SOPs and National Trustee selection guidance available (deferred to 2013)	SOPs and National Trustee selection guidance available			The SOPs fully implemented by LWA as a National Trustee
		Source

	Indicator	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011	Target (2013)			Target (2014)
	ICCTF window investment guideline and project selection mechanism	N/A	N/A (new purpose after AR in March 2011)	ICCTF window investment guideline and project selection mechanism available (deferred to 2013)	ICCTF revised business plan, funding strategy; window investment guideline and project selection mechanism available			Investment & Fundraising Strategy fully facilitated and managed by ICCTF (MWA and its Sec.)
		Source

INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)			DFID SHARE (%)
	6,200,000
INPUTS (HR)	DFID (FTEs)

OUTPUT 1	Indicator 1.1	Baseline March 2010	Milestone Aug 2010	Milestone Jun 2011		Milestone Jan 2012	Target (2013)		Target (2014)	Assumption
Priority climate change projects (Land Based Mitigation, Energy and Resilience and Adaptation) selected, supported, monitored and evaluated	Number of proposals received.	Nil	2 proposals received for 2010	3 proposals received for 2011		3 proposals received for 2012	Call for small grant proposals conducted; 6 proposals received under Small Grant Program for 2014		Nil
		Source

	Indicator 1.2	Baseline March 2010	Milestone Aug 2010	Milestone Jun 2011		Milestone Jan 2012	Target (2013)		Target (2014)
	Number and type of activities conducted or supported by ICCTF secretariat for the project selection	Nil	Land Based Mitigation, Energy and Resilience and Adaptation projects targetted	2 workshops/meetings on project assessment/selection and 3 coachings/trainings for proposal development conducted		2 workshops/meetings for project assessment/selection and 3 workshops for proposal development conducted	2 workshops/meetings for project assessment/selection; 3 trainings for proposal development conducted		6 capacity building programs on project proposal strengthening conducted for line ministries and CSO's (eg pipeline projects)
		Source

IMPACT WEIGHTING	Indicator 1.3	Baseline March 2010	Milestone Aug 2010	Milestone Jun 2011		Milestone Jan 2012	Target (2013)		Target (2014)
35%	Number of Climate Change Project selected, monitored and evaluated	Nil	2 projects monitored and evaluated	3 projects monitoried and evaluated		programmatic monitoring and financial spot check conducted 4 times (quarterly)	3 climate change project monitored and evaluated; Each project will have quarterly programmatic monitoring and financial spot check conducted, in total 12 times		Impact Evaluation conducted at the end of projects (Health, Agriculture and Forestry) and shared with donors
		Source					RISK RATING
						Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)			DFID SHARE (%)
	5,800,000
INPUTS (HR)	DFID (FTEs)

OUTPUT 2	Indicator 2.1	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011		Milestone Jan 2012	Target (2013)		Target (2014)	Assumptions
Functioning policy dialogue and increased awareness of ICCTF nationally and internationally	Number and type of policy dialogue conducted	Nil	4 Quarterly Policy Dialogues	4 Quarterly Policy Dialogues		4 Quarterly Policy Dialogues	10 National Policy dialogues conducted		6 National policy dialogues conducted	Policy dialogue encompasses a broader spectrum of climate change and development issues, aimed to improve coordination and information sharing among ICCTF, GOI, development partners, CSO and private sector. It may include SC meetings; policy cordination forum; workshops/discussions.
		Source

	Indicator 2.2	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011		Milestone Jan 2012	Target (2013)		Target (2014)
	Number and type of awareness raising activities conducted	Nil	2 awareness activities for potential audience conducted	Public Relation and Communication for ICCTF		Public Relation and Communication for ICCTF	3 major events of awareness raising including: - Regular quarterly newsletters. - Participation in COP and media campaign		Implementation of awareness raising including: - Reguler quarterly newsletter - Participation in COP - Media/journalist award/fellowship

IMPACT WEIGHTING
20%
		Source:					RISK RATING
						Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)			DFID SHARE (%)
	100,000
INPUTS (HR)

OUTPUT 3	Indicator 3.1	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011		Milestone Jan 2012	Target (2013)		Target (2014)	Assumptions
Capacity of ICCTF governance, and related stakeholder (Government of Indonesia and CSO's ) developed	Number and type of capacity development programmes for ICCTF and related stakeholder (GoI and CSOs)	Nil	4	A rapid capacity assesment conducted		Capacity Building for ICCTF Governance and potential beneficiaries	10 capacity building activities on thematic climate change issues for related stakeholders for annual reporting on GHG emissions reduction and resilience increase		10 Capacity building activities conducted for ICCTF governance and related stakeholder (GoI and CSO's);	Certification (Indicator 3.2 Target 2014) is aimed at assessing and certifying robust ICCTF fiduciary management and finance sytem and performance in compliance with national and international standards and regulations
		Source

	Indicator 3.2	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011		Milestone Jan 2012	Target (2013)		Target (2014)
	Number and type of activities conducted to establish a fully staffed and functioning ICCTF national trust fund	Nil	4	Design capacity development programs for selected entities		Implement capacity development program for selected entities	National Fund Manager appointed; an institutional set up required for a nationally managed trust fund established (Kepmen/Permen); data base system (finance, HR, project management) established; conversion of contract from UNDP to GOI ; - Review of Fund Raising Strategy and Endorsement of Business Plan		- MWA ICCTF as Satker under BAPPENAS established and operational; - Executive Director mobilised; HR strategy revised; - ERP System operational; - 6 workshops and 3 conferences/seminars participated; - 3 training conducted; - Certification by an international audit firm conducted
		Source

IMPACT WEIGHTING
45%						High
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)			DFID SHARE (%)
	300,000
INPUTS (HR)		o