Type of Review: Annual Review
Project Title: BUILDING A RELIABLE INVESTMENT CLIMATE PROGRAMME IN KENYA (brick)
Date started: March 2013

Date review undertaken: March 2014
## Introduction and Context

What support is the UK providing?
The UK is providing £12.5 million to contribute to growth, sector competitiveness and poverty reduction by improving the environment for businesses and economic development in Kenya. This is done through three specific outputs: / (a) Output 1: Improved business regulatory environment through reduction in burdensome red tape at county and national levels that prevents Kenyan businesses from growing to their full potential and curtails effective competition among and between firms in the market. This includes legal and regulatory reform aimed at reducing the time and cost of businesses to engage with both county and national governments, opening up key markets to competition and easing clearance of goods at the port of Mombasa and border points with regional countries. Activities will include automation of government-to-business services where relevant/possible and increased transparency to improve governance. / (b) Output 2: Improved competitiveness and regulatory quality that leads to growth in private sector participation in the agribusiness and infrastructure (power) sectors. This includes opening up the seeds and pyrethrum sectors, establishing a warehousing receipting system in Kenya and facilitating private sector participation in the provision of renewable energy. / (c) Output 3: Building a more effective business environment for partnerships between the public and private sectors through identifying the binding constraints to the investment climate, innovation, improved export competitiveness and capacity building for public private partnerships (PPPs). This includes updating the 2007 national enterprise survey, work on specific value chains (food processing, textiles, leather, and furniture), special economic zones (SEZs), and PPP transaction support to the PPP Unit in Treasury and PPP nodes in Government of Kenya (GoK) agencies. / This annual review relates to the second phase of the Kenya Investment Climate Programme (KICP 2), implemented by the World Bank Group’s International Finance Corporation (IFC), the Bank’s Finance and Private Sector Development department as well as DFID’s funding for the Kenya Private Sector Alliance (KEPSA), all of which are components of BRICK. / Funding will run for four years, 2013/2014 to 2016/2017.

What are the expected results?
The programme will contribute to an expanded private sector that creates more jobs through improvements in the business environment. Specific results will include: / Private sector compliance cost savings to businesses of $100 million over the programme period. / Increased competition in 2-3 key markets critical to the economy. / Reduce the time to export and import by at least 25 and 26 percent respectively over project period. / 10,000 farmers reached through warehousing receipts, better quality seeds, and competition in the pyrethrum sector and $10 million investment in agribusiness. / $60 million of investment generated in renewable energy; 50,000 Mwh/year of renewable energy expected to be produced. / At least 5 PPP transactions ready for market entry. / At least 6 policy reforms linked to export competitiveness adopted by Government of Kenya.

What is the context in which UK support is provided?
Kenya’s business environment has been deteriorating over recent years and this has limited the private sector’s ability to grow, create jobs and contribute to economic development. In the 2014 World Bank Doing Business Report, Kenya ranks 129th of 189 countries, a 51 country drop from 2008. A recent African Development Bank report on the state of Kenya’s private sector observes that while the country is a promising place to do business, the private sector faces recurrent challenges that limit it reaching its full potential. / The lack of market competitiveness and uncompetitive practices cause specific disadvantages for the poor. The maize, seed and pyrethrum sectors have been severely constrained by distortionary government practices over the years and promoting choice and competitive practices could help increase farmer incomes to producers and reduce costly burdens on poor consumers. / The supply and quality of infrastructure for business is less than optimal. If current levels of infrastructure in the energy and transport sectors persist, GoK’s objectives to reach middle income status by 2030 will not be achieved. Kenya needs a stable and transparent environment that would encourage the private sector to participate in these spaces and contribute to growth. / UK support is important given Kenya’s limited capacity to design and implement the reforms necessary to turn around the above situation. Investment climate reform is essential for the country’s growth and employment objectives.

## Section A: Detailed Output Scoring

Output 1: Reformed regulatory environment
Output 1 score and performance description: A (Output met expectation) / Objectively Verifiable Indicators ( ) = unit of measurement Baseline 2013 Milestone 2014 Achieved Status Sources of Verification Comments / 1.1 Number of procedures, policies or practices, adopted nationally, stemming from Regulatory Impact Assessments (RIAs) or environmental regulations Blank Blank N/A N/A National and subnational authorities There is no milestone or target in the logframe so the indicator cannot be assessed. The milestone and targets should be added. / The intervention planned to partner with a central regulatory authority. However, the devolution process has posed a challenge to engage with an appropriate authority as the mandate of agencies is not yet clear. The original programme proposal included technical assistance to the GoK to support the completion of three RIAs. This has been held up on the same basis as above. / 1.2 Number of procedural requirements to register a SME (Nairobi, Mombasa and Kisumu) 10 10 10 On track Subnational authorities, businesses and business organizations/ Sub-nation DB 2012 On track, as for the first year there was no targeted reduction (the 2015 Milestone being 9, and downwards from there). Whilst on track, it has been affected by the hold up in moving forward promptly in 1.1. / Initial analytical work conducted and recommendations developed to streamline business registration in the pilot counties (Nairobi, Mombasa and Kisumu). / The reports on the single business permit (as a key input in business registration) have been validated with Kisumu and Mombasa. / 1.3 Web-based business regulatory portal developed and fully transactional under design developed and tested Several portals have been designed, developed and rolled out/being piloted. On track and exceeding target, but indicator to be revised as it only refers to one portal. Subnational/ county authorities Energy Regulatory Commission (ERC) portal up and running. / The electronic single window (eSW) was rolled out on a pilot basis in October, 2013 and is now operational. It will be officially launched over the coming 2 months. / Scoping work conducted and dialogue in process with county officials to work further on ICT requirements. / Land use portal (as an extension of existing Nairobi construction permits portal) is under development / ICT roadmap for Nairobi ready but yet to be disseminated / BRICK is in its first year of implementation. Over the period, special emphasis has been placed on engaging programme counterparts, identifying a GoK reform champion to lead the work, developing baselines and conducting initial diagnostics and analytical work. Given the new government, emphasis has also been placed on evaluating new information and government priorities with a direct bearing on planned programme activities. / Indicator 1.1 Milestones and targets have not been defined, making it difficult to assess progress. However, based on planned activities, it is clear that progress has been held up because no central regulatory authority could be identified. GoK has been in transition over the reporting period and the mandates for relevant institutions are yet to be made clear. The original programme proposal included technical assistance to the GoK to support the completion of three RIAs, but these have also not been possible based on similar devolution-related delays. Milestone targets should be agreed so that future reporting is robust and more easily measurable (see recommendations). These targets will factor in the timing and progress issues caused by the devolution process and associated delays. / Indicator 1.2 is on track. Related to the above, devolution has commenced with significant challenges and counties continue to face severe funding mobilisation and capacity constraints. BRICK has conducted initial analytical work and developed recommendations to streamline business registration in the pilot counties (Nairobi, Mombasa and Kisumu). The reports on the single business permit (as a key input in business registration) have been validated with Kisumu and Mombasa. Proposed recommendations have been accepted in principle by counties. / Indicator 1.3 is exceeding expectation. However, the indicator needs to be amended to ensure it covers all web portal activities, as currently it refers to just one portal. The ERC portal is fully developed and deployed while the eSW is developed and being piloted. Further portals are under design for the subnational work. The indicator currently focuses on a business regulatory portal but broader ICT and e-governance work relevant to reforming the regulatory environment has been used to assess progress. / Following the success of Phase I of the Program, the project is improving the functionality of the Construction Permits (CP) automated system with the City County of Nairobi, following the recommendations of the County Government. This includes the development of a land use portal as an extension of the CP automated system. / Scoping work related to ICT-needs has been conducted and an ICT roadmap for Nairobi is ready but is yet to be disseminated. A cooperation agreement has recently been signed with the County Government of Kisumu and implementation work should begin soon. / In the Renewable Energy (RE) sector, an RE e-portal has been developed for use in tandem with the Energy Regulatory Commission, considerably reducing information gathering time for private investors and is online and functional: www.renewableenergy.go.ke. / Trade logistics: / The launch of the Kenya National Electronic Single Window System (eSW) through the Trade Project’s support for KENTRADE and stakeholder agencies is set to be a transformative endeavour in the country, reducing the time and cost to import and export. The eSW was rolled out on a pilot basis in October, 2013 and is now operational. It will be officially launched over the coming two months. / The eSW will enable exporters/importers and clearing agents to conduct international trade transactions electronically from their offices and reduce human interaction. This is also expected to reduce the time and cost for international trade which is critical for Kenya’s competitiveness. To date, there are 7 GoK agencies using the eSW for applications and approvals of licenses for import and export processes. / An e-payment system was introduced, allowing traders/clearing agents to receive invoices and retrieve the same via the single window and make payments at any of the 20 participating banks, reducing physical interaction and travelling time. Services level standards were adopted by Kenya Maritime authority and the port community at Mombasa for use by services providers and this is expected to lead to improved service delivery.
Recommendations: / Counties have had a slow start engaging with the national government, faced with revenue mobilisation challenges and with capacity shortages. At the national level, institutional mandates have been defined, performance contracts concluded and signed off and implementation has commenced in earnest. The programme team senses potential coordination challenges emerging. / Due to the challenges at county level and the ‘wish list’ presented to BRICK by each county, the programme should review planned activities to better respond to individual county needs. The team should also aim to resolve identified constraints, including a re-look at pilot counties in which to intervene, within two months of this review. / To be more transformative, BRICK is considering automation of business registration processes and discussions are ongoing with the GoK. This is particularly important since the project team does not foresee this service being devolved to the 47 counties as required by the Constitution. In the absence of this, business people will continue travelling to Nairobi to incorporate companies’ severely constraining SME creation and stifling entrepreneurship. BRICK’s programme management team to conclude on this with the Registrar General’s Office within two months of this review. / BRICK should include a capacity building component across the programme in order to address the shortage and limited capacity of staff, and hand hold new technical staff that are being recruited from the outset. A request for funding for this activity has been submitted to DFID. DFID is considering the request. / Support to GoK is needed to address coordination gaps to ensure success of programme implementation. Programme management to address over the coming three months. / In light of Nairobi County’s plans to establish a full enterprise resource plan (ERP), BRICK will have to re-evaluate continued planned activities and engagement with Nairobi on subnational regulatory reform. The focus is likely to turn to enhancing the construction permit system and incorporating a development planning module. Programme management to resolve this with Nairobi County and conclude a cooperation agreement two months after this review. / Output title should be revised, along with indicators and milestone to ensure that all activities within the programme are encapsulated and milestone targets are realistic and measurable. In particular, indicator 1.1 should be revised as the mandates of national/county level authorities are made clear, allowing RIAs to take place. Indicator 1.3 to be revised as it only refers to one portal, and should include other ICT/web portal work related to the output. / Impact Weighting (%): 60% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Effective competition
Output 2 score and performance description: B (Output moderately did not meet expectation) / Objectively Verifiable Indicators ( ) = unit of measurement Baseline 2013 Milestone 2014 Achieved Status Sources of Verification Comments / 2.1 Number of sector investigations completed by the Competition Authority of Kenya, and effective competition procedures finalized* 1 1 1 On track Competition Authority of Kenya (CAK) *Indicator includes investigation of anti-competitive practices and merger review, in addition to sector studies. / One merger case in agro processing completed (dairy industry) with the CAK. CAK exempts only small firms below 1 billion KES from merger review. Given the size of the firms involved the transaction was not exempted, but instead the merger was assessed and permitted by the CAK. / 2.2 Number of businesses (in dairy, cereals, coffee, seeds, and fertilizer sectors) using the warehouse receipts system (WHS) WHS system developed 100 0 Not on track, indicator to be revised East African Grain Council, Warehouse Receipts Council, Commercial Banks Agribusiness work not commenced as implementation plan in process. / Sectors on which agribusiness work will take place have been revised from the list in the indicator, now being seeds, pyrethrum and warehouse receipts. / Warehouse receipts study to establish baselines to be undertaken. / Pilot work by EAGC on 4 warehouses indicates that banks currently lend to 420 beneficiaries (farmers and farmer groups) under the pilot receipted warehouse scheme, which is expected to increase when formal receipting starts. / Formal receipting law not currently in place, but in process, this will enable establishment of formal baselines once passed. / Indicator 2.1 is on track. This indicator includes investigation of anti-competitive practices and merger review. Several activities have been undertaken during the review period relating to capacity building of the Competition Authority of Kenya (CAK). As a result of this one merger case in agro-processing (dairy industry) was completed, with CAK permitting the case to go forward. CAK exempts only small firms below the threshold of 1 billion KES, and hence given the size of the firms involved, the transaction was assessed and permitted. Further sensitization and stakeholder engagement through two workshops on competition enforcement and merger review were conducted, and 80 hours of training on competition analysis and international best practices on relevant practices for CAK decisions were provided to CAK staff. / This indicator needs to be discussed and reviewed so that it is more reflective of the competition team’s work, which is not limited to sector studies but includes investigation of anti-competitive practices and merger review. / Competition Policy / Key support was provided to CAK for the analysis of anti-trust cases and merger notifications. This resulted in pro-competition decisions and improved capacity at the Authority, with CAK issuing a decision on a complex merger case in agro processing. Areas for collaboration were also identified between the Communications Commission of Kenya (CCK) and CAK, as well as areas where investment can be unlocked through advice on pro-competitive regulations. Collection of information to calculate indicators on restrictive product market regulations (PMR) for Kenya was completed in collaboration with CAK and the information validated with stakeholders. This was conducted in the areas of: network services, retail, professional services, treatment to foreign investors and state participation in business activities. A Cooperation Agreement with CAK was agreed after receiving the Attorney General's comments, signed on January 20, 2014. / Indicator 2.2 is not on track and it is felt that the indicator and associated milestones should be revised following this review. This is because the Warehouse Receipts Bill - that will allow progress on this indicator - is still awaiting approval from Parliament. After careful scoping, consultation and evaluation of feasibility, the project has decided to work on three key sectors (seeds, pyrethrum, and warehouse receipts), in lieu of the broader work on the additional sectors highlighted in the original report and in this indicator. The project continues to engage with the Ministry of Agriculture on the Warehouse Receipts Bill. The indicator needs to be revised with new milestones and the target sectors re-identified. / At the current time, there are four pilot warehouses operating under the East African Grain Council (EAGC) using warehouse receipts under a non-formalized system. These are expected to translate into the formalized receipted system and numbers to increase once legislation is enacted and operationalized. Data from the EAGC currently shows 420 farmers (including several farmer groups) receiving credit from banks from the four pilot warehouse receipting sites. Project targets tentatively aim for an increase of 5,000 farmers and traders accessing the warehouse receipts system to store goods and access credit within one year following project completion (end 2017).
Agribusiness / Design of agribusiness interventions has been finalized, after the project engaged actively with the Ministry of Agriculture and sector stakeholders such as the East African Grain Council (EAGC), fully incorporating their priorities in order to bring them on board. The project areas are fully scoped and include improving seeds regulation, reviving the pyrethrum industry and establishing a warehousing receipt system to improve farmer access to credit. Included in the project objectives is the passing of good practice for warehouse receipts legislation within one year of approval. This would provide post-enactment implementation support, and assistance in the drafting and enactment of ‘seed sector’ and ‘competitive and investment inducing’ regulations for the pyrethrum industry under the reformed Kenyan agricultural framework. BRICK has continually engaged and more recently made progress with the Ministry of Agriculture in supporting the drafting of the above sector laws and regulations. / Recommendations: / The BRICK team has consistently engaged the Ministry of Agriculture, other GoK stakeholders and donors in the agribusiness space. As a result of these consultations, the bulk of planned activities will consist of seeds, pyrethrum and the establishment of a warehousing receipt system in Kenya, instead of the sectors outlined in the original indicator. Some provision in the implementation plan will be retained to tackle new emerging value chain work. Programme management must follow up closely with Ministry of Agriculture and other stakeholders on this and other potential interventions over the coming three months after review. / Output title should be revised, along with indicators and milestone to ensure that milestone targets are realistic and measurable. Indicator 2.1 needs to be revised so that it is more reflective of the competition team’s work, which is not limited to sector studies but includes investigation of anti-competitive practices and merger review. Indicator 2.2 and its milestones should be revised following this review because the Warehouse Receipts Bill that will allow progress on this indicator is still awaiting approval from Parliament. Additionally it should reflect the new focus on the key sectors identified. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Effective environment for public private partnerships
Output 3 score and performance description: B (Output moderately did not meet expectation) / Objectively Verifiable Indicators ( ) = unit of measurement Baseline 2013 Milestone 2014 Achieved Status Sources of Verification Comments / 3.1 Number of private sector companies involved in renewable energy public private initiatives 5 5 On track: at least 5 PPP transactions ready for market entry. Whilst this is not a direct measure of the indicator, it is a better measure of intended progress. This is because the agreed indicator should have referred to PPP transactions ready for market entry, and not tied to renewable energy. This indicator will need to be revised to this end. On track Energy Regulatory Commission (ERC) / Ministry of Industrialization and Enterprise Development; PPP unit, National Treasury Too early to determine or report / Renewable Energy (RE) E-Portal developed and fully functional which aims to ease the document preparation and information-gathering time taken for private sector companies seeking to enter the RE market. (see also 1.3) / At least 5 PPP transactions ready for market entry (on track) / Progress: Procurement of transaction advisors for 3 transactions: Nairobi Southern by-pass operation and management concession, Kisumu port and Nyali Bridge underway. / 3.2 PPP and fiscal commitment and contingent liability framework enacted and operational Developed Enacted Not enacted. Not on track but at least 6 policy reforms linked to export competitiveness have been adopted by Government. Indicator should be revised to ensure that the correct results are measured to track progress in this area. Ministry of Industrialization and Enterprise Development; PPP unit, National Treasury At ­least 6 policy reforms linked to export competitiveness have been adopted by Government across four value chains (furniture, textiles, leather and food processing). Diagnostics work on the four priority sectors is just beginning and the policy reform agenda is yet to be identified. / 3.3 Firms in special economic zones in terms of a) number b) investments c) number of people employed TBD once SEZ is set up (a) 0 (b)& (c) TBD N/A. These milestones need to be defined and this Annual Review process has shown that the indicator should be divided to measure the sections a, b, and c distinctly. Delayed Ministry of Industrialization and Enterprise Development Project’s previous engagement had stalled because of elections, devolution and government restructuring creating uncertainty amongst stakeholders. / Reengagement has since begun with a new client – the Ministry of Industrialization and Enterprise Development – who has shown commitment and renewed interest. / Since enabling SEZ law is a prerequisite for market-opening, and the involvement of firms in SEZs, further data on this indicator is not currently available. Once the enabling legislation is passed, formal baselines will be established. / BRICK will be seeking additional funding from DFID to carry the SEZs work forward. / The project has been supporting the GoK to implement reforms and build institutional capacity to promote the development of a robust market for PPP financing. This aims to effect substantively broader-based growth in infrastructure and social investment across all sectors. Furthermore, the project is in the process of undertaking a set of diagnostics to detect bottlenecks hindering competitiveness of sectors and export, and will make recommendations for reforms. / We have scored this output a B as progress against the original indicators is indirect. However, progress around this output objective is largely on track in working towards building an “effective environment for public private partnerships”. Revising the indicators are recommendations from this review. / Indicator 3.1 is on track with activities but some results are too early to gauge as the target is June 2015 (milestone to be revised in logframe). The indicator tracking the number of private sector companies involved in renewable energy (RE) public private initiatives captures a different metric and has been left at zero pending confirmation. The project uses its own indicator of ‘number of investor/private partnership leads' to gauge progress, which is targeted at 5 by June 2015, this should be reflected in the formal logframe. This is a better measure of intended progress because the agreed indicator should have referred to PPP transactions ready for market entry, and not tied to renewable energy. This indicator will need to be revised to this end. / At least 5 PPP transactions are ready for market entry. Further progress includes the procurement of transaction advisors for 3 transactions: Nairobi Southern by-pass operation and management concession, Kisumu port and Nyali Bridge underway. GoK has published a list of 50 PPP projects approved by Cabinet. / Indicator 3.2 is not on track but at ­least 6 policy reforms linked to export competitiveness have been adopted by Government across four value chains (furniture, textiles, leather and food processing). Diagnostics work on the four priority sectors is just beginning and the policy reform agenda is yet to be identified. Indicator should be revised to ensure that the correct results are measured to track progress in this area. / Key Achievements: / Export competitiveness diagnostics conducted and report submitted to GoK. / Legal and policy experts recruited to work with KEPSA on policy reform agenda including increasing KEPSA’s capacity for policy analysis, advocacy and member-focussed services. / Report on review of MSE policies and programs submitted to GoK. / Technical expertise provided towards the new National Tourism Strategy. / Informal sector survey completed and the dataset is available. / Terms of reference for value chain diagnostic work on food processing, textiles, leather and furniture agreed with stakeholders from public and private sector and public-private working groups established. / Indicator 3.3 There is no milestone measure but based on progress on planned activities this indicator is assessed as being on track. The indicator should be reviewed and milestone targets defined so that progress can be monitored. Over the years, engagement had stalled because of the lack of predictability arising from the absence of SEZ legislation, as well as from the elections process, devolution, and government restructuring. These have created uncertainty amongst stakeholders. Reengagement has begun with a new client – the Ministry of Industrialization and Enterprise Development – who has shown commitment and renewed interest. The enabling SEZ legislation remains a prerequisite for market-opening and the involvement of firms in SEZs. Once the enabling legislation is passed, formal baselines will be established. Overall project targets originally include two investor private partnership leads and US $50m in investment generated. / Renewable energy / Initially the project planned to deliver its renewable energy objectives through addressing wheeling regulations. However, an initial assessment of Kenya Power and Lighting Company’s (KPLC) customer base, sources of revenue and energy purchase requirements showed that opening the market to eligible customers through wheeling regulations could potentially affect its financial performance. The GoK requested the team to examine under what conditions it would be possible to bring competition between KLPC and the private sector. Based on this request BRICK delivered a draft option note for market opening, highlighting the key issues related to an open access regime in Kenya. The note is under discussion with the GoK.
Recommendations: / There is strong demand from GoK to scale up support for tourism and innovation policy and capacity building including establishing an innovation observatory. Programme team to follow up over the coming three months. / Given KPLC’s response to proposed wheeling regulations, BRICK is exploring working on off grid solutions as a possible alternative mode of engagement. BRICK should work closely with the Ministry of Energy, Energy Regulation Commission and other key stakeholders over the coming three months to agree next steps. / The component has been extended in timeframe by two years so the logframe should be revised to reflect this. Indicator 3.1 will be revised so that it measures its intended result on PPPs. Indicator 3.2 should be revised to ensure that the correct results are measured to track progress in this area. There is a need to revise the 3.3 indicator on SEZs so that it becomes output based, rather than focusing on outcomes (number of firms) and impacts (investment). It should also be divided to measure the sections a, b, and c distinctly. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Y / In accordance with the BRICK Business Case, outcome level indicators and associated milestones were amended during the first year of implementation. Output level changes will be made following this annual review through the process outlined in the ‘Conclusions and Actions’ section below. / 1.2 Overall Output Score and Description: / A. (Outputs met expectation). / BRICK is registering strong performance despite what has been a challenging transition environment in Kenya. GoK counterparts are now fully engaged and activities are expected to rapidly pick up over the coming reporting period. Some areas were not on track owing to delays beyond the control of BRICK, and in other places indicators/milestones were unrealistic. However, given the results achieved, and the impact weightings for each output, this project scores an A. The indicator and milestone issues will be addresses through the planned logframe revision. / 1.3 Direct feedback from beneficiaries / Activities are for the moment far removed from the ultimate beneficiaries. This should be reviewed over the next reporting period and options for gaining beneficiary feedback explored.
1.4 Summary of overall progress / BRICK began implementation at a time when a new GoK was voted into power, and with that the beginning of the devolution process, 47 county governments replacing what were 175 local authorities. There were initial delays to BRICK’s planned activities therefore, as the roles of the new GoK, counties and associated institutions took root. Counties have been slower at settling down to commence work and continue to face acute capacity challenges. However, the GoK has renewed interest in investment climate reform and the private sector is a strong priority. Overall progress is on track.
1.5 Key challenges / The devolution process has brought about numerous challenges, key among them counties resorting to drastic revenue mobilisation measures that have adversely affected businesses and particularly the poor since agriculture, their main source of livelihood, has not been spared. In some cases, costs for obtaining licenses have gone up by 150-300% in several counties over the last few months in addition to livestock, market, parking, burial and other charges. The BRICK team foresees these challenges continuing at least in the short to medium team and this will have a direct bearing on county related work and businesses. / Coordination gaps at the national and county levels continue to play out i.e., among Ministries/institutions at the national level and between national and county levels. / It is anticipated that connectivity between GoK trade facilitation agencies and the national electronic single window (eSW) is likely to pose a challenge. This is due to limited human resource and financial capacity, which may prevent the institutions from either interfacing or enhancing the ICT infrastructure necessary for effective operation of the eSW.
1. 6 Annual Outcome Assessment / The BRICK programme is registering good progress so far and the team is confident that it will more than achieve its stated objectives, including at the outcome level. Rigorous assessment of impact is being developed and is a key component of the overall program.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / The project is on track against financial forecasts. Output 1 has had some delays in implementation due to challenges posed by devolution of powers and functions to the newly formed counties that have been in existence for less than a year. Acute capacity challenges, ongoing recruitment of technical staff, protracted engagements with national government on distinction of roles, controversial revenue mobilisation measures that have in some places caused riots in businesses and court cases. Programme activities and spend are expected to pick up significantly over the coming period and to an extent will also be based on GoK demand and absorption. / 2.2 Key cost drivers / Total BRICK expenses for the last 11 months (March 2013-February 2014) amount to US$ 2.7 million including the IFC administrative fee of 5% (US$ 133,909). The major cost drivers are staff costs (41.4%), consultant fees (29.8%), travel costs (19%) and overhead costs (9.9%). / Key cost drivers therefore include fluctuations in fuel prices where relevant to travel costs, and the availability of locally recruited and internal (World Bank Group) experts verses that of international consultants. / 2.3 Is the project on-track against original timescale: Y/N / Despite implementation delays under the subnational component of Output 1(explanation provided above), the project is on track.

3. Evidence and Evaluation
The programme undertook a logframe validation exercise and shared revised logframe indicators at outcome level based on this exercise strengthening the ‘theory of change’. Outcome level changes have been agreed. However, it is recommended that the programme should undertaker a comprehensive logframe revision immediately after this review and agree on output level indicators. Project implementation expected to accelerate in the coming year. / The Programme Baseline Report (December 2013), confirmed targets for compliance cost savings through primary data, as well as compiling a review of individual projects within the BRICK framework. During baseline development, the programme team validated the theory of change. BRICK will continue to monitor the realization of results, and will complete end-line studies after project implementation. / Secondary sources will continue to be monitored through the programme’s life cycle, including the city councils of the counties with which sub-national work is being undertaken; the Ministry of Industrialization and Enterprise Development; the PPP unit within the National Treasury; the Competition Authority of Kenya (CAK); the Energy Regulatory Commission (ERC); the Pyrethrum Board of Kenya (PBK) and the East African Grain Council (EAGC). / Additionally, the programme plans a warehouse receipts system impact analysis study, working in cooperation with the EAGC and other sector stakeholders. The study will aim to measure changes in structured trade and crop collateralization in the market as a result of the launch of WRS, tracking data from warehouses and participating banks. Farmer level studies on selected receipted warehouses may also be included.

4. Risk
4.1 Output Risk Rating / Medium / 4.2 Assessment of the risk level / Key Risks Output(s) that will be most affected Mitigating Plan / Devolution of roles and responsibilities to counties and capacity challenges. Output 1 (subnational reform component). BRICK will continuously engage with the pilot counties right from inception and also incorporate and dedicate resources to capacity building. / Political environment may / negatively impact the ability to deliver the project as planned (e.g. change in government agenda or elected leaders, difficult securing political consensus for reform, government officers and/or agencies maybe benefit from status quo and resist project implementation, political interest groups disrupt project). The success of the renewable energy component depends on the Government’s openness to improving regulations/policy to attract private investment in the energy sector. If the clients are not committed to private participation in power, the project will not be able to achieve the intended impact. Constant engagement with the client to understand change in direction and keeping donors updated of plans to ensure alignment and complementarity of interventions. / Capacity challenges on the part of client counterpart agencies can limit the pace of reforms and activities implemented. This is seen in engagement with the Competition Authority of Kenya and other stakeholders where implementation on key deliverables has been slowed due to client constraints. Output 1: Competition policy merger work has been implemented, but activities on restrictive practices focused instead on training, postponing other deliverables to a future reporting period. The need to assess client counterpart capacity before implementing is of key importance. This allows work to proceed in synergy with the client’s staff members to ensure ownership and uptake of work implemented and more sustainable outcomes in the longer term. Focus on other areas within the competition team’s scope of work has largely mitigated for postponement due to client constraints.
Risk of funds not being used as intended / Low. BRICK funding is managed by International Finance Corporation (IFC) and the World Bank, both proven and reliable institutions with strong internal checks and balances in place. External audits are conducted regularly. / 4.4 Climate and Environment Risk / IFC projects comply with performance standards outlined in the environmental and social sustainability guidelines. No environmental effects are expected across project components. Continuous care is taken to analyse and mitigate for those that may arise during implementation.

5. Value for Money
5.1 Performance on VfM measures / No VfM measures have been agreed yet for the project, and it is recommended that these be agreed by July 2014. / Economy / Since 41% of the project’s costs are staff costs, and 30% consultancy costs, the most appropriate measures of Economy would be standard VfM indicators that DFID Kenya has developed on staff remuneration per day and consultancy fees. However, since the indicators have only just been developed, there was not time to reach agreement with the IFC on reporting them. This is included as a recommendation. / Efficiency and Cost Effectiveness / DFID is funding work by the Foreign Investment Advisory Service (FIAS) of the World Bank Group into developing VfM indicators for investment climate projects. The findings of this are expected in June 2014. It therefore makes sense to wait to finalise indicators of Efficiency and Cost Effectiveness, since they need to be comparable and linked to international best practice. / 5.2 Commercial Improvement and Value for Money / The Memorandum of Understanding for this grant is structured to incentivise good performance. BRICK submits invoices every six months, against which DFID check that they are delivering activities on target and in line with the agreed schedule through the financial and narrative reports that the team send. / In terms of the actions that the IFC are taking to promote VfM, there are some examples of good practice as highlighted in the table below: / 3 Es Good practice Example / Economy Use of best practice procurement processes. Procurement and contracting are undertaken in alignment with World Bank Group guidelines governing such activities. Procurement beyond the US$ 50,000 threshold is subjected to competitive bidding and the project team frequently consults with the procurement teams during project implementation / Reviewing salaries against the local market WBG salaries in Kenya are pegged at the 75th percentile of market comparators/institutions. / Efficiency Selecting the most appropriate types of Inputs balancing cost and quality The project prioritises the use of local consultants that are significantly cheaper than international ones. The latter are only engaged if there is a gap at the local level and this approach ensures that technical expertise is retained. / The project is making use of World Bank staff from other regions in order to minimise the use of consultants. / Ensuring quality of Outputs through quality assurance and monitoring Every product is quality assured by at least one global expert, and studies are published whenever possible, exposing them to external scrutiny. / Requiring contributions from partners to ensure commitment The IFC require a minimum 10% in-kind contribution from GoK, and are looking into financial contributions also. / Cost Effectiveness Ensuring that activities are joined-up across Outputs Project managers of the different programme outputs meet formally at least every three months to ensure coordination. / Consulting with and influencing government and other key actors in order to maximise Outcomes. The IFC works closely with private sector leaders to ensure joined-up dialogue with GoK over investment climate reforms. / The above examples are for the project as a whole – DFID should discuss with the managers of each output what they are doing to promote VfM before the next Annual Review. / 5.3 Role of project partners / The implementing partners, IFC and KEPSA, have made positive progress on programme results, and additionally their finances are on track and in accordance with agreed timelines. Unforeseen circumstances outside of the control of the project have been the primary cause of delays in activities. / 5.4 Does the project still represent Value for Money : Y/N / Yes, on the following basis: / Results: the BRICK team are performing well against results targets within their control. IFC’s technical expertise to deliver programme interventions remains strong and impact measurement and verification mechanisms robust. / Costs: are in line with budget forecasts so do not have a negative impact on VfM. / Theory of Change: the original Theory of Change has been validated by BRICK and will be further analysed by an independent consultancy team. / VfM actions: some VfM good practices have been identified, although deeper analysis is needed. / VfM measures: have been not been identified but will be in coming months. This will allow more rigorous of the project’s VfM. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable.

7. Conclusions and actions
This review notes that over the coming 12 months, there should be a significant pickup in programme activities as the GoK will be more settled and in their second year of administration. This follows devolution-related delays in the first year. BRICK have submitted a request for additional funding, which DFID are reviewing, to reflect this planned scale up. / Recommendation Timeframe / BRICK and DFID plan to meet to consult on the logframe re-design and agree a final, new version of the logframe by mid-June 2014. This will aim to capture all output related activities, ensure indicators and milestones are realistic and measurable, and re-assess the outcome and impact level objectives for this project. June 2014 / BRICK and DFID will engage the managers of the different programme outputs in a discussion of good VfM practices over the next 6 months. September 2014 / Activities are for the moment far removed from the ultimate beneficiaries. This should be reviewed over the next reporting period and options for gaining beneficiary feedback explored. Six months and progress checked March 2015 / Output 1 / Due to the challenges at county level and the ‘wish list’ presented to BRICK by each county, the programme should review planned activities to better respond to individual county needs. The team should also aim to resolve identified constraints, including a re-look at pilot counties in which to intervene, within two months of this review. Within two months / To be more transformative, BRICK is considering automation of business registration processes and discussions are ongoing with the GoK. This is particularly important since the project team does not foresee this service being devolved to the 47 counties as required by the Constitution. In the absence of this, business people will continue travelling to Nairobi to incorporate companies’ severely constraining SME creation and stifling entrepreneurship. BRICK’s programme management team to conclude on this with the Registrar General’s Office within two months of this review. Within two months / BRICK should include a capacity building component across the programme in order to address the shortage and limited capacity of staff, and hand hold new technical staff that are being recruited from the outset. DFID should BRICK’s additional funding request related to this. In coming months / Support to GoK needed to address coordination gaps to ensure success of programme implementation. Programme management to address over the coming three months. Within three months / In light of Nairobi County’s plans to establish a full enterprise resource plan (ERP), BRICK should re-evaluate continued planned activities and engagement with the county on subnational regulatory reform. The focus is likely to turn to enhancing the construction permit system and incorporating a development planning module. Programme management to resolve this with Nairobi County and conclude a cooperation agreement two months after this review. Within two months / Output title should be revised, along with indicators and milestone to ensure that all activities within the programme are encapsulated and milestone targets are realistic and measurable. In particular, indicator 1.1 should be revised as the mandates of national/county level authorities are made clear, allowing RIAs to take place. Indicator 1.3 to be revised as it only refers to one portal, and should include other ICT/web portal work related to the output. June 2014 / Output 2 / The BRICK team has consistently engaged the Ministry of Agriculture, other GoK stakeholders as well as donors in the agribusiness space. As a result of these consultations, the bulk of planned activities will consist of seeds, pyrethrum and the establishment of a warehousing receipt system in Kenya, instead of the sectors outlined in the review indicator. Some provision in the implementation plan will be retained to tackle new emerging value chain work. Programme management must follow up closely with Ministry of Agriculture and other stakeholders on this and other potential interventions over the coming three months after review. Within three months / Output title should be revised, along with indicators and milestone to ensure that milestone targets are realistic and measurable. Indicator 2.1 needs to be revised so that it is more reflective of the competition team’s work, which is not limited to sector studies but includes investigation of anti-competitive practices and merger review. Indicator 2.2 and its milestones should be revised following this review because the Warehouse Receipts Bill that will allow progress on this indicator is still awaiting approval from Parliament. Additionally it should reflect the new focus on the key sectors identified. June 2014 / Output 3 / There is strong demand from GoK to scale up support for tourism and innovation policy and capacity building including establishing an innovation observatory. Programme team to follow up over the coming three months. Within three months / Given KPLC’s response to proposed wheeling regulations, BRICK is exploring working on off grid solutions as a possible alternative mode of engagement. BRICK should work closely with the Ministry of Energy, Energy Regulation Commission and other key stakeholders over the coming three months to agree next steps. Within three months / The component has been extended in timeframe by two years so the logframe should be revised to reflect this. Indicator 3.1 will be revised so that it measures its intended result on PPPs. Indicator 3.2 should be revised to ensure that the correct results are measured to track progress in this area. There is a need to revise the 3.3 indicator on SEZs so that it becomes output based, rather than focusing on outcomes (number of firms) and impacts (investment). It should also be divided to measure the sections a, b, and c distinctly. June 2014

8. Review Process
The Annual Review was initially conducted and drafted by the KICP-2 Team at IFC, in February and March 2014. / Results were checked and quality assured by DFID’s Wealth Creation Team who manage this project, with consultation from DFID Kenya’s Accountability and Results Team.