Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: International Finance Facility for Immunisation (IFFIm)
Programme Value: £1.63 billion		Review Date: October 2017
Programme Code: 111073 & 201185	Start Date: 2007	End Date: 2029

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020
Programme Score	A	A	A+	A
Risk Rating	Medium	Medium	Moderate	Moderate

Summary of progress and lessons learnt since last review

The core function of the International Finance Facility for Immunisation (IFFIm) is to accelerate the availability and predictability of funds for immunisation. Overall, IFFIm continues to deliver efficiency by being able to mobilise long term resources from donors.

The principal policy analysis since the 2016 annual review has been the consideration of four potential strategic roles to enable IFFIm’s resources to deliver the best value for money while remaining within its mandate:

1. Providing financial commitments for market shaping: Utilise IFFIm’s unused long-term assets while generating a number of benefits in relation to (i) increasing and diversifying the uses of IFFIm; (ii) expanding Gavi’s market shaping toolkit; (iii) staying within Gavi’s mandate while not requiring a change to the Finance Framework Agreement (FFA); and (iv) maximising Gavi’s financial efficiency. Progress: IFFIm donors have endorsed this approach and IFFIm will continue to advance this initiative with a target to complete and implement the structure by early-2019.
2. Supporting cold chain equipment optimisation platform (CCEOP): IFFIm’s access to a growing socially responsible investor base could provide unique funding opportunities for CCEOP, including through impact investment products. Progress: IFFIm donors have suggested that a specific IFFIm investment in CCEOP may not be required at the current time given that the Board has approved a funding envelope from Gavi’s core funding and there is an ongoing process of integrating CCEOP with countries’ Health System and Immunisation Strengthening (HSIS) grants. The CCEOP has also started relatively recently and there is, as yet, insufficient evidence of impact of the investment, to make a compelling case for a separate bond issuance. IFFIm will continue to monitor the situation and will continue to advise and provide lessons on the relevance of the IFFIm mechanism for ‘climate sensitive’ or ‘green’ bonds in the development financing area.
3. Providing a funding tool to respond to disease outbreaks: IFFIm funds could have a potential use in funding Gavi’s response to a future vaccine-preventable emergency disease response. Progress: This concept has been put on standby until Gavi defines its future role in outbreak responses. There is also the understanding that IFFIm funds remain available for the frontloading of funds, should they be required by Gavi in a vaccine response to an outbreak (e.g. IFFIm funds were available during the Ebola epidemic to fund a rapid scale up of an Ebola vaccine, if this had been needed).
4. Supporting vaccine scale-up as part of the current Gavi Vaccine Investment Strategy: This is an uncontroversial approach which has been a feature of IFFIm’s funding to Gavi e.g. the frontloading of funding for the hugely successful global scale up of the pentavalent vaccine. Progress: This will be further defined through Gavi’s Vaccine Investment Strategy development process, expected to conclude in late 2018.

The UK has been fully involved in this ongoing analysis. The IFFIm team has been consultative in its deliberations and has sought consensus from IFFIm donors on the way forward with the indicators.

IFFIm has continued to provide lessons and advice to other similar mechanisms being considered in the development space, for example a mechanism currently being developed by the World Bank team in the education sector.

Summary of recommendations for the next year

1. IFFIm to continue its analysis of potential strategic roles, take forward the market shaping contribution in concrete terms, and track / monitor other areas, always open to options to improve the value for money of the IFFIm mechanism.
2. In considering strategic options, IFFIm to ensure that it does not move outside of the Gavi mandate and propose options that fall outside of the purposes for which donors originally invested in the IFFIm mechanism i.e. to scale up lifesaving vaccines in developing countries.
3. IFFIm to continue to monitor and deliver value for money in its operations against the criteria set out in the Value for Money section.
4. IFFIm to consider whether it would it would be warranted to update the analysis of whether the impact of the mechanism is saving additional lives through the frontloading mechanism and resultant faster scale up of vaccines in developing countries.
5. (internal): DFID and the IFFIm team to jointly re-evaluate the logframe and consider whether additional indicators are required to measure value for money of IFFIm, as well as to measure progress against the provision of commitments for market shaping.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-201185/
DevTracker Link to Log frame:

Outline of the programme

The International Finance Facility for Immunisation (IFFIm) is a financing mechanism that frontloads donor pledges to fund immunisation programmes managed through Gavi, the Vaccine Alliance. IFFIm uses long-term pledges from donor governments as backing to sell 'vaccine bonds' in capital markets, making large volumes of funds immediately available for Gavi programmes.

Developing countries assessing whether to adopt a new vaccine look for assurance that programme support will continue until they can take over full financing. Likewise, vaccine manufacturers investing in new or expanded production that can take several years of lead time need confidence that there is guaranteed demand. IFFIm is therefore an important component of the long-term, predictable funding required to support Gavi programmes.

The diagram below illustrates how IFFIm works, showing how legally-binding donor pledges are turned into funds which are immediately available for vaccination programmes.

IFFIm was originally designed to enable Gavi to scale up rapidly in order to meet immediate and urgent needs, and to accelerate progress towards Millennium Development Goal 4 (reducing child mortality). The intention was to disburse US$4 billion of frontloaded and predictable financing to Gavi in order to avert 10 million future deaths; this would have required US$7 billion of funding from donors[1]. In total, IFFIm has received legally binding pledges from donors of approximately US$6.5 billion spanning 23 years. The UK is providing a total of £1.63 billion to IFFIm. UK support is made up of two legally binding pledges, one made in 2006 for £1.38 billion and payable over 20 years from 2007 – 2026, and the second for £250 million, made in 2009 and payable over 20 years from 2010 – 2029. The UK is the largest donor to IFFIm. This review applies to both tranches of UK commitments to IFFIm.
[1] This is because the pledges are over 20 years and due to the time value of money in order to achieve frontloading of $4 billion for programme financing, a higher nominal value of pledge is required.

A key feature of IFFIm is its favourable treatment of pledges on donor governments’ balance sheets. While commitments are attributed to donors at the time of pledging, pledges are only reflected as government expenditure when payments are made to IFFIm. This means that governments can make long-term pledges to IFFIm without the full value immediately appearing on government balance sheets.

IFFIm has supported Gavi in giving clear signals to the pharmaceutical industry around the size and sustainability of vaccine markets in low income countries. Gavi’s market shaping work has encouraged investment and competition in vaccine production (including from manufacturers in developing countries).

The rate at which programmatic results are achieved depends on both the level of financing available from IFFIm and how rapidly Gavi calls down IFFIm funds; Gavi may call down support more slowly if it has high levels of direct funding from donors in the short term. Estimates of deaths averted depend on a number of factors, many of which are outside IFFIm’s control and depend on Gavi programming and policy decisions – including the mix of vaccines supported by Gavi and the countries funded, since vaccines have widely differing results in terms of deaths averted, chronic health conditions prevented, and efficacy in different regions and countries. It is logical to relate expectations of lives saved through IFFIm funding to our overall expectations of lives saved through total Gavi financing.

The Gavi, IFFIm and AMC investments are consolidated under the same logframe. The focus of the IFFIm review is on the efficiency of IFFIm as a funding mechanism, recognising IFFIm’s role as a financing instrument of Gavi. The Gavi results are presented in the Gavi Annual Review.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Within the consolidated logframe IFFIm contributes to the overall Gavi outcome. Gavi has made strong progress against the consolidated logframe outcome indicators in 2016:

- Lives Saved: 1.2 million achieved against a milestone of 1 million
- Children vaccinated: 62 million achieved against a milestone of 50 million
- Gavi transitioned countries that continue to implement Gavi-supported vaccines: 100%

Gavi has made a strong start against the measurable 2016-2020 results targets to immunise an additional 300 million children and save 5-6 million lives. Using WHO/UNICEF data and agreed methodology, Gavi estimates that in 2016 (the first year of its new strategy), an additional 62 million children have been immunised and more than 1.2 million future deaths averted. This puts Gavi on track for its 2016-2020 targets, although improvements in coverage and equity will be needed to accelerate the results in the following years.

Overall output score and description: A

Whilst progress against the three output indicators has been mixed (exceeded one, met one and not met one), overall IFFIm continues to prove its worth as a leading global development innovative financing instrument and effective tool for development financing.

Key lessons

IFFIm has efficiently frontloaded donor resources to enable the scaling up of life saving vaccine programmes in developing countries. The frontloading has enabled countries to scale up cost-effective vaccines at a much faster rate than would have been possible, saving millions of lives.

Over the past two years, IFFIm has looked at options to enhance the value for money which it delivers. IFFIm has been able to do this efficiently, at minimal administrative cost, and in a way which does not move outside of Gavi’s mandate.

Key actions (see recommendations above)

Has the logframe been updated since the last review?

This is the first annual review against a consolidated Gavi logframe in which IFFIm becomes one output contributing to the overall Gavi investment outcome of vaccinating children, saving lives, and supporting immunisation systems which are sustained when countries transition from Gavi support.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Demonstration that IFFIm is a feasible, efficient and acceptable mechanism, and is an effective tool for development financing.
Output number per LF		1 (6 – Gavi logframe)	Output Score	A
Risk:		Moderate	Impact weighting (%):	100%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
6.1 Net Present Value (NPV) of disbursement to Gavi: NPV of disbursement for other uses (such as interest cost, etc.) ≥90:10	≥90:10	Exceeded: / 2015: 93.1 : 6.9 / 2016: 94.3 : 5.7
6.2 The spread between IFFIm's cost of financing and that of the / weighted average cost for donors for cumulative outstanding issuances	IFFIm to raise finance at the same cost or lower than the weighted average cost for donors	Not Met: / Current average IFFIm funding costs for outstanding issuances: 3M US$ Libor + 20 bps (2015: +10 bps) / Current donor average weighted funding costs: 3M US$ Libor - 2 bps / (2015: +20.3 bps)
6.3 Proportion of IFFIm disbursements allocated to programmes within Gavi Board mandated policies and the Gavi 2016-2020 Strategy	100%	Met: / 2016: US$ 100 million (100%)

Key Points

6.1: This indicator is a measure of IFFIm’s efficiency as a funding mechanism. It shows how much of the funds raised by IFFIm on capital markets over its lifetime have been used for the core purpose of making disbursements to Gavi compared to other uses (i.e. interest and management costs). Net present value (NPV) is used to compare the value of payments made at different points in time. As of the end of 2016, 94.3% of the NPV of funds raised have been disbursed to Gavi to fund its activities, an improvement compared to 2015 when this percentage was just slightly above 93%. This improvement is driven by the impact of new pledges, as well as wider economic factors including the continued low interest-rate environment. The 2016 result is significantly better than the 90:10 target ratio.

6.2: This indicator is a further measure of IFFIm’s efficiency, comparing the cost of funds raised by IFFIm to the weighted average of the cost of equivalent funds raised by individual donors. The indicator specifically assesses outstanding issuances, i.e. all bonds which have been issued by IFFIm and are still being repaid, against the weighted average cost for donors for raising funds at the same time as those issuances.

In 2016, the weighted average cost of IFFIm’s outstanding bonds was 3M US$ Libor +20 bps, 0.22 percentage points higher than the weighted average cost of funding of IFFIm’s donors, which was 3M US$ Libor -2 bps. This has been driven principally by the continued low interest rate environment combined with the earlier downgrade of IFFIm’s credit rating.

While IFFIm’s credit spread has remained high since it was downgraded to AA/Aa1/AA (S&P, Moody’s, and Fitch) in 2012 and 2013, the ECB’s quantitative easing bond purchase programme has significantly lowered the spreads of euro denominated bonds issued by some of IFFIm’s donors (particularly Spain, Italy and France). The tighter spreads have resulted in a lower weighted average cost of IFFIm’s donors compared to IFFIm’s own borrowing cost.

6.3: Indicator 6.3 was introduced to ensure that the IFFIm Board is focused on maintaining IFFIm’s role as a key funding instrument for Gavi, and that all of the funds disbursed by IFFIm are used for Gavi Board mandated policies and the 2016 – 2020 Strategy. In 2016, IFFIm disbursed to Gavi a total of US$100 million, all of which was allocated to Gavi Board approved programmes. IFFIm has stayed within this target historically.

Summary of responses to issues raised in previous annual reviews (where relevant)

R1. The Gavi secretariat should present updated and detailed analysis to IFFIm donors regarding the potential future roles and the resultant recommendations discussed at the workshop in June 2016, before March 2017 (see recommendation 2).

COMPLETE: An update with analysis of IFFIm’s four strategic initiatives was presented to IFFIm donors at the IFFIm donor meeting in June 2017. Gavi and the IFFIm Board have developed these initiatives as per the donor guidance received at the June 2016 donor workshop. Originally planned for Q1 2017, the meeting to update IFFIm donors was rescheduled to coincide with the IFFIm donor meeting at the Gavi Board so as to enable full donor participation. In May, the draft briefing materials were circulated and a donor call organised to provide an opportunity for donors to review the draft materials and clarify questions and concerns they had prior to the June meeting.
R2. The Gavi secretariat to manage another constructive donor meeting ahead of or alongside the IFFIm Board in March 2017. This should enable a discussion for donors on the next steps.

COMPLETE: Gavi and IFFIm Board enabled a constructive donor meeting ahead of the IFFIm Board meeting in June 2017 to discuss in detail the ongoing progress in developing the four strategic roles. During the meeting, IFFIm also addressed queries and concerns that the donors raised at the June 2016 donor workshop. At the June meeting, donors provided guidance and support on how to prioritise further development of these initiatives. One important outcome of the meeting is an agreement among the IFFIm Board, Gavi and donors on key activities and a timeline for each initiative.

R3. The Gavi secretariat, IFFIm Board and the Treasury Manager to effectively manage the end-2016 bond issuance and to report to donors on the comparative weighted average cost of financing for donors.

COMPLETE: In October 2016, IFFIm successfully issued 3-year US dollar floating rate benchmark vaccine bonds raising US$ 500 million. The issuance marked IFFIm’s first return to the international U.S. dollar benchmark market since 2013 and was the third time since IFFIm’s founding in 2006. The bonds were oversubscribed demonstrating IFFIm’s continued effectiveness in outreaching diverse investors in a variety of markets to support Gavi’s life-saving mission.

Following the issuance, the Gavi Secretariat reported to donors on the comparative weighted average cost of financing for donors. IFFIm’s funding cost for the 2016 issuance was 3M $LIBOR +29.4 bps. This is almost 0.22 percentage points higher compared to the average of its donors (3M $LIBOR +7.5 bps) using their comparable domestic government bond issuances.

R4. The Gavi secretariat, together with the IFFIm Board and Treasury Manager, to continue to support donors to ensure the successful signing of the 2015 pledge agreements.

COMPLETE– All remaining new pledges announced at Gavi’s 2015 replenishment have been successfully signed. In May 2017, Gavi signed new pledge agreements with France and the Netherlands for EUR 150 million (2022-2026) and USD 66.7 million (2017-2020) respectively. Gavi had signed the new pledge agreement with Australia for AUD 37.5m (2016-2020) in June 2016.

R5. The Gavi Secretariat to manage openly and transparently with IFFIm donors the potential pressure from other donors to use IFFIm for activities outside its own or Gavi’s mandate, building on the consensus reached at the donor workshop.

ONGOING: The IFFIm Board provides a regular update to IFFIm donors (primarily through donor meetings) on relevant ongoing activities that the Board members are undertaking in their personal capacities, such as ongoing discussions by other organisations to explore the potential replication of IFFIm or an IFFIm-like funding vehicle. Gavi is in regular communication with the IFFIm Board to ensure that any new development pertaining to these efforts are timely and transparently communicated to the donors. As per donors’ request, Gavi and the IFFIm Board regularly reinforce the need to keep other IFF discussions distinct from IFFIm in order to avoid any confusion between these two initiatives.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

As mandated in IFFIm’s Finance Framework Agreement, IFFIm has no employees. IFFIm outsources all administrative support to Gavi, and outsources its treasury function, together with certain accounting and financial reporting, to the World Bank.

Treasury management fees cover bond issuance (market research, design, and execution); investment management; financial risk management (hedging of pledges and bonds); management of donor pledges and payments; fund management (commitments, disbursements, programme tracking); ratings maintenance including the gearing ratio model; liquidity monitoring; accounting and financial reporting; and reporting to donors and for IFFIm Board Meetings.

VfM performance compared to the original VfM proposition in the business case

As IFFIm is an innovative financing arm of Gavi, it demonstrates economy by its low governance costs and treasury / investment management fees which are more than offset by investment gains from investable assets.

In 2016, treasury management fees were US$2.0 million, a decrease of 13% from the previous year. The decrease was primarily due to lower bond issuance and investment management costs. These fees were stable at around US$2.3 million over the past several years following its peak in 2011.

Following a significant drop in 2015, the governance costs have slightly grown to US$ 2.0 million, an increase of 5% from the previous year. This was largely due to administrative costs related to bond issuance activities. However, the governance cost attributable to administrative support from Gavi has decreased in 2016 to US$1.0 million (52%) from US$1.1 million (59%) in 2015.

Table 1 presents the actual IFFIm governance costs, Treasury Manager fees, and the investment income from IFFIm’s inception in 2006 until the end of 2016. IFFIm’s investment income is generated from its investible assets, namely its cash holdings as mandated by its liquidity policy. In 2016, the investment income increased significantly (over +70% vs. 2015), driven by the improvement in coupon income from high-quality credit products, prolonged credit spread and cross currency basis tightening, and actively managed cross currency arbitrage strategies. Table 1 demonstrates that investment income earned from assets in 2016 more than offset the cost of governance and management of the IFFIm portfolio.

Table 1: Overview of governance costs, Treasury Manager fees and investment income, 2006 – 2016 (US$ millions)
	2006	2007	2008	2009	2010	2011	2012	2013	2014	2015	2016
Governance Costs	1.6	2.2	2.8	3.0	2.9	2.7	3.0	2.7	2.8	1.9	2.0
Treasury Manager Fees	1.9	1.3	1.8	2.0	2.2	2.6	2.4	2.3	2.3	2.3	2.0
Investment Income	3.5	14.4	4.5	10.8	5.7	8.0	6.3	3.8	3.0	4.8	8.2

As evidenced in the Output assessment, IFFIm continues to deliver efficiency in terms of its ability to borrow at relatively low rates compared to UK and other IFFIm donors, and by effectively front loading donor pledges to deliver upfront value-for-money financing to Gavi.

Overall, IFFIm has been able to mobilise long term resources from donors in a more efficient way collectively than if they had done so individually. Despite the increase in the cost of funds for the outstanding issues compared to the IFFIm donor average in 2016, the overall cost of financing for all bond issuances since IFFIm’s inception has remained lower than that of its donors by 0.088 percentage points.

Although recent bond issues have had a higher cost of funding than that of the weighted average donor, in 2016, IFFIm was within the 10%, a target that it has historically been maintained. Factors such as the significant change in the economic environment (principally the historically low interest rate environment) and the effect of the downgrade of IFFIm’s credit rating on its cost of borrowing have led to this difference in performance.

It is important to remember that IFFIm at inception was expected to pay, on average, a higher rate of interest than its donors, with this higher cost of funding outweighed by the benefits of frontloading funding to Gavi. The 2005 IFFIm Project Memorandum based its analysis on IFFIm being only 3.5% more expensive in NPV terms than financing the programme through a normal grant. Despite this, in the past years, IFFIm was able to borrow at lower rates on average than the donors’ composite cost because of the behaviour of the financial markets. This is considered an unforeseen benefit.

IFFIm is operating with a significant negative swap exposure[2], the size of which means that it must set aside more money to mitigate risk[3]. Despite these constraints, IFFIm will still be able to meet all its currently agreed future funding commitments to Gavi. In addition, the main negative effect of high swap exposure is that it places a constraint on the gearing ratio. This has not been a significant risk in the past year since IFFIm’s current gearing ratio is relatively far from the limit. The IFFIm Board and the World Bank are considering the best and most effective ways to manage the swap exposure issue on an on-going basis.
[2] IFFIm enters into swaps with the World Bank to protect both IFFIm’s assets and its outstanding debt from movements in foreign exchange and interest rates. The value of these swaps is minus US$739 million as of July 31st 2017, which means that in the hypothetical case that IFFIm went into default, the World Bank would incur a cost of US$739 million. The value of the swaps will naturally unwind (decrease to zero) as pledges are paid and bonds mature.
[3] IFFIm is required to maintain 12% additional capital over and above the 70.3% set by the gearing ratio limit (Q2 2017); in theory this means that IFFIm can only frontload 58.3% of the net present value calculated in US dollars of all the donors pledges to Gavi.

IFFIm’s effectiveness lies in its ability to:

- Provide Gavi with flexibility either to frontload resources over a shorter term, or to draw down funds over a longer period, enabling Gavi to use funds when they are needed most.
- Provide long-term, predictable funding to enable Gavi to support market shaping activities, reinforce Gavi’s financial strength, and enhance Gavi’s ability to make long-term funding commitments.
- Offers donors a cost-effective way to spread contributions over future years and to have an immediate impact.

IFFIm has leveraged donor pledges of US$ 6.5 billion over a 25-year period to raise US$ 5.7 billion in cash over the 2006 to 2016 period. To date, IFFIm has provided approximately one fourth of Gavi’s funding to support its life-saving vaccination programmes. IFFIm’s funding has helped Gavi immunise close to 580 million children and avert more than eight million future deaths. Gavi has also has been responsible for more than 300 vaccine introductions and campaigns, including those protecting against the leading causes of diarrhoea and pneumonia, two of the biggest child killers.

Assessment of whether the programme continues to represent value for money

IFFIm has so far been able to mobilise resources in a more efficient collective way than if donors had done so individually, which is further evidence of delivering on the VfM proposition. It is expected that IFFIm will continue to represent good value for money barring any significant market downturns.

IFFIm has played a key role in supporting Gavi’s evolution as a global health organisation. This will continue as IFFIm is expected to provide US$1.3 billion over the 2016 – 2020 period, representing approximately 13% of Gavi’s overall resources in the period. As outlined above, it is expected that IFFIm will continue to be less than 10% more expensive in NPV terms than traditional donor grants, while also enabling greater frontloading of resources.

Assuming that operational costs continue at the same level, and wider market conditions do not deteriorate further, then it is expected that IFFIm will continue to represent good value for money. The new roles for IFFIm could also represent an opportunity to further improve the value for money proposition.

Quality of financial management

IFFIm’s financial reporting is in line with international best practice. Financial forecasts for IFFIm disbursement are aligned with Gavi’s needs and are reported to the IFFIm Board on a quarterly basis. The IFFIm financial statements are audited by KPMG, an external independent auditor, who also issues unqualified audit opinions.

The World Bank is IFFIm’s treasury manager; it manages IFFIm’s finances to the same prudent standards that it manages its own finances. With its strong institutional reputation and financial market expertise, the World Bank enables IFFIm to leverage donor pledges for Gavi’s vaccination programmes through the issuance of vaccine bonds on international capital markets.

IFFIm and the World Bank carefully review and negotiate treasury management fees every year to ensure cost optimisation.

IFFIm and the World Bank actively manage IFFIm’s funding cost to maximise its overall efficiency while also taking into account the opportunity that any new market provides to Gavi in increasing its profile and visibility.

Date of last narrative financial report
Date of last audited annual statement	31 December 2016

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk

IFFIm is a well-functioning instrument which has operated efficiently and achieved credibility in the international bond markets. IFFIm has been able to continue to operate and to fund Gavi programmes at low cost despite losing its original triple-A rating. S&P and Fitch both rate IFFIm as AA (negative), and Moody’s rates IFFIm as Aa1 (stable). IFFIm’s credit ratings have remained unchanged since its last outlook revision by Fitch from stable to negative on 30 June 2016. IFFIm’s rating is primarily based on the rating of its two largest donors, the UK and France; if their ratings deteriorate then further downgrades to IFFIm are possible. The strength of donor support and commitment, and the credibility of the World Bank as Treasury Manager, are both cited as positive aspects supporting IFFIm’s current credit rating.

A key risk for IFFIm continues to be around managing currency swap exposure and its impact on attracting new pledges. Exchange rate volatility and credit rating downgrades have led to high levels of exposure imposed on the Treasury Manager. New long term pledges were requested in US dollars with donors being asked to subsume the currency risk or hedge future movements themselves. All new pledges have been signed and agreed; while the Netherlands’ payments are in US dollars, the payments from Australia and France are in Australian dollars and Euros respectively. The Australian payments are converted to US dollars as they are received. For the French pledge, to be paid from 2022 to 2026, the IFFIm Board and Gavi reached an agreement with France concerning continued engagement with the World Bank to find ways to manage the currency risk of the new pledge.

Outstanding actions from risk assessment

IFFIm financial management is governed by the IFFIm legal agreements, including the Finance Framework Agreement. These set out how donor payments are made and how funds are managed by the World Bank as Treasury Manager, and transferred to Gavi. There is a very low risk of funds not being used as intended i.e. not transferred to Gavi to fund immunisation and health systems strengthening programmes. The success of IFFIm may lead to increased pressure from other donors to use it for activities outside its own or Gavi’s mandate; however the commitment to use IFFIm solely to support Gavi’s immunisation and health systems strengthening programmes was further consolidated during the IFFIm donor meeting in June 2017. The Gavi Annual Review covers the safeguards in place to protect funds from misuse at programme level – i.e. following their transfer from IFFIm to Gavi.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

IFFIm has provided US$2.6 billion to Gavi as of March 2017; this represents approximately 18% of Gavi’s total resources since 2000 (US$14.0 billion), and 21% since its inception in 2006. This is below its original target of providing US$3.3 billion by the end of 2015, due to Gavi exceeding its replenishment targets for the 2011 to 2015 period and not requiring additional frontloading of IFFIm funds at the scale originally envisaged. In its first five years of operation, IFFIm provided more than half of Gavi’s total funding (53%); this is evidence of its ability to frontload resources.

The IFFIm logframe had previously concentrated on the public health benefits attributed to IFFIm funding; the new logframe explicitly recognises that IFFIm is a financing tool for Gavi to use as it needs to do so. This new logframe therefore concentrates on the efficiency of IFFIm’s operating model. Over the 2016 – 2020 strategic period, IFFIm is expected to disburse a further US$1.3 billion between 2016 and 2020, representing approximately 13% of Gavi’s overall forecasted resources in the period. The first tranche of this disbursement, in the amount of US$ 100 million, occurred in December 2016.

Performance of partnership (s)

Partnerships continue to perform well, with the World Bank acting as a highly engaged, efficient and credible Treasury Manager. The World Bank and the IFFIm review continue to engage to discuss options that could alleviate the pressures presented by the negative swap exposure. The IFFIm Board, the Gavi secretariat, and the IFFIm donors have acted effectively in partnership in considering new potential strategic roles for IFFIm to further enhance its value for money.

Asset monitoring and control

The IFFIm Board and the World Bank continue to monitor market issues that affect IFFIm’s performance, and have put in place a limit on the gearing ratio (70.3% as of Q2 2017); with a further 12% additional capital to be held as a result of the risk management buffer (making the effective gearing ratio limit 58.3%). The actual gearing ratio was 22.9% as of the end of Q2 2017, down from 28.3% at the end of Q2 2016.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not relevant

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

IFFIm was independently evaluated in 2011[4]. This evaluation assessed “whether the IFF concept is proven and whether the IFFIm pilot has worked”. A number of key strengths and weaknesses were identified, including that it had successfully demonstrated a proof of concept but that it had not fully utilised the potential the model offers in terms of frontloading and predictability.
[4] http://www.gavi.org/results/evaluations/IFFIm-evaluation/

The IFFIm donor meeting in June 2017 reviewed the progress of IFFIm’s four strategic roles identified to support Gavi’s mandates through comprehensive donor consultations including the IFFIm donor workshop in June 2016. Donors expressed satisfaction at the progress and provided guidance and endorsement on how these roles will be further prioritised. IFFIm will continue to engage with donors to further evaluate the progress and seek guidance as necessary. In addition, the World Bank and the IFFIm Board are engaged in assessing whether there are other potential options to alleviate the pressures presented by the negative swap exposure.

Monitoring progress throughout the review period

DFID monitors IFFIm’s progress via quarterly reports issued by the World Bank, bi-annual IFFIm donor meetings, and regular dialogue with the Gavi Secretariat. DFID also has a good overview of the progress Gavi made against its 2011-2015 strategic plan, as outlined in the Project Completion Report for the 2011 – 2015 Gavi investment, along with initial progress against the 2016 – 2020 Strategy in the 2016 Gavi Annual Review.

This IFFIm Annual Review involved discussions with Gavi staff in Geneva, the IFFIm team in Washington DC by videoconference and further desk based analysis carried out in consultation with the Gavi Secretariat. Sources of information included: previous IFFIm annual reviews, Gavi Annual Review 2016, and data from the Gavi Secretariat, World Bank and IFFIm website. Scoring was conducted internally by the DFID Global Funds Department team based on the evidence provided.
## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process