Type of Review: Annual Review

Project Title: Support for the European Bank for Reconstruction and Development (EBRD) to provide technical assistance to Middle East and North Africa reform countries

Date started: March 2012
Date review undertaken: March 2014
ARIES Project Number: 203056

Description	Scale
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

Introduction and Context
What support is the UK providing?
The UK is providing £5m (€5.97m) to the European Bank of Reconstruction and Development (EBRD) to enable it to provide technical advice and assistance to countries in the Middle East and North Africa (MENA) Region, specifically Egypt, Tunisia, Morocco and Jordan. / The UK’s funds are contributing to the EBRD’s Multi-Donor Account (MDA) for technical cooperation in (what the EBRD titles) the ‘Southern and Eastern Mediterranean’ (SEMED) region. Donor contributions to the MDA as at 31 December 2013 were €21.6m (out of a total amount of €22.8m pledged). The UK is currently the largest bilateral donor to the MDA. / Figure 1: Donor contributions as of 31 Dec 2013 / The MDA was established by the EBRD in 2011 (with the activities of the MDA starting in March 2012) as part of the EBRD shareholders’ decision to expand activities to prospective new countries of operations in the SEMED region and enable the Bank to employ technical experts and incur other costs to provide direct advice and training to private and public sector clients in the new countries. The MDA supports activities including: strengthening business management of small and medium sized enterprises (SMEs) and increasing their access to finance; improving the productivity of agricultural businesses and widening their range of local input suppliers; developing projects for the financing of socially desirable and environmentally acceptable infrastructure improvements; reform of legal, social and environmental policies to achieve stronger, more inclusive and more sustainable growth. / UK funding is supporting a 3 year programme spanning financial years 2011/12 – 2014/15. An additional £50,000 of funding will be used to carry out an independent evaluation of the intervention in the final six months of the programme.

What are the expected results?
The UK’s funding is expected to contribute to an impact of ensuring inclusive and sustainable growth in the MENA region. It will do this by, in combination with contributions from other donors, delivering the outcome of increased investment and private sector growth in Egypt, Tunisia, Morocco and Jordan. It is intended to result in: / Outcome 1: £500m of total annual EBRD investments, linked to technical cooperation, in the four SEMED countries by 2014; / Outcome 2: A total increase in employment of 4,250 in businesses that have received direct financial and technical assistance from the EBRD by 2014, including an additional 2,125 women employed; / Outcome 3: A cumulative increase of £400m of Public-Private Partnership (PPP) investments in infrastructure improvements as a result of donor-funded technical cooperation from the EBRD; / Outcome 4: Significant legal, social and environmental policy reforms to promote more inclusive and sustainable growth, made by at least 6 public sector and 18 private sector clients. / The programme is expected to deliver 5 outputs: / Output 1: Strengthened ability of SMEs to grow sustainably. / Output 2: Strengthened agricultural productivity and improved food supply chains. / Output 3: Strengthened conditions for financing socially desirable and environmentally acceptable infrastructure. / Output 4: Strengthened capacity of government and private sector entities to implement legal, social and environmental reforms to support inclusive and sustainable growth. / Output 5: Better evidence collected and disseminated of priority policy needs and expectations for successful reform.

What is the context in which UK support is provided?
The need for more inclusive and sustainable economic growth in MENA countries / The wave of uprisings that swept across several countries in the Middle East and North Africa (MENA) in early 2011, and which became known as the ‘Arab Spring’, highlighted a number of underlying economic, political and social problems. Although the MENA region generated GDP growth of almost 5% a year over the decade 2000-2010, many countries were less successful in providing widespread economic opportunities for their people. / Unemployment has remained high in many of the countries of the region. Current unemployment rates are between 12-18% in Egypt, Tunisia and Jordan[1], compared to a global average unemployment rate of around 6%[2]. Unemployment is especially high among young people. According to the World Bank, average youth unemployment in the region is around 28%[3], and where young people do work, they are typically employed in low paid, low productivity jobs. / Unemployment among women is also a key concern. The unemployment rate for women in the region is approximately 21%, compared to 9% for men[4]. And despite the middle income status of MENA countries, poverty remains a significant challenge. Per recent data, more than 14% of the population live below $2 per day in Egypt and Morocco[5]. / Achieving more inclusive economic growth is therefore fundamental to sustaining successful political transition and meeting the needs of aspirant populations, particularly young people, in the ‘Arab Spring’ countries. / Key economic reform challenges in the ‘Arab Spring’ countries / The political changes brought about by the Arab Spring have created opportunities for addressing key economic and social challenges. There are several areas of reform that are important for generating more inclusive and more sustainable economic growth, including: / strengthening conditions for private sector development, particularly for SMEs. SMEs offer significant potential for employment creation in these countries but face constraints, including high regulatory barriers and lack of access to finance. / improving the functioning of agricultural markets by strengthening food production and ensuring more integrated agricultural supply chains. MENA countries import around 50% of their food consumption[6]. / upgrading infrastructure at national and local levels, including in transport, power and water. According to the World Bank, MENA countries overall need to invest between $75 - $100bn per year in infrastructure[7] to grow at previous rates and to boost competitiveness. / strengthening the ability to trade. MENA is one of the least integrated regions in the world, with a share of world non-oil exports that is under 1%. There is scope to increase growth and make it more inclusive by strengthening capacity to trade, especially of SMEs. / The UK’s role in support of economic reform in ‘Arab Spring’ countries / Despite the current opportunities countries such as Egypt, Morocco, Tunisia and Jordan face constraints in implementing key reform measures required. Aside from political constraints, there are also gaps in terms of the technical capacity and the financial resources needed. Challenging economic conditions following the Arab Spring, associated with declines in inward investment and tourism revenues, have made these constraints more binding in the short term. The UK, alongside the broader international community, has a role to play in supporting these countries in their reform efforts and in helping them to achieve greater social and economic inclusion. / Why the UK is supporting the EBRD / The amount of funding and technical expertise the UK can provide directly to support economic reform in ‘Arab Spring’ countries could not be expected, on its own, to deliver the changes on the scale required. More is likely to be achieved by working with and through other institutions that are better placed to channel more substantial financial and technical resources. The UK identified the EBRD as an institution through which it should channel support to the region for the following reasons: / The EBRD is expanding its geographical mandate and is a ‘new player’ in the region. The UK, including through the Deauville Partnership, has emphasised the value and importance of the EBRD becoming an additional form of support to the region, particularly given its specialised role of providing direct assistance for private sector development and its relevant experience of supporting economic transition in other contexts; / The EBRD is expected, in due course, to invest up to €2.5bn per year[8] in the region. This follows the full ratification of changes to its Articles and full country presence being established. To date, Morocco, Tunisia and Jordan have become countries of operation, and therefore have full access to the capital resources of the EBRD. The approval of Egypt as a county of operation has yet to happen. In the meantime, donor resources can enable the Bank to start providing technical assistance to businesses and public sector clients, and help prepare the ground for substantive investments. In addition to the MDA, the EBRD is drawing on grant inputs through other channels including direct contributions from the EU’s Neighbourhood Investment Fund and through EBRD’s own resources. The UK’s contribution to the MDA is therefore expected to help facilitate new assistance to the region. / By making a funding contribution to the EBRD for its new operations in SEMED, the UK expects to gain opportunities to work closely with the Bank to help shape its approaches in ways that address the fundamental challenges around economic and social exclusion in the region, including for youth and women, and that incorporate strong approaches to targeting and monitoring results.
[1] Source: Egypt 12.7% (2012); Tunisia 18.3% (2011); Jordan 12.2% (2012) – Unemployment rates, World Development Indicators, World Bank
[2] Source: Global Employment Trends 2014: Risk of a jobless recovery? International Labour Office, 2014
[3] Source: Global Employment Trends 2014: Risk of a jobless recovery? International Labour Office, 2014
[4] Source: Global Employment Trends 2014: Risk of a jobless recovery? International Labour Office, 2014
[5] Source: Egypt 15.4% (2008); Morocco 14% (2007 - % of population living below $2, World Development Indicators, World Bank
[6] Source: International Food Policy Research Institute: MENA Strategy (2010)
[7] Source: World Bank Institute 2011 (See https://wbi.worldbank.org/wbi/news/2011/05/20/addressing-critical-mena-infrastructure-gap-public-private-partnerships)
[8] Source: EBRD Board paper on the geographical expansion to SEMED. This paper refers to the Bank’s ability “to sustain over the medium term an additional level of annual business volume of up to € 2.5bn over and above the operational objectives set up in CRR4”. The CRR4 stands for Capital Resources Review (a medium term strategy of EBRD) which spans the years 2011-2015.

Section A: Detailed Output Scoring
Output 1: Strengthened ability of SMEs to grow sustainably
Output 1 score and performance description: / B – Outputs moderately did not meet expectation.
Progress against expected results: / Indicator Milestone 2013 Achieved 2013 / 1.1 Annual number of enterprises (of which majority female managed[9]) receiving business advice under Business Advisory Services (BAS) programme 80 (20) / Cumulative: 160 (40) Cumulative: 26 (2) / This is a material improvement on last year (when only 1 enterprise was receiving support). The proposal that was rejected by another donor in 2013 would have added 60 BAS clients. (Therefore, across SEMED more broadly there are 209 BAS clients of which 43 are majority female owned/managed.) / 1.2 Annual number of enterprises (of which majority female managed) receiving business advice under Enterprise Growth (EGP) programme 45 (12) / Cumulative: 45 (12) Cumulative: 23 (2) / Again this is a material improvement on last year when only 2 enterprises were receiving support, neither of which was female-owned. The proposal that was rejected by another MDA donor would have added 33 EGP clients. (Therefore, across SEMED there are 59 EGP clients of which 10 are majority female owned/managed.) / 1.3 Annual number of enterprises (of which majority female managed) financed directly under EBRD's Local Enterprise Facility (LEF) 20 (5) / Cumulative: 20 (5) Cumulative: 6 (0) / Last year, the MDA supported the setting up of LEF operations in SEMED and this year 6 new projects were signed by EBRD, there are 7 expected to be signed in 2014. / 1.4 Percentage of business advisory projects scoring as successful or highly successful 80% N/a / As was the case last year, it is too early for projects to have finished. EBRD to conduct a review in 2015. / General: Small Business Finance and Advisory Support / Failure to meet this log-frame indicator is due the fact that i) a donor vetoed a proposal that would have resulted in more SME clients being supported by the MDA and that ii) bilateral EU funding swept up a significant amount of SME clients that the MDA would otherwise have supported. Instead of working with EBRD to agree revised DFID log-frame indicators over 2013, it was decided to focus efforts on designing a donor-agreed Results Framework. Further detail is provided below. / Background: BAS, EGP and LEF make up EBRD’s service offering to SMEs and these are described below. This forms a large proportion of the activities funded under the MDA (circa 50%). The overall objective of the programme is “to support economic transition and to achieve enterprise change in viable SMEs. Specific objectives and expected impact on SMEs include: i) Enhanced competitiveness of assisted SMEs (as seen by increased exports, productivity and sales, new foreign contacts, new production line/technology, changes in product ranges and production processes); ii) Stimulated sectors with high growth potential (through disseminated best practices, shared successful models); iii) Strengthened and sustainable infrastructures of local business advisory services (as seen by increased supply of services, broadened range of services, improved quality, increased consolidation of the industry)”. / Output 1.1: Business Advisory Services (BAS) / Typically this service is offered to SMEs with less than 150 employees. Eligible SMEs receive a grant of up to 75% of the cost of the advisory service, capped at €10,000. This grant is wholly financed from the MDA. / Across SEMED at 31 December 2013, the average BAS grant ranged from €4,500 to €5,600 with an average share of 36%-42% provided by the SME. In most countries over 50% of assisted enterprises employed less than 50 people and at least 70% of assisted enterprises had not used external consultants in the past. / The number of SEMED enterprises received support under BAS is below the expected milestone as the MDA requires all donors to unanimously approve project proposals and in October 2013 one donor vetoed a project proposal which would have added 60 BAS clients[10]. If this proposal had been accepted the cumulative number of enterprises reached would have been over 80. / There were also delays with setting up operations due to the time spent on recruiting local BAS teams. Further turbulences and instabilities on the political front have had a negative impact on the economic situation reflecting the operational challenges of doing business against an uncertain political and economic backdrop in the SEMED region. / Furthermore, at the start of EBRD’s SEMED operations and due to delays with setting up the MDA, bilateral EU funding for SME support activities in Egypt, Tunisia and Morocco continued for longer than expected and consequently the MDA to date has only supported activities in Jordan. Therefore, when looking at EBRD’s activities in the SEMED region more broadly and including those activities funded through the EU, the figures are more impressive with 209 enterprises receiving support under BAS (of which 43 are majority female owned/managed enterprises). / Taking into consideration EBRD’s broader SEMED performance, failure to meet the log-frame milestone is due to an unrealistic milestone being set for the MDA. This was noted in the 2012 Annual Review, and considerable work has been done by donors and EBRD to revise targets for the log-frame over the course of year. The final revised donor-agreed Results Framework (see Section B; 1.1 for an overview) will provide updated figures on realistic expectations for the remainder of the year. / Output 1.2: Enterprise Growth Programme (EGP) / This service is offered to larger firms with between 150-500 employees. Eligible SMEs receive a grant towards the advisory services, capped at €50,000. As opposed to using local consultants, EGP assistance involves the provision of international, industry-specific, management expertise. / Across SEMED as at 31 December 2013, the average EGP project cost ranged from €7,500 to €9,800 with an average cost share of 10%-20% provided by the SME. The average number of staff in assisted enterprises was 250 people. / The number of enterprises receiving support under EGP is below expected milestones. As mentioned before, the main reason for this is the donor veto of a project proposal which would have added 33 EGP clients. If the proposal had been accepted the cumulative number of enterprises reached would have been more than 45. This activity was funded by the EBRD’s net income in the end. As before, failure to meet the log-frame milestone is due to the difficulty of managing the different donor objectives in multi-donor managed accounts and not an issue with EBRD performance in the region. A shared results framework across donors will help reduce the risk of individual donors vetoing activities. / EBRD’s broader SEMED performance is more impressive (59 enterprises receiving support under EGP of which 10 are supporting majority female owned/managed enterprises). / Output 1.3: Local Enterprise Facility (LEF) / This is a vehicle for EBRD investments in SMEs including the provision of pre and post investment support. In 2012, the MDA supported EBRD building on-the-ground capacity in SEMED with LEF dedicated bankers now posted in Amman, Cairo and Casablanca. / The 6 LEF investments (€23.3m of financing; employing 3,700 staff) signed by EBRD in 2013, is below the milestone. This continues to be the case when investments in the pipeline are taken into consideration (7 investments with a total of €38m expected to be signed in 2014). / The on-going expansion of LEF to SEMED has so far been very positive, and the only difficulty encountered by the EBRD team has concerned the struggle to identify from London a substantial number of local SMEs ready and willing to receive LEF financing. The Bank has recently approved € 5m from its net income to allow it to take greater risk and invest in companies that otherwise would have had difficulty to qualify for EBRD support. / The failure to meet the log-frame milestone is more to do with an unrealistic milestone being set for the MDA that did not reflect the difficulty of an organisation setting up new country operations. This will be rectified through the process of changing DFID’s log-frame to match the donor-agreed Results Framework. / Output 1.4: Percentage of business advisory projects scoring as successful or highly successful / As part of every consultancy assignment (under the BAS, EGP or LEF) EBRD ensures that the criteria for success are listed. This includes metrics like increases in turnover or profit margin etc. / As was the case last year, it is too early for projects to have finished and therefore to assess performance of EBRD’s services. As more projects under the SME support programmes are progressing towards completion, the EBRD will monitor the results at project level one year after project completion to assess impact and progress made. Information (in line with OECD DAC criteria) will be collected to assess project impact looking at an increase/decrease in turnover, number of employees, access to external finance and further use of consultancy services. Feedback on the achievement of the targets will be made available to donors in early 2015. / DFID conducted site visits of few clients under the BAS/EGP/LEF programmes as part of beneficiary feedback process. 3 BAS clients were visited in Jordan, 2 EGP clients were visited in Egypt, 1 LEF client visited in Jordan. See Figure 3 for details. As part of the beneficiary feedback, DFID re-evaluated its rationale for donor support for this activity including i) EBRD criteria for support ii) the broader market development impact of EBRD support to an individual firm and iii) the impact on job creation. DFID will continue to review the SBS programme over 2014 and in light of EBRD’s evaluation results in 2015. / The rationale for donor support is linked to the sustainability of EBRD interventions. In the case of EGP, for example, sustainability on the individual project level is built when an EGP project comes to successful closure and skills and knowledge have been transferred to the beneficiary. The increased competitiveness of EGP clients puts pressure on their peers, forcing them to improve their operations, hence having a demonstration effect at the sector level. Equally, managers of EGP beneficiary companies move on within an industry sector or the wider economy transferring their improved skill set further. Per EBRD, this is what has been observed on almost 2,000 EGP projects across 35 countries. In the case of BAS, a key element is the development of a sustainable infrastructure of local business advisory services, which contributes to the improved performance of the SME sector once EBRD exits a country. The BAS clients’ continued engagement of local consultants at their own cost after a project (over 50% on average do so within a year of project completion) EBRD would argue is a clear indication of improvement in markets’ sustainability. Finally, there is evidence that EBRD support contributes to greater access to finance, levering existing and future investments, and improvement of the business environment through policy dialogue. In relation to EBRD’s support to job creation, as observed on many projects in the SEMED region, labour is not a critical component in the cost structure. Therefore, increasing competitiveness does not directly imply a reduction in jobs. Furthermore, sustainable jobs can only be created by sustainable enterprises. / Recommendation: / DFID and EBRD should revise DFID’s log-frame for the remaining period of its support to the MDA in light of the new Results Framework (June 2014) / DFID and EBRD to review the SBS programme to ensure subsidy is continues to be targeted appropriately and is not excessive (December 2014) / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[9] Majority women-owned and/or women-managed” and all data is captured and reported accordingly
[10] DFID confirmed that the rationale for the rejection was not due to an issue with the quality of proposal.

Output 2: Strengthened agricultural productivity and improved food supply chains
Output 2 score and performance description: / B – Outputs moderately did not meet expectation.
Progress against expected results: / Indicator Milestone 2013 Achieved 2013 / 2.1 Annual number of agribusiness clients receiving EBRD assistance through donor-funded technical cooperation Annual: 10 / Cumulative: 20 Cumulative: 2 / As was the case last year, 2 agribusiness clients are receiving support in Jordan – the Zalloum Group (biscuits and canned food) and the Hammoudeh Group (vertical integration of bird supply chains). / 12 DCA projects have been launched across SEMED / 2.2 Percentage year-on-year increase in number of input suppliers to EBRD agribusiness clients 10% Not applicable / There is no evidence yet to suggest that agribusiness clients have increased their numbers of input suppliers. / 2.3 Percentage of projects with agribusiness clients scoring as successful or highly successful 80% 100% / Based on one completed project with Zalloum Group. / Output 2.1 Support to Agribusiness Clients under the Direct Company Assistance (DCA) Programme / The Bank has continued to work on the Direct Company Assistance (DCA) programme, an EGP-type programme addressing the needs of agribusiness SMEs. The overall objective of the programme is to provide technical assistance – targeting value chain inefficiencies – to selected agribusiness companies in SEMED to prepare them for EBRD financing. / To date, two projects have been started in Jordan, with one project completed as of December 2013. A further pipeline of up to two projects exists for H1 2014. The first project started in Jordan, with Universal Industries Co. (Zalloum Group), was aimed at increasing efficiency in production for their biscuits and canned foods factory, as well as providing guidance on product development and effective sales and marketing strategies for their biscuits. The project was completed in November 2013 after 11 visits from the consultants – a confectionary product development expert and a confectionary marketing expert – over a period of 18 months. The second client is Jordan Poultry Processing and Marketing Company, the programme is providing assistance to promote the vertical integration of their live bird production, focusing on bird nutrition, feed milling, transport, and direct retailing. To date there have been nine visits by the Senior Advisor, a veterinary poultry expert. / Work is expected to commence in Q1 2014 with Jordan Potato and Corn Chips Company (Mudieb Haddad Group), providing HR advisory to help the company achieve a structure that is transferrable across group companies. / Performance against the first indicator continues to be significantly below the milestone. As with output 1, bilateral EU funding for business support activities in Egypt, Tunisia and Morocco continued for longer than expected. Therefore, the MDA only funds DCA activities in Jordan. The DCA clients across SEMED are higher at 12. / Furthermore, pipeline development for the DCA programme has been challenging in 2013 as it has been hard to find clients that are both suitable for technical assistance inputs as well as for further financing. / EBRD is seeking to rectify this with a number of events planned in 2014 to increase the visibility of the programme in the region. / Finally, the failure to meet the log-frame milestone is due to an unrealistic milestone being set for the MDA that did not reflect the difficulty of an organisation setting up new country operations. This is not felt to be an issue with EBRD performance in the region and will be rectified through the process of changing DFID’s log-frame to match the donor-agreed Results Framework. / Output 2.2 Increase in number of input suppliers to EBRD agribusiness clients / This is not an indicator that is measured by EBRD. This is because it is very limiting as there a number of ways that performance across the agri-business sector could be assessed including through improvements in competitiveness etc. Therefore, this indicator will be removed from an assessment of agribusiness clients and instead the new proposed Results Framework looks at output indicators like increases in turnover or profit margins. / Output 2.3: Percentage of business advisory projects scoring as successful or highly successful / As mentioned before, as part of every consultancy assignment EBRD ensures that the criteria for success are listed. This includes metrics like increases in turnover or profit margin which are agreed by both the client and the consultant. / As was the case last year, it is too early for projects to have finished and therefore to assess performance of EBRD’s services. / DFID conducted a site visit of the one completed DCA project, Zalloum Group. The success of this DCA project was evident with the sale of biscuits in Jordan over the course of the programme more than doubling and per the client there is potential for sales to triple and even quadruple in the coming year. The increased turnover resulted also in better financial results not only for the biscuit factory but also for their vegetable processing plant, which is also part of Universal Industries Co. The focus on sales, product development, and marketing efforts were transplanted by the management on the vegetable processing plant with positive results. As mentioned earlier, DFID re-evaluated its rationale for donor support for this activity including i) EBRD criteria for support ii) the broader market development impact of EBRD support to an individual firm and iii) the impact on job creation. See earlier comments on the rationale for continued DFID support. DFID will continue to review the rationale for subsidy of clients in the DCA programme over 2014 and in light of EBRD’s evaluation results in 2015 looking at factors like contribution to food security, job creation etc. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Strengthened conditions for financing socially desirable and environmentally acceptable infrastructure
Output 3 score and performance description: / A+ – Outputs moderately exceeded expectation. / Progress against expected results: / Indicator Milestone 2013 Achieved 2013 / 3.1 Cumulative number of comprehensive PPP feasibility studies completed (of which lead to investment agreements) 5 (3) 15 (4) / As was the case last year, this does not necessarily relate to solely to PPP feasibility studies. Instead the Bank has used the MDA to carry out several preparatory studies for investments. / 3.2 Cumulative number of sub-sovereign investments in infrastructure resulting from EBRD technical cooperation 3 Covered above / 3.3 Percentage of studies and projects for which environmental, climate risk and social impact assessments completed according to best practice 100% 100% / Output 3.1 and 3.2: Number of feasibility studies completed and investment leveraged. / As was done in last year’s Annual Review and as previously agreed with EBRD, output 3.1 and 3.2 are interpreted as relating to all investment feasibility studies (and not just those that are PPP or infrastructure focused) in order to provide a more exhaustive picture of EBRD’s activities. To date, the MDA has funded 15 investment related feasibility studies. These have mainly been in the areas of infrastructure and access to finance. / As agreed with EBRD, highlighting sub-sovereign investment[11] leveraged in not helpful. Going forward, DFID will look at total investment leveraged. Of the 15 investment related feasibility studies funded by the MDA, 4 have resulted in €189m in follow-on investment from EBRD and are likely to contribute to a further €145m in further investment. / It is useful to note here that the revised Results Framework aims to further develop the indicators for this output by both explicitly referring to the value of investment leveraged[12] as well as discussing investments in terms of beneficiaries targeted (e.g. infrastructure users, energy capacity installed). The following two examples highlight the potential beneficiaries reached by MDA supported infrastructure investments: In Morocco the MDA has supported two infrastructure investments with the Office National de l’Électricité et de l’Eau Potable (ONEE), a state-owned utility company. One is for due diligence supporting the signing of a €60m loan with the company in March 2013. The loan will finance part of the final phase of the Programme d’Electrification Rurale Global and a pilot smart grid study to prepare for the deployment of smart metering and decentralised renewable energy generation. It is expected that the EBRD’s investment will provide electricity access to 1,234 remote villages impacting 650,000 people. The EBRD is also providing a €65m sovereign guaranteed loan to ONEE, to support the expansion of drinking water supply services in Morocco. The Bank’s support to ONEE will help ensure access to drinking water for over 480,000 people in rural communities. / The continued rationale for donor subsidy is that SEMED is a very difficult operating environment and EBRD are still expanding their operation into this area. However, DFID will aim to conduct reviews of a few investments over 2014 (and as part of the programme evaluation) in order to ensure that subsidy is targeted appropriately. / Output 3.3: Environmental, climate risk and social impact assessments / Output 3.3 is not a robust as it is a mandatory requirement for EBRD infrastructure projects to include environmental and social impact assessments. This was noted in the 2012 Annual Review. However, going forward as was agreed with other donors through the discussion on the Results Framework, this output will be re-drafted to shift the focus from “preparation” to “implementation”. / Recommendation / DFID and EBRD to review investments to ensure subsidy is targeted appropriately and not excessive (December 2014) / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[11] DFID will work with Policy Department and EBRD to assess if there is any continued benefit including another indicator to suggest the growing maturity of the sub-national government and some freedom of operation without sovereign guarantee.
[12] In addition to value of investment leveraged, DFID will assess to what extent it might also be possible to include a discussion on source of funding and terms of investment.

Output 4: Strengthened capacity of governments and private sector entities to implement legal, social and environmental reforms to support inclusive and sustainable growth
Output 4 score and performance description: / B – Output moderately did not meet expectation.
Progress against expected results: / Indicator Milestone 2013 Achieved 2013 / Annual number of sovereign clients receiving high quality advice from EBRD on legal, social or environmental reforms Annual: 10 / Cumulative: 20 Cumulative: 11 / Annual number of private sector clients receiving high quality advice from EBRD on social and environmental reforms Annual: 30 / Cumulative: 60 Not possible to aggregate. / Output 4.1: Number of sovereign client receiving high-quality advice / Progress against this milestone has been below target. / In 2013 there were two policy dialogue projects ongoing: secured transaction reforms in Morocco and local capital market development in SEMED. These projects currently involve 11 public sector entities. / Projects in the pipeline include, policy dialog work on derivatives in Morocco, private equity in Tunisia and a project on the Clearing & Settlement Depositary System for Government Securities is being discussed with the Central Bank of Egypt / The poor progress against milestones is due to the MDA resource being used to fund studies to help support EBRD’s expansion into SEMED as was always the intention. There have been over 19 projects which have related to assessments EBRD have done in order to support its various activities. For example, Country Law Assessments of Tunisia, Morocco, and Jordan, which analyse the state of legal transition in SEMED. The data collected is going to be used by the EBRD when preparing the country strategies for the three SEMED countries. In addition to being available to the public, the documents are being used when preparing strategic actions by the Legal Transition Team in the countries in question. / As was noted last year, the milestones for this output were unrealistic. Considerable work was done by EBRD on a revised Results Framework following donor feedback and this output will be replaced as part of the review of the DFID log-frame in light of the revised Results Framework. / In order to gauge quality of service, over 2013 each project that EBRD submits to donors for approval is now accompanied with a Result Matrix which defines the project’s main Outcome, Outcome Indicators, and Outputs. Outcome indicators of policy dialogue and capacity building projects are very varied but can include: acceptance by client of policy recommendations; enactment of a new law; number of trained judges, etc. As part of the new Results Framework, EBRD will now report on the percentage of projects having achieved (or on track to achieving) defined outcomes as per the respective Results Matrices. / Output 4.2: Number of private sector clients receiving high-quality advice / As was the case last year, progress against this output has been difficult to assess, partly due to lack of information on the nature of support provided to BAS or EGP clients. / There have been over 6 private sector clients that have received advice from EBRD on social and environmental reforms including and this is likely to increase significantly: / Sustainable Energy Finance Facilities (SEFFs): Under this initiative led by the EBRD, the Bank and other IFIs will extend credit lines to finance energy efficiency and sustainable energy investments in various businesses. No loan agreements have been signed yet, but this is expected to reach around 500 clients. / Launch of a financial product targeting women under the Microcredit, gender, and access to finance in Morocco / As was noted last year, the milestones for this output were unrealistic. Considerable work was done by EBRD on a revised Results Framework following donor feedback and this output will be replaced as part of the review of the DFID log-frame in light of the revised Results Framework. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 5: Better evidence collected and disseminated of priority policy needs and expectations for successful reform
Output 5 score and performance description: / A – Outputs met expectation.
Progress against expected results: / Indicator Milestone 2013 Achieved 2013 / Comprehensive 'Life in Transition' survey carried out across Egypt, Tunisia, Morocco and Jordan with full results published. Not applicable Not applicable / As noted in 2012, the study was rejected for funding by some donors to the Multi-Donor Account and is instead being funded from the Bank’s own resources. / Number of focus countries for which Business Environment and Enterprise Performance Surveys carried out and disseminated to practitioners Not applicable Not applicable / As noted in 2012, the study was rejected for funding by some donors to the Multi-Donor Account and is instead being funded from the Bank’s own resources. / Good quality environmental and social impact assessments and policy reviews completed Assessments completed for all four countries 3 / Assessments completed for Morocco, Tunisia and Jordan. Egypt assessment delayed due to political uncertainties. / The Environmental and Social Assessments for Morocco, Tunisia and Jordan have been completed. / The country-level assessments carried out for Morocco, Tunisia, and Jordan have identified the main environmental and social challenges for these countries, the relevant institutions and legislation related to environmental and social issues, and the gaps between environmental and social legislation in Morocco, Tunisia, and Jordan with the EBRD's Environmental and Social Policy and its Performance Requirements. / A Board-level decision has been made to postpone the initiation of the country assessment for Egypt until the relative political uncertainties in this country subside. / The 2012 Annual Review recommended the removal of this output and this will happen as part of the development of the new Results Framework. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / A number of changes were suggested in the 2012 Annual Review of changes to be made to the DFID log-frame. Instead of unilaterally discussing results framework with one donor, it was agreed to create a shared results framework with all the donors to the MDA. This shared Results Framework was approved in March 2014 during the annual meeting of donors to the MDA. / This Results Framework forms the first attempt by EBRD to collate results across its various technical co-operation contracts and it is a significant achievement. When the donors started with support to MDA, there were no results reporting in place. This has been a major shift (both culturally and in the way of thinking about results) for the Bank. Over the course of 2013, a significant amount of work has been done by EBRD on creating a Results Framework with MDA donors, with DFID providing significant technical input. / In addition, EBRD now prepare project-specific results matrices in advance of funding. Each results matrix reports on outputs and outcomes attributable to the funding and impact. Formerly, outputs (largely consultancy reports) were the end of the reporting line; no outcomes were reported. / The Results Framework then aims to aggregate up the outcomes of each individual results matrix. / The Bank is seeking to assess and improve the potential inclusion impact that its projects may have on groups such as women, young unemployed or communities in remote rural locations. On this basis, it has adopted a new methodology which has allowed the Bank to integrate a focus on social inclusion into its transition methodology. This represents a step change in how inclusion (including gender) is considered at the Bank as it has a direct effect on scorecard results. The UK has been pro-active in supporting the inclusion agenda including by recognizing it in the MAR Update. Major advances have been made in EBRD’s work on gender with the Strategic Gender Initiative making strong commitments. In addition to the Microfund for Women project in Jordan, the MDA has supported a number of projects with a gender component including research work on legal frameworks and access to finance, business development services in Egypt and gender audits of firms carried out by EBRD. DFID is further supporting this work by seconding a gender specialist to work part-time at the EBRD alongside Bank staff working on gender. / There are also potential challenges in ensuring that EBRD assistance to the region is focused on promoting economic and social inclusion. The UK believes that ensuring inclusive economic participation is an integral part of successful transition to functional market-based economies and is critical for the region. But there are on-going discussions taking place among EBRD members on how the Bank’s mandate to promote transition should be interpreted. / 1.2 Overall Output Score and Description: / A – Outputs met expectation. / 1.3 Direct feedback from beneficiaries / As part of the Annual Review, direct beneficiary feedback has been obtained and beneficiary site visits conducted. A summary of this is provided below. / Country Project Description Beneficiary / Client & Description Type of Review / Jordan Implementation of EBRD BAS in Jordan Mijana Restaurant and Café: Lebanese restaurant / EBRD support: ISO Food Safety System DFID confirmed that client satisfied with service provided by EBRD. / Jordan Implementation of EBRD BAS in Jordan Arab Technical Group: Heating, air-conditioning and ventilation company. EBRD support: Focused on getting certification. DFID reviewed operations of the client and confirmed that client satisfied with service provided by EBRD. / Regional -Jordan Local Enterprise Facility SEMED Expansion MicroFund for Women: Provision of finance for poor women EBRD support: The MDA supports strengthening institutional capacities for small business lending. EBRD have provided a $4m loan which will allow MFW to extend the remit of its lending to include loans for growing microfinance clients until these clients are eligible for full access to the commercial banking system. DFID reviewed operations of the client and interviewed a number of clients of the MicoFund. DFID confirmed that client satisfied with service provided by EBRD. / Regional - Jordan Direct company assistance for agribusiness companies Universal Industries Co. / Zalloum Group: Biscuits and canned foods factory. EBRD support: Project focused on production efficiencies and product development. DFID reviewed operations of the client and conducted a site visit. DFID confirmed that client satisfied with service provided by EBRD. / Regional - Egypt Implementation of EBRD EGP in Egypt, Morocco and Tunisia Mohm Furniture: Well-known brand in Egypt, producing office furniture for the last 30 years. EBRD support: Focused on a range of organisational areas to support increase in turnover. DFID reviewed operations of the client and conducted a site visit. DFID confirmed that client satisfied with service provided by EBRD. / Regional - Egypt Implementation of EBRD EGP in Egypt, Morocco and Tunisia Trust: Car seat manufacturer established in 1995 now making 1,000 seats a day. EBRD support: Support to increase sales, which would require an increase in workers. DFID reviewed operations of the client and conducted a site visit. DFID confirmed that client satisfied with service provided by EBRD. / Figure 2: Beneficiary feedback / A number of investment related projects are still at an early stage of implementation and therefore it is recommended that further beneficiary feedback be obtained over the course of 2014. / Informal feedback from countries has been gathered, through UK embassies, which has generally been welcoming of the EBRD’s new role in the region. / As projects supported by the MDA reach completion, beneficiary feedback will be received by the EBRD and reported. Beneficiary feedback will also be collected as part of the independent programme evaluation. / Recommendation: / DFID and EBRD should continue to ensure that mechanisms are in place (in terms of both identification and engagement) to factor beneficiary feedback into the final Project Completion Review and Independent Evaluation, specifically for those areas of EBRD activity that were not reviewed as part of the 2013 Annual Review (Ongoing)
1.4 Summary of overall progress / Summary of progress / The MDA was established in 2011, with the first technical co-operation projects approved for funding in February 2012. Since then EBRD have continued to make progress with disbursements. In 2013, 11 new projects were funded from the MDA taking the total to 40 projects at a total project value of €15.1m. / Initially MDA funds were used by the EBRD to scale up its presence in the region and the EBRD has made good progress in this with setting up offices, recruiting staff and commissioning studies to aid its understanding of the region. / One of the key features in 2013 has been the shift towards lending operations and policy dialogue. Unlike in 2012, when a large share of MDA resources used to initiate market demand studies and sectoral assessments, increased funding has been allocated to prepare and implement investment projects. This trend suggests that the Bank has gained sufficient understanding of local markets - also as a result of donor-funded studies and analysis – and is now ready to move to the final phase of its expansion to SEMED, i.e. full-scale operations. / The MDA is increasingly supporting EBRD’s operational activities in the region. The MDA has been successful in supporting EBRD increase its SME clients in the region, through the roll out of BAS, EGP and LEF services. The MDA has also supported investments made by EBRD in infrastructure and the extending of financial services across the region. The MDA has also supported a number of policy dialogue projects with the public sector across the region. Stakeholders, including governments in the region, have welcomed the new role the EBRD is playing, supported by the UK and other donors. / Some logframe milestones have been unrealistic for the programme, and this is reasonable given the lack of evidence at programme inception of what the EBRD could realistically be expected to deliver in the new region and by when. Furthermore, there have been instances of donors vetoing specific project proposals put to the MDA. As mentioned earlier, the delivery of a shared Results Framework for the MDA was a major success for EBRD and will make the monitoring of results much clearer and better ensure both EBRD and all donors are working to the same objectives. / Source of funds / As mentioned in the 2012 Annual Review, some logframe deliverables have been supported by other donors or funding sources rather than the MDA because such funding (e.g. from the EU) has sustained activity for longer than originally expected, or because other donors to the MDA have rejected relevant activities and therefore EBRD has funded the activity from its own resources. / EBRD has been responsive to requests by donors (and a recommendation in DFID’s 2012 Annual Review) to put in place clearer arrangements to decide which projects should be funded from which funding sources and, where possible, to encourage co-financing between instruments. A concrete proposal was presented to donors in 2013. / Over the course of 2013, some donors have also requested that clarity be provided by EBRD on when it will use the Bank’s own financial resources to fund projects. This would not only further leverage donor resources for activities in SEMED, it would also give donors clarity on the grant funds available in SEMED. / Deauville IFI Platform / The secretariat chairmanship for the Deauville Partnership IFI Coordination Platform is currently with the EBRD. The UK will continue to support EBRD in making the most of this role. / Recommendation: / DFID and EBRD to work with other donors to provide clarity on when and how EBRD’s net income (the Shareholder Special Fund) will be used to provide grant funds to SEMED (Summer 2014)
1.5 Key challenges / Specifying results / There are challenges in specifying the expected results from the programme as EBRD is new to the region, the UK is contributing to a multi-donor instrument with some differences in donor preferences, and that the EBRD is in the early stages of strengthening its attention to results. Furthermore, specifying results are further complicated by the fact that multiple funding sources sometimes contribute to a project, therefore making it harder to associate results with the MDA. The Results Framework is an important first step in improving the results reporting. However, DFID will continue to provide advisory inputs to support EBRD in strengthening this. / Recommendation: / DFID should continue to provide advisory inputs to the EBRD’s efforts in strengthening approaches to results and consideration of social inclusion including gender (Ongoing)
1.6 Annual Outcome Assessment / Indicator Milestone 2013 Milestone 2014 / Outcome 1: £500m of total annual EBRD investments, linked to technical cooperation, in the four SEMED countries by 2014 £300m (c.€360m) £500m (c.€600m) / Outcome 3: A cumulative increase of £400m of Public-Private Partnership (PPP) investments in infrastructure improvements as a result of donor-funded technical cooperation from the EBRD; £240m (c.€290m) £400m (c.€480m) / Outcome 2: A total increase in employment of 4,250 in businesses that have received direct financial and technical assistance from the EBRD by 2014, including an additional 2,125 women employed; 2000 (1000) 4250 (2125) / Outcome 4: Significant legal, social and environmental policy reforms to promote more inclusive and sustainable growth, made by at least 6 public sector and 18 private sector clients. 40% 60% / Outcome 1: EBRD investments supported by the MDA in 2013 totalled €224m at the end of 2013. This was made up of signed investments of €189m and investments about to be signed of €35m. This is below the 2013 milestone of €360m. It is anticipated that the 2014 milestone will be met as a further €411m of EBRD investments are planned during 2014, taking the total to €635m. / Outcome 3: As discussed with DFID colleagues and agreed with EBRD during 2013, this outcome was always intended to capture wider investment leveraged (beyond EBRD) and the wording is currently unclear. Furthermore, as mentioned previously the distinction between PPP and non-PPP investments is not a key feature of this programme. / At 31 December 2013, there were no non-EBRD investments as a result of MDA support in 2013. However, non-EBRD investments about to be signed totalled €110m. This is still below the 2013 milestone of €290m. However, it is anticipated that the 2014 milestone will be met as a further €1,029m of non-EBRD investments are planned during 2014, taking the total to €1,139m. / In summary, it is anticipated that the total investment leveraged by the MDA (EBRD and non-EBRD resources) will be around €1.77bn, which is in excess of the €1.1bn target for the programme. This is on the assumption that nothing drops from the investment pipeline and that MDA donors approve funding for projects. / Outcome 2: It is too early to identify and assess changes in employment that have resulted from direct donor-funded EBRD assistance to businesses / Over 2014, DFID will aim to work with EBRD to establish an estimation of jobs from DFID’s support the MDA. Both in terms of “directly” created jobs (i.e. the number of real people taken on by firms) and “indirectly” created jobs (i.e., those that are not directly observable but are created usually through the provision of finance and are estimable based on a formula). / Outcome 4: It is too early to identify the percentage of sovereign and private sector clients implementing legal, social and environmental policy reforms advised by EBRD. / Recommendation: / DFID and EBRD to work together to establish a formula for the estimation of jobs created as a result of MDA provided support (Summer 2014)

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Disbursements have been made to the EBRD’s MDA according to schedule. As at December 2013, donor pledges to the MDA had reached €22.8m. Total projects approved by the donors of the MDA are €15.1. Therefore, funds available in the MDA for new projects total circa €7.2m. / The breakdown of below demonstrates that very few projects are complete and the majority are still disbursing. Per EBRD, total cash disbursements on MDA projects totalled € 4m. This appears reasonable given that the majority of MDA projects are multi-year consultancy contracts payable only on completion. / Figure 3: MDA projects based on current state / Recommendation / DFID to consider a no-cost extension for the programme as the majority of the projects are due to complete post the period of DFID’s 3-year programme. This will allow any subsequent development results to be accounted for. (June 2014) / 2.2 Key cost drivers / The key cost drivers are: / The types of projects that are supported through the Multi-Donor Account and the kinds of consultant expertise required – some being more expensive than others. / The balance between the use of local staff and consultants and London-based (or international) staff and consultants. The latter are typically more expensive. / The extent of other costs incurred, including travel and security costs. / 2.3 Is the project on-track against original timescale: Y / Whilst the EBRD has experienced some delays, and there has been less than expected progress against some logframe indicators, the EBRD has made impressive progress in establishing its regional presence and mobilising assistance. Many of the programme targets remain realistic although, as noted above, some adjustments in some areas are needed which will be done as part of the review of the log-frame.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There are some changes in the evidence on the kinds of activities the EBRD can support in the region, resulting from the evolving expansion of the EBRD into the region. It is now somewhat clearer what support the EBRD can provide and the timeframes for doing so. This information should be used to reconsider the logframe, milestones and targets. / Where an evaluation is planned what progress has been made? / DFID have decided to delay this to January – March 2015. After discussion with EBRD, it was felt that this was prudent given that none of the MDA funded projects (both investment and non-investment related) were complete. Therefore, delaying the evaluation allows DFID to ensure that it is reviewing a better representation of completed projects.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The risk level for the programme is still considered to be medium. / Delays in implementation of technical assistance projects. The EBRD could experience further delays in implementation of some activities, for instance due to delays in recruitment or further problems with consultant performance. / EBRD assistance not sufficiently focused on economic and social inclusion priorities. There are risks, particularly with the pressure to implement quickly, that EBRD technical assistance and investments will not be targeted to produce outcomes that enable full economic participation, including for women and young people. Such focus could also be affected by board level discussions on the EBRD’s mandate. The DFID secondment to the EBRD gender team would go some way to alleviating this. / Lack of coordination. There remain risks around lack of coordination of EBRD assistance with that of other IFIs and donors, although the EBRD has played a strong role in the Deauville Partnership and will continue to do so through its secretariat role for the Deauville IFI Co-ordination platform. / Delays in full regional expansion. EBRD’s ability to follow-up on technical cooperation activities with investments, and hence the outcomes of the MDA, will be constrained if there are further delays to Egypt becoming a country of operation. / Deterioration in SEMED country conditions. Deterioration or lack of progress in building political conditions for economic reform in countries could limit the impact of the EBRD. The EBRD has demonstrated, however, its ability to operate with a range of clients in countries notwithstanding problems with the political and policy environments.
Risk of funds not being used as intended / The risks of funds not being used as intended are considered to be low, as EBRD has good due diligence measures in place at project level and technical cooperation projects are well supervised by the EBRD donor co-financing unit. / 4.4 Climate and Environment Risk / Climate and environment risks remain medium. / The programme is funding technical assistance linked to investments in areas that pose environmental and climate risks: infrastructure development, business growth. Environment and climate assessments are routinely carried out to Bank standards and the process was previously assessed by a DFID climate adviser as being robust. / In several cases, EBRD activities are aimed at reducing risks of climate change and at promoting environmental sustainability. For instance, with MDA funds, the Bank is: advising public and private clients in Morocco on improving energy efficiency, carrying out preparatory work for a new regional energy efficiency fund, and providing technical assistance for better management of scarce water resources in Jordan.

5. Value for Money
5.1 Performance on VfM measures / Two key value for money measures were identified for this programme: / Cost per job. Given lack of evidence collected by the programme to date it is not possible to assess value for money in terms of the cost of jobs created as a result of direct, donor-funded, EBRD assistance to businesses. / Investments leveraged. A total of €334m of EBRD investments are being initiated or are in the pipeline as a result of technical assistance supported by the MDA. The UK can claim that its contribution to the MDA has leveraged at least 26% of this investment value, representing a ratio to contribution of 15:1. Whilst this is significantly below the leverage ratio expected for the lifetime of the programme of 47:1, the current ratio is an underestimate and likely to grow significantly over time. / 5.2 Commercial Improvement and Value for Money / EBRD’s procurement of commercial services, including consultancy support, is still considered to be acceptable. / 5.3 Role of project partners / The UK is the largest bilateral donor to the MDA, but in total there are 9 donors to the Account. This helps to ensure that the UK’s resources are combined with those of others to support a significant scale of activities, outputs and outcomes. / There are also challenges in contributing to a MDA alongside a significant number of other donors, particularly given the scope for individual donors to veto individual project proposals with a value greater than €150,000. Experience with the MDA so far has demonstrated the need for a common understanding of priorities among donors. As mentioned earlier, the Shared Results Framework will prove a useful tool for ensuring better agreement between EBRD and donors on critical results that should be targeted. / 5.4 Does the project still represent Value for Money : Y / Even though it has not been possible yet to fully assess the value for money being realised through the programme, it is clear that there is a lot being achieved in terms of investments being leveraged. Further assessment is needed in due course of the impact of such investments, and technical assistance activities, on jobs and economic and social inclusion. / 5.5 If not, what action will you take? N/A

6. Conditionality
6.1 Update on specific conditions: N/A

7. Conclusions and actions
The UK’s £5m contribution to the EBRD’s Multi-Donor Account for technical cooperation is continuing to enable a key institution with experience of promoting transition, a focus on private sector development, and potentially significant resources to invest, to start operating in reforming countries in the MENA region. The EBRD has established a strong presence in the region and, with UK and other donor funds, has initiated a number of worthwhile technical cooperation activities. A number of investment projects have been established by the Bank. / Some logframe milestones have been unrealistic for the programme, and this reasonable given the lack of evidence at programme inception of what the EBRD could realistically be expected to deliver in the new region and by when. The creation of a Shared Results Framework for the MDA is a major success for EBRD and will make the monitoring of results much clearer and ensure both EBRD and all donors will be working to the same objectives. / There are medium risks to future delivery, including risks around country conditions, delays in full regional expansion, further implementation delays, lack of focus on economic inclusion as a transition priority, and possible lack of donor coordination in country. These risks will require monitoring and management (including through the actions below). / The key actions arising from the review are: / DFID and EBRD should revise DFID's log-frame for the remaining period of its support to the MDA in light of the new Results Framework (June 2014) / DFID and EBRD to review the SBS programme to ensure subsidy is continues to be targeted appropriately and is not excessive (December 2014) / DFID and EBRD to review investments to ensure subsidy is targeted appropriately and not excessive (December 2014) / DFID and EBRD should continue to ensure that mechanisms are in place (in terms of both identification and engagement) to factor beneficiary feedback into the final Project Completion Review and evaluation, specifically for those areas of EBRD activity that were not reviewed as part of the 2013 Annual Review. (Ongoing) / DFID should continue to provide advisory inputs to the EBRD’s efforts in strengthening approaches to results. (Ongoing) / DFID and EBRD to work with other donors to provide clarity on how EBRD’s net income (the Shareholder Special Fund) will be used. (Summer 2014) / DFID and EBRD to work together to establish a formula for the estimation of jobs created as a result of MDA provided support. (Summer 2014) / DFID to consider a no-cost extension for the programme as the majority of the projects are due to complete post the period of DFID's 3-year programme. This will allow any subsequent development results to be accounted for (June 2014)

8. Review Process
The review was carried out by the lead adviser for the programme, with inputs from other regional advisers in DFID (results and evaluation, economist and social development), UK staff in country, and UK staff at the EBRD. / The review involved consideration of the EBRD’s two semi-Annual reports for 2013 (December 2013 and June 2013) and consultation with EBRD staff. The review involved a number of site visits in Jordan and Egypt in order to obtain beneficiary feedback. / A non-MENAD economist provided an independent review of the final report.