Business Case

Summary Sheet

Title: Building Core Systems in the Government of Sierra Leone
Project Purpose: To improve core systems in public financial management, revenue and procurement to underpin sustained poverty reduction and economic development.
Programme Value: £25 million		Country/ Region: Sierra Leone
Senior Responsible Owner: Sarah Somoudi
Project Code:	Start Date: 01 Jan 2016	End Date: 31 Dec 2017
Overall programme risk rating:	High
Quest Number:

Intervention Summary (2 Pages)

What support will the UK provide?

The capability of government to raise domestic revenue, formulate and execute sound budgets, spend public money wisely and accountably, including in procuring goods and services, are all essential building blocks underpinning sustained poverty reduction and broad-based economic development. Commitment and effort are required over several years to take the necessary actions, tackling weaknesses and establishing robust policy, systems and practice.

The Building Core Systems programme is the next phase of assistance from the UK to help the Government of Sierra Leone take forward this agenda.

DFID will provide up to £25 million of support to the Government of Sierra Leone in 2016 and 2017. This will be made up of: up to £10 million a year of performance-based financing earmarked for spending on health workers’ salaries (HWS); up to £2 million a year for technical assistance.  A further £0.5 million a year will be used to fund diagnostics and monitoring activities, including a Public Expenditure and Financial Accountability (PEFA) assessment.The approach is in line with DFID’s very latest thinking on provision of financial aid[1].
[1] THE FUTURE OBJECTIVES AND ROLE OF FINANCIAL AID. Chief Economist’s Office, September 2015.

What are the main programme activities?

Policy dialogue with Government focussing on the ‘core systems improvement’ agenda, supported with performance-based funding. DFID and three other development partners (DPs, the World Bank, the African Development Bank and the EU) will work with the Government of Sierra Leone (GoSL) to identify and agree priority actions to build the systems, improve the practices and tackle the priority reforms which are essential for Sierra Leone’s continued development. In this phase, DFID’s engagement will focus in four areas: revenue and tax collection; transparency and value for money in procurement practices; budget credibility and execution; and management of the wage bill. These areas are closely aligned with the priorities of the other DPs.

Assistance will be triggered by the achievement of agreed milestones, and it will be earmarked against HWS. Each milestone is independent and achievement of the agreed target triggers disbursement of the funding attached to it. The milestones will be output-based and under the control of the Ministry of Finance and Economic Development (MOFED), National Revenue Authority (NRA) and the National Public Procurement Authority (NPPA).

Technical assistance directly linked to the specific milestones. The UK is providing substantial technical assistance under existing programmes on domestic revenue and on public financial management. TA provided under this intervention will be focused on procurement, wage bill and payroll management and budget execution.

Short term, diagnostic and monitoring support. This will be used to fund diagnostic and monitoring reports, including a PEFA.

Why is UK support required?

Sierra Leone is one of the poorest countries in the world. Depending solely on domestically generated revenue will mean that it takes an unacceptably long time for its people to escape poverty. In the last couple of years, Sierra Leone has been hit by the crises of the Ebola outbreak and cessation of iron ore production following the collapse of the international price. The economy has contracted, reducing government revenue, while demands for spending remain high.

Poverty rates remain high and human development outcomes are low: From a very low base, Sierra Leone achieved significant improvements in its Human Development Index (HDI) score between 2000 and 2011. However, in 2014 Sierra Leone was still ranked 183 out of 187 countries[[1]]. It has the lowest life expectancy in the world[[2]].
[[1]] Human Development Report 2014, based on 2013 data
[[2]] World Health Organisation, World Health Statistics 2014

The UK has been working with Sierra Leone for several years to address weaknesses in core systems, recognising that these are critical in laying the foundation for Sierra Leone’s development and eventual exit from aid. Continued efforts are required to bring policy, systems and practice to an adequate standard.

What are the expected results?

The project impact will be accelerated development. The project outcome is strengthened core systems and improved practice.

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

The project is consistent with the approach approved by the Secretary of State in July 2015. It directly addresses goals 2 and 3 of the DFID Strategic Development Plan and contributes towards the achievement of Sustainable Development Goal 8. The findings of DFID Sierra Leone’s Inclusive Growth Diagnostic (IGD) emphasised the need for effective public financial management to support economic development.

What are the key risks to the success of the programme?

Acheivement of the objectives of the programme depends on GoSL commitment to taking the necessary action, and sustaining the momentum in the face of resistance from those who oppose change. Progress has been mixed, with some good progress in some areas and weaker progress in others. Ebola has tended to stall progress, and momentum needs to be re-established.

The GoSL must maintain macroeconomic stability, indicated by remaining on track with the IMF Extended Credit Facility Programme (ECF). If the Programme does slip off track, for example, if the debt limits are breached, we may suspend our financial aid in line with the suspension of the ECF.

Strategic Case

Context and Need for Intervention

The UK is proposing to provide funding to GoSL in order to i) relieve pressure on the national budget; ii) incentivise core systems strengthening; and iii) maintain policy dialogue with the GoSL. The strategic case will explain the context behind these three objectives and hence explain why the intervention is required.

Sierra Leone is one of the poorest countries in the world and has been hit by the crises of the Ebola outbreak and cessation of iron ore production. Sierra Leone was the second fastest growing economy in the world in 2013 with robust GDP growth in real terms during the first half of 2014. However, the economy was hit first by falling iron ore prices in late 2013, and this was followed by the outbreak of Ebola in May 2014. These crises have had a major impact, severely reducing GDP and government revenues.The economy is projected to contract by 21.5% in 2015[2].
[2] Projection from the IMF Mission in September 2015.

Poverty rates remain high and human development outcomes are low. From a very low base, Sierra Leone achieved significant improvements in its Human Development Index (HDI) score between 2000 and 2011. However the Ebola crisis is likely to have reversed some of these gains and in 2014 Sierra Leone was still ranked 183 out of 187 countries[[1]]. It has the lowest life expectancy in the world[[2]].
[[1]] Human Development Report 2014, based on 2013 data
[[2]] World Health Organisation, World Health Statistics 2014

Expenditure needs outstrip domestic revenue capacity. For example, in 2014 Sierra Leone spent $48 million on health, or $7.95 per capita. DFID estimates that for the health sector to adequately provide a package of essential services, around $25 per capita should be spent per year[3]. This would require a further $103 million.
[3] This is a broad estimate made by in-country experts. Figures are quoted in US Dollars.

Following the Ebola crisis, DFID is changing the way it does business with Sierra Leone, encouraging the GoSL to demonstrate commitment to results and progress more frequently. We are pushing for rapid and real change and are tracking our funds very closely. One example of this approach is our work with the President’s Delivery Team which is implementing the Ebola recovery plan. Initial evidence from the 9 month recovery planning and implementation phase is that the Delivery Team is functional; driving a focus on results; and that there is strong Presidential buy-in for improved public service delivery. Our Building Core Systems Programme will follow this approach by being 100% performance based and earmarking funds. This is also in line with the very latest thinking in DFID on delivering financial aid[4].
[4] THE FUTURE OBJECTIVES AND ROLE OF FINANCIAL AID. Chief Economist’s Office, September 2015.

The UK has been working with the Government of Sierra Leone for several years to build core systems and the new approach will build on this. Our work has included substantial technical assistance programmes in the National Revenue Authority (NRA), Audit Service Sierra Leone (ASSL) and other key PFM functions. The DFID Sierra Leone portfolio is now being redesigned with a sharper focus on strengthening service delivery results in basic services and core systems in economic development. In supporting GoSL core systems, financial aid will be critical to ensure that the underlying systemic issues are addressed over the coming two years, so that the GoSL can increasingly absorb international aid and better deploy its own revenues. This fits with the trend in some DFID countries which are moving from directly financing service delivery to supporting government capability and accountability. It involves not just tackling the legislation and systems but also the practice and culture.

UK intervention to improve core systems will mean Sierra Leone is better able to respond to future crises. It should be noted that this was the largest Ebola outbreak on record and arguably would have overwhelmed governments anywhere, not least in Sierra Leone which is a fragile state suffering from weak institutional capacity. However, stronger systems will reduce the role DPs need to play in future crises. The UK stepped in and invested approximately £427 million to arrest the spread of the outbreak of Ebola and address the immediate social and economic effects. Furthermore, commitments of £240 million have been made by the UK for the next two years for rebuilding and recovery.The Ministry of Health and Sanitation (MOHS) was slow to respond to the Ebola crisis and the Auditor General’s audit report on the use of Ebola Funds released in December 2014 uncovered inefficiencies in the MOHS and in particular, a lack of proper documentation around procurement. This lack of supporting documentation is a symptom of what the DFID Sierra Leone IGD describes as “the informality of government operations”. These weaknesses in governance and institutions significantly contributed to delays in establishing a robust government-led response.

There have been some improvements in Public Financial Management (PFM) over the recent decade and areas of GoSL commitment but there are still areas of significant concern. The figure below shows results from the most recent three PEFA analyses (the 2014 PEFA used data from 2012 and earlier). The results show a declining trend in budget credibility, which includes both revenue and expenditure outturn compared to the budget as well as composition of outturn compared to the budget. The 2011 Fiduciary Risk Assessment (FRA) also identified budget credibility as the weakest point in the PFM system[5] and the draft 2015 FRA confirms the same. This area has therefore been identified by DPs as an area of focus for policy dialogue over the short and medium term. Improvements were made in the areas of predictability and control in budget execution; and external scrutiny and audit. Specific areas of improvement were legislative scrutiny of external audit reports scope; and nature and follow-up of external audit. A major breakthrough was in 2007/8 when, after the UK and other donors withheld budget support payments, the audit report was made public and public hearings of the Public Accounts Committee (PAC) in Parliament were introduced, allowing the clearance of the long backlog of reports.
[5] The FRA says: One of the most significant areas of fiduciary risk in Sierra Leone is the credibility of the budget, which is a fundamental component of any PFM system. A lack of budget credibility undermines the entire PFM system, reducing the effectiveness of comprehensiveness and transparency, or a strong budget cycle.

Average Score

GoSL has shown significant commitment to improving revenue collection as evidenced by recent commitments to the IMF and demonstrated results in this area: for example, the GoSL met its 2014 revenue collection target as specified by the IMF (after accounting for the impact of the two crises) and within the category of predictability and control in budget execution in the PEFA analyses the improvements came from tax collection indicators. Also within this PEFA category, effectiveness of payroll controls and transparency, competition and complaints mechanisms in procurement showed no overall improvement between 2007 and 2012. Results from recent DP budget support Progress Assessment Framework (PAF) reviews have marked out the areas of procurement and payroll as two main areas of concern where additional effort is required to facilitate improvement.

The GoSL raised public sector wages in 2015, although the rise was lower than set out in the Medium Term Wage Policy due to the decline in revenues following the crises and the rise was minor in real terms. It is estimated that the wage bill will accounted for up to 74% of total domestic revenue in 2015 (excluding grants). In February 2015, an IMF review stated that “the macroeconomic assumptions underpinning the medium-term wage policy strategy completed in late 2014 are no longer sustainable as they were prepared before the Ebola outbreak and the recent crisis in the iron ore sector”. GoSL has agreed to update the assumptions and adopt a revised strategy. GoSL has also begun to implement policy in the direction of reducing the wage bill including imposing a wage freeze for the civil service. In conclusion, considering the limited fiscal space, there is serious need for reform in the management of the payroll. Encouragingly, GoSL appear to be willing to reform and indeed have already begun to make changes in this area and requested DFID support in doing so. The IMF are working with us and GoSL to this end.

Sierra Leone’s domestic revenue mobilisation performance is weak compared to other West African economies, but as stated in paragraph 9, commitment to reform is good. NRA reports show the revenue to GDP ratio in Sierra Leone has varied between 10 and 15% since 2001. NRA’s last published revenue to GDP ratio (2013) was 12.8%. The revenue to GDP ratios in Cote d’Ivoire, Senegal and Liberia are approximately 16%, 20% and 26% respectively and Sub-Saharan Africa as a whole averages around 22%[6].
[6] World Bank, 2012.

In summary, key areas where improvements in core systems and practices are required are i) budget credibility, ii) wage bill and payroll control; iii) public procurement practices and iv) revenue mobilisation. Other areas of the DFID portfolio and other DPs are already addressing some of these areas. We expect to provide TA to help with procurement, wage bill and payroll control and budget credibility. We are liaising with the other DPs to ensure that each TA programme is complementary and works towards common goals. On revenue, DFID’s new programme implemented by ASI, Revenue for Prosperity (R4P), commenced in October 2015.

Commitment to the Partnership Principles

Financial aid will only be disbursed if the GoSL demonstrates sufficient commitment to the Partnership Principles. DFID Sierra Leone monitors these on an ongoing basis, updating the document and discussing the conclusion with GoSL. The most recent update took place in September 2015. The September 2015 assessment confirmed credible commitment on the part of GoSL across each principle.

With respect to Partnership Principle 1, Poverty reduction and the MDGs, GoSL was assessed as showing highly credible commitment with a flat direction of travel. 69% of discretionary spending in the 2015 budget was allocated to poverty reduction and the GoSL remains on track with its IMF programme. The Ebola crisis and iron ore price shock mean that Government will need to make some difficult spending choices to maintain macroeconomic stability and continue to spend on poverty reduction. It will be important that Sierra Leone stays on track with the IMF programme; the UK and other DPs attach significant importance to this.

With respect to Partnership Principle 2, Respecting human rights and other international obligations, GoSL are assessed as displaying medium level commitment with a flat direction of travel. Emergency powers assumed to combat Ebola were used responsibly and proportionately. However, there is some concern amongst NGOs and CSOs about their space to operate.

Commitment levels are also medium with respect to Partnership Principle 3, Strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption, and the direction of travel is flat. The assessment finds that fiduciary and corruption risks remain high; core systems are weak in this regard. This is evidenced by the disappointing audit report into the use of Ebola funds released by the Auditor General in December 2015. That said, GoSL was assessed as demonstrating a credible commitment to making further progress in financial management and accountability. Evidence for this assessment includes the Auditor General issuing a ‘qualified’ opinion on the 2013 public accounts, (an improvement over the opinion on the 2011 and 2012 accounts); and the fact that the GoSL did not suppress or delay the audit findings on Ebola funds. The Minister of Finance, along with the President and Central Bank Governor, played pivotal roles in identifying remedial action in the banking sector and NRA.

A medium level of commitment was also concluded for the 4th Partnership Principle: Strengthening domestic accountability. The press and civil society benefit from a degree of freedom, despite recent indications of increased government intolerance to public criticism. After a long process, the Government secured accreditation to the Extractive Industries Transparency Initiative in April 2014 and has subsequently published further information in that sector (linked to budget support targets). The findings of the Auditor General’s report and hearings of the PAC continue to be made public despite increasingly sharp recommendations and they have provoked lively public debate, especially in response to the management of Ebola funds. Civil society groups are increasingly involved in and engaged with budget processes.

Consequences of not intervening

The case for a new programme rests on whether this type of programme is the most effective way to achieve important development progress and the impact it will have on our relationship with government and the programmes of other DPs. General budget support has provided the main platform for dialogue with government on critical reforms, primarily essential economic policy measures and those to build accountability (public financial management, transparency in procurement processes and adherence to the rules). The actions to release funds have increasingly centred on these, with DPs pressing Government on critical reforms. To withdraw from financial aid would likely mean losing our voice in policy discussions, or at least the strength of our influence would be significantly weakened.

The IMF reported in February that the GoSL has become more dependent on donor grants, with grants as a percentage of government revenues rising from 19.4% in 2013 to an estimated 32.9% in 2015 due to Ebola and the iron ore price slump, before dropping back to 29.4% in 2017. Not intervening would reduce the overall revenue available to GoSL and hence reduce the quality of service delivery, negatively impacting the people of Sierra Leone. It would also mean foregoing the multiplier effect we hope to achieve from intervening whereby we trigger improvements in core systems and practices and through this channel generate more GoSL revenue. Strengthening core systems and practices is also important in a fragile state such as Sierra Leone in order to improve resilience of the state to absorb shocks. Intervening with a financial aid instrument centred on improving MOFED systems will support our “Resilient Zero” programme which focuses on institution strengthening, predominantly the public health system, enabling Sierra Leone to manage any future outbreak of Ebola. Not intervening would undermine these efforts because the system should be strengthend as a whole and this would leave Sierra Leone in a more vulnerable position.

There will also be indirect effects. As DFID has taken a leading role in budget support over many years, globally and in Sierra Leone, DFID withdrawing entirely will be seen as a strong signal that we have lost confidence in the instrument, and may trigger others withdrawing.
Due Regard to Gender

Although the intervention is unlikely to specifically target women and girls through its areas of focus, there will be differential impacts (both intended and otherwise) of most public policy reform (and implementation approaches) on different groups. We will ensure that, where appropriate, technical advice and policy analysis is informed by an understanding of how policy choices affect equity and inclusion broadly (including but not limited to gender) and seek to ensure that monitoring systems reflect this – for example through monitoring the second partnership principle relating to human rights.

How the programme fits with the country programme objectives

The SoS has provided a steer on the priorities following our submission on the scale of the UK pledge for New York. The SoS made it clear in approving the pledge that it is to ‘be explicit that it is in response to GoSL committing to a new way of doing business, with a strong focus on delivery’. The UK pledge, including this project, is grounded in the context of Sierra Leone’s recovery from Ebola. DFID and Sierra Leone’s objective of reaching and maintaining a “resilient zero” (cases of Ebola) and kick-starting Sierra Leone’s economic recovery are central. To this end financial aid to Sierra Leone will be essential as it is expected to result in stronger core systems. This will open up more fiscal space for the GoSL to deliver on its commitments with less reliance on international aid or taking on expensive debt.

Partners in delivery of financial aid and policy dialogue

The EU, AfDB and WB all provide financial aid to GoSL and the four DPs together (i.e. including DFID) make up the multi donor budget support group (MDBS), uniting to engage in policy dialogue with the GoSL on key reforms. This partnership is set to continue as all DPs design new programmes for 2016 and beyond. The PAF was designed to harmonise the indicators that DPs measured GoSL progress against when assessing success of the budget support programmes and for linking performace-based traches to. We will continue to work as part of the MDBS group because working with other DPs during policy dialogue is helpful in influencing GoSL. It also allows for the technical and historical issues behind the policy issues to be captured and incorporated into policy discussions. The way in which DPs work together needs to be made more efficient however, including through a restructuring of the PAF process.

Decisions already taken

The current programme of general budget support finishes this year and will not be continued in its current form. The UK is increasingly making use of payments by results in its programming and has further explicitly stated that any future financial aid to government should be “clearly earmarked for specific purposes”. In line with these objectives, assistance will be triggered by the achievement of agreed milestones, and it will be earmarked against HWS.

Ahead of the UN conference, Ministers considered the size and shape of DFID’s programme over the next two years and a major pledge was made by the Secretary of State in New York. She made clear that it will be programmed in support of the Presidential priorities presented and respresents a major uplift in resources earmarked for Sierra Leone. In discussing DFID’s approach and programme in Sierra Leone in the next two years, Ministers asked for a submission to allow them to consider the case for a new, policy-focused financial aid programme. The Secretary of State provided a steer that any such programme should support the ambitious and new two year strategy she has just agreed for DFID Sierra Leone. This will be consistent with the emerging policy outlined above.

The Impact and Outcome that we expect to achieve

Impact:  Accelerated development, as measured by improvements in non iron ore GDP, scores on the human development index, the gender inequality index and reductions in the poverty headcount. The population of Sierra Leone will be the benficiaries.

Outcome:  Strengthened core systems and improved practice. This will lead to accelerated development by allowing the GoSL to increase its expenditure in absolute terms on economic development and poverty related expenditure. The GoSL provides data on the portion of the budget spent on poverty related expenditure and we will track this in absolute terms in the logframe. This in turn allows GoSL to raise the quality and quantity of the services it delivers to the population. These services (health, education, WASH, infrastructure and so forth) underpin economic development. Economic development allows people to take control of their lives and prosper. Hence we expect to see improvements in HDI and gender indices, albeit with a lag.

## Appraisal Case

What are the feasible options that address the need set out in the Strategic Case?

Counterfactual – ‘do nothing’ option. The UK does not provide direct financial aid to the GoSL.

A programme of technical assistance focussed on core systems with no financial aid component. Under this option , the UK would provide no direct financial resources to the GoSL. TA would be employed across the core systems identified.

Performance–based financial aid instrument with complementary TA programme. Financial aid to the GoSL is fully earmarked against key GoSL development expenditure (meeting the UK government’s manifesto commitment to fully earmarked financial aid). Disbursment of financial aid is driven purely by performance against milestones in core sector reforms with no fixed tranches. Technical assistance is provided and is focused on the key core sector reforms identified.

Assessing the strength of the evidence base for each feasible option including delivery routes

Paragraphs 30 to 44 below assess the evidence base supporting (a) the case for financial aid to governments, (b) financial aid in Sierra Leone, (c) performance-based financing and (d) the role of technical assistance in building core systems. The evidence presented below demonstrates that there is a strong argument for providing financial aid to governments in developing countries and that this is supported by the experience of financial aid in Sierra Leone. The evidence supporting a results-based approach focusing on core systems is less conclusive but is strong enough to give confidence that such an approach could reap dividends in Sierra Leone. The evidence supporting the role of technical assistance in building core systems is of good strength.

Evidence supporting the provision of financial aid directly to developing countries budgets

Financial aid to government can lead to improved policies, increased resources and better public financial management…

There is a wealth of evidence that attempts to evaluate the extent to which “budget support” or financial aid to governments has resulted in improved policies and public financial management in receipient countries. A 2014 synthesis of seven budget support evaluations carried out in Tunisia, Mali, Zambia, Tanzania, South Africa, Mozambique and Morocco concluded that “budget support can achieve significant results within a diverse and often challenging set of contexts. In particular, it has contributed in important ways to upgrading the capability of these governments to manage their public finances, to deliver services and to regulate economic activity, for the benefit of their citizens.”[7] OECD evaluations in Zambia, Tunisia and Mali also concluded that financial aid has contributed to improving budget management and increasing public financial resources.[8] In a 2012 review of PFM reforms in fragile countries the World Bank found that a key determinant of success in achieving core PFM reforms is the degree of political commitment, which in turn is driven by governments’ goals. The Bank found that governments that seek access to the major provision of aid or debt relief are more likely to enact PFM reforms or let them happen. An ODI cross-sectional analysis of PEFA assessments in 100 countries also found that the share of total aid provided as unearmarked financial aid is positively and significantly associated with better PFM quality.
[7] Fiscus (2014), Synthesis of Budget Support Evaluations – Volume 1
[8] OECD (2011) Assessing the Impact of Budget Support, Case Studies in Mali, Tunisia and Zambia, OECD Evaluation Insights Number 2

DFID has substantial experience with budget support operations across its priority countries. For example, DFID Mozambique provided general budget support to the Government of Mozambique for over 10 years. The post completion report noted that budget support had: helped increase public expenditure on priority sectors; helped facilitate sound macroeconomic management; helped strengthen PFM systems; played a useful role in carving out space for dialogue with government on important issues; and offered lower transaction costs for government and donors.

The underlying principle of financial aid, using country systems, is a core element of the Paris Declaration on Aid Effectiveness and Accra Agenda for Action. “Increasing alignment of aid with partner countries’ priorities, systems and procedures and helping to strengthen their capacities” is a central tenet of the Paris Declaration. By putting financial aid through Sierra Leone’s systems, the UK and other MDBS partners meet Paris Declaration commitments. MDBS partners further require good quality fiduciary controls before disbursing their funding and require Government to provide access to their accounts and to describe their budgeting processes. While this effect is difficult to measure, reaching MDBS fiduciary requirements and opening their books up to audit instils a degree of fiscal discipline in the GoSL.

But the impact of financial aid is weaker where there is limited political will…

However, the 2014 synthesis also found that budget support funding is not correlated with policy leverage and that, in low-income countries, budget support tended to influence reforms where interests of the recipient and the donor converged. This finding is in line with a number of studies on the impact of budget support which find that the strength of the relationship between financial aid and PFM reforms is difficult to determine and the causality is not always clear (i.e. did improvements in PFM incentivise donors to provide more financial aid?) For example, the Independent Commission for Aid Impact (ICAI) in May 2012 suggested that the incentive effect of additional budget support financing, is “moderate at best”, especially when dealing with complex institutions, budget systems and political systems[9]. The DFID Project Completion Review of Mozambique’s general budget support found that financial aid has proven less effective at driving change in the way that corruption is tackled; and has not succeeded in generating effective dialogue on inclusive economic development. The 2011 OECD evaluation found that support provided to implementation of public financial management and other reforms was effective when government and society were already committed to these reforms, but financial aid alone was not able to generate this commitment. Preliminary results from the ongoing evaluation of budget support in Sierra Leone supports these findings, emphasising that impact achieved through policy dialogue has been undermined by the absence of an in-built process of “buying-in” political and wider administrative support.
[9] ICAI (2012) The Management of UK Budget Support Operations

Evidence supporting the provision of financial aid in Sierra Leone

Budget support in Sierra Leone has been effective in expanding GoSL spending on poverty reduction and incentivising some policy reforms…

DFID has provided general budget support to Sierra Leone since 2001. Over this period, budget support has targeted a range of objectives including; (i) incentivising reforms to improve core PFM systems; (ii) providing immediate relief to people in the form of improved service delivery; (iii) absorbing the impact of fiscal shocks; (iv) maintaining a good relationship with Government in order to retain and enhance influence beyond reforms linked to financial aid; and (v) investing in the long term capability of the state. The UK is the only bilateral Budget Support donor and sits on the Multi-Donor Budget Support (MDBS) group with the World Bank, African Development Bank and European Union.

The UK’s current budget support instrument to Sierra Leone, entitled the ‘Inclusive Growth and Prosperity Grant’, will come to an end in December 2015. This programme was approved in April 2013 and provided up to £45 million in general budget support (GBS) directly to the Government of Sierra Leone between 2013 and 2015. This support comprised a fixed payment of £10 million (core tranche) and an additional amount of up to £5 million based on performance on implementing reforms and achieving development results (variable tranche).The programme has scored well against the project logframe in both its annual reviews to date, scoring an A (outputs met expectations) in both its first and second reviews. The first annual review concluded “that this intervention is broadly meeting its objectives despite some areas of concern. The strong focus of the dialogue on improving fiscal and macroeconomic management has helped bring about a significant breakthrough but challenges remain in implementing longer-term PFM reforms, particularly in procurement. These also impact on the extent to which the Government is able to demonstrate VfM in its spending, and therefore in its use of UK funds. There is a need to develop stronger links with a selection of ministries, departments and agencies that are central to meeting the objectives of GBS in Sierra Leone. These include those involved in service delivery to strengthen links with sector programmes and highlight bottlenecks and inefficiencies through technical and policy discussions.”

It should be noted that the first Annual Review of budget support took place in an altogether different context to that which Sierra Leone currently finds itself in. In the last year of the project Sierra Leone suffered from two significant exogenous shocks, the Ebola outbreak and a collapse in commodity prices hitting Sierra Leonean iron ore production. Both have had harsh economic consequences; GDP growth fell dramatically, with an economic contraction of up to 21% projected in 2015. Despite these considerable shocks, the GBS programme scored an A (outputs met expectations) in its second Annual Review. The review concluded that “all outputs scored an A overall and hence the programme scores an A. There were some particular successes, notably in the improved credibility of the budget as measured by the variance between budgeted and actual primary expenditure in 2014; the percentage of spending attributed to PRSP priority areas; and the swiftness with which the PAC reviewed the audit report on the use of public Ebola Funds. However, the share of procurement transactions above the competitive threshold through open competition (measured for 2013) was very disappointing and has resulted in concern among the development partners over the quality of procurement transactions.”

There are further a number of independent studies and reviews of budget support in Sierra Leone that provide good evidence that financial aid has had a positive impact on the level of poverty-related expenditure in Sierra Leone and in some cases, has encouraged reforms in core systems. A 2012 ODI case study on public financial management in Sierra Leone concluded that the dependence of GoSL on financial and technical support from donors has driven PFM advancements, though political commitment has been important.[10] A 2009 review of budget support in Sierra Leone found that it has been a ‘valuable instrument for achieving the objective of a more effective, responsible and accountable government’,[11] whilst the high dependence on budget support and the role that the UK has played in Sierra Leone’s development has provided GoSL with strong incentives to push forward and implement PFM reforms. An example of the effectiveness of budget support can be seen from 2007 when budget support was suspended because of concerns around the misuse of public funds and the ability of ASSL to adequately audit public accounts. This led to the development of joint PFM reform strategy and a breakthrough decision to publish the Auditor General’s reports prior to the completion of the relevant PAC report.
[10] ODI (2012) Public Financial Management Reforms in Fragile States: the Case of Sierra Leone.
[11] Bartholomew (2009)

The ongoing 2015 evaluation of budget support in Sierra Leone (2002 – 2013) found that the most significant input of budget support was to provide counter-cyclical funding in periods of low aggregate demand and low domestic revenue. These funds were particularly important in the early post-conflict years (2002-2006), and then in 2014. In both periods, it had a major importance both as a stimulus to aggregate demand and as a source of discretionary financing for government. In terms of incentivising policy reforms, the focus has largely been on PFM and governance and the evaluation found that the provision of TA has been associated with improvements in PFM but the indicators and policy dialogue were only successful in accelerating some change that would have happened anyway.

But Budget Support has not delivered the core systems reforms Sierra Leone needs…

The strategic case above outlines the significant weaknesses in core systems and practices in Sierra Leone and explains the rationale for this programme to focus on key reforms in a more targeted way. The ongoing evaluation of budget support in Sierra Leone[12] found that significant weaknesses exist in the strength of the policy dialogue around core systems between DPs and the GoSL. This includes the absence of an underlying process of reform design and implementation which policy dialogue would build on.  A framework for policy design and implementation should exist and should include an in-built process of “buying-in” political and wider administrative support. DP coordination also needs to improve. The most recent DFID Annual Review of budget support, concluded in June 2015 found that the process by which the budget support PAF is agreed and assessed needs to be substantially improved. It recommended that DPs should engage in more follow-up on the PAF throughout the year to ensure ministries, departments and agencies (MDAs) are aware of the process. At the request of donors, MOFED convenes MDAs only a month prior to the official assessment. MDAs are then stretched when asked to provide evidence against the previous year’s indicators. Donors should engage with the GoSL throughout the year (including through a mid-year review process) to ensure a smooth process where MDAs are continually apprised of what is expected. Lessons can be learned from the past; the resumption of budget support in 2008 began with a series of workshops that included MDAs, Central Bank officials, MOFED and DPs. This helped the MDAs understand that they have a role in the success of budget support. It would be advisable to include this form  of engagement in the new intervention. DFID will lead this process to improve DP harmonisation, thus strengthening the voice of DPs.
[12] Independent Evaluation of Budget Support to Sierra Leone 2002 - 2013

Evidence supporting results-based financing

The evidence around performance based aid approaches is limited but encouraging...

Over the past five years, DFID has made increasing use of payments by results (PBR) in its programming. Justine Greening, UK Secretary of State for International Development stated that the UK is “becoming a world leader in pioneering innovative Payments by Results (PBR) programmes for tackling complex development problems”[13]. PBR involves paying for something after it has been delivered; this is the model financial aid will take under this programme. Disbursement of financial aid will be 100% delivery-based.
[13] DFID, (2014), ‘Sharpening Incentives to Perform: DFID’s Strategy for Payment by Results’

The evidence supporting PBR approaches is still nascent as it remains a relatively new development instrument. The existing evidence base is mixed. An evaluation of a DFID pilot PBR programme in education in Rwanda found that, while there was “a high level of government ownership”, the project did not make a significant contribution to an observed increase in completion rates. The evaluation did say however that it was too early to assess whether the programme will achieve results or constitute value for money. DFID is also running a results based financing programme in health in Uganda. Early indications from evaluations of the programme are that the programme has been associated with improved treatment practice, higher customer satisfaction, and improved value for money[14]. The World Bank’s payment by results instrument, Programme for Results (P4R) provides further evidence around the approach. The Bank have approved 22 P4R operations worth $3.5 billion and a recent two year review of the instrument found that “implementation is moving well and achieving desired results.”[15] This should be viewed as weak evidence however as the instrument is relatively new and it is too early to assess its development impact.
[14] DFID, (2014), ‘Sharpening Incentives to Perform: DFID’s Strategy for Payment by Results’
[15] World Bank (2015), Beyond the Boundaries: Program-for-Results and the Role of Leverage in Scaling up Results

Evidence on the role of technical assistance in building core systems

Technical assistance can play a fundamental role alongside financial aid in securing core system reforms...

DFID guidance on PBR points out the importance of capacity development that is needed to ensure that the programme can deliver the results in question. The design of this programme therefore includes technical assistance focused on improving the ability of GoSL to deliver the agreed results.

There is a significant evidence base supporting the provision of technical assistance to support core systems and the approach is used throughout DFID programmes across the world. The 2015 evaluation of budget support in Sierra Leone found the contribution of TA to be very positive, noting that it helped to address important capacity needs with respect to PFM functions and core governance areas and shaped the changes identified.

This intervention supports the building of durable capacity in Sierra Leone’s administration, focused on areas of PFM. The programme has an allocated fund for TA that will be used to draw in expertise (national or international) to improve the skills base and practices around PFM in Sierra Leone. This is likely to be delivered through specific training courses and on the job mentoring. TA hired will be mandated to ensure a sustainable transfer of skills to national staff. The 2015 budget support evaluation points to successful reform progress linked to embedded TA, both national and international. The evaluation explains that this approach has been demonstrated to work in Sierra Leone through international TA assigned to ASSL and NRA programmes of support and long term national TA across MOFED, which served to strengthen the institution. These experiences show that when TA support is embedded and demanded by the insitutions, it is an effective mechanism for sustainable improvements in local capacity and we will learn from these successful models of TA.

Assessment of Evidence

Option	Strength of evidence
Counterfactual – ‘do nothing’ option	Medium - The evidence presented above demonstrates that budget support has, and will continue to have, a positive impact in terms of generating fiscal space for the Government and incentivising some reforms. The counterfactual to this intervention where the UK does not provide financial aid to the GoSL is likely to have an adverse impact on these areas. The strength of evidence supporting this assertion is medium however as Sierra Leone has received significant budget support resources from the UK since the end of civil war; it is difficult therefore to assess this option against the recent historical precedent.
A programme of technical assistance focussed on core systems with no financial aid component.	Good – There is good evidence, both internationally and within DFID, supporting the use of technical assistance to improve core systems. There is already substantial UK technical assistance in Sierra Leone in key functions of government. There is limited evidence to suggest however that TA alone would reach the stretching impact this programme seeks to achieve.
Results–based financial aid instrument with complementary TA programme focussed on specific reforms	Medium – There is limited evidence around performance-based financial aid as it is a relatively new and innovative instrument. However, initial experiences in Tanzania, Pakistan and Mozambique have been positive. The World Bank’s Program For Results lending instrument has further provided good examples of where this approach can work. The World Bank’s Pay and Performance Projcet is modelled on the P4R approach and uses disbursement linked indicators to deliver financial aid directly into the consolidated fund. There is very limited experience of this instrument in Sierra Leone however. Evidence around the use of complementary technical assistance and how it can result in PFM systems reforms is strong.

Conclusion on options

Based on the evidence presented above, option (iii), ‘Results–based financial aid instrument with complementary TA’ is the preferred option. Option (i), the counterfactual ‘do nothing’ option is discounted due to the good evidence around the use of financial aid and technical assistance to improve core systems in low income countries. Option (ii) ‘technical assistance focussed on core systems with no financial aid component’ is likely to have some benefits as the evidence base around technical assistance is good both internationally and in the Sierra Leonean context. However this option is unlikely to provide sufficient incentives to the GoSL to undertake the stretching reforms targeted by this programme. The UK already provides substantial TA resources to core functions in the Sierra Leonean government, including the NRA and ASSL. Further TA may facilitate reforms the GoSL already intends to do but the purpose of this programme is to provide incentives to accelerate reforms in core systems. Abandoning financial aid would also risk the UK losing our voice on important issues discussed within the MDBS group; it would be more difficult to unite with development partners with one voice on important issues. Finally, as discussed in the Strategic Case, the GoSL is facing severe fiscal pressures at the moment and will continue to do so until at least 2017, according to the IMF. There is a real need for external support therefore and the resources provided under this programme can ease the fiscal pressure. These resources are also substantial enough to represent a real incentive to the GoSL to work towards the achievement of the programme’s Disbursement Linked Indicators (DLIs). Finally, this support should strengthen our relationship with the GoSL. On this basis, option (iii) is the recommended option.

What is the likely impact (positive and negative) on climate change and environment for each feasible option?
The direct impact of financial aid on either the climate or the environment is expected to be minimal. The risks and impact are indirect, manifested through the operations of GoSL in protecting the environment through regulation, enforcement and direct interventions. The financial aid programme offers a platform to raise concerns about how the natural resource-led growth is managed, particularly the environmental impact of this. This could focus on various policy issues ranging from specific issues such as reviewing fuel pricing policies to wider issues such as the risks that climate change and environmental degradation pose to achieving the objectives in the PRSP and in the future.
If any, what are the likely major impacts on social development?

The underlying rationale for the project is to expand the GoSL’s ability to spend on broad based economic development. The GoSL has committed in its Agenda for Prosperity (A4P) to undertake actions to reduce poverty in Sierra Leone and stimulate inclusive economic growth in the country. This programme will provide direct support to the GoSL to achieve these goals. We will continue to monitor progress on social development in the project logical framework. This will include indicators assessing Sierra Leone’s scores on the Human Development and Gender Equality Indexes and directly assessing the proportion of development expenditure in the budget.

For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any?

Sierra Leone’s civil war was fuelled in large part by the mistrust of government, the failure to deliver basic services and grievances related to what was perceived as widespread and endemic corruption. Over a decade on from the end of the civil war, these issues remain a major component of the public dialogue, and corruption issues regularly appear in the press. The development of administrative capacity to raise and manage finances, and to deliver public services in a transparent and accountable manner is therefore a key component of a long term strategy to prevent future unrest. In the aftermath of the Ebola crisis and the audit report that accompanied it, and in advance of national elections, corruption and transparency, as well as core service delivery outcomes can be both drivers of fragility or stability in Sierra Leone. Through this intervention, DFID will support the GoSL to improve systems for public financial management, which it is hoped will reduce state fragility over the medium and longer term, and promote a sustainable exit from aid dependency.

Economic appraisal of the preferred option

This business case does not present a full cost-benefit analysis for the project and instead presents evidence demonstrating that, if the programme achieves its impact, the indicative benefits of improvements in the targeted areas will be substantial and will easily justify the costs of the intervention. We use this approach due to difficulties in attribution and the potential risk the benefits of the programme are overstated, throwing doubt on the robustness of a benefit to cost ratio or a net present value calculation. In sum, financial aid does not easily lend itself to traditional ex ante cost benefit approaches. This approach is in line with other DFID payment by results programmes, e.g DFID Mozambique’s Economic Development Policy Grant. The appraisal will however provide some cost-effectiveness measures of the minimum benefits required for the project to break even and justify itself in economic terms.

The programme has been designed to achieve two tiers of benefits. The first will be improvements in core systems and this will be achieved through directly linking disbursement of resources to indicators of success in these areas. Core systems will be further bolstered through targeted technical assistance under the programme. The second tier is the direct provision of resources to a budget line that is fundamental to poverty reduction: health workers’ salaries (HWS). As well as satisfying the UK Government’s explicit commitment to earmarking financial aid, this will provide vital resources to the delivery of a core basic service in Sierra Leone and is aligned with the GoSL’s priorities. The health sector is under particular strain following the Ebola crisis, the resulting death of over 100 health workers and the pressing need to restore basic services to the population.

Potential benefits from strengthening core systems

Improved transparency, greater competition and value for money in national procurement. Paragraph 8 in the strategic case outlined the serious concerns DPs have around public procurement in Sierra Leone. Compliance with the National Procurement Act is weak; with over 50% of procurement transactions solely funded by the GoSL (i.e. not through development partners) that should have been subject to open competition bidding actually being awarded through sole sourcing of contractors. According to data provided by the NPPA, the total value of public contracts (over the threshold for competitive bidding) awarded in Sierra Leone in 2014 amounted to approximately £51 million pounds. Based on performance against the PAF indicator on procurement for 2014, 58% or £29.7 million, of these contracts were not opened up to competition. Evidence from the European Commission on competitive bidding in the EU found that, when using competitive bidding “contracting authorities spend on average between 5-8% less than they had originally ear-marked” and that “based on aggregate data presented below, there seems to be a relationship between the number of tenders received and extent of savings. The higher the number of bids, the greater the savings realised.”[16] Assuming that the pool of potential bidders in Sierra Leone would be significantly lower than in the EC and that this would reduce the negotiating power of the GoSL, we apply a conservative estimate of 4% value for money savings through open procurement. Applying this figure to the 2014 figures, if all contracts above the legally mandated competitive threshold had been subjected to open competitive bidding, value for money savings would have amounted to approximately £1.2 million. This calculation is a conservative estimate that serves to demonstrate that, at limited cost, increased use of open competition can reap significant VFM gains for Sierra Leone.
[16] European Commission, (2009) Internal Market Scoreboard number 19

Although not quantified here, improving transparency in procurement is also likely to lead to a reduction in corrupt practices in procurement in Sierra Leone. Increased competition in procurement will, in theory, lead to greater transparency around the awarding of high profile contracts. This in turn should lead to greater public trust in GoSL procurement practices.

Well-developed and well-executed national budget. As indicated in the strategic case above, there has been a declining trend in Sierra Leone’s PEFA scores on budget credibility. In its most recent PEFA assessment, Sierra Leone scored a D against indicators assessing both aggregate budget credibility and the credibility of budget targets in key MDAs. The GoSL has consistently overspent against budget – for example in 2012, aggregate government expenditure was 23% over what was budgeted. The PEFA assessment stated that this was largely due to financing capital expenditure.

In the absence of strong revenue generation, this expenditure is fueling significant fiscal deficits. These deficits require financing and the GoSL uses a combination of external and domestic financing (or relies on DPs to provide more grant financing) to service these deficits. The IMF programme has capped the volume of nonconcessional external financing the Government can take on. The Fund project that, in light of increased domestic borrowing to finance public investment, domestic debt will increase substantially over the next few years, from 9.2% of GDP in 2013 to 20% by 2016. The World Bank has expressed concern that the locked-in nature of domestically financed expenditure exposes the GoSL and leaves little room for fiscal manoeuvres in the event of a shock. Treasury Bill yields have fallen in recent years from 30% to almost 2%. The Bank advise that in the event Treasury Bill yields were to escalate suddenly to previous levels there would be little room for a fiscal adjustment on the expenditure side.

There is also some evidence that high government borrowing may be crowding out lending to the private sector. Once the government borrows heavily from the domestic market, a shortage of loanable funds arises, increasing interest rates. Between 2008-2010, a period of large deficit financing, the interest rate was an average of 13.6%. The evidence outlined above demonstrates the importance of improving and maintaining better budget credibility and budget execution. Sierra Leone is currently in a weak fiscal position and overspending against the budget will likely necessitate expensive borrowing and the possibility that private sector investment is stymied.

Improved domestic revenue mobilisation. The Strategic Case has clearly demonstrated the weakness in revenue generation in Sierra Leone both absolutely and relative to its regional peers with domestic revenue to GDP in 2013 of only 12.8%. The revenue position has been further compromised by the Ebola and iron ore crises. The table below, from the IMF’s most recent published Review of Sierra Leone’s Extended Credit Facility, demonstrates how revenue projections are markedly down on projections made before Ebola. The Fund project that the ratio of revenue to non-iron ore GDP in 2016 will be just 10%.

Revenue mobilisation will need to expand dramatically to meet the target set out in Sierra Leone’s Poverty Reduction Strategy Paper (the Agenda for Prosperity, A4P) of achieving a revenue-to-GDP ratio of 35% by 2035. The A4P further states that “on the basis of the projected expansion in economic activity and increased iron ore exports, domestic revenue is projected to increase from 12.7% of GDP in 2013 to 14.2% in 2018.” The targeted revenue to GDP in 2017 therefore, when this project ends is 14.2%. In light of the current economic situation, the IMF are projecting a revenue to GDP ratio in 2017 of 10.8%. To put this into perspective, based on current IMF projections for non-iron ore GDP, the IMF are projecting revenue collection will be $1.1 billion over the next two years. In order to achive the original A4P targets, again using the current non-iron ore IMF GDP projections, Sierra Leone would need to collect $1.5 billion over the next two years. While it should be noted that the original A4P targets were formulated in a different context and were possibly over-ambitious, a difference of $400 million between the two estimates is stark and demonstrates the level of effort that will be required to get Sierra Leone back on track with its A4P targets.

This intervention will target revenue mobilisation in Sierra Leone through the inclusion of a DLI. The UK is already supporting the NRA with a large TA programme. If necessary this programme will supplement this long-term TA programme to provide targeted TA resources aimed at enhancing revenue mobilisation. Finally, the UK will continue to use policy dialogue to encourage improvements and reforms in this area. This multi-faceted approach will hopefully facilitate greater improvements in revenue mobilisation than those projected by the IMF. Indeed, for the entire project to break even in terms of its overall costs, it would need to lead to an increases of 0.37% and 0.33% in Sierra Leone’s revenue to GDP ratio over that being projected by the IMF. Considering the substantial effort being put into this issue through both this intervention and the complementary R4P programme, these appear to be reasonable targets.

Potential benefits from earmarked financial aid resources to HWS

As well as incentivising reforms in core systems this intervention will provide direct resources earmarked against a line item in the budget. The design team for this intervention has considered a number of line items that the financial aid component of this intervention (up to £20 million over two years) could be earmarked against. The key criteria for the team were (a) the development impact of the expenditure, and (b) the ease of securing receipts against the expenditure at the right times of year to fit with our planned disbursements. The team considered a number of potential line items and areas, including health workers’ salaries (HWS, which the UK has previously supported); energy provision; Water Sanitation and Hygiene (WASH); feeder roads; and transfers to local councils for service delivery. Following an appraisal process, the team concluded that payment of HWS would satisfy criteria (a) and would further contribute to the UK Government’s manifesto commitment to save lives from malaria and work towards ending preventable child and maternal deaths. The team believe HWS is the most suitable to satisfy (b) because DFID Sierra Leone has supported HWS before and are familiar with the process and also, because HWS are due to be paid every month, they are unlikely to be delayed beyond our planned disbursement dates. This is in contrast to capital projects under the other options, which often involve large once-off payments and are subject to delays; this could lead to delays in our disbursements and undermine the predictability of our aid.

DFID support to HWS under the free healthcare initiative (FHCI) spanned a five year period and ended in early 2015. The support provided funds for an uplift in HWS. Since the iron ore price collapse and Ebola crisis, the state budget has become extremely tight and so earmarking to HWS ensures that this uplift in HWS that proved so beneficial, will not be undermined and resulting benefits will not be lost. Benefits will come in the form of ensuring that HWS are paid in full and on time; healthcare workers will have greater certainty over when and how much they will be paid than they would in the absence of our earmarked financial aid. This will i) maintain the higher level of commitment of healthcare workers since the DFID-funded uplift in salaries and hence the standard of services they deliver; ii) limit the incentives for improper charging on the part of health workers, contributing to enhanced uptake of healthcare services post-Ebola; and iii) through funding HWS DFID can raise the profile of the scrutiny of the health workers’ payroll.

An evaluation[17] of the DFID support to HWS between 2010 and 2015 confirmed that the salary uplift was critical to the success of the FHCI. Prior to March 2010, the GoSL health workforce was operating at a very low level of commitment, with high levels of absenteeism and a constant distraction of the search for additional income and incentives to charge for services that were intended to be free. A health workers’ strike was threatened in protest of their low wages. The announcement of greatly enhanced salary scales had an immediate effect in attracting new recruits and changing the incentive structure for existing employees. It is difficult to quantify the benfits, and indeed the evaluation does not attempt to. However it is clear that relative to a counterfactual where all or some of these gains acquired over the five year period are eroded, the earmarking yields significant benefits to Sierra Leoneans in the form of access to quality health services.
[17] An Evaluation of DFIDSupport to HWS in Sierra Leone, 2012: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/206761/evaluation-support-healthcare-workers-salaries-Sierra-Leone.pdf

Conclusion on Preferred Option

The evidence and potential indicative benefits presented above demonstrate that the potential benefits of the project are likely to substantially outweigh the costs. It is concluded therefore that the intervention represents good value for money.

        Theory of Change for Preferred Option

Output Area 1:  Well-developed and well-executed national budget

Input 1: Technical Assistance for specific reforms, diagnostics and monitoring (£4m)

Impact: Accelerated development

Outcome: Strengthened core systems and improved practice.
Output Area 2:  Improved domestic revenue mobilisation

Output Area 3: Improved transparency and enhanced value for money in national procurement

Input 2: Policy Dialogue

Input 3: Financial Aid (£20m)

Output Area 4:  An efficient public sector wage bill

Improved healthcare service will result from earmarking

How the outcome will translate to the impact

The project outcome is “strengthened core systems and improved practice.” This will lead to the project impact “accelerated development” by i) allowing the GoSL to increase its expenditure in absolute terms on economic development and poverty related expenditure, because improved systems and practice will open up more fiscal space; and ii) funds will be spent more efficiently via improved core systems and more efficient practices.

How the outputs will translate to the outcome

Output 1: a well-developed and well-executed national budget results in budget credibility which underpins the PFM system and as explained above is currently a significant area of weakness in Sierra Leone. Improvements in this area would mean, for example, that i) the composition of expenditure would more closely reflect the budgeted expenditure, lending increased predictability to the process thus allowing MDAs to spend as they planned; ii) revenue would be more accurately forecast; and iii) the level of off budget spending that is unreported would drop. The GoSL did meet the 2014 PAF target requiring a less than 15% deviation between composition of expenditure of actual and originally budgeted primary expenditure but there is still ample room for improvement. Improvements in these areas would lead to more funds for MDAs to spend and they would have more predictability over them. This would represent an improvement in the PFM system, allowing for higher quality service delivery.

Output 2: Improved domestic revenue collection methods, such as collecting tax arrears, ensuring all those who should be registered to pay taxes are registered, and ensuring tax payers pay on time would result in more revenue being collected, transferred to the budget and available for spending on poverty reduction and economic development.

Output 3: Improved transparency and more competition in national procurement will lead to value for money savings. These savings can be diverted to poverty reducing or productive expenditure.

Output 4: A more efficient wage bill would mean reducing the bill as a proportion of the budget and as a propotion of domestic revenues, for example by making cuts where salaries do not represent good value for money, and are relatively high for the outputs being produced. A prime example is workers who have not been removed from the payroll since their departure. If the wage bill were reduced, it would free up more fiscal space for discretionary spending on poverty reduction and economic development.

How the inputs will translate to the outputs

Technical assistance directly linked to the specific reforms associated with the DLIs will help solve problems and build capacity towards GoSL achieving the targets set by the DLIs. Technical assistance will be placed strategically following an analysis of what needs to be done to achieve each of the outputs. Diagnostic work will assist in tracking performance and understanding where there are areas for improvement, possibly indicating areas for further TA inputs.

1. Policy dialogue will operate at both the technical level and political level and will allow DPs to learn more about GoSL systems and where there is opportunity for reform within the areas we are most interested in and it will allow DPs to influence GoSL and problem solve alongside them to achieve the DLIs.
2. Financial aid will provide funds for the GoSL to spend against the selected budget line item; probably HWS. The funds will also be linked to the output-based DLIs to serve to incentivise action from GoSL, leading to achievements against outputs 1 to 4.

The benefits of earmarking financial aid to HWS

Predictable, reliable payment of healthcare workers will strengthen delivery of healthcare services. Earmarking to HWS ensures that the salary uplift provided through the FHCI will not be undermined and resulting benefits will not be lost. Benefits will come in the form of ensuring that HWS are paid in full and on time; healthcare workers will have greater certainty over when and how much they will be paid than they would in the absence of our earmarked financial aid. This will i) maintain the higher level of commitment of healthcare workers since the DFID-funded uplift in salaries and hence the standard of services they deliver; ii) limit the incentives for improper charging on the part of health workers, contributing to enhanced uptake of healthcare services post-Ebola; and iii) through funding HWS DFID can raise the profile of the scrutiny of the health workers’ payroll.There is of course the uncertainty over the size of our disbursement that meeting the DLIs creates but the GoSL will have to spend on HWS and then send DFID the receipts before DFID disburses, hence the predictability of HWS disbursements is secured even without DFID reimbursement.

What measures can be used to monitor Value for Money for the intervention?

A full set of Value for Money indicators (both quantitative and qualitative) will be developed as part of the Delivery Plan for 2016. These are expected to include:

Economy:
- Fee rates and overall cost of TA
- Cost of diagnostic tools such as a PEFA compared to the past and to other countries
- Government progress in implementing procurement reforms

Efficiency:
- Measures to monitor government progress towards DLIs and PAF indicaotrs (such as a % of PAF indicators that should be on track by the Mid-year Review)
- Speed with which we respond to TA requests

Effectiveness:
- Take up of DFID funded TA and advice
- Evidence of increased funds directed to poverty-related expenditure
- Monitoring of GoSL expenditure to understand operational efficiency (e.g. budget execution rates) and allocative efficiency (e.g. distribution across sectors, across economic functions)
- Stable macroeconomic environment (at least on track with IMF Programme)

Summary Value for Money Statement for the preferred option

The programme is designed to represent good value for money through a multiplier effect. That is, the impact of the programme on core systems, both directly and via its complementarity with other DFID programmes focused on core systems reform. These mechanisms have been articulated in the theory of change description. The programme should also achieve good value for money directly through its outputs and this is guaranteed by the fact that DFID will not pay if DLIs are not met. Examples of value for money that can be achieved through direct effects include influencing procurement practices. The economic appraisal explains that value for money savings to GoSL could amount to £1.2 million a year with improved practices.

Commercial Case

A Fiduciary Risk Assessment (FRA) was carried out in October this year and results are being compiled. The Parternship Principles Assessment (PPA) was carried out in September. The continued implementation of the programme will be contingent on the findings satisfying of the FRA and the regular updates of the PPA satisfying us that GoSL systems are capable of delivering the outcomes intended. We will submit an Information Note to the SoS on the findings of the FRA before the end of 2015 and hence before the start of this programme. Based on our knowledge of GoSL systems; the progress made against PAF and logframe indicators during our present budget support programme; PEFA scores and the 2011 FRA we conclude that GoSL systems are currently capable of delivering the intended outcome. That is, we believe that strengthening of core systems and practices leading to more fiscal space is possible under the programme, given the systems in place already. Given the weaknesses in core systems that have been identified in the Strategic Case, and following the advice of the Chief Economists’ Office, we are not intending to target service delivery outcomes. The SoS made a commitment at the UN conference in early July 2015 to improve the delivery of basic services in Sierra Leone. As such, we are addressing service delivery elsewhere in the DFID Sierra Leone programme and view financial aid as a tool to improve systems and practices.

Earmarking
The Accountant General and the Bank of Sierra Leone can provide proof that the funds have been spent on HWS in the form of the approved and processed payroll and the evidence of bank transfers to the accounts of the health workers.

The TA component
DFID has made international commitments to use and to strengthen country systems and therefore in addition to channelling funds through country systems we have a capacity building element built in; the TA component. This will focus on raising standards and improving value for money in procurement. However, consistent with the financial aid package as a whole, we will not be using this system for delivery, we are working to strengthen it. DFID will be responsible for procurement of any TA in the programme.

The TA and diagnostics and monitoring component will be designed to respond flexibly to emerging needs; in order to do this a range of instruments may be deployed. The most appropriate instrument and funding type (from a cost effectiveness and efficiency perspective) will be chosen on a case-by-case basis. These could include:

- Contracts: We may use contracts to deliver a specific diagnostic or monitoring report to DFID, to provide short-term TA to deliver a discrete output to GoSL and DFID, or longer term TA to support more sustained engagement with GoSL. These would be directly managed by DFID and competitively tendered according to contract value and so forth. Different contracting models will be explored, again on a case by case basis, but we would expect not to use simple input based contracting but rather use performance-based and output-based contracts. As explained in the Management Case, we would expect to agree with the GoSL the key areas of TA support and we expect to contract one provider to deliver the entire TA package over an approximately 18 month period, in order to limit transaction costs and ensure a holistic approach.
- Bilateral arrangements with other DPs (either multilateral or bilateral): In particular circumstances we may choose to sub-contract another donor organisation to provide a specific piece of TA, or to deliver a specific diagnostic/monitoring report where they have an established comparative advantage.
1. We may use the Professional Evidence and Applied Knowledge (PEAKs) framework to call down short-term TA service suppliers if we judge that they are likely to deliver a fast track, high quality output. This is likely to be used to contract TA to investigate in detail what the 18 month TA programme should focus on and work with us to design the programme, in early 2016.
2. From our experience with one of our current TA programmes with GoSL, we have noticed that TA from other African countries is generally better received. We will attempt to respond to this by ensuring adverts go out across Africa (and other developing regions[18]). We will use networks in-country (with other DPs) as well as within DFIDto help identify good potential suppliers and build up the potential supplier base.
  [18] DFIDMozambique also detected this trend and relate it to TA from developing countries and BRICS.

## Financial Case

The nature and value of expected costs

Flow of funds	The GoSL will receive all disbursed financial aid which will be deposited in the consolidated fund and will be earmarked to HWS. / TA funds will not pass through the GoSL accounts but will be procured by DFID through third party agencies or frameworks. This is also the case for the diagnostics and monitoring component, which will be contracted out by DFID through third party agencies or frameworks.
Costs to be incurred directly by DFID	DFID will directly pay the financial aid component to GoSL.
Costs to be incurred by / third party organisations	There is a budget of £2 million a year for the TA component and this will be spent through third parties. This forms a relatively large portion of the programme budget, in line with the latest shift in the DFID approach to providing financial aid[19]. / As noted in the commercial case, the TA component will be designed to respond flexibly to emerging needs; in order to do this a range of instruments may be deployed. The choice of instrument will affect the financial management and reporting required. / Contracts: DFID will directly manage contracts. Funds will be tied to the delivery of defined, and largely discrete, outputs (be that support to GoSL reform, provision of specific advice or completion of a diagnostic report). Each contract will clearly set out the conditions against which funds will be disbursed and how financial reporting should be completed. / Bilateral arrangements with other donor (bilateral or multilateral) partners: Where we choose to subcontract with another donor organisation we will ensure that each administration agreement is also focussed on the outputs to be delivered as the basis for UK funding (e.g. an Externally Funded Output agreement with the World Bank).
Financial aid to governments	UK funds will be strictly linked to achievement of four targets each calendar year. Each DLI will specify the target and will have £2.5 million attached to it. It will be paid only once evidence of achievement has been obtained and verified by DFID. Transition to the second year of the programme will be contingent on sufficient buy-in and political will being demonstrated by GoSL to reform core systems and hence meet the targets. That is, if the targets have not been met and the programme does not disburse at all in the first year, the programme would be cancelled unless there is a compelling reason for failure (e.g. an exogenous shock). UK funds will be disbursed in up to 4 tranches in each calendar year (there may be 1 tranche for each DLI if they are achieved at different times of the year). It is anticipated that 2 DLIs will be assessed and disbursed against in July of each year and 2 in November. Disbursements will be made directly from the UK Government account to the GoSL consolidated fund account.
Affordability	At a High Level UN Conference in New York in mid-July 2015, the SoS pledged £240m for Sierra Leone over the following 2 years. Approximately 10% of this is being budgeted by DFID Sierra Leone to take the form of 100% results-based financial aid, with a TA component attached (and a policy dialogue component that has no costs attached). This marks a significant reduction in our exposure to fiduciary risk.
[19] THE FUTURE OBJECTIVES AND ROLE OF FINANCIAL AID. Chief Economist’s Office, September 2015.

Cost profiling and forecasting

We do not expect the GoSL to meet any of the DLIs in the first quarter of the calendar year, hence we can forecast all disbursements to take place in UK financial year 2016/17 and and then 2017/18. We would like to retain the flexibility to make small TA payment in the final quarter of the UK financial year 2015/16 as we anticipate short term TA in January or February to undertake the design phase of the longer programme. The vast majority of TA costs will fall in 2016/17 and 2017/18. For the diagnostics and monitoring component it is also unlikely that funds would be spent between January and March 2016. The budget for the TA package is relatively high, given that the cost of long term TA through PEAKS is approximately £200,000 and typical consultancy rates through agencies range from £500 a day to £900 a day. A 2 month contract would then be in the range of £20,000 - £36,000. However, we are keen to keep the budget relatively high because we anticipate significant need for TA to tackle problems with procurement. This may involve placing TA in several or many of the multiple procurement departments across GoSL MDAs and local councils and we would like to have the flexibility to do this in order to tackle the problem from a broad, systemic perspective. TA in the area of budget credibility and wage bill management is also envisaged.

The cost schedule is as follows. It is not possible to breakdown the payments to monthly or quarterly payments because of the uncertainty as to when GoSL would meet the DLIs and we need to retain flexibility around commissioning TA and diagnostic work. The timeline is short because we do not want to extend the programme beyond 2017 because national elections are due in early 2018 and we would like to discuss any new programme with the new Sierra Leonean government. Moreover, as this is a new instrument we would like to assess its impact after 2 years before proceeding with something similar.

High Level Programme Budget Profile
£ millions	2016/17	2017/18
1. Financial Aid (maximum)	10	10
2. Technical Assistance (maximum)	2	2
3. Diagnostics and Monitoring (maximum)	0.5	0.5
Total	12.5	12.5

Financial and fraud risk assessment

Because the financial aid is earmarked, the chief risk is that it is not spent on the selected line item (HWS). We will ensure that we receive regular receipts from GoSL to prove that all of the funds have been spent on the line item, as budgeted. A mechanism to receive the receipts will be set up in advance of any payment being made. The receipts will be audited by ASSL each year as well, in which we have faith in the quality of output (see Management Case). We are not attempting service delivery through the programme (apart from the selected budget line item) and our risk is contained to one earmarked component of the budget; the health workers’ payroll. During the lifetime of the FHCI (2010-2015) the health payroll was cleaned up and the evaluation[20] notes that “there is widespread confidence about the accuracy of payroll data. With DFID Sierra Leone support the healthcare worker payroll has been cleaned and an effective payroll management system has been put in place”. In 2015, DFID Sierra Leone has sought to consolidate these gains by contracting the Clinton Health Access Initiative (CHAI) to ensure the payroll is kept clean. The main risks to the programme are around whether we successfully incentivise and support GoSL to reform core systems. So the risk of fraud is assessed as medium. The assessment is not of low risk because of the high level of corruption in Sierra Leone.
[20] An Evaluation of DFIDSupport to HWS in Sierra Leone, 2012: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/206761/evaluation-support-healthcare-workers-salaries-Sierra-Leone.pdf

For the TA and diagnostic component we will use agencies with whom DFID has an established reputation and where possible we will negotiate costs down.

Monitoring, reporting & accounting for funds

We will receive proof from the Accountant General and the Bank of Sierra Leone that funds have been spent on HWS and we will disburse upon receipt of them (and after DLIs are met).

Any funds not disbursed because the associated DLI target was missed will be returned to DFID headquarters.

Management Case

Management arrangements for implementing the intervention

The programme will be governed by a bilateral Memorandum of Understanding (MoU) with the Government of Sierra Leone. This will follow the format required for a financial aid programme. The Bilateral MoU will address the following:
- The core objectives of the financial aid;
- The mechanism by which DFID commitments will be tied to successful meeting of targets associated with the DLIs and the process by which these DLIs will be agreed and assessed in order to inform commitments;
- Reference to the technical assistance/institutional capacity building elements of the programme and how these are to be agreed and implemented alongside key GoSL counterparts.
- The role that ongoing assessment of the GoSL commitment to the Partnership Principles will play in implementing the programme, how this will be assessed, and how responses to these assessments will be managed;
- Financial management, reporting and auditing arrangements;
- Fraud and whistleblowing arrangements.

Design of the DLIs will be critical to success of the programme. Eight DLIs have been designed. These are in the areas selected for attention, based on the rationale in the Strategic Case and marked as the four outputs of the programme. The DLIs are designed to push GoSL to find practical solutions to achieve the specified output and the DLIs were agreed alongside GoSL. Lesson learning in DFID has led to conclusions that it does not work to use conditionality to force through policy choices that governments do not want, and for financial aid to be truly effective policy priorities between donor and government need to be at least partly aligned, with clear agreed objectives to which both parties are genuinely committed. Where necessary we will provide TA to support them with their plans. DFID already has a large TA programme working with the NRA and is a major contributor to a World Bank Trust Fund which includes some short term TA across the spectrum of PFM issues. We will use this existing TA, to the extent possible, to work with GoSL to achieve the DLI targets. The DLIs are independent of one another and with different timelines attached so achievement of one area will not be hampered by a lack of achievement in another. Through our policy dialogue, communications with GoSL at the political and technical levels and with our TA we will keep abreast of progress on an ongoing basis, helping to solve problems where they arise. Formal monitoring of progress will take place using the DFID log-frame and the PAF, as set out below.

We will ensure the GoSL knows that if DLIs are not met in full we will not under any circumstances disburse against them and funds will go back to London rather than be re-programmed in Sierra Leone. Similarly GoSL will be informed that if it does not demonstrate sufficient political will to meet the agreed targets in 2016 and if it fails to meet the DLIs entirely (for reasons other than exogenous shocks), then this would be a trigger point for us ceasing financial aid and so the 2017 budget will be cancelled. In terms of an exit strategy, this means that TA contracted under the programme will not be contracted into 2017 until it is clear that the programme will extend into the second year. We do not anticipate cancelling the programme in 2017 based on our understanding that there is political will and we have been designing the DLIs alongside GoSL to ensure buy-in. However, having this credible threat at our disposal may help with incentives for GoSL and will ensure that DFID funds are used to maximum effect. We can refer to the experience of DFID Pakistan which recently withheld a performance-based financial aid payment.

Monitoring and assessment of the programme will take place throughout the year via several mechanisms. These are described in the table below.

Monitoring Tool	Description	Who is responsible
DLIs	Eight DLIs have been designed, against which disbursement is linked. Each DLI is worth the same amount of money and GoSL must fully meet the target in order to receive any of the disbursement to which it is linked. / Some of the DLIs will need a set time period over which to be achieved (for example if we adopt the indicator relating to the percentage of procurement contracts that must be subject to open competition this will need to be specified over a set number of months and will therefore have a clear deadline. For other indicators, such as the DLI to “boost GST by X billion Leones”, disbursements can be made as soon as the target is met, although a cut off date will exist (probably July of the year in question). Progress will be monitored on an ongoing basis with the frequency determined by the data availability. The DLIs can be independently achieved. We will review progress towards the DLIs on an ongoing basis including regular reporting on progress from GoSL heads of component and any DFID-funded TA in the areas of concern. It will be clear up front exactly what constitutes meeting the target- a technical note will be prepared and agreed with GoSL before 2016 to this end. The PAF process has taught us how important it is to question all details of the technical note to guard against any ambiguity and to ensure the indicator is directly and objectively measurable.	DFID SL alongside GoSL and TA.
Logframe	The DFID log-frame is being designed alongside the DLIs and in conjunction with GoSL. An Annual Review will take place in December 2016 and a PCR in December 2017.	DFID SL
Budget Support Progress Assessment Framework (PAF)	This is a set of about 15 indicators agreed between GoSL and the 4 financial aid DPs. In some cases, some DPs have money attached to several indicators but the scene is complex with each DP having a different disbursement method and, in 3 of the 4 cases, a different set of indicaotrs that are also linked to disbursement or ‘success’ of the programme (i.e. it guides the Annual Review score). Despite the complexity of the monitoring landscape, the PAF has inherent benefits in terms of focussing policy dialogue; it is useful in providing structure and evidence around core topics for meetings wth GoSL at technical and Heads level as well as in the soon-to-be-resurrected PFM Donor Working Group. The PAF process needs improvement if it is to provide real incentives to GoSL to take action. This is partly because the time taken to agree annual indicators means that they have not been agreed until part way through the year in which activity is being monitored. It is also partly because of DP’s separate sets of triggers and DLIs and logframe indicators that take attention from the PAF. While there is some overlap between the indicators, increased overlap would streamline the process. To solve these two problems we have reignited the discussions towards a multi-year PAF, adding 2017 in order to provide longer term clarity on what we are monitoring and avoid indicators being agreed late. These indicators could be adjusted over the years but agreement at the outset should incentivise GoSL to dedicate resources to achieving each indicator if it is made clear that it is not a temporary concern for DPs that will disappear the next year. We are also lobbying DPs to include as many of their own indicators in the PAF as possible and we have included all ours in the proposed new multi-year PAF. We will also use PAF indicators for our logframe. This will lend importance to the PAF indicators because they will represent financial gain and reputational gain (to the extent the GoSL is concerned about our Annual Review results). It will also streamline the process and the dialogue. As well, achieving maximum overlap between our log-frame and the PAF will reduce the total number of indicators associated with financial aid in Sierra Leone and relieve the burden on GoSL for data collection. We also need to address the timing of the PAF Review which currently takes place alongside the onset of rainy season and collides with DP and GoSL colleagues’ leave dates, thus prolonging the process and diluting the impact of discussions as key people are often absent. We are therefore exploring the option of moving the annual PAF Review from May/June to March/April. We plan to introduce a Mid-year Review to ensure progress is on track and raise the profile of the PAF, and possibly even more frequent monitoring. The PAF should then become a very useful tool to assist with monitoring core systems and practices.	DFID SL alongside counterparts of AfDB, WB and EU and GoSL.
PPA	Financial aid will only be disbursed if the GoSL demonstrates sufficient commitment to the Partnership Principles. The PPA will be discussed with GoSL on a regular basis. The objective is to make GoSL more aware of how their actions are seen by the UK and responded to by the UK. Any deterioration of commitment to the Principles will result in DFID raising the issues directly with the Minister of Finance without hesitation.	DFID SL
PFM Donor Working Group	Historically, a donor PFM working group existed but it disintegrated several yers ago. DFID will resurrect this forum; DPs have expressed their desire to participate but success will be subject to them prioritising it and attending, which cannot be guaranteed. However, the PFM Working Group will be more technical in focus than other MDBS meetings and hence should be useful for all DPs and encourage thir buy in; we will highlight this specific nature of the Working Group. The Working Group will select important topics to discuss (such as tax, procurement payroll), will establish joint DP positions and then work alongside GoSL to solve problems and improve performance in PFM. We will learn lessons from other DFID country offices (for example DFID Tanzania) on how these groups can most effectively be structured; DP participation and motivation will be vital to secure and maintain.	DFID SL and Governance Advisor
Head of Office (HoO) meeting Minister of Finance	The DFID Head of Office (HoO) for Sierra Leone has regular meetings with the Minister of Finance.	DFID HoO
TA	Where TA is employed under the programme, consultants will have reporting obligations to DFID against their ToR. Consultants will also be expected to collect data for monitoring of some DLIs and logframe outputs and can be useful sources of information when updating the PPA.	Consultancy firms
Ministerial monitoring	At the end of 2016 we will update Ministers on which DLIs were met; how much was disbursed; confirm the earmarked funds were spent as intended; provide an update on the performance against the PPA and seek approval of the DLIs for the following year. A submission along the same lines will be made at the end of 2017 to update Ministers on the outcomes during 2017.	DFID SL

The use of the earmarked funds will be monitored closely. We will collect receipts to show our funds were spent as earmarked on the chosen line item. ASSL will review GoSL accounts on an annual basis and have proven their strength in this in recent years with well-written, published audit reports and rising PEFA scores associated with external scrutiny. Their reports will inform us on the spending practices around HWS.

The risks and their management

Achievement of the objectives of the programme depends on GoSL commitment to taking the necessary action, and sustaining the momentum in the face of resistance from those who oppose change. Progress has been mixed, with some good progress in some areas and weaker progress in others. Ebola has tended to stall progress, and momentum needs to be re-established. To mitigate this risk we are designing the indicators alongside GoSL and providing TA.

The GoSL must maintain macroeconomic stability, indicated by remaining on track with the IMF Extended Credit Facility Programme (ECF). This will include staying within the debt limits set by the Programme in order that the country is not assessed as being at high risk of debt distress. The GoSL will need to prioritise investments carefully in order to maintain this stability and say within the debt limtis. If the Programme does slip off track, for example, if the debt limits are breached, we would suspend our financial aid in line with the suspension of the ECF.

Availability of financing from other sources may reduce GoSL incentives. Evidence from the Budget Support Evaluation, covering budget support activities since 2002 in Sierra Leone showed that when availability of funds from other sources rises, there is sometimes an associated downward trend in domestic revenue. While causality is difficult to determine it suggests there might be a drop in determination to collect own-source revenues when there is less need. This is a low level risk because of the particularly low revenue following the iron ore price crash. Nevertheless, through a renewed focus on policy dialogue with GoSL we aim to mitigate this risk; we are designing DLIs alongside GoSL and will provide TA and engage in policy dialogue in order to facilitate achievement of the DLIs.

There may be a greater degree of volatility in disbursement against DLIs because the instrument is 100% performance based with no reward for partially met targets. This will make it relatively unpredictable for GoSL and for DFID accounting stystems. Preparing for volatility as well as striving to ensure the DLIs are met will be the mitigating actions. DFID HQ will account for potential of volatility in disbursements and likely return of DFID Sierra Leone funding to centre. DFID will ensure the enhanced policy dialogue around PFM is targeted to provide advice and assistance with problem solving to GoSL that directly facilitates achievement of the DLIs. DFID will also ensure GoSL and the IMF (who closely assist with and monitor budget planning) are aware of the stringent nature of the DLIs and factor in the potential for volatility accordingly.

Mobilisation and timing

Sierra Leone’s fiscal years are calendar years and our programme is designed to follow this. The DLIs will be agreed in year n-1 (i.e. this calendar year) and GoSL will have until July of year n to achieve two of them and November of year n to acheve the remaining two (and early achievement of eligible targets can be rewarded early). Disbursements will take place in year n. This means indicators must be selected for which there are data readily available and no significant lag time in collecting data. Towards the end of year n, DLI targets for year n+1 will be confirmed (assuming the programme is being continued). The GoSL then will have year n+1 to achieve the targets. No disbursements would be made after December of n+1 (2017).

Because the TA component will take time to mobilise, we have begun discussions with GoSL and other DPs on where we can usefully place TA alongside our discussion on the DLIs.

In December, ToR will be prepared for short term TA to produce a detailed design for an approximately 18 month TA programme to cover the four areas of our focus. This should be executed by the end of January 2016 and the tender for the full programme put out in February 2016.

Upon SoS approval, a DFID Bilateral MoU will be signed with the GoSL; this will have been discussed at a provisional and technical level with GoSL counterparts in advance to ensure rapid turnaround.

DFID Sierra Leone has begun discussions with GoSL and DPs regarding arrangements for the PAF and the PFM donor Working Group. This process will be continuous and we aim to have the Working Group active and a new multi-year PAF and PAF process agreed by January 2016.

Acronyms

AFDB – African Development Bank
ASSL – Audit Service Sierra Leone
CHAI - Clinton Health Access Initiative
DLI – Disbursement Linked Indicator
EU – European Union
FHCI – Free Healthcare Initiative
FRA – Fiduciary Risk Assessment
GoSL – Government of Sierra Leone
HDI – Human Development Index
HoO – Head of Office
HWS – Health Workers’ Salaries
IGD – Inclusive Growth Diagnostic
MDAs – Ministries, Departments and Agencies
MEST – Ministry of Education, Science and Technology
MOFED – Ministry of Finance and Economic Development
MOHS – Ministry of Health and Sanitation
NRA – National Revenue Authority
PAF – Progress Assessment Framework
PEAKS – Professional Evidence and Applied Knowledge Services
PEFA – Public Expenditure and Financial Accountability
PFM – Public Financial Management
PPA – Partnership Principles Assessment
SoS – Secretary of State
TA – Technical Assistance
WASH – Water, sanitation and hygiene
WB – World Bank

## Smart Guide
## The Business Case

- Sets out the case for a programme, adapted to suit the context
- Explains very clearly what the programme will do within what timeframe and is explicit about the risks and uncertainties and how they will be managed
- Records an understanding for DFID, our partners and intended beneficiaries about what we are planning to do and the results we expect to achieve
- Allows DFIDto report to the UK public on what we are doing with taxpayers’ funds

The Business Case is structured around the Treasury 5-case model. Within this broad framework the design should be adapted to suit different contexts and investment types. The content is indicative, not prescriptive and teams are encouraged to use judgement in making a logical argument to make the case in a way that suits the individual investment. There is also a set of questions in the Smart Rules that design teams should consider during the process. This is not a checklist and only the questions relevant to the context should be answered.

Teams should refer to the considerations below as a guide to writing the business case

Intervention Summary (2 Pages)
A succinct and unambiguous description of what the project will do. The summary sets out the problem the programme will address, what it will do and what the money will be spent on. It sets out the expected results in the context of the Operational Plan and DFID’s wider priorities and a summary of risks. The accompanying submission should set out any sensitive information that supports the case (e.g. risk tolerances and escalation measures)
Strategic Case
This section makes the case for DFIDintervention by setting out the overarching context and the problem to be addressed. It should be clear what the programme will do and how with evidence. It should link to – but not repeat – the Operational Plan with a clear illustration of how the programme contributes to DFIDglobal and portfolio priorities of poverty reduction.
Appraisal Case
The Appraisal Case explores how we will address the need in the Strategic Case in a way that optimises value for money. It appraises genuinely feasible options for achieving the objectives, including high level commercial choices , with a summary of the quality of evidence. The appraisal considers delivery mechanisms including capability and capacity, costs and benefits, risks and likelihood of success. It concludes with a preferred option.
Commercial Case
This section provides more detail on implementation and how value for money will be achieved. It sets out the procurement approach and requirements, proposed funding instrument and how the choice of instrument will be used to ensure vfm. It considers the market place response to this intervention with an explanation of how supplier performance would be managed. It sets out the procurement policies, capabilities and systems of the third party entity to ensure we get vfm.
Financial Case
This section sets out issues of affordability and the sources of funding. It includes a high level budget which does not impair VfM in procurement exercises for individual contracts. It sets out how funds will be disbursed and how expenditure will be monitored, reported and accounted. It highlights the evidence underpinning a judgement that funds will be used for the intended purposes.
Management Case
This section focuses on governance and management arrangements and the ability to deliver. It sets out the management implications for the business unit/ level of effort with realistic timings for mobilisation and start up. It outlines out the expected roles and responsibilities, including DFID’s own resourcing strategies (SRO, project team etc). / It sets out how it will respond to changes in context and the key elements of the Delivery Plan, key milestones and decision points where we can course correct. It includes a clear illustration of the risks, tolerances and approach to escalating problems and issues as well as exit and possible closure scenarios.