Type of Review: Annual Review

Project Title: China UK Global Health Support Programme (GHSP)

Date started: January 2013

Date review undertaken: 14-20 March 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context
What support is the UK providing?
DFID will provide £12 million over five years from October 2012 to September 2017.

What are the expected results?
The Impact of the GHSP is a China-UK partnership that contributes to improved global health policy and outcomes. / The Outcome of the GHSP is the China - UK partnership helps China improve its contribution to global health and achieve the potential of its health cooperation. / Outputs / Increased capacity to distill, disseminate and apply Chinese experience in improving health outcomes and strengthening health systems. / Improved understanding amongst Chinese officials and researchers of best practice in international health development cooperation (including bilateral and multilateral). / Enhanced capacity of Chinese officials and researchers to contribute to global health policy and governance. / Pilot partnerships apply China experience and international best practice in development cooperation in five developing countries that are preferably DFID priority countries and including cross border (with an Asian country) / Pilot partnerships will have the achievement of health outcomes as their desired impact. The programme will support Chinese expertise and technical assistance, but will require external funding or partnering for infrastructure or commodities. / Within these outputs DFID will also learn from China’s domestic experience and China’s approach to bilateral cooperation for health, as well as China’s engagement in global health.

What is the context in which UK support is provided?
Need to be addressed: / Progress towards the health related MDG targets is slow, particularly in Africa. New approaches and new players need to be engaged if progress is to be accelerated. / China’s Role in Global Health / China has achieved the health MDGs 4 and 5 and is on track with MDG 6, and has experiences to share with other countries. There is an increasing demand for learning from China’s achievements, and for Chinese assistance to address these outstanding health issues. China is beginning to meet this demand, building capacity to share experience and supply assistance. / China is an increasingly important contributor to global health efforts, including as a board member of key WHO and Global Fund to Fight HIV/AIDS, TB and Malaria (GFATM) decision-making bodies. China provides £108 million annually in bilateral health cooperation, and £18 million to global health agencies. / China’s White Paper on Foreign Aid seeks to improve its effectiveness. To achieve this objective, China needs an increased ability to engage in global health debates, needs to be able to draw upon its own experience of making progress, needs to better understand the public health needs of partner countries and to develop best practice for provision of international development cooperation in the health sector. / Partnership between UK and China / China intends to build this capacity to contribute to global health, both bilaterally and globally, to maximise and fulfil its potential contribution. UK support to China can help this process. This programme will enable the UK and China to build a strategic relationship on global health issues, drawing on the UK’s strong track record of working with China on health systems reform, HIV/AIDS and TB prevention and control in China. / The Governments of the UK and China signed a Memorandum of Understanding in 2011 to develop a partnership in international development. This programme will strengthen this partnership and help build Chinese capacity to increase engagement in global health. The partnership will support China’s own aim of improving the effectiveness of its international development cooperation in health (China Foreign Aid Policy). The programme will enable the international community to learn from China’s domestic experience and from China’s principles for and approach to international development cooperation for health. The UK and China will work together on issues of common concern, globally, or in third countries if requested. / Changes in context over the first year of the project: / Health has a higher profile in China’s health and development policy as a result of Ministerial Round Table supported by GHSP / There is growing support (particularly from MOFCOM) for the idea of pilot partnerships in low-income countries to implement lessons learned from China’s experience. / There is agreement that China should develop a national Global Health Strategy. / All these changes give signal added impetus and ownership of GHSP.

## Section A: Detailed Output Scoring

Output 1: Increased ability to distil and disseminate Chinese experience in improving health outcomes and strengthening health systems that is relevant to Low Income Countries (LIC).
Rating A - Outputs met expectation / Calendar year 2013 constitutes the inception phase of GHSP starting with the official launch workshop in January. For logframe/monitoring purposes, baseline is considered the point at which PIAs started project implementation. For convenience, we assume that implementation started 1st January 2014. The rating is therefore based on achievements specified in the first work plan and the outcome of interviews conducted with the three Project Implementation Agencies (PIAs). / The Project Management Office with support from the Technical Advisory Group has selected PIAs for OUTPUT1 following an evaluation of proposals in the three research Areas agreed by the Strategic Oversight Committee (SOC): a) Disease Prevention and Control, such as malaria, AIDS, Tuberculosis, Schistosomiasis, polio, etc. b) Reproductive Health / Maternal and Child Health care such as reducing maternal mortality ratio and infant mortality rate, such as safe motherhood, Maternal and Child Health, Expanded Programme of Immunization, Nutrition intervention for women and children, and c) Health Systems Strengthening, including universal health coverage, Human Resources for Health, etc. / Evaluation Procedure: PIAs were selected through open tender. The call for Expression of Interest (EOI) was published 26th June 2013. 36 agencies (universities, research institutes, technical/professional institutions and centers at national or provincial level) responded. Out of these, 25 were considered qualified but only 13 met the requirements to be shortlisted. The later group was then invited to prepare full proposals in August. The Evaluation Expert Panel (EEP) evaluated their proposals August/September and recommended 3 winning tenderers who got the highest proposal scores. After confirmation by SOC late 2013, three contracts were signed 26 January 2014 by PMO with the following PIAs: / To note: the budget originally proposed by the PIAs has been reduced through a process of negotiation with the PMO. The bidding process has contributed to getting well-qualified partners. The subsequent budget adjustments ensure value for money. / Research Areas in Global Health Winning Tenderer Budget RMB / GHSP-CS-OP1-01 / Disease Prevention and Control National Institute of Parasitic Disease, China CDC 3,441,538 / GHSP-CS-OP1-02 / Reproductive Health / Maternal and Child Healthcare Global Health Institution, Fudan University 3,780,000 / GHSP-CS-OP1-03 / Health Systems Strengthening School of Public Health, Peking University 4,057,200 / GHSP-CS-OP1-04 / The Practice and Experience Dissemination of China Integrated Care Pathway and Payment Reform National Health Development Research Centre 5,996,760
Progress against work plans / All three elements of this output have made progress since contracts were signed. OUTPUT1/1 - work has commenced in synthesizing China’s experience in malaria and schistosomiasis control and an initial field visit to Zanzibar has taken place. OUTPUT1/2: a planning workshop involving all national and international partners has taken place, with agreement on specific areas of concern to the three developing countries (Ghana, Lao PDR and Vietnam. OUTPUT3/3: a similar planning workshop has taken place with all international partners to agree on focus areas for the synthesis work (health financing, governance and human resources). / In addition to the three main project elements, a fourth area has been included which builds on earlier bilateral cooperation in the area of clinical pathways and payment reform. This element of the project will now offer support to other countries based on China’s experience. Reform of clinical pathways offers a means by which the project both contributes to better health outcomes in partner countries as well as a means of increasing value for money (through reducing inefficiencies and waste in health spending). / Recommendations: / No specific recommendations at this stage on OUTPUT1. See OUTPUT2 and 4 for recommendations with regard to future work on health systems strengthening and Universal Health Coverage / Impact Weighting (%): Unchanged: 20% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? / Yes. Risk rating revised downwards in the light of a) positive reaction by African and other low income countries to learning from Chinese experience, suggesting that the lessons emerging in initial workshops are relevant; b) the proposals prepared by PIAs suggest good analytic capacity to synthesize information; and c) rapid progress in forming partnerships following award of contracts. The only downside risk to be monitored in subsequent reviews concerns the capacity of Chinese institutions to lead complex collaborative consortia involving several international partners.

Output 2: Improved understanding amongst Chinese officials and researchers of best practice in international health development cooperation (including bilateral and multilateral)
Rating A - Outputs met expectation / PIAs for OUTPUT2 have been selected following evaluation of proposals on Centre of Excellence in Health Development Aid in China. The main objective is to improve the capacity of Chinese institutions in the field of development assistance for health (DAH) with support from GHSP. The aim is thus to create a Centre of Excellence for external health aid provided by China. The Centre will operate as a network, eventually providing a platform for government officials and researchers by organizing various kinds of activities, furthering their understanding of best practices for DAH. Government officials will be able to develop and implement better policies to emphasize China’s role in external DAH; researchers will better participate in development and implementation of policies on DAH of China; and ultimately bilateral and multi-lateral collaborations on health between China and other countries will be strengthened. / Evaluation Procedure: The Call for EOI was published 26th July 2013. 21 agencies presented EOIs in August. Out of which, 14 were considered qualified but only 5 met the requirements to be shortlisted and were invited to prepare Proposals in August. The EEP evaluated their proposals October/November and recommended 3 winning tenderers. SOC confirmed the following PIAs on 29th November 2013. / The rating is based on completion of activities specified in the annual work plan and indications of progress following signing of contracts. / Centre of Excellence in Health Development Aid Winning Tenderer Budget RMB / GHSP-CS-OP2-01 / Centre of Excellence in HDA School of Public Health, Peking University 3,999,240 / GHSP-CS-OP2-02 / Centre of Excellence in HDA China National Health and Development Research Centre 3,995,028 / GHSP-CS-OP2-03 / Centre of Excellence in HDA National Institute of Parasitic Disease, China CDC 3,999,834
Progress against expected results: / Contracts with the PIAs have not yet been signed. However, there has been considerable progress in developing work plans, which suggest that the need to have a more clear division of labour between the three PIAs is well understood. A launch workshop for the PIAs and partners involved in OUTPUT2 and OUTPUT3 is planned for early April. / A significant element of this output is the annual course on Health Diplomacy. The course in 2013 involved a range of partners from African countries. The 2014 course will involve partners from other BRICS countries. While the course is welcomed and valued by senior officials and participants, it will be important to consider the opportunity cost to the PIA implementing OUTPUT2/1 given the proportion of their budget devoted to this activity. / During the year the 4th Africa-China Health Roundtable was held and a fifth meeting is planned for August 2014. This activity while conceptually part of OUTPUT2 GHSP financial input is separately financed. More detailed comments are contained in the narrative report. The key issue is to ensure that future roundtables result in concrete follow-up activities. / Recommendations: / The Strategic Oversight Committee should consider how the network of PIAs involved in OPs 2 and 3 will in the future be constituted more formally as a Global Health Network and communicate the results of its decisions to PIAs. Issues to be considered include: governance and coordination roles (in particular the respective roles of government and academic institutions in governance and coordination); whether or not a further round of bidding is required; resource allocation and funding disbursement processes. / In the further development of work plans it will be important to ensure sufficient time and resources be devoted to country case studies (e.g. those proposed for Uganda and malaria control in Africa). Direct observation of Chinese investments in countries, and participation in joint annual reviews with other development partners are critical to the development of an understanding of best practice and thus they are central to the objective of capacity building. It is our view that these activities should be given greater weight than the development of textbooks. / In line with point b) it is recommended that the project seeks opportunities for senior officials from the government and PIAs to participate, initially as observers, in joint health sector reviews in Africa, to be facilitated by WHO through the International Health Partnership. Follow up should involve the WHO Country Office in Beijing and WHO HQ in Geneva. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 3: Enhanced ability of Chinese officials and researchers to contribute to global health policy and governance.
Rating A - Outputs met expectation / PIAs for OUTPUT3 have been selected following the evaluation of proposals on Global Health Policy Development and Governance. The main objectives are to improve the capacities of Chinese institutions in the field of global health policy development and governance. The project will strengthen their long-term capacities through policy and academic research, organization and participation of national and international trainings and exchange, international conferences, etc. To disseminate China’s successful experiences, cultivate a number of government officials and researchers with the background knowledge of global health, and provide technical support for Chinese government on developing national global health strategies and participating in global health affairs. / Evaluation Procedure: Call for EOI was published 26th July 2013. 13 agencies presented EOIs in August. 6 qualified agencies submitted Proposals in September and 2 of them were presented to the EEP for evaluation in October/November. These two were recommended winning tenderers. SOC confirmed the following PIAs on 29th November 2013. / Centre of Excellence in Global Health Policy Development and Governance in China Winning Tenderer Budget RMB / GHSP-CS-OP3-01 School of Public Health, Peking University 4,499,546 / GHSP-CS-OP3-02 School of Public Health, Fudan University 4,498,200
Progress against expected results: / We note the strong degree of synergy between OUTPUT2 and OUTPUT3. This is evidenced by collaboration and discussion between the PIAs involved that has taken place already. There is evidence from our interviews that a clear division of labour is beginning to emerge. This should be further advanced at the launch workshop scheduled to take place in April 2014. / A key development in the last year is agreement within government to develop a national policy for China on Global Health similar to those prepared by other OECD countries, including the UK. The development of such a policy falls under this output and has the potential to become a key outcome of GHSP. / Recommendations: / At the design stage there was no agreement to proceed with a Chinese Global Health Strategy. Given that this will now go ahead, successful development and negotiation across government of such a strategy should be recognized in the Business Case and theory of change as a key outcome of GHSP. / This output suggests the need for better preparation of Chinese delegations to key global health meetings. With regard to the WHA, more could be done with the WHO country office and WHO HQ to help officials get a better sense of priorities (within an overcrowded agenda) and to develop policy positions. / Given the overlap between OUTPUT2 and OUTPUT3 it is recommended that they be given equal weighting (25%). See also proposal to change the weighting of OUTPUT4 below. / Impact Weighting (%): 25% / Revised since last Annual Review? Yes. There is considerable synergy between OUTPUT2 and OUTPUT3, we therefore recommend that they be given equal weighting. / Risk: Low / Revised since last Annual Review? No

Output 4: Pilot partnerships apply China experience and international best practice in development cooperation in Low Income Countries and cross border (probably to include in the first instance Malaria, Universal Health Coverage, Maternal and Child Health, Polio and Human Resources for Health).
Rating A - Outputs met expectation / Output four is based on the idea that pilot initiatives in a range of developing countries would be developed out of the collaboration between Chinese institutions and their international partners. At the design stage this was seen as a sequential process. However, it is evident from the interviews with PIAs and discussions with senior officials that there is a keen interest in developing this aspect of GHSP more rapidly, in effect in parallel with the other OUTPUTs. We note that plans are being discussed for collaboration in relation to a) malaria and schistosomiasis control; b) maternal and child health, and c) health systems strengthening. / In the narrative report we suggest that the speed of development will vary between these three groupings. Work in a) could proceed more or less immediately. Work in b) could be initiated in the coming year. Work in c) however involves systemic change in the countries concerned (e.g. in health financing). This requires a somewhat different approach and it is recommended that a prior step is for Chinese officials to take part in annual joint sector reviews in order to build experience of working with other development partners on sector policy. This does not necessarily imply that China will adopt the position of a traditional donor. Rather, China’s contribution of experience should be seen as a practical expression of south-south cooperation. / The final point in relation to OUTPUT4 concerns management of expectations. From all our interviews it is clear that expectations on the Chinese side focus on building capacity and capability. In terms of increasing research and analysis skills, these are clearly a means to an end. However, a project that results in a government endorsed global health strategy is a valuable outcome in itself in terms of the future impact of Chinese investment in the health sector, and Chinese engagement in Global Health Governance (see OUTPUT3 above). At the same time, the project needs to prove its worth in terms of the impact of short-term interventions generated as a result of the planned collaboration between Chinese institutions, international partners and developing country governments. / Our review suggests that the prospects for OUTPUTs are positive and the OUTPUT should be judged as being on track.
Recommendations: / In line with the original project design and theory of change we recommend that this output retain the highest weighting, but that it should be lower than originally proposed. We recommend weights of 20, 25, 25, 30% respectively for OUTPUTs 1-4. / Impact Weighting (%): 30% / Revised since last Annual Review? Yes, see above / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? / An Independent Evaluation Team has been recruited directly by DfID China. Following an orientation meeting in January 2014, the logframe has been revised in order to clarify the description of outputs, to define key terms and indicators, and approaches to monitoring. Collection of baseline data is currently underway and will be reported shortly. It is our understanding that the revisions to the logframe are concerned to increase the clarity and to ensure effective monitoring. They do not change the fundamental structure or purpose of the project. / 1.2 Overall Output Score and Description: / A - Outputs met expectation / 1.3 Direct feedback from beneficiaries / Feedback from senior officials in NHFPC and MOFCOM has been very positive. There is clear interest and ownership of the project and it is seen as being of significant long-term value for China. While other OECD partners have expressed similar interests in supporting China’s role in global health, GHSP is seen as the primary vehicle. It is also said that the project has contributed to increasing the profile of health as a component of Chinese development cooperation. / PIAs equally are enthusiastic about the prospects for the project, noting of course, that their work has only just begun. While there are difficulties to be overcome (notably in relation to payment of overseas institutions) we had a strong sense that the GHSP has made a positive contribution to enhancing Chinese leadership of the various consortia.
1.4 Summary of overall progress / The activities carried out by PIAs are detailed in the sections above. / The design of the project has required a long inception period but this would appear to be justified given its innovative nature. Specifically, the first year has resulted in the establishment of project governance - the strategic oversight committee (SOC), the Technical Advisory Group (TAG) and the Project management Office (PMO). These building blocks will enable more rapid progress in the future. / Defining priorities and the criteria for awarding contracts collaboratively has had the effect of increasing ownership on the part of both NHFPC and MOFCOM, building partnerships within and between Chinese academic institutions (extending beyond health to other disciplines), and securing value for money. / There can be little doubt that the role defined for the PMO has been and will in the future be critical in ensuring that GHSP provides value for money. This is evidenced by the fact that the level of effort required to manage the project is, given past experience of the centre that hosts the PMO, much less than has been required to run other DfID and World Bank projects, with no apparent loss of effectiveness. Moreover, the PMO has secured the engagement of many international partners at far less than current market rates.
1.5 Key challenges / Project implementation: / For outputs 1-3, the key challenges are a) that Chinese institutions are able to manage and lead complex consortia. Evidence to date in this regard is promising; b) That capacity building is seen not just in terms of producing academic papers and textbooks, but building experience of development cooperation in practice. Our recommendations cover this issue; c) that the health and diplomacy course continues contributes to the outputs of the project in terms of creating a link between Chinese experience and follow up by participants in other countries: d) that the GHSP contribution to the China-Africa Roundtable defines a follow up programme of work relevant to the needs of participating African countries. / Technical advice and support: / Technical Advisory Group (TAG) / The role of the TAG is to provide advice to the Project Management Office and to prepare meetings of the SOC. To date the TAG has met face to face only on a very limited number of occasions and its work has been dominated by the tasks of reviewing and selecting PIA proposals. The review team are of the view that the need for technical advice is likely to increase as implementation proceeds. The issue to be addressed therefore is how to increase the capacity of the TAG. / While there are many people well-qualified to join the TAG group as senior members, the vast majority are members of one or more of the consortia implementing the project. Involvement in the TAG would make them ineligible to continue as implementers. An alternative would be to recruit a more junior technical support team, with a role that focuses particularly on support to the PMO. Such a support team can give the PMO greater insight into what the project is seeking to achieve in technical terms. It can also act as a filter in singling out the issues that require the attention of the senior members of the TAG. / Recommendation: Opinions are divided as to whether a second-tier technical support team (TST) should be formally attached to PMO or whether they should be managed as an extension of the TAG. The Annual Review team however suggests that this issue be taken up for decision at a forthcoming meeting of SOC. / Project management: / Discussions with PMO staff and PIAs suggest there are some problems in the way that the project is currently managed. A theme that underpins many of the concerns is the perceived need to reconcile project management procedures based on Chinese rules and procedures with those that are required by DfID. It is our view that some of these differences can be resolved and have been discussed at length with the PMO. There remains one issue of concern that is going to require the attention of the SOC. / Problems discussed with the review team include the nature of the contracts with PIAs (specifically how invoices are presented), the limited management capacity of PIAs (taking academic staff away from their main duties), flexibility to change the details of annual work plans without recourse to the SOC, and the level of payments to international partners. The review team understands that all these issues have been discussed at length with the PMO staff and that the project provides a degree of flexibility within which they can all be resolved. Specifically in relation to the payment of international consultant, the Project Management Manual specifically notes that, if required, market rates can be applied. With regard to the issues listed in this paragraph the Review Team do not make any immediate recommendations. However, we do recommend that the next Annual review ensure that these issues have been satisfactorily resolved to the satisfaction of all stakeholders. / The one issue where action is required concerns the transfer of resources by PIAs to international partners. Our understanding from PIAs and the PMO is that current Chinese rules do not allow such payments to be made in convertible currencies - institution to institution. There is a work-around that has been used by some of the PIAs already. This requires the use of individual allowances for financial transfers. These individual allowances are capped and, we understand, that their use is an imposition on the individuals whose allowances are thereby reduced. It is not in the power of DfID to change a government-wide system. Nevertheless this represents a risk to the project. We therefore recommend that this issue be discussed by the SOC as a matter of urgency and a decision on how to proceed be communicated to the PMO and to all PIAs.
1.6 Annual Outcome Assessment / After the successful completion of project inception period GHSP is in a position to realize the project outcomes defined in the Business Case. The Annual Review reaffirms the evidence underpinning the project outputs. The most notable development in terms of the theory of change is agreement by government to develop an overall national Global Health Strategy. This should be recognized as an intermediate outcome in its own right.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / From the interview with PMO staff it appears that the project is on track with regard to actual versus anticipated expenditures. This to be confirmed by the annual report of the PMO, which is expected shortly. / 2.2 Key cost drivers / The cost drivers identified in the business case remain unchanged. A key issue concerns the balance of resources allocated to international consultants. If these were paid at market rates the balance of project expenditures would shift markedly to foreign institutions. However the rates negotiated represent very good value for money and have been accepted by PIAs. In effect, several foreign institutions, including those in the UK are providing a significant subsidy to the project. / 2.3 Is the project on-track against original timescale: / Yes (assuming January 2014 is the starting date for implementation of OUTPUT1, OUTPUT2 and OUTPUT3.) Also see notes above in relation to the timing of OUTPUT4 which is likely to be advanced from what was originally proposed.

3. Evidence and Evaluation
Assess any changes in evidence and implications for the project / The Annual Review has strengthened the evidence supporting the likelihood of achieving the outputs of the project in several areas as noted above. / 3.2 Where an evaluation is planned what progress has been made? / An independent evaluation team has been contracted and has started work in defining indicators and collecting baseline data

4. Risk
4.1 Output Risk Rating: Low / The overall Risk for all the Output is defined in the logframe as follows: / The risk rating for OUTPUT1 is Medium: the lessons learned from China's experiences are not relevant or not transferrable to other countries. The risk management includes joint research with institutions from LICs interested in using Chinese experiences. / The risk for OUTPUT2 is Low: the willingness and capacity of Chinese institutions to participate in the programme is not high enough. The management of the risk includes PMO's monitoring and reporting to SOC on numbers of institutions participating in bids, tenders, and programme activities. / The risk for OUTPUT3 is Low: that willingness and capacity of Chinese institutions to participate in the programme is not high enough. The management of the risk includes PMO's monitoring and reporting to SOC on numbers of institutions participating in bids, tenders, and programme activities. / The risk for OUTPUT4 is Medium: the pilot partnerships do not secure funding for necessary goods and commodities required for their implementation. The management of this risk consists of exploration by SOC, DFID, NHFPC and 3rd party governments of various options for linking pilot partnerships with new or existing funding sources. / 4.2 Assessment of the risk level / More detailed comments on risk in relation to different elements of OUTPUT 1-3 are noted in section A above. The most significant change is to lower the risk rating for OUTPUT1 from medium to low. Risks in relation to project management are detailed in section B. / In summary the overall risk rating remains low.
Risk of funds not being used as intended / The Review team found no evidence of funds not being used as intended at this stage in the project. We reemphasis the need to come to an agreement as to how funds are transferred to international partners (see section B) / Climate and Environment Risk / Remains Category C

5. Value for Money
5.1 Performance on VfM measures / The project has the potential to achieve value for money in terms of its outputs and eventual outcome. Interviews with NHFPC and MOFCOM recognized that while China has been a significant investor in health development, relatively little attention has been paid to the achievement of results. A better understanding of current practice in development, reviews of past experience in Africa and exposure to the practices of other development partners are likely to increase the focus of Chinese aid on the achievement of value for money in future. Some projects, in addition, are likely to have an impact on value for money. A good example is the work on using standardised treatment practices and linking these to the performance of providers. This is an issue of concern to many countries (e.g. India and South Africa) that are undergoing health care reforms. The experience of China’s own health sector will be particularly useful in this regard. / 5.2 Commercial Improvement and Value for Money / Section A above details the response to the tender to contract with the project. The process of competition required that participating institutions took into account value for money considerations - in regard to their own costs and those of their international partners. However, we note that the scaling back of proposed budgets depended on the development of benchmark costs by the PMO more than commercial competition per se. Nevertheless, as noted above, the costs of project management and the price paid for international consultants appears to be lower than existing market rates and should be seen as a significant achievement in terms of VfM, provided that no loss of effectiveness results. / 5.3 Role of project partners / It is too early to judge at this stage whether changes in performance on the part of PIAs merit scaling up or down of payments. Nevertheless, there is the potential to act on performance information as the project progresses further into the stage of implementation. / PIAs have responsibility for managing their budgets. Most do not have their own project management staff and have given this responsibility to junior academics. Future reviews will need to examine how they handle this new responsibility. / For the PMO to be more effective in driving DfID’s concerns for VfM it is important that the staff understand better the nature of the project they are managing. This will be an important role of the Technical Support Group recommended in Section B. / DfID China maintains pressure on the PMO to obtain value for money. Given that the project is at an early stage, it is tempting for the PMO staff to constantly refer questions back to NHFPC or to DfID. A future review should consider the degree to which PMO takes fuller responsibility for these issues itself. / 5.4 Does the project still represent Value for Money : Yes. The assumption detailed in the Business Case about the potential value for money gains through more effective and efficient Chinese aid remain valid and the risk of Chinese experience not being relevant to LMICs appears to have reduced (see notes on OUTPUT1 and OUTPUT4). The way project governance and management is designed focuses on value for money and efficiency. The main challenge, as noted above, is for the PMO to internalize these concerns in its own operations.

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
The review takes place at an early stage of implementation, but finds that time and resources have been well invested in creating a strong sense of ownership by key government ministries (NHFPC and MOFCOM) and among PIAs. / The design focuses on the development of partnerships within each group of PIAs. The challenge as the project progresses is to build a sustainable and well-managed and coordinated network that can support improvements in Chinese development cooperation. / Recommendations set out in Section A focus on seeking opportunities to expose Chinese officials and researchers to the realities of development cooperation in the field as a key element of capacity building. / Project management of GHSP is complex but the Annual Review finds that all the building blocks are in place to support implementation. Ensuring the availability of technical advice through a technical support group and ensuring that the PMO internalizes the management philosophy of the project constitute our key recommendations.

8. Review Process
The annual review was conducted by Dr. Andrew Cassels, international consultant and team leader, and Mr. Yunfu Song, national consultant. (Terms of Reference, see Annex 1) / Dr. Cassels drafted the Annual Review Report with the inputs from Mr. Song. / The review was based on document reviews including: / Detailed Guidance (How to Note)- Reviewing and Scoring Projects / Business Case (Intervention Summary) of GHSP / GHSP Logframe / Orientation Meeting Report by the Independent Evaluation Team / PIAs Implementation Tendering Proposals / Work Plans for main activities / Relevant meeting minutes and activity reports by PMO， / Half year progress report by PMO / Briefing to Annual Review Team members late February prior to conducting the Interview in Beijing / Interviews undertaken from 10th to 14th March 2014 in Beijing. The AR Team met separately with DFID China, SOC, PMO and PIA (face to face or via telephone). Agenda and list of interviewees are at Annex 2) / Debriefing to DFID China / Drafting and finalizing Annual Review Report to DFID China by 20th March 2014 / To note: It is recommended that future annual reviews, to the extent possible (recognizing that some TAG members are resident overseas), be conducted by means of face-to-face interviews.