Type of Review: Annual Review

Project Title: Dialogo – Democratic Governance Support Programme

Date started: February 2012	Date review undertaken: March 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Introduction and Context
What support is the UK providing?
The UK is supporting the Democratic Governance Support Programme (Dialogo) which aims to improve good governance, accountability and responsiveness at Municipal level. The programme works with different stakeholders including Municipal institutions; civil society and civic groups; and the media, building communication between these different stakeholders to work together and solve municipal level problems. It includes a particular focus on women and youth. The programme works in five municipalities: Maputo, Quelimane, Beira, Tete and Nampula. / The programme runs from February 2012 to February 2017. In its first year, the inception phase, the programme spent £1.2 million. The budget for four year implementation phase (2013-2017) is £6.8 million. The programme is run by a Programme Management Unit (PMU) based in Maputo.

What are the expected results?
The overall vision and mandate of the program is that regular, mutually-productive interactions between citizens and local governments will improve governance and strengthen democracy at the local level. At the same time, increased awareness of these interactions through media coverage and independent research on these same local issues will be reflected in national policy. / As a result of the activities under this programme, women, young people and men will increasingly participate in a meaningful way in the decision-making and political processes at a local level in the target municipalities. They will have a better understanding of the possibilities and limitations of municipal level government, and will have established processes and channels for discussion and communication between citizens and decision-makers. These will act as a decompression chamber for social and economic frustration. / At impact level citizens’ priorities will begin to be a part of the municipal agenda. In the target municipalities, the project will see up to a 5% increase in the quality of citizen participation in municipal governance (from 22.4% in the Baseline Survey); and citizens will report an increase in the accessibility and importance of municipal assemblies and councils. / At outcome level there will be increase to 24% (from 17% in the Baseline Survey) of respondents who say that information accessed about Municipal Council business (such as solid waste collection) was easy to both find and understand; an 8% increase (from 0.6% to 8.6%) of respondents who say that help in addressing problems affecting the neighbourhood is always or usually forthcoming from CSOs; and a 8% increase (from 49% to 57%) in respondents who feel their opinion is taken into account in community meetings. / At output level, the program will increase the number of CSOs engaging with municipal institutions on priority issues; and support civic groups on engagement practices. The programme will increase the number of media programmes on municipal governance and electoral processes; train journalists; and install ICTs in media outlets. And with the municipalities, it will increase communication initiatives to disseminate municipal information; and support each municipality Action Plan.

What is the context in which UK support is provided?
Mozambique’s formal commitment to democracy is apparent in its legal and planning framework. The Constitution of the Republic establishes a democratic system of government, with a strong bias in favour of Presidential power. The Government of Mozambique’s current five-year plan highlights a commitment to continuing with a people-focussed process of decentralisation, promoting good practice in governance in order to combat poverty and promote social, economic and cultural development. This includes the consolidation of democracy and reinforcing civil society participation in local development. / However, the country faces political, financial and administrative accountability deficits. The institutional checks and balances between the executive, legislature and the judiciary are weak, and there is no clear separation between the ruling party, Frelimo, and the state. Frelimo is entrenched in power, increasingly dominant in and intertwined with the private sector. There is growing evidence of senior political leaders and government officials using office to seek rents. Poverty is not decreasing (despite economic growth) and there is a growing perception of increasing inequity in the distribution of wealth and services, with women suffering disproportionately. / At the municipal level, democratic governance is a work in progress. Municipal institutions were first elected in 1998, with elections taking place every five years. Dialogo research during the inception phase confirmed that citizens and municipal governments are not effectively communicating or partnering to solve local issues. Some platforms or structures exist for public engagement, but these are have not been effectively used. In particular, participation by women and youth seems disproportionately low. The baseline study confirmed that this is resulting in little accountability for the policies and programmes funded or executed by municipal governments. / Additionally, as was made clear during the inception phase of Dialogo, different municipalities’ present different challenges – both politically and in terms of the capacity of stakeholders including civil society, media and municipal institutions. For example, the baseline survey showed that the capacity of civil society is higher in Nampula than in Tete; while the municipal institutions in Quelimane are more responsive than in Maputo. / Municipal elections in November 2013 have significantly changed the political context within which Dialogo is working. In the run up to the elections, the Frelimo government became more sensitive to challenge with some civil society organisations being intimidated or prevented from working entirely. The state media became more partisan while private media outlets have become noticeably less critical of government policies. / During the elections themselves, the security environment deteriorated. There were incidents of violence with civilians reportedly killed by the police. The opposition party, Renamo, frustrated at their waning political and economic influence, boycotted the elections and while they did not target the elections specifically, attacked government buildings and vehicles in the centre of the country. The government responded with the use of military force, resulting in localised violent clashes killing soldiers, Renamo members and civilians. With memories of the 16 year Frelimo-Renamo war still fresh, there has been an increasingly tense environment where even rumours of a Renamo presence has caused communities to flee. / In terms of the results of the municipal elections, nationwide Frelimo won 49 of the 53 the Municipal Presidents (mayors), with the opposition party MDM increasing from two to four. In terms of the Municipal Assemblies, Frelimo’s nationwide share of seats decreased from 80% (in 2008) to 69%; while MDM’s increased from 19% (2008) to 30%. In Dialogo municipalities, there are now three MDM mayors and three MDM led Assembles (Beira, Nampula, Quelimane); while in Maputo and Tete, MDM’s share of seats in the assemblies has significantly increased. The results also mean that in all Municipalities, the Mayor’s party also holds the majority in the Assembly (not previously the case in either Beira or Quelimane). This should lead to greater consistency between the actions of the two main municipal institutions. / Most analysts agree (and as seen by the review team) that these political changes in the municipal institutions have begun to foster a new sense of accountability. There is a sense that citizens can, to some degree, reject Municipal institutions that do not respond to their needs. Civil society groups say they feel increasingly able to represent citizens and advocate for change. There is an increased awareness across political parties of the need to develop inclusive institutions at the municipal level for dialogue with civil society, civic groups and the media in tackling municipal issues. / Looking ahead, 2014 will see Presidential and general elections. This could mean that the space nationwide for civil society and in particular the media, to operate could diminish further. In addition, political parties will be seeking to limit their opponents’ successes. For example, MDM municipalities could find themselves under certain restrictions from central government. How much the municipalities are affected by elections remains to be seen.

Section A: Detailed Output Scoring
Output 1: Civic Engagement
Output 1 score and performance description: A + / Despite some indicators not being met in some municipalities, overall the majority of Output 1 indicators were exceeded. During 2013, Dialogo has rightly, given the political context and the municipal elections in particular, focused on working with civil society and overall there has been significant and rapid progress. The PMU spent a considerable part of 2013 identifying implementing partners and ensuring a match in vision with Dialogo. This was a crucial process but meant that implementation with CESC only began in June and with local CSOs in August. This makes the achievement of this output all the more impressive. Even in a more challenging context (Tete) there is a strong sense of opportunity for CSOs to engage at the municipal level and push municipal officials to make good on campaign pledges. / Number of civic groups assisted on engagement practices / Maputo Beira Tete Quelimane Nampula / Milestone 15 9 9 12 8 / Achieved 5 3 15 15 22 / The numbers of civic groups assisted at the local level have, with the exception of Maputo and Beira, exceeded the target indicators. Dialogo understands civic groups as the set of grassroots organizations or informal groups of citizens that, in the face of issues that significantly affect their living conditions, organize and mobilize themselves (in their neighbourhoods, market, churches, etc.) to carry out actions aimed at creating positive changes. / The large number of civic groups assisted in Nampula reflects that there are already numerous well-established civic groups there. This has allowed both the CESC facilitator and the CSO partner, Facilidade, to work with civic groups; in other municipalities it is just the former. / Where the indicator was not met, Dialogo is working to increase its support to civic groups. In Beira, the Dialogo local partner PNDH is investing in supporting the new community development committees, created by the municipality to identify issues/problems in the neighbourhoods and communicate them to the municipality. In Maputo, Livaningo has helped organize three social audit committees to assist with mobilization, participation and monitoring of the participatory budgeting process. / In all municipalities, targets should be revised to better align with expected results. Additionally, as is common with most of the reviewed output indicators, clear guidance on interpreting and counting each indicator is required to ensure consistency in reporting across the programme. / 1.2 Number of coalitions working around priority issues / Maputo Beira Tete Quelimane Nampula / Milestone 1 1 0 1 1 / Achieved 2 1 1 1 2 / The target of one coalition per municipality (except in Tete) was exceeded in three municipalities and met in two. Examples of coalitions working around priority issues include: / the Dialogo partner in Maputo, RUth, has created a network of associations to advocate for urban transport improvements; / CESC is supporting civic groups in Maputo to work as a coalition to present their joint priorities to municipal authorities; / in Nampula there is a coalition between Dialogo partners (Association of Widowed Women, Wamphula Fax and Radio Encontro ) to advocate for improved sanitary facilities at a local market; and / a coalition of CSOs, organized by Facilidade in Nampula, has been established to co-ordinate their activities on Municipal issues. / The programme defines a “coalition” as a platform of CSOs working together on issues. It might be more effective to widen this definition given the potential benefit from working with other types of organisations including the private sector or more informal groupings e.g. church groups. For example in Tete there are significant opportunities to for CSO to engage with the private sector on municipal issues. In addition, it would be useful to measure what the “priority issues” are (e.g. is it all about budgeting processes, or land use, or waste collection?). This would provide a better sense of how the programme is responding to the specific needs of each municipality. / 1.3 Number of CSOs (including civic groups) that engage with municipal institutions on current priority issues (disaggregated by type of organization - youth and gender focused). / Maputo Beira Tete Quelimane Nampula / Milestone 4 3 2 2 4 / Achieved 5 5 7 28 7 / The target was exceeded in all five municipalities. When disaggregated all municipalities had at least one group that was focussed on gender and youth. The large number of CSOs engaging with municipal institutions in Quelimane reflects the creation of a platform of 27 CSOs who engaged both jointly and individually with municipal institutions, particularly on budget processes. / Further guidance is needed on reporting on this indicator to determine whether an organisation needs to be focused on either youth or gender, or on both to be counted.
Progress against expected results: / Progress against Output 1 is clearly on track. Below is analysis that leads to recommendations to further increase the impact of this output. / Capacity of CSO and civic groups / As was noted in the Inception Report, Dialogo is not designed to be a capacity building programme. But it faces a number of capacity related constraints with concerns around the ability of CSOs and civic groups to fully engage in complex municipal issues. Dialogo partner CSOs, whose experience has often largely focussed on direct service delivery, have had to switch to engaging government to deliver, which requires a new type of approach in terms of advocacy, lobbying and engagement with municipal officials and institutions. In Tete, for example, Fundacao Apoio Amigo (FAA) are capable but potentially over-stretched, while in Nampula, the CSO partner, Facilidade is well-connected to the municipality but its civic groups need significant support in understanding the basic building blocks of accountability. In addition, some of the partner CSOs’ strategic direction may not necessarily coincide with Dialogo goals; and there is the issue of co-option and political capture. Dialogo assesses this risk to be highest in Maputo. The PMU has recognised this risk, and on the basis of partner capacity assessments, has provided mentoring and coaching to CSOs. / But the PMU cannot and should not attempt to build capacity of CSOs on its own. It has neither the structure nor the budget to do so. Rather, it needs to bring in other programmes that specialise in capacity building to provide this support. There are already some good examples of this collaboration taking place MASC but more could be done to build this link including with non-DFID programmes e.g. Agir. This will likely need to be done at the central level by the PMU with DFID support, recognising that it is a complex process. / The Role of Facilitators and local CSOs / In each Municipality, Dialogo has a facilitator, managed through CESC. Facilitators are already working well with civic groups, with 14 Community Action Plans developed in 2013. But their role must go beyond this. Their most crucial role should be linking the civic groups to the programme’s other partners (civil society/ other concerned stakeholders, municipality and media); and drawing in technical and other support from related programmes. This requires working closely with the local CSO who will, according to the theory of change, provide the “vertical link” between the programme and the municipality, taking the concerns of civic groups and media to the municipal institutions. / In Nampula this is working well. For example, the facilitator was able to support the Mayor’s initiative for a “voluntary clean-up day” bringing in the civic groups to help clear rubbish and the local radio station to encourage further citizen involvement. There also appears to be a clear division of responsibility between the facilitator (supporting civic groups and linking them with the other programme groups) and the CSO (taking civic groups concerns to the municipal level and playing the advocacy role). This coherent, issue-based approach is exactly how Dialogo was intended to work - and Nampula now has some evidence that this approach is effective. / But there are examples where the theory does not fit reality. This may be because the local CSO organisation is more experienced in working with civic groups and does not have the capacity to play the “vertical linking” role to the municipality. In Tete, civic group’s community action plans did not involve CSOs, and the CSO platform was in the process of developing a separate action plan. Although plans for the platform and community action plans will differ in content and focus, they should be complementary and mutually coherent. Civic groups are focussed on community development – and ultimately so is the work of CSOs. / This points towards the need for a more flexible, individual approach in each municipality, based on the reality of capacity of both the CSO and the facilitator. If the local CSO simply does not have the expertise/ability to work with the municipality, can the facilitator adapt to support this role, or are there other options? A more flexible approach is necessarily more complicated but is likely to be more effective. / Gender / One of the key principles underpinning Dialogo’s programme logic is the need for inclusion of women and youth. Positively, there is a gender and social inclusion strategy to guide partners. But while there were exceptions (e.g.Parliamento Juvenil (PJ) in Tete and the CESC civic groups in Nampula), partners were largely unable to point to any specific actions to mainstream gender into work at the municipal level, or indeed to fully articulate the challenges relating to gender inequality. An additional challenge is that each municipality is likely to face different issues in relation to gender. One approach would then be to ask each Dialogo municipal team to identify the key “gender issue” and then set out their approach to address it during the year. This may not necessarily be about the number of women in each meeting or in each CSO (as the current targets set out). This would make their strategy more grounded in reality and more directly relevant to partners. / Recommendations: / To avoid inconsistent reporting the PMU needs to develop indicator guidance for 1.1. and 1.3 for DFID review and approval, including any revision of targets based on these definitions. / DFID needs to develop stronger incentives for collaboration on CSO capacity building between Dialogo and other programmes such as MASC, AAA and Dialogo. This would ideally be through the introduction of targets and indicators relating to collaboration. Additionally Dialogo consortium members can continue to work with other initiatives (e.g. Agir, and MUNISAM partners, donor forums) to look for mutual support. / In terms of how facilitators and CSOs work together, the PMU should take a more flexible, individual approach in each municipality, based on the reality of capacity of both the CSO and the facilitator. As part of this, Dialogo should consider how to develop platforms to bring together all Dialogo stakeholders in each municipality. The proposed municipal observatory is linked to the annual budget and planning cycle and would be one such platform, but more frequent opportunities to engage across stakeholders would be beneficial. / The definition of a “coalition” should be broader to include private sector and informal groupings. This could add significant value if well considered and implemented. Leveraging private sector investment would be a strong example of VFM and could be done so without compromising CSO independence if handled well. / In due course, PMU should consider monitoring the type of issues coalitions are engaging municipal institutions on to provide a better sense of how the programme is responding to the specific needs of each municipality. / As part of implementing their gender strategy and of taking a more individual municipal approach, the PMU needs to work with each of its municipal partners to identify the key “gender issue” and then set out their approach to address it during the year. / Impact Weighting: 40% / Revised since last Annual Review? Yes. In the last annual review Output 1 (“knowledge of democratic principles by citizens”) was weighted as 15%. But in response to recommendations from the inception review, the programme was reduced from five outputs to three. This meant that the impact weighting in the three remaining outputs increased. Output 1 has the greatest impact weighting in 2013 reflecting the focus on this work in the first year of implementation. / Risk: Medium / Revised since last Annual Review? No

Output 2: Strengthen and Engage Media
Output 2 score and performance description: A / Despite agreements with media partners being signed relatively late into the programme year, there has been solid progress. Interactive media programmes on municipal issues were held in each municipality and ICTs have also been installed in three municipalities. Positively, there was also evidence of the media working together with the civic groups to promote their concerns. Going forward, the programme will need a clearer strategy on the use of ICTs and to focus on linking with other programmes to provide capacity support to media partners. / 2.1 Number of interactive media programmes (radio, television, newspaper) on municipal governance / Maputo Beira Tete Quelimane Nampula / Milestone 1 1 0 1 2 / Achieved 1 TV programme / 3 press articles 1 TV programme / 4 press articles / 12 radio programme transmissions 1 TV programme / 6 press articles 1 TV programme / 5 press articles / 8 radio programme transmissions 1 TV prog / 32 press articles 13 radio programme transmissions / Targets were exceeded in all municipalities. Dialogo’s approach is different in each municipality given the different gaps in media coverage. For example, Nampula and Maputo have a relatively diverse and active private media covering municipal issues, whilst in Tete Dialogo funds 50% of a Canal Mozambique (CM) journalist in order to have any private media coverage of municipal issues at all. Nampula has had significantly more media programmes due to the programme’s two media partners starting work sooner than in other municipalities. Targets will have to be reviewed and guidance on reporting against this indicator developed. Without this inconsistent counting or double counting against other similar indicators is possible. / 2.2 Number of trained journalist on several issues (1st year on electoral process) / Maputo Beira Tete Quelimane Nampula / Milestone 23 5 3 3 8 / Achieved 8 2 1 6 8 / Targets were only met in two of five municipalities with Maputo only achieving a third of its target. The implementer of the training, EISA, has returned the unused grant funds. The PMU reported that poor performance against this indicator was due to saturation of coverage by a number of actors and is representative of poor coordination of efforts between donors and implementing agencies in the run up to elections. However, all journalists from the five target municipalities that attended training provided by EISA/CIP were funded by Dialogo. Other partners funded training of journalists from other municipalities. No further training of journalists is planned. / 2.3 Number of media programs and articles about electoral process from media grantees / Maputo Beira Tete Quelimane Nampula / Milestone 4 4 0 2 5 / Achieved 5 6 5 17 18 / Targets were exceeded in all five municipalities. Socio produced TV debates and interviews (through STV) with candidates providing the opportunity for citizens to share their views, ask questions, and discuss their problems and expectations related to municipal governance. Frelimo candidates did not attend the debates and it may have been more effective to use a different format in order to ensure their participation. Nevertheless, Socio has since decided to produce an additional programme of live debates on municipal governance related issues – a positive sign of the sustainability of Dialogo’s approach. / The programme also supported local media partners to produce programmes on the electoral process. In Nampula the review team saw evidence of high quality radio programmes around the elections, including a live debate between candidates and collaboration with Dialogo civic groups. The PMU also reported that their media partner in Quelimane Nova Radio Paz organised a live debate between the candidates and disseminated civic groups’ manifestos (based on CESC’s support to civic groups; Community Action Plans). / As noted above, this indicator needs to be clearly differentiated from indicator 2.1. / 2.4. Number of investigative journalism pieces on priority issues reported by independent media / N/A. No targets were set in the first year of implementation. The PMU is currently exploring a partnership with the Association of Investigative Journalism to work on local governance issues. / 2.5. Number of media outlets where ICT were installed / Maputo Beira Tete Quelimane Nampula / Milestone 1 1 0 1 2 / Achieved 0 1 0 1 2 / Substantive targets were met in three of five municipalities (in Tete the target was 0). The ICT installed were largely Frontline SMS and the creation of a Facebook page for each organisation. The outcome indicators also show that the three municipalities with ICTs are using them. The PMU reports that in Quelimane, Nova Radio Paz received over 1,000 “likes” for their Facebook page in four months. The review team also heard from the media partners (in Nampula) how they had used ICTs to increase their reach but at the same time that not all ICT was appropriate (e.g. Frontline SMS). / The target was not met in Maputo. This was because the PMU assessed there would be greater impact by working with larger media outlets such as STV, O Pais and Savana; rather than working with a large number of individual private radio stations in Maputo. Radio stations in Maputo either were focused only on music, were not legally established, or had very limited listenership. / This being said, the PMU continues to discuss with some of the larger media organizations in Maputo how they might be able to integrate ICTs into their work.
Progress against expected results: / Capacity: of Media organisations and of others to work with media / As with civil society capacity, the issue of building media capacity is not the objective of Dialogo but it is an implementation challenge. In the same way, Dialogo will need to (and already does) bring in organisations that specialise in media capacity to provide support to Dialogo media partners. For example, the media partners in Nampula have attended IREX training and a number of planned IREX initiatives can assist the media in Tete (through a possible placement of a Mozambique Independent Television (TIM) cameraman in Tete municipality or training for the media in ICTs). / There is also a challenge around the capacity of other Dialogo partners to work with and use the media. Targeted training for local Dialogo stakeholders, including municipal officials, could improve the flow of information and lead to a more joined up approach to policy advocacy – as well as increased trust. Dialogo reports indicate that the flow of information between CSOs and the media is strongest in Beira, Quelimane and Nampula. Positive approaches from these sites can be shared through IREX or CESC facilitators. / ICT strategy / Currently Dialogo does not have a clear overall strategy on ICTs, including on what is available and what is effective at the municipal level. There are many more innovative ways to use ICTs in this sector for a range of tasks, from mapping, data collection or citizen monitoring to reporting and advocacy, with most platforms open source and free at the point of use. At the same time, this needs to be balanced against what will actually be used by communities, including women. But access to social media is relatively good and will only increase as the project moves forward particularly amongst youth. / Value of money: terms and conditions and the size of grants / In Tete and Nampula a number of Dialogo partners including the media (but also CSOs, civic groups, observers, media, facilitators) raised concerns around incentives. These included the lack of allowances for transport and internet access; and the poor quality of office space. In addition, the PMU needs to consider if the size of grants is sufficient for partners to have impact. For example, the impact of an emailed weekly news bulletin might be significantly increased if there was a budget for there to be a printed version once a month. / It does not present good VFM for a programme the size of Dialogo to squeeze costs at the grass roots level where some of the most important work takes place. At the same time, there is a limited pool of grant funds available. These issues therefore need to be handled proportionally but should absolutely not be ignored. The PMU recognises this but will need to continue to pay close attention to local partners, ensuring appropriate incentives are in place. / Recommendations: / Output 2 targets should be reviewed based on context and reconfigured for year 3. In particular, indicators need to be clearly defined so as to ensure consistency and avoid double-counting between indicators (e.g. between 2.1 and 2.3). e.g. the SOICO debate series Municipios em Movimento (on STV and in the O Pais newspaper) was about both municipal governance issues and the electoral expectations of the citizens regarding the new candidates. As such, these appeared under both indicators. / Increase access to other actors’ capacity building expertise to support Dialogo media partners. IREX has a wide programme which includes a focus on gender which could be particularly important for Dialogo. Further attention should be paid to target municipalities that have a less developed media sector – particularly Tete – leveraging support from IREX and CAICC programmes where possible. / Consider how to build the capacity of programme partners to work with the media. This will need to be approached differently in each municipality but might involve encouraging the municipality to appoint a press spokesperson. / Dialogo should develop a more comprehensive and multi-year strategy for the progressive application of information technology in improving municipal governance. / Reassess terms and conditions of partners as well as the size of grants – could a small change in resources have a significant impact? / Impact Weighting: 30% / Revised since last Annual Review? Yes. In the last annual review Output 2 (“media’s ability to contribute to democratic processes”) was weighted as 20%. But in response to recommendations from the inception review, the programme was reduced from five outputs to three. This meant that the impact weighting in the three remaining outputs have increased. / Risk: Medium / Revised since last Annual Review? No

Output 3: Engagement of Municipal Institutions
Output 3 score and performance description: A / Dialogo had not planned to make significant progress on this output in 2013 given the municipal elections and the risks around political association (being seen as a political instrument of a particular party) and efficiency (little point agreeing communication platforms with municipalities who then change). Despite this, Dialogo has made early progress, signing MoUs with four of the five municipalities and working with new Municipal Councils and Assemblies to assess their needs and Dialogo’s support. The PMU will need to focus on this output over the next six months and deliver results before the space for action closes in the run up to the October general elections. / 3.1 Number of communication initiatives to disseminate municipal institutions informations / No targets for 2013. / 3.2 Dialogo Municipal Technical support Plans designed, agreed and implemented with municipal institutions / No targets for 2013. / Despite this, Dialogo has made some early advances under both 3.1 and 3.2. In the past year Dialogo has signed MoUs in four municipalities (the exception being Maputo), and Technical Support Plans are being worked up. These will be finalised by 15 April. In addition, Dialogo civic groups, CSOs and media partners have engaged municipalities both in the run up to elections and in the development and presentation of community action plans by civic groups. For example in Nampula, because of Dialogo, civic groups have met with the Assembly five times and with the Council four times to discuss their concerns. / Although the review was unable to meet the Mayor in Tete, discussions with the President and Vice President of the Municipal Assembly indicated a strong willingness to engage with the programme and use it as a platform to assist them in consultation with their constituents. In Nampula the Mayor was well-informed about Dialogo and saw advantages in working closely with the programme. He had numerous ideas about how to include CSOs in the work of the municipality and Dialogo will need to manage expectations about how much they can deliver – but this is a positive position to be in. The Municipal Assembly was less informed about the programme and clearly faces capacity constraints with many of the members being entirely new to Municipal governance. The number of new incumbents in all five municipalities presents both risks in terms of capacity but also is a huge opportunity to launch a higher degree of cooperation. / In terms of the indicator, if it is anticipated that implementation of the Plans could be longer than a one year engagement, this indicator may need to be split or revised entirely. Additionally, reporting guidance is required on what is counted under this indicator as community action plans and technical support plans to municipalities are not the same thing. / 3.3 Number of dissemination/advocacy activities on lessons learnt/best practices/ municipal studies beyond target municipalities / The target of three sites has not been met. The PMU explained that municipal elections delayed this process as the programme is at too early a stage of implementation to consider best practice exchanges, which is a realistic assessment of the situation at the time of review. They will need to review if the end target (16 activities by Feb 2017) is achievable given the lack of progress in 2013.
Progress against expected results: / Taking an individual approach but learning from each other / In 2013 the overall focus of the programme was rightly directed more at the demand than supply side of municipal governance. As the PMU is well aware, in the year ahead, the focus will need to be on working with municipalities. Dialogo will need to continue to take an individual approach with each municipality, tailoring its support according to the gaps and demands of each. For example, an area mentioned by all stakeholders in Tete was the budget – whilst other municipalities, particularly Maputo, are advanced in participatory budgeting, in Tete municipal officials are still unwilling to openly share the municipal budget. / Exchanges between Dialogo municipal actors on the demand side are currently part of the programme workplan, however this does not currently extend to municipalities. If managed well such exchanges between peers could present dividends in terms of embedding positive practices in municipal governance, such as participatory budgeting. This could be achieved with the support of ANNAM, but with caution in relation to any perceived political allegiance of ANNAM as network for municipal authorities. / Capacity of Municipalities / As with civil society and media, there are differing capabilities within Dialogo’s five municipalities. And as before, Dialogo cannot solve this problem on its own and therefore needs to work closely with others, acting as a broker to bring in additional support. Work has already begun on this by Dialogo’s partnering with Pro-Maputo on participatory budgeting at the municipal level. This will need to be a gradual process, taking each municipality at a time and assessing what works and what does not. / Other relevant programmes that work in some of the same municipalities as Dialogo include Concern Universal’s Municipal Social Accountability Monitoring Programme (MuniSAM) that supports citizens monitor the municipal budget; and the PDA[1] programme that supports Municipal Councils both in terms of technical assistance and directly by for example, constructing roads and providing equipment. In Nampula, the Provincial civil society platform (that brings together all civil society working in the Province into thematic groups) is considering starting a Municipal sub-group under the Governance group (a direct consequence of Dialogo’s intervention in Nampula). This would be a useful forum for Dialogo to better co-ordinate with others, bringing in their expertise where necessary and building on what they are doing (e.g. can Dialogo civic groups play a role in monitoring how the Municipality has used PDA support?). Another potential platform for this is that of a ‘municipal observatory’ bringing together all stakeholders around the annual planning, budget and review cycle to introduce a participatory and accountable process in addressing municipal priorities. / Consolidate while looking ahead to increased demands from municipalities / Looking ahead, there is a risk of municipalities not being able to meet citizen expectations. Stakeholders raised this with the review team in Tete and while in Nampula the municipality was eager to hear and respond to citizen demands, it was not clear it had the capacity or structures to do so. This increased pressure on the municipalities may result in them requesting more support from Dialogo. For example, as highlighted by the Mayor in Nampula, a key issue for the municipality (and the key concern of citizens as identified in the baseline survey) will be increased jobs and economic opportunities and they need help delivering this. But the current programme structure may not be able to respond to increased demand from municipalities and this risks both municipalities becoming disillusioned with what the programme can offer; and misses an opportunity to leverage greater openness and communication with civil society. The focus for the next year should be embedding the programme’s support to municipalities and consolidating the interaction between the programme’s three strands. In due course however, DFID and the PMU will want to consider if and how to provide increased support to municipalities without risking the programme delivering on its core objectives. The programme is still to deliver at full potential and so should not be overloaded. / Recommendations: / Clearly define the logframe indicator 3.2 in relation the technical support plans or community action plans and differentiate between targets for planning and actual implementation. Consider revising target for indictor 3.3. / Prioritise technical support plans to support the quality of work in municipalities as well as to increase officials’ buy in to the Dialogo programme (particularly important amongst the newly elected officials who will need a full introduction to the programme). The plans should be disseminated to civic groups. / Keeping in mind political risks, the PMU should consider establishing exchanges between municipal officials, whether through ANNAM or another platform. / Identify and use synergies with other programmes working with municipalities e.g. PDA, MuniSam. Municipal civil society platforms or municipal observatories may be forums to do this through. Working with the World Bank participatory budgeting should help Dialogo increase its “offer” to municipalities but it will need to be an iterative process. / For the next year the programme will need to consolidate and refine its support to municipalities. But DFID and the PMU should begin thinking about if and how to increase their support to municipalities, if effective. This should include examining the possibility of restructuring the budget and contract, if necessary, to reallocate resources. / The balance of target municipalities has now shifted from Frelimo to MDM led municipal councils. DFID and the Dialogo PMU will need to continually assess whether this is having wider implications for programme delivery, particularly through temperature checks with Frelimo centrally. Political/ political economy analysis should be regularly updated in 2014 both to determine the operational implications of the shift in municipal leadership as well as the wider context in the run up to and following national elections. / Impact Weighting: 30% / Revised since last Annual Review? Yes. In the last annual review Output 3 (“democratic decision making processes in municipalities”) was weighted as 25%. But in response to recommendations from the inception review, the programme was reduced from five outputs to three. This meant that the impact weighting in the three remaining outputs have increased. Output 3 should not have been weighted so highly in 2013 given the constraints on implementing this output in the municipal election year. But going forward, a 30% weighting seems appropriate. / Risk: Medium / Revised since last Annual Review? N
[1] Part of the ‘Municipal Development Program’ (PDA), a wider programme of support to municipal governance through a consortium of 4 donors.

Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Y / Yes, significantly. Following the inception review, the PMU conducted an analysis of the programme’s strategy which resulted in a revision of the programme’s theory of change and theory of action. The most significant revision was focusing the programme on three processes of civic, media and municipal engagement. This meant taking out the specific outputs on the electoral processes; and advocacy and research on municipal processes. This has been reflected in the logframe which now has three outputs only. This has made the programme far more focused and coherent. / Finally, some additional outcome indicators were added ensure results being captured are not only based on citizen perception but also on factual changes. These are commented on in section 1.6. / 1.2 Overall Output Score and Description: A / 1.3 Direct feedback from beneficiaries / The review team met with civic groups and local CSOs, the media, and municipal officials in Nampula and Tete. All were positive about the Dialogo programme and the interaction and engagement to date. / As has been described above, in some cases there are concerns about the terms and conditions of employment, resources and incentives, and support but at this stage this these problems can be fixed through adequate consultation and negotiation – but as stated above, they should absolutely not be ignored as the work at community level is ultimately what the programme is about in target municipalities. It is too early to determine the impact or indeed a full impression of the Dialogo programme from the wider community. Following a more sustained period of implementation and the results of a repeat survey the programme will be better placed to assess this, ideally before the next DFID annual review.
1.4 Summary of overall progress / Despite implementation only starting in the second quarter of the programme year, Dialogo has had a positive and busy year. It has made progress implementing recommendations from the inception review, including major changes to the PMU (a new Team leader, operations manager, Municipal Governance Manager and ME&L officer). The programme has been focused down from five outputs to three (cutting out elections and advocacy/research as separate outputs). EISA’s role has been reduced given the reduction of the electoral component. And challenge funds have been largely replaced by direct grants. However, issues that still need to be addressed include: the link between citizen observers and media that has remained weak; and learning between municipalities that still needs to be strengthened. See Annex 5 for further details of progress against the inception review’s recommendations. / In terms of programme delivery, it has made good progress in working with civil society: supporting civic groups draw up Community Action Plans; partnering with local CSOs; and importantly achieving results in terms of opening up new and more frequent communication channels between citizens and municipalities. It has established partnerships with local and national media outlets which have covered the elections, providing more information to citizens about both the process and the candidates. Dialogo has built relationships with both the old municipal members and the newly elected ones. / Dialogo’s theory of change now has evidence that it works. There are numerous examples of the media, civic groups, CSOs and municipalities working together to resolve municipal issues. Over the next year, the programme needs to consolidate these relationships and continue to focus on delivering results in terms of linking up the three groups to work together to resolve issues that are important to citizens.
1.5 Key challenges / Building effective support to municipalities / As highlighted above, in 2013 the programme rightly focused on its work with civil society. But in 2014, there is a short window of opportunity before the general elections to support municipalities to increase their level of openness and transparency; and their interaction with citizens. This will require agreeing Action Plans with municipalities setting out clearly what support Dialogo will provide to the municipality but also how the other elements of the programme, civil society and the media, will interact with the municipality. This second part may need to be a follow up process but agreeing this early on would provide clarity to all three partners as well as increase the impact of all of their work. / Adopting a more flexible, individual approach to each municipality / The context in each municipality is different in terms of political incentives; capacity of Dialogo partners; and priority issues. As the PMU has already identified, there are different risks to programme delivery in each municipality too (see Annex 3 for details). This means there are different needs in each municipality and therefore the programme will need to adapt its approach to suit five different realities. This could mean that in some municipalities CESC’s role is increased so that civic groups interact directly with the municipality, rather than go through the local CSO partner. Or that ICTs are expanded in Maputo but not in Nampula. It will also mean working with other programmes in that particular municipality. For example, there might be opportunity to work more closely with MuniSam in Quilemane or due to the limited CSO capacity in Beria, to work more closely with MASC in that particular municipality. At the same time, there should continue to be a focus on learning between municipalities. This follows from the recommendation in the inception review to promote horizontal learning between municipalities and between the different actors involved / A more flexible approach will be more complex but should be more effective. In addition, given the progress made during 2013 in terms of setting the programme direction; and establishing partnerships and ways of working, the PMU is in a strong position to adopt a more nuanced, individual approach. / Citizen observers / There are three Citizen Observers (COs) in each municipality. They role is to assess and record the political context of the municipality, making videos of what they see are the main issues affecting communities and feeding these back to the PMU. The idea is that these feed into programme and risk management. But the strategy for making the best use of these videos is not clear. Although there are exceptions, there are no clearly established mechanisms for this information to be shared with facilitators, CSOs, municipalities or with DFID. This may not have been part of the original purpose of CO’s role, but observers may have a great deal to contribute to other stakeholders understanding of the situation on the ground. The COs report that they do not know what the objective of their role is, that there is no job description and that they receive no feedback on their products. They cannot tell communities what happens as a result of their work and so are losing any credibility. The PMU has been working to manage the expectations of COs, and believes increasing use of stories by local media and CSOs will help with this. The media adviser may want to produce an approach paper on this. / Gender / As mentioned above, gender has not yet been successfully integrated into the work at the municipal level, albeit with some positive and notable exceptions. Given that this is a key foundational principle of the programme, the second year of implementation should ensure that this starts to become more central to discussion at the municipal level. The Dialogo gender strategy needs to be implemented and will require the technical support of the PMU to drive it forward. / Secretary of State’s challenge on measuring results / DFID’s Secretary of State put a challenge to DAI Europe as the lead contractor for the programme to develop and test a more innovative approach to capturing and reporting the results of this programme especially in those hard to measure, qualitative areas. This ‘results framework’ could be used as a model for other similar interventions across DFID on how to measure softer results. The challenge was to work on such a results framework within the first year on the programme, so that by the Mid-Term Review, the programme could report against its softer results. The Secretary of State requested that a Key Performance Indicators (KPIs) was included on this point and this is being worked on. / A considerable amount of effort has been put into the results framework by the PMU for the Dialogo programme, using the baseline data to develop a wide range of well thought through outcome indicators, as well as a process of outcome mapping. To this extent the challenge is on track to being met. However, as has been described in certain sections above, some of the output indicators are too vague and should be better defined to ensure consistent and accurate reporting – although most are not numeric, confusion here could undermine the credibility of the results framework as a whole. But beyond the logframe, DAI Europe needs to take responsibility for this meeting this challenge, not just the PMU.
1.6 Annual Outcome Assessment / The majority of the outcome indicators will be assessed through the mid-term evaluation’s perception survey and so there is currently no data on them. However, during 2013 three new outcome indicators were included based on outcome mapping to ensure the programme was monitoring processes as well as perceptions. In addition, there are two outcome indicators on the media that do not require a perception survey and can be measured now. / The 2013 outcome mapping milestones have not been reached for two indicators but has been met for one. The level of CSO engagement capacity on municipal governance is not as high as expected nor is the level of municipal institutions’ capacity to engage with municipal actors. The level of media capacity to promote public debate around municipal governance issues and work with municipal institutions and CSOs has been met. In addition, the other outcome indicators for the media not based on the perception survey have been largely met. The media partners are using their ICTs and large numbers of citizens are participating in the media space on municipal governance, particularly in Quelimane and Nampula. / Nonetheless, the outcomes are broadly on track. The programme has made good progress in delivering its outputs despite only being at the delivery stage for the last eight months rather than the whole year.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / Overall, the programme is on track against financial forecasts with a 94% execution rate from a total budget in 2013 of £1,726,561.43. The actual expenditure of the programme is £1,625,796.74 of which £1,404,434.43 corresponds to deliverables and outputs and £221,362.31 to grants. / Dialogo’s contract is structured as a fixed-price contract around programmatic deliverables and outputs. The management of the budget on this fixed element is contractually an internal issue of DAI and the PMU are not required to provide detailed reporting on spend. / The ratio of their spend on the fixed-price budget is: / 65% (£912,882.38) on programmatic support which includes monitoring, evaluation and learning, direct technical assistance and grant management (including associated travel costs); / 35% (£491,552.05) on administrative overheads such as rent, utilities, security, audit, etc. / The programme has a 33% underspend on their grants forecast of £331,800. This was mainly due to municipal engagement activities being postponed until after the November 2013 elections and due to grant making to civil society and media organizations not occurring as rapidly as expected. / This programme has a technical assistance component that was created to allow flexibility to cover annual review costs and other consulting services during the implementation phase. The forecasted budget on this component for 2013 was £10,541.53 of which £4,760.13 (45%) was spent. / On DFID’s side, one of the main challenges with this programme is in recording the accruals since the shift from cash basis to resource accounting. This has had negative implications on the forecaster for the current financial year. Going forward, DFID will clarify financial information requirements to the PMU and ensure the forecaster and ARIES are updated according to the changes in the programme. / 2.2 Key cost drivers / The PMU has identified five main cost drivers associated with the implementation of the programme: / Domestic flights / Municipal learning workshops / PMU staff costs / External consultant costs / Office administrative costs / These cost drivers are tracked as part of the VFM monitoring under indicator one of the economy category. / 2.3 Is the project on-track against original timescale: Y / The project is on track against the original timeline. There is an option for a three year extension to the beyond 2017. This could be an opportunity to maximise return for investment as the programme begins to increase its delivery rate.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Dialogo’s theory of change was revisited in February 2014 during the programme’s annual Theory of Change (ToC) Workshop in Maputo bringing together its programme partners. The workshop showed that many of the assumptions and risks identified in the November 2013 ToC workshop remained valid, confirming that the relevance and rationale of the programme. Indeed there is increasing evidence of the rationale for the programme given the increased willingness in municipalities to work more openly and involve with civil society. / 3.2 Where an evaluation is planned what progress has been made? / There is a plan for a mid-term evaluation of Dialogo, which for a five year programme that started in February 2012 means mid 2014. However, as was recognized in the inception report, Dialogo had a slow start. Doing a mid-term evaluation when the programme has only been implementing for 18 months would not be useful. Instead, taking the mid-term point of the implementation phase and timing the evaluation to be at the same time of year as the baseline survey would mean an evaluation in August 2015. This would also then inform to inform the decision on whether the programme should be extended beyond 2017 by a further three years as was set out in the original contract. Planning for this evaluation, which will be done by the PMU, should begin now. / The mid-term evaluation should be used to assess progress since the baseline survey. This assessment should be used for more than just Dialogo’s monitoring. Dialogo, with support from IDS, should ensure their partners understand where there has and has not been progress, as well as informing other relevant stakeholders of the results (e.g. parliament, donors, ANNAM).

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The programme is established and broadly delivering it’s outputs. But it cannot be reduced to “low” given the risks to programme delivering in 2014. There is only a very short window for delivery before the elections in October 2014; and a new risk was identified during the Theory of Change workshop that of the independence of the media. This reflects feedback from media partners that they are feeling increasing pressure from the central government not to overtly criticise their policies. This is likely connected to the looming general elections. / The PMU has updated its risk analysis and identified specific risks to in each municipality. Beira appears to be the highest risk municipality in terms of having: limited “change agents” with capacity and resources to create local level change; and NGOs/CSOs unable to absorb funds and design programmes. Dialogo has set out clear mitigation strategies for each of these risks for example working closely with the capacity building programme MASC and ensuring facilitators can provide support where necessary. See Annex 3 for details.
Risk of funds not being used as intended / Dialogo undertakes due diligence on all new grantees before they are awarded funds. Where the due diligence assessments suggest that there are insufficient procurement systems in place, the PMU procures on their behalf and provides assets in kind. It then also provides training in asset management as follow-up. / The first annual audit of the inception phase period was conducted in July 2013 by Ernst & Young. It made three recommendations. Of these, the PMU addressed two (payment of IRPS on rental properties, even if not rented in the name of the PMU; and preparation and maintenance of attendee lists for all events where programme funds are expended); and is currently working to address the third, that the PMU switch from a system of financial recording that relies on Excel sheets for data input into DAI’s Oracle system into a system where financial data is entered directly into a financial accounting package, and then exported into DAI’s global Oracle system. As this is not a trivial change, and as DAI globally is currently piloting a system that would resolve this issue, the PMU opted to wait for the results of the pilot before proceeding with the change. It is anticipated that significant progress against this recommendation will be made by the end of quarter two of the second year of implementation. / 4.4 Climate and Environment Risk / Low. The PMU travels extensively and this will have a negative impact on the environment. But some of the issues the programme works on environment pollution, land use, water supplies and litter collections should in the long term have a positive impact.

5. Value for Money
5.1 Performance on VFM measures / Dialogo’s approach to Value for Money (VFM) is based on the recognition that programmatic decision-making requires a solid, quantitative understanding of programme results as well as the costs to deliver those results. The PMU further considers improving VFM as a process of continuous improvement – VFM is never ‘achieved’, there is always room for increasing VFM. / For the second year of its implementation phase (i.e. 2014), Dialogo has identified eight VFM indicators from the Effectiveness, Efficiency and Economy categories. The PMU also sees opportunities for increasing the number of and quality of indicators going forward, especially with respect to increasing VFM of partners’ activities. This narrative expands on the descriptions in the annexed VFM matrix (see Annex 2), and specifically aims to explain how indicators relate to programme outcomes and results: what information they provide to the PMU. / Effectiveness / Indicator Rationale Data Year 1 Comments / # of activities developed in collaboration with complementary programmes / implementers. It is expected that activities developed in collaboration with complementary programmes or implementers will be more effective in terms of success, sustainability and cost effectiveness than those developed solely by DIALOGO. Qualitative information on extent of collaboration during activity development, for all PMU activities. Target 25% 10/17 grantee projects developed in consultation with complementary programmes / implementers (7/10 media projects & 3/7 civil society projects). / Achieved 59% / % of grant-funded projects implemented successfully. Determining the VFM effectiveness of grant-funded projects requires going beyond log-frame level indicators of success, and looking as well at contractual compliance, level of technical support required, and other key factors. Success of project implementation is assessed through a scoring system (1-10) which looks at both compliance as well as degree of achievement of project results and objectives. Target Average score of 8 Of 17 projects finalized with partners, 4 have ended by the end of Implementation Year 1 (CAICC, SOICO, EISA and Radio Chiveve's 2013-2014 grants). Final evaluations of these projects will be completed by the end of April, 2014. / Achieved TBD / The indicator regarding the number of activities developed in collaboration with complementary programmes / implementers was included based on the expectation that activities designed with input and feedback from like-minded implementers, donors or other actors would be more successful than those developed solely by the PMU and an implementing partner. The initial Y1 target of 25% of activities was exceeded, with 59% of activities being developed in collaboration with programmes such as the World Bank’s ProMaputo project, IREX’s Mozambique Media Strengthening program, FORCOM and CIEUM’s radio station support programmes, and others. Disaggregating this information shows that while 70% of partners’ media activities were developed in collaboration with other partners, a lower proportion of civil society projects (43%) were developed in a similar manner. Of course having a high percentage of activities developed collaboratively is only important if these activities are indeed of higher quality, or are more sustainable. This information will be collected in part from grantee annual / end of project evaluations, where reflections into quality and participatory design will be explored. The PMU at this point will continue to seek participation from relevant actors in the design and technical direction of programme activities when appropriate, and will attempt to determine from evaluations the extent to which this collaboration is improving programme quality. / The second indicator in this category, the % of grant-funded projects implemented successfully, has yet to be quantified as 1) annual / end of project evaluation tool has not yet been finalized, and 2) projects are only now coming to a close. In addition to quantitative scoring of programmatic achievement, the evaluation will also look at the amount of PMU (and partner) resources spent to accomplish outputs and outcomes. This tool will include sections that allow the PMU and implementing partners to reflect both on the impact of participation in programme design as well as VFM within partner projects. / Efficiency / Indicator Rationale Data Year 1 Comments / Cost per civic group supported, and per person participating in media space for citizen voice on municipal governance issues during the reporting period. While DIALOGO works with a large number of partners supporting a range of activities, the programme predominantly uses two methods to reach citizens: engagement with civic groups and support to the media. Tracking costs of working with these civic groups and media institutions provides an indication of efficiency in reaching these citizens. While estimates of media audience (listenership, viewership or readership) are extremely difficult to obtain given the lack of solid survey data, the number of citizens participating in supported media spaces is able to be quantified and gives an important indication of value for money. With respect to support of civic groups it is important to keep in mind that different partners provide different levels and types of support. This being said, noting cost per civic group supported is still useful information. Average cost per civic group supported and per person participating in media space for citizen voice on municipal governance issues during the reporting period. Cost based on grant, sub-contract or direct implementation cost, and does not include PMU management, monitoring or administrative costs. Target £15,000 per civic group £15 per person participating in media space Target of £15,000 per civic group was based on 15 groups planned to be supported by CESC, three in each municipality. CESC expanded support to 24 groups, and four additional partners supported 89 additional groups. Note that for media participation, figures are based on total grant amounts; some grants extend past the end of Implementation Year 1, meaning the number of participants might increase, and costs decrease. / Achieved £3,560 per civic group £11.67 per person participating in media space / # of days to process a grant (from announcement to first fund transfer, for Challenge Fund grants; from presentation of initial proposal to first fund transfer, for non-competitive grants) Processing of grants is a time-consuming process. A reduction in the number of days to complete the grant making process - while ensuring that each step is followed according to agreed procedures - will result in additional time for other programmatic activities, and is an indication of programme efficiency. Average number of business days to process a grant during period, data on which part of grant-making process was most time-consuming. Target 45 days Average work days from initial proposal submission to contract signature: 35.4; average work days from signature to first funds transfer: 9.2 days Length of first step considered to be due to some proposals being submitted during end of Inception phase, when commitments could not be made, and the fact that contracts with municipal partner NGOs changed several times in nature between initial proposal delivery and finalization / signature. / Achieved 44.6 days / % of DIALOGO budget spent on direct programmatic support versus administration and other overhead costs Dialogo's non-grant budget comprises of spending on programmatic support (including ME&L, direct TA and grant management, including associated travel costs) and on administrative overheads (rent, utilities, security, audit, etc.). A strong programme to administration spending ratio coupled with sound management practices indicates maximum funds are available for programmatic activates. A / (A+B) A = spending during period on programmatic costs B = spending during period on administration and overhead costs Target 67% Programme Costs / 33% Administration Costs Based on Implementation Year 1 figures from March 2013 to February 2014. Note that all PMU administrative and finance support for grantee activities are included with "Administration Costs". All grantee direct costs included in programme costs. Target based on commercial proposal. / Achieved 65.0% Programme Costs / 35.0% Administration Costs / Cost per annual municipal engagement action plan Although municipal engagement action plans, and activities, will vary significantly between municipalities and years, for purposes of understanding VFM effectiveness it is important to track total costs per municipal action plan in order to gauge sustainability and cost effectiveness. Annual direct (including, e.g., in kind purchases of goods or services) and indirect (including, e.g., PMU TA and travel) costs for implementation of participatory municipal action plans. Target N/A No municipal engagement action plans finalized / budgeted in Year 1. / Achieved N/A / Indicators in this category provide information on the level of PMU effort dedicated to major activities and types of activities, and cost information on major programmatic approaches. / The first of these indicators, the cost per civic group supported and the cost per person participating in media space, include information from activities managed by different partners. In the case of support to civic groups, this includes activities implemented by CESC as well as by grantee partners. In the case of support of media organizations, costs are based on media grantee activities. / The fact that the cost per civic group supported during the first year of implementation was £3,560 – well below the initial target of £15,000 – is due primarily to 1) CESC expanding the number of civic groups with which it was working and 2) several grantee projects also providing support to civic groups. Since the type of support provided by different grantee partners and by CESC differs, it is difficult to compare related costs. Going forward the PMU will attempt to link these costs to specific programme outcomes, such as municipal issues receiving attention from municipal authorities. / With respect to the second part of this indicator, the cost per person participating in media space, costs between media partners varies greatly as different partners are at different stages in their ability to engage with their audience, and as grantees’ activities engage with audiences in different ways. For example, Radio Encontro has been quite successful in its use of ICTs to increase participation, with over 1,200 people participating directly for an average cost of £4.67 per person. SOICO’s televised debates, on the other hand, directly included 680 people (£34.31 per person), but reached a much higher indirect audience through TV broadcast and related newspaper articles. As the media partners continue to roll out ICTs, the PMU will be using this cost data to identify partnerships where performance is either greater or less than expected, and seek to replicate successes or address weaknesses. / The second indicator in this category, the number of days to process a grant, provides information on where the PMU is spending effort in the grant-making process. The figures from the first year of implementation (average of 35.4 work days from submission of first proposal to signature of grant agreement), indicates that significant time is spent with partners to develop and finalize their grant agreements, including ME&L systems and targets, work plans, programmatic approaches, and budgets, and completion of the financial due diligence process. This figure is particularly high in this first year of the inception phase as some proposals began to be discussed during the late part of the inception phase, but were put on hold pending the signature of Dialogo’s implementation phase contract and the development of the programme’s theory of action. As such, the PMU expects that projects prepared in the second year of implementation will take considerably less time. The amount of time from contract signature to first receipt of funds (9.2 days) indicates that significant time is spent in obtaining proper bank information from grantees, and in internal PMU approvals, funds requests, and payments. This number can certainly be reduced by improving internal systems, which will translate into the ability for partners to implement activities more quickly. / The third indicator in this section relates to the % of Dialogo’s budget spent on direct programmatic versus administration and overhead costs. Given that the programme’s budget is largely fixed, with substantial amounts allocated to PMU salaries and operational costs, the PMU does not expect that these figures will fluctuate significantly, but tracking this information is important to ensure that spending remains in line with contractual agreements. It is important to note that some costs, such as all PMU finance and administration costs related to support of grantee partners, are considered overhead costs. Also, all grantee costs are considered programme costs, including administrative components of grantee budgets. Given that the majority of Dialogo’s budget is allocated to maintaining the PMU with appropriate technical and administrative capacity, potential increases in available programme funds from DFID, as has been discussed, would certainly increase VFM from this perspective. / The final indicator in this category, the cost per municipal action plan, is designed to capture the VFM of support to municipal institutions (i.e. municipal councils and municipal assemblies) through in-kind support of jointly-prepared municipal action plans. While the indicator currently focuses on costs related to each plan, based on DFID feedback, the PMU will be re-thinking this indicator to include information on the sustainability of activities, in terms not only of costs, but also level of effort required from municipal authorities to continue with activities post-Dialogo. / Economy / Indicator Rationale Data Year 1 Comments / Cost per major cost driver: 1) domestic RT airfare (per trip); 2) municipal learning workshops (per workshop); 3) PMU staff costs (as % of overall spending for period); 4) external consultant costs (total per day of consultancy); and 5) Maputo office administrative costs (as % of overall spending for period). Key drivers of cost, e.g. domestic flights tickets, can be minimized by sound management practices, especially advanced planning and coordination between PMU staff and partners, municipal institutions, etc. Municipal learning workshops, in particular, require significant travel, lodging and per diem costs - minimizing such is important to maintaining VFM. The use of external consultants is an important means to bring expertise to the project, but can also be a considerable expense - keeping these costs to reasonable levels is important for maintaining overall programme economy. While PMU staff costs and Maputo office administrative costs are largely fixed, tracking these costs over time will allow for a better understanding of significant cost drivers. Cost per major cost driver during quarter, including historical comparisons. 1) domestic RT airfare (average per trip); 2) municipal learning workshops (average per workshop); 3) PMU staff costs (as % of overall spending for period); 4) external short-term consultant costs (average per day); and 5) Maputo PMU office administrative costs (as % of overall spending during period). Target 1) £500 2) £5,000 3) 42% 4) £450 5) 4.3% Additional major cost drivers could be added in the future. Targets for #1, #3 and #5 based on commercial proposal. Implementation Year 1 external STTA average The PMUly rate lower than expected due to large number of hours worked by several junior consultants on municipal baseline studies. / Achieved 1) £396 2) £2,622 3) 38.5% 4) £157.45 5) 5.5% / % of grants awarded on a competitive basis Grants awarded on a competitive basis are expected to be more cost-effective than those awarded through direct solicitations. A / B A = # of grants awarded through Challenge Fund competitive process B = # of grants awarded since start of implementation phase Target 0% No competitive funding planned or carried out in Year 1. / Achieved 0% / The two indicators under this category aim to provide the PMU and DFID with cost information on Dialogo activities, specifically information for five major cost drivers: airfare; municipal learning workshops; PMU staff costs; STTA consultant costs; and Maputo office administrative costs. Tracking these costs will allow the PMU to monitor the impact of management decisions made to increase savings, for example monitoring the impact of finalizing learning plan travel arrangements significantly in advance of workshop dates. The PMU also regularly reflects on costs driving the programme, and will suggest additional cost drivers if identified. / The final indicator is the % of grants awarded on a competitive basis; competitive grants targeted at large, national media organizations and research institutions are expected to start either in the latter part of the second year of implementation, or the third year. It is expected that proposals received through competitive processes will be of higher quality and be more cost competitive than proposals solicited directly from implementers. The PMU understands that this indicator alone does not provide sufficient data to judge the VFM of competitive vs. non-competitive grants, and will endeavour to include additional information along with this indicator. / It was agreed that targets for year 2 would be set by 30 April 2014. At this time, the PMU will also reconfirm the current set of VFM metrics – based on experience in using them this year and the management information utility they provide – and if they want to introduce any changes or additions this will also be communicated no later than 30 April. / 5.2 Commercial Improvement and Value for Money / The PMU completes due diligence assessments on its grantees to ensure that they have sufficient systems in place, particularly for financial management and procurement. Where the due diligence assessments suggest that there are insufficient procurement systems in place, THE PMU procures on their behalf and provides assets in kind. It then also provides training in asset management as follow-up. / 5.3 Role of project partners / As contract manager, the PMU is actively working to try to ensure good VFM within this project. They developed the VFM metrics reported above and are using this as a monitoring tool within the programme. / They have worked with their grantees to develop detailed reporting formats by which grants for proposals are submitted. In this process they have set rates for certain costs (e.g. hotels, flights, per diems) which grantees must use in preparing budgets, to ensure some cost control. These will be reviewed periodically by the PMU (and any increase will come out of the ‘fixed price’ part of the contract i.e. costs borne by them and not by DFID). / The review team discussed with them that as projects are now well underway – and some even completed – the team should work with grantees to monitor and analyse budget execution in the same way. This would help grantees take a critical look at their own initial budgets, and broader operational planning, and understand any significant discrepancies between budgets and actual spend. This should help to improve budgeting by repeat grantees over the medium term. / At present, the PMU do not set any VFM metrics for grantees (linked to the consolidated metrics they report back to DFID). We discussed the possibility of them beginning to discuss VFM more with their grantees to ensure that the core principles of cost economy, efficiency and effectiveness are understood throughout the programme. / The PMU should continue to seek opportunities to collaborate with other DFID funded programmes such as CSSM and CEP. A particular area to consider working with CSSM is on capacity building of grantees given that Dialogo does not have this component. / 5.4 Does the project still represent Value for Money / Although only at the end of its first year of implementation, the programme is delivering Value for Money. It is making good progress towards the results targeted across outputs and is doing so within the budget agreed. There was good performance against all of the specific VFM metrics established. THE PMU are taking concrete measures to deliver VFM through this project (e.g. through their interaction with stakeholders, particularly grantees) and in their reporting (e.g. through the development of and reporting against a set of clear VFM metrics). / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Dialogo is a ground-breaking programme in Mozambique, but also more broadly in developing a collective action approach to tackling issues of municipal governance. For that reason the learning and sharing element of the programme is fundamental as is the need for a contextually rooted, flexible and iterative approach to solving municipal governance problems. This appears to characterise the approach that the Dialogo consortium continues to take, resisting the temptation to apply a ‘one size fits all’ formula. This makes programme management and technical support complex, but ensures local considerations drive the programme, rather than from the top down. This has meant that there is a great deal of variance in terms of results between sites as the capacity of actors but also the opportunity to get behind initiatives which have momentum at the local level can differ greatly. It is too early to have a good sense of progress towards outcomes as post-election implementation is in its very early stages. / Recommendations for action are included above and consolidated in Annex 4 to this annual review. The Dialogo will need to take note of these and address them in as the implement the next year of the programme. Where contextual changes are such that they render recommendations no longer valid, Dialogo can discuss these changes and agree them with DFID.

8. Review Process
The team was led by Governance Adviser in DFID South Africa. Inputs were provided by DFID Mozambique Governance Adviser; Programme Manager; and Economic Adviser. / The team visited Tete and Nampula municipalities. They interviewed the Municipal Councils and Assemblies, CESC facilitators, Civic Groups, Citizen Observers, Dialogo partner CSOs and Dialogo media partners. Importantly they also met with other programmes working on municipal issues not supported through Dialogo e.g. PDA and MuniSam.