Type of Review: Annual Review

Project Title: Palestinian Market Development Programme (PMDP)

Date started:	January 2013 (actual start date: October 21st 2013)
Date review undertaken: 14 April 2014

## Introduction and Context

What support is the UK providing?
By October 2019, the UK will provide up to £11 million for the Palestinian Market Development Programme (PMDP) to strengthen the competitiveness of the private sector in the Occupied Palestinian Territories (OPTs). / First, the PMDP will provide grants[1] and technical assistance to mitigate the risk associated with business development in the fragile context of the OPTs. Second, it will also undertake market analysis to identify and address market failures. Third, it will strengthen inward investment and transfer of ‘know how’ to Palestinian institutions. / The EU is co funding the programme with Euro 5.5 million bringing the total budget of the programme up to £15.3 million. The EU’s contribution is channelled through a delegated agreement with DFID.
[1] PMDP will encourage SMEs to take a risk to invest in developing new products or/and enter new markets by sharing the risk through matching the cost of the firms’ investment which may range between (25%-75%) of the total cost.

What are the expected results?
By 2019, the PMDP is expected to help 480 Palestinian firms to develop and improve 250 new products and enter 350 new markets. Over 240 companies will be expected to report improved performance on an annual basis, 96 to report increased exports and 72 to start using their own funds to develop their businesses. Overall our support will leverage a minimum of £40m of additional attributable sales.

What is the context in which UK support is provided?
What need are we trying to address? / Although the OPTs' real GDP growth reached 9.9% per cent in 2011, this was largely driven by donor supported public sector growth, and has failed to address high unemployment and high poverty rate. Unemployment in the West Bank increased to 20.1% in the first quarter of 2012 and in Gaza, increased to 31.5 %. The poverty headcount was estimated to be nearly 23% in 2009. / Developing a sustainable economic base will depend largely upon the establishment of a dynamic and productive private sector to reduce this high unemployment and poverty. Increasing GDP will in turn increase tax revenues for the PA promoting fiscal sustainability and reducing donor dependence. However, restrictions imposed by the Government of Israel on the movement of people and access to resources, coupled with high cost and inadequate skills of labour force has significantly reduced the competitiveness of Palestinian firms. If firms are to compete successfully in domestic and international markets, they need to shift from the production of low value added, labour-intensive goods towards high value added goods and services. / The UK and EU support will help firms, directly or through broader market system assistance, to raise their productivity, move up the value chain, and become more innovative and competitive. This is especially relevant to the service sector, particularly the IT-enabled, which is the least affected sector by political barriers and will benefit from the presence of highly educated work force and entrepreneurial Palestinians. / The programme is part of the UK’s wider support to Palestinian state building efforts and the Middle East Peace Process. / What we are doing to tackle the problem / To help strengthen the competitiveness of the Palestinian private sector, the PMDP will: / Provide matching grants and technical assistance to firms or consortia. Recipients are selected under a competitive process which targets firms looking to innovate their products/services, develop new products and services, improve processes and enter into new markets. / Undertake market analysis and facilitation. Analysis will identify how market systems in selected sectors operate, and factors which drive performance. This could, for example include facilitating trust building between small firms and large aggregators, information exchange, access knowledge and best practice, as well as influencing a strategic demand for the matching grant component. / Provide technical assistance to Palestinian institutions. This assistance will strengthen investment promotion and after care, promote trade to and inward investment from key international markets and mobilise the Palestinian diaspora to play an active role in economic development in the OPTs. Activities will include capacity support to the Palestinian Investment Promotion Agency (PIPA) to strengthen foreign and local investment in the OPTs. In addition, the deployment of experts will be explored in key markets to improve commercial representation and to mobilize potential diaspora investment, knowledge and technological transfer. / Who implements the support we provide? / Development Alternatives Inc Europe (DAI Europe) was awarded the contract to implement the programme following a competitive procurement process. A further contract was awarded for the programme evaluation supplier (GDSI) to quality assure results on quarterly basis, conduct annual assessments, and carry out a final evaluation at the end of the programme. We also contracted the World Check company (Vetting services company) to vet all recipient businesses against links to terrorism. / Finally, the programme is being overseen by a Steering Committee from DFID, the EU, and the Palestinian Ministry of National Economy (MoNE). / The programme did not achieve its expected targets in the first year mainly due to the prolonged procurement process to start implementing the programme. Therefore the annual Review will focus on progress made during the inception phase (October 2013 – February 2014).

## Section A: Detailed Output Scoring
Output 1: Improved private sector skills and innovation
Output 1 score and performance description: C (Outputs substantially did not meet expectation) / Progress against expected results: / Indicator Baseline FY 13/14 Milestone Achieved Score / Number of enterprises assisted 0 60 (of which 20% are women owned/managed firms) 0 C / Number of new markets (domestic and foreign) entered 0 20 0 / Number of new / improved products (including services) developed 0 10 0 / Number of Business Service Providers (BSPs) gaining recognised certification due to PMDP (e.g ISO, human resources, export) 0 0 0 / As the programme started later than envisaged due to the procurement process, it did not achieve its expected targets for the first output. However, the inception phase has laid important foundations to deliver output 1. DAI Europe developed the operations manual which describes the main concepts, principles and procedures of the PMDP finance and operations system to ensure consistent, effective and transparent operations. The Grants Manual describes all the processes and procedures required to obtain a grant from PMDP by firms and includes due diligence measures. The Grants Manual was approved and information sessions inviting firms to apply for grants have taken place across the West Bank, Gaza, and East Jerusalem. / The PMDP team has also developed a Communication and Outreach Plan which communicates the programme’s goals and objectives. The plan has been designed to allow flexibility in the various tools used to deliver the programme’s messages and objectives.
Recommendations: / DFID will review the inception phase, seek advice from advisers and provide comments and feedback to DAI to ensure the report meets the programme’s objectives and proposed implementation plan is in line with best practice by mid of April. / DFID and DAI Europe to revisit the logframe and make amendments to reflect the findings of the inception phase by May 2014. / Impact Weighting (%): 70% / Revised since last Annual Review? / No. This is the first annual review. / Risk: Medium / Revised since last Annual Review? / No. This is the first annual review.

Output 2: Market System failure in specific sectors addressed
Output 2 score and performance description: ( C ) Outputs substantially did not meet expectation
Progress against expected results: / Indicator Baseline FY 13/14 Milestone Achieved Score / Number of high quality studies / scoping studies prepared to reveal market failures in selected value chains (High quality defined as: relevant topic, good use of analysis, objective, clear recommendations targeted at policy makers) 0 4 0 C / Number of interventions based on the studies' recommendation taken forward (e.g facilitation, directing firms / consortiums to the matching grant scheme) 0 2 0 / Again, in the four months of operation, the PMDP team have not been able to deliver against these milestones. However, the PMDP laid out the approach and activities to deliver the objectives of output 2. The PMDP team developed a plan to identify and prioritize critical market systems and carried out detailed diagnoses to develop intervention plans to address market failures. / In order to select the sectors that offer the highest potential, PMDP team analysed the imports and exports per sector and ranked them according to their impact on sector growth, employment and broader economy. The ICT and agriculture sectors have been prioritised in the first year. Tourism and construction will be postponed to year two. / Along with the two lead sectors, PMDP will start working on implementing some of the findings of the Business services study conducted under the previously DFID funded project Facility for New Market Development (FNMD). / Recommendations: / DFID will meet monthly and work with DAI Europe on the selection and interventions to address specific market failures by June 2014. / DFID will meet monthly with DAI Europe to ensure that studies and interventions will address gender issues and include analysis of any failures that impact women, youth, and the poor during the course of the programme. / DFID and DAI Europe will review the logframe indicators under this output to reflect findings of the inception phase by May 2014. / Impact Weighting (%): 15% / Revised since last Annual Review? / No. This is the first annual review / Risk: Medium / Revised since last Annual Review? / No. This is the first annual review

Output 3: Strengthened Trade and Investment linkages with international markets
Output 3 score and performance description: ( C ) Outputs substantially did not meet expectation
Progress against expected results: / Indicator Baseline FY 13/14 Milestone Achieved Score / Number of activities completed as part of PIPA's strategic plan (To be further developed in the inception phase of the project) 0 3 0 C / Number of investment related activities directed at investors including diaspora (To be further developed at the inception phase of the project) 0 0 0 / Number of people trained on commercial representation abroad (To be further developed at the inception phase of the project and discussion with the MoNE) 0 0 0 / Although there was no significant progress against the lograme indicators due to the late start of the programme, the inception phase developed a clear plan to achieve targets under this output. PMDP team conducted several meetings with the Minister of National Economy, and heavily engaged with the Palestinian Investment Promotion Agency’s (PIPA) management and staff. / The PMDP team conducted 10 individual meetings and interviews with PIPA’s department heads and staff members and discussed the roles of the various departments including their current and past activities. Through the same interviews, PMDP conducted an informal assessment of PIPA’s individual staff members’ capacity and capability. One of the key findings was the state of uncertainty among PIPA’s staff, given the recent changes in the management and potential organisational changes. A weekly meeting is scheduled with PIPA’s acting CEO to provide continuous assistance and help PIPA’s to manage the change process. / PMDP conducted an initial mapping of the main Palestinian diaspora clusters around the world and of their various initiatives to establish economic linkages with Palestine. This initial mapping included country-by-country analysis and will serve as the foundation on which PMDP will continue to build during implementation. / The PMDP prepared a draft scope of work / Job Description for the proposed Commercial Trade Representatives. This draft will serve as a starting point to discuss with the stakeholders to agree on the recruitment of overseas commercial representatives. / Recommendations: / DFID will seek advice from advisers and meet DAI monthly to ensure the plans to work with PIPA and recruiting commercial representatives meet the programme’s objectives and are in line with best practice by August 2014. / DFID and DAI Europe will revisit the output indicators and milestones and make amendments to reflect the findings of the inception phase by May 2014. / Impact Weighting (%): 15% / Revised since last Annual Review? / No. This is the first annual review. / Risk: Medium / Revised since last Annual Review? / No. This is the first annual review.

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? / No. This is the first annual review. The logframe will be revised based on the findings and recommendations of the inception phase. We will finalise and submit a revised logframe by May 2014 for approval. / 1.2 Overall Output Score and Description : ( C ) Outputs substantially did not meet expectation / 1.3 Direct feedback from beneficiaries: / No direct feedback was collected from beneficiaries for the annual review. The inception phase has developed mechanisms to collect feedback from beneficiaries in the course of the programme including success stories.
1.4 Summary of overall progress / This is the first annual review of the programme covering Jan 2013 – Feb 2014. The programme did not achieve its expected targets during this period because it started later than envisaged. The late start was due to unexpected delays in procurement of the implementer under the Fragile and Conflict Affected States Framework Agreement (FCAS). After a competitive procurement process, we selected DAI Europe to implement the programme and signed the contract on 26 September 2013 with the programme commencing 20 October 2013. Therefore, this annual review focuses on progress made during the inception phase of the programme (October 2013-Feb 2014) to pave the way to achieve the intended results. / The inception phase of the programme lasted four months and ended in Feb 2014. During the Inception period, PMDP has become fully functional with the majority of key technical positions filled, a full operational team in place, office premises in Ramallah and Gaza secured and necessary equipment procured. The PMDP kicked off the first Steering Committee meeting that encompassed DFID, the EU, and the Palestinian Ministry of National Economy (MoNE) on 28th January 2014. / An inception phase report has been submitted to the Steering Committee to review and provide feedback by March 2014.
1.5 Key challenges / The main challenge during the inception phase was the availability and recruitment of qualified staff to fill the key positions, with several successful applicants declining job offers. The PMDP was able to employ the needed staff with the right technical skills for the programme during the inception phase and now we have a competent team to implement the programme. / Other challenges that will continue to face the programme during implementation include: / Movement and access restrictions continue to remain as the most important constraints. / Risk aversion among enterprises resulting in failure to make long-term investments in production capacities. / Damaged infrastructure and lack of quality electricity supply in Gaza due to the political situation will remain a difficult challenge to overcome by Gazan firms. / These challenges and other risks were further identified in the risk section below.
1.6 Annual Outcome Assessment / Given the late start of the programme, there was no progress against the outcome indicators. / The outcome’s milestones per year will be revisited and revised based on the findings and recommendations of the inception phase. We will finalise and submit a revised logframe by May 2014 for approval.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The budget’s forecast was revised after signing the contract with the implementer. Expenses to date are on track against the revised forecast. / Key cost drivers / The main cost drivers of the programme we used during the procurement process are the staff costs, running expenses, and the matching grants. We assessed the suppliers’ proposed staff cost rate, number of staff, running cost, and budget of the matching grants and selected the implementer supplier who demonstrated best value for money. These cost drivers were identified during the development of the business case and will continue to drive the cost of implementation of the programme. For the evaluation supplier’s contract, in addition to the staff cost rate and expenses, the evaluation plan’s methodology (surveys, interviews, geographical locations..etc) was another key cost driver. / 2.3 Is the project on-track against original timescale: No / The project was intended to start on July 2013. However, delays in procurement meant that programme activities did not start until 21 October 2013.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is no change to the theory of change and the assumptions used in the project design. However, the inception phase is suggesting that the targets, logframe indicators and milestones be changed. In addition, the evaluation supplier is currently working closely with the implementing supplier and will produce its inception report that will assess the theory of change and assumptions in relation to the monitoring plan. We have been working closely with both suppliers to ensure that PMDP has robust monitoring and evaluation plan and data will be disaggregated based on gender, age, and location. / 3.2 Where an evaluation is planned what progress has been made? / We have procured an external evaluation service provider (GDSI UK) in January 2014 under DFID’s Global Evaluation Framework Agreement (GEFA). GDSI will quality assure results on a quarterly basis, conduct annual assessments, and carry out a final evaluation at the end of the programme. GDSI have been working closely with DAI Europe, Steering Committee members, and other stakeholders to prepare a detailed evaluation plan for the programme by mid April 2014. We will seek advice from the DFID evaluation advisers to ensure the plan is robust and meets DFID’s quality guidelines.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / We judge that a ‘medium’ risk level remains appropriate overall. Updated risks for the programme and the mitigating actions are discussed in Annex 1.
4.3 Risk of funds not being used as intended / The risk of financial fraud is low. DFID’s PrG have assessed DAI Europe’s financial capacity at the pre-qualification stage under the FCAS Framework Agreement process to ensure that there is very low or no financial risks. / The risk of financial misappropriation/fraud has also been minimised through implementation of a number of measures. DAI Europe is required to undergo independent audits annually. As part of the inception phase, DAI Europe also submitted a detailed operational manual with robust internal controls and procedures to mitigate against any financial risk or fraud. We will work closely with the DFID Regional Commercial Adviser to check that the procedures ensure adequate separation of duties, checks and balances are in place for the execution of all financial transactions. Finally, all transfers to contractors are checked by DFID’s project officer and approved by either the DFID Senior Policy & Programme Officer or the Team Leader of the wealth creation team. / 4.4 Climate and Environment Risk / We continue to assess the risk as ‘minimal’. The project is unlikely to lead to any direct environmental impacts. The inception phase has incorporated environment and climate change issues into the programme’s procedures including opportunities to raise awareness of environmental and climate change issues. For example, under the matching grant scheme climate and environmental issues will be assessed, and activities that may have negative impacts will not be supported. On the other hand, activities which have environmental benefits will be encouraged such as meeting international standards (eg. ISO14001) for environmental management systems.

5. Value for Money
5.1 Performance on VFM measures / It is too early to assess most of the VFM measures set out in the business case due to the late start of the programme. For example, the efficiency measures depend on outputs 1, 2 and 3 being up and running. This is not yet happening. On economy, although it is not yet possible to calculate administration fees as a percentage of overall costs, the implementing agency has agreed a maximum mark up of 13% on top of the actual costs of the inputs (such as staff salaries). / As identified in the inception phase, the PMDP will take a three-pronged approach to maximise VFM. First, it will incorporate a range of indicators covering the 4Es (economy, efficiency, effectiveness and equity) into M&E data collection for analysis and reporting on an annual basis. VFM indicators will also be disaggregated (where appropriate) by sex and sector. Secondly, PMDP will benchmark the results wherever possible against DFID-funded and other development programmes in the OPTs and elsewhere. Finally the team will carry out cost-benefit assessments using discounted cash flow analysis so as to generate estimates of net present value (NPV) and internal rate of return (IRR) of selected programme interventions. / VFM work will be closely coordinated with the external evaluation supplier. / 5.2 Commercial Improvement and Value for Money / We carried out a competitive procurement process under FCAS framework to select a supplier to implement the programme. We developed a robust and clear terms of reference tender to encourage adequate competition in close consultation with DFID’s Commercial Adviser and Procurement Group. Three bids were received, which were assessed against robust technical and financial criteria. The technical assessment was carried out by representatives from DFID, the EU, and the Ministry of National Economy while DFID’s Procurement Group evaluated the financial offers. DAI Europe’s bid scored higher against the criteria compared to the other bids thus delivering the best value for money. / A further contract was awarded for the programme evaluation supplier (GDSI) through a mini-competition under DFID’s Global Evaluation Framework Agreement (GEFA). We also contracted the World Check company (Vetting services company) in line with DFID’s procurement procedures. / Role of project partners / See above. / 5.4 Does the project still represent Value for Money: Yes / 5.5 If not, what action will you take? N/A

6. Conditionality
6.1 Update on specific conditions / N/A (only applicable to Direct Financial Aid given to a partner government).

7. Conclusions and actions
The programme did not achieve its expected targets during this period because it started later than envisaged. The programme’s inception phase took place from October 2013 to Feb 2014. During this period, PMDP has become fully functional with the majority of key technical positions filled, a full operational team in place, office premises in Ramallah and Gaza secured and necessary equipment procured. In addition, it paved the way to deliver the outputs of the programme and prepared a detailed implementation plan. / Actions: / DFID will review the inception phase, seek advice from advisers and provide comments and feedback to DAI to ensure the report meets the programme’s objectives and proposed implementation plan is in line with best practice by mid of April. / DFID and DAI Europe to revisit the logframe and make amendments to reflect the findings of the inception phase by May 2014. / DFID will meet monthly and work with DAI Europe on the selection and interventions to address specific market failures by June 2014. / DFID will meet monthly with DAI Europe to ensure that studies and interventions will address gender issues and include analysis of any failures that impact women, youth, and the poor during the course of the programme. / DFID will seek advice from advisers and meet DAI monthly to ensure the plans to work with PIPA and recruiting commercial representatives meet the programme’s objectives and are in line with best practice by August 2014.

8. Review Process
The annual review has been completed by the DFID Wealth Creation Programme Officer and the Senior Policy and Programme officer in Jerusalem with input from relevant DFID advisers. DFID’s Deputy Head of the Palestinian Programme based in Jerusalem quality assured the review. / The review was based largely on the inception report submitted by the implementing partner DAI Europe.

## Annex 1: Risks Register

Risk	Probability	Impact	Mitigation
Macroeconomic and country risks
Movement and access restrictions deteriorate in the West Bank and Gaza.	Medium	High	Equip DFID with evidence and case studies from project to help their dialogue with relevant authorities (OQR, EU, UN, FCO). Adjust programming if needed to respond to emerging needs as a result of more restrictions.
Gaza conflict between Israel and Hamas.	High	Medium	Adjust programming to respond to emerging needs as a result of conflict.
Escalation of conflict in the OPTs.	Medium	High	Adjust programming to respond to emerging needs as a result of conflict.
Aid flows sharply decline reducing economic growth.	Low	Medium	This programme designed to enable a robust economy independent of aid. Sustainability is one of the main principles of the M4P approach that will be applied.
Aid coordination remains weak and the proliferation of donor programmes undermines sustainable market development efforts.	Low	Medium	DFID and the EU will facilitate further donor coordination efforts. DAI’s longstanding relationship with key donors and stakeholders in the OPTs, as well as current implementation projects, will help facilitate coordination.
The programme introduces its own market distortions.	Medium	Medium	Direct support can cause distortions and the Palestinian market already suffers from abnormally high risk which itself creates distortions. This scheme is specifically designed to compensate for these distortions by addressing the root causes of market failures and distortions.
PMDP not sufficiently changing root causes of market failures.	Medium	Medium	PMDP alone cannot change the root causes of market failures. The project will work very closely with MONE, the EU, the World Bank, and other major donors to ensure that concerted efforts are exerted to enable maximum impact.
Major economic shocks, such as global economic stagnation, take place.	Low	Medium	The programme is sufficiently flexible to work on both export oriented businesses and domestic industries and services. During economic crisis, businesses will be encouraged to focus more on improving competitiveness of local products and services to enable import substitution, rather than exports.
Results- and activities-level risks
Inadequate performance or impartiality of PMDP’s management, administrative, and technical staff.	Low	Medium	DAI Europe has assembled a carefully selected and vetted team with significant combined experience working on similar projects. In addition, DAI’s robust project management systems ensure checks and balances on all our staff and help us monitor performance and conflicts of interest.
Insufficient business interest in or ability to make use of the matching grant scheme.	Low	High	PMDP is going to take proactive measures to maintain and encourage more demand. PMDP will use effective marketing and communication tools to reach clients across over oPT taking into consideration marginalized areas and areas named by “Area C”.
Inappropriate (fraudulent) or ineffective use of grants provided.	Low	High	Procurement of services by the grantees will be carried out jointly by the recipient firms and PMDP in order to minimise fiduciary risk. This will result in joint accountability between the client and the programme staff on cost, value for money and quality of services. Periodic audits will be conducted. In addition to that, PMDP will have an assessment panel that will approve each grant.
Palestinian Business Service Providers (PSPs) do not provide sufficiently high quality services.	High	Medium	This issue has been identified as a market failure to be addressed in the programme. Local BSPs with certification (supported through the programme) will be included in the roster from which firms can select to provide services. In addition to that, PMDP will conduct performance evaluation per grant to update the qualified BSP roster. On the other hand, PMDP will take into consideration the feedback provided by the grantees after each assignment.
Direct/indirect financial benefit to terrorist organisations through: a) grant funds being used to help businesses with links to such organisations; .b) businesses use funds in contravention of EU/UK terrorist financing law; or c) taxing or extorting businesses for funds.	Low/ Medium	High	a) PMDP will vet all recipient businesses using World Check. This procedure will prevent businesses with clear link to such organisations from receiving grants or any kind of support. b) DFID’s contract with DAI will ensure compliance with EU/UK terrorist financing law, with grant agreements with recipient companies committing them in writing to not provide direct or indirect financial benefit to terrorist organisations. c) This is covered under b).
Measuring of PMDP results biased and not objective.	Medium	Medium	This risk will be mitigated through the evaluation supplier to measure results throughout the lifetime of the project. These results will be compared against results produced by DAI and action will be taken in case of major discrepancies. DFID staff will also conduct field visits and will verify first-hand the quality of the results collated by both contractors.
The MONE are incapable to provide support to business representatives abroad once the project is completed.	Medium	Medium	This will be mitigated through a formal memorandum of understanding signed by the PA to ensure that the PA will pick up the activity and cost of commercial representatives after the end of the programme. This activity will also be closely assessed on an annual basis to ensure viability and results before proceeding into the next year of support.
Agreement on reporting and support structure for commercial trade representatives (CTR) is not reached between MoNE and MoFA	Low	Low	Move CTR component closer to be managed by private sector organization.
Lack of support from trade and investment support organizations such as PIPA and Paltrade	Low	High	Continues engagement early on during the programme implementation will eliminate the probability of happening.
Diaspora are not willing (hesitate) to cooperate due to previous reputation.	Medium	Medium	Activities should not link to achieve fast linkages and achievement. This is a continuous activity to build trust, perception to utilize Diaspora network and referrals to open the doors for other investment not necessarily by Diaspora themselves.
Government push for centralizing diaspora’s efforts	Low	Low / Medium	Build synergies with the newly established centre.
Grantees are not willing to report periodically on supported projects	Medium	Medium	The PMDP grants agreement will include an article which indicates that each grantee should report periodically on grant intervention.
Change management in PIPA is not fully adopted by PIPA’s management, staff and MoNE	Low	High	Keep a high level and continuous engagement with PIPA re-enforcing the need of change.
Frequent changes in government leading to the need to re-establish project momentum.	High	Medium	Will need to formalize all agreements on engagements and next steps with Gov. counterparts.
Instability in PIPA as a result of any court’s decision forcing management changes and associated risks	Medium	Medium	Conducting PMDP as professional as we can and precede engagement with caution.
Programme management risks
The capacity of the implementing partners to deliver the programme is inadequate.	Low	High	Careful selection and screening of project partners will avoid this risk. Selection will be made on evidence of past high quality delivery experience in similar programmes. After selection, close monitoring of results and implementation quality will enable DAI to flag out issues early enough to enable corrective action.
Environmental, social, and governance risks
Programme has a detrimental effect on the environment, either directly or indirectly through its beneficiaries.	Low	Low	An ESG risk policy will be developed for the project. This will trickle down to our agreements with partners and beneficiaries.
Failure to deliver intended benefits on women and marginalized areas	Low	Medium	PMDP draw gender strategy to target women and small businesses in marginalized areas. In addition to that, PMDP will use the most effective communication tools to reach out all peripherals areas across over the oPT.