Project Completion Review

Project Title: Humanitarian Support to UNICEF Nutrition Surveillance

Aries Project Number: 201823
Date started: November 2010	Date review undertaken: January 2014

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
Department for International Development (DFID) provided £2,000,000 to United Nations Children’s Fund (UNICEF from) October 2010 to November 2012 to support nutrition surveillance in Ethiopia to improve the timely availability and quality of nutritional data. Originally intended to be completed within 2 years, the programme was extended for a 3rd year – within the original budget - due to lengthy delays in start-up resulting from slow government approvals. / The overall cost of the programme is £4.3 million with 47% provided by DFID, 28% by the World Bank and 25% by UNICEF.
What were the expected results?
The goal of the project was to improve targeting, coverage and quality of the humanitarian response. The primary outcome was to improve timely availability and quality of nutrition data using a nutrition surveillance approach linked to agro-economic baseline data and early warning. / Resources were focused on improving data quality and the rapid flow of information from sub district/district levels for analysis and use. / The main outputs of the programme include: / Timely availability of nutrition indicators from existing programme data systems. Existing sources include the Community Based Nutrition (CBN) programme, Therapeutic Feeding Program (TFP), Expanded Outreach Strategy (EOS) and Child Health Days (CHD); / Timely availability of quality bi-annual nutrition survey indicators; / Increased knowledge of and guidance on nutrition data collection and interpretation in pastoral areas.

What was the context in which UK support was provided?
Around 11 million children are currently under-5 in Ethiopia[1]. According to the 2011 Ethiopia Demographic Health Survey (DHS)[2] of these children an estimated: / 4,884,000 are stunted - reflecting the cumulative effect of chronic malnutrition. / 1,067,000 are wasted - reflecting an acute or recent nutritional deficit. / 3,157,000 are underweight – reflecting children with a double burden of malnutrition who are wasted and stunted. / Ethiopia is making progress towards food and nutrition security. As seen in Figure 1, both stunting and underweight prevalence have decreased by more than 10% between 2000 and 2010. The decrease has been steady, with both falling by 1.34 percentage points per year over the 10 year period. Wasting, which measures the more immediate effect of malnutrition, seems to have fallen slightly from around 12% in 2000 and 2005, to 9% in 2010. However, Undernutrition is still a public health problem and an overarching development concern, affecting not only food insecure areas of the country but also food secure areas. As shown in Figure 1, stunting affects 44% of children under five years of age (DHS 2011). Ethiopia ranks 7th highest in the world for rates of stunting, contributing 3.5% to the global total of stunted children. Ethiopia is also one of the ten countries that account for 60% of the global burden of wasting in children under 5 years old[3]. While wasting rates are high even during ‘normal’ years, in times of stress, wasting rates rise to alarmingly high levels and regularly exceed emergency thresholds. / Figure 1: Trends in Children’s Nutritional Status / The causes of malnutrition in Ethiopia are myriad and complex. Furthermore there is limited work being undertaken in Ethiopia to explore the reasons behind the nutrition trends or on understanding the underlying causes of wasting or stunting.According to UNICEF’s conceptual framework, the three layers of determinants affecting nutritional status are notably dietary intake, care practices and environmental health factors. / Although many of the underlying causes of malnutrition are structural and chronic, they often manifest themselves in widespread prevalence of acute malnutrition that surpasses emergency thresholds and requires a humanitarian response. This is particularly the case following a shock such as a drought, resulting in even less satisfactory dietary intake, or floods resulting in displacement and poor sanitation conditions. / Humanitarian financing needs in Ethiopia are some £200 - £400 million annually. The UK is the second largest bilateral humanitarian donor to Ethiopia (after the USA), contributing some £57 million in 2011 and £43 in 2013 in humanitarian assistance. Timely and quality nutrition information is required to determine the scale, nature and location of humanitarian needs. With available funding rarely sufficient to meet all the requirements, rigorous prioritisation is required to ensure that the assistance available reaches those most in need. This requires the availability of timely and quality nutrition information. / Challenges to obtaining the right nutrition information at the right time to inform the humanitarian response including barriers to inter-sectoral information sharing (for example between health and water and sanitation offices’ and agencies), myriad and not necessarily coordinated sources of nutrition information, limited coverage of nutritional surveys and delays in publication, lack of a central system for analysis and presentation of all available nutrition information, and varying capacity in government structures to collect and utilise nutrition information. / This nutrition surveillance project had ambitious objectives in terms of increasing the quality and availability – and in places independence - of nutrition information to inform the humanitarian response, and also to embed nutrition surveillance as a regular facet and responsibility of government structures rather than responsive to shocks and external to government. / In the initial programme proposal, there was the “fast-track”concept. The concept was that woreda health officials would phone key indicators (TFP/CBN/CHD) vertically to regional officials as part of early warning. Ultimately, this concept was not accepted by the Government. In the proposal, it was also planned to have surveys implemented by livelihood type. However, the government insisted on only having woreda level surveys, so that the results could be interpreted within administrative boundaries. / After the first year of slow implementation rsulting from lengthy delays in securing government endorsements for the approach, significant results have been achieved over the life of the project as a result of two Annual Reviews and several review meetings between DFID and UNICEF which addressed the concerns of the government, identified key constrains and suggested action points. The project strengthened existing systems of data collection and analysis, supported the implementation of semi-annual nutritional surveys in four of the most food insecure regions, and developed systems in Afar and Somali Regions where no or limited nutritional data was available. The actions of this project have further developed and enhanced the early warning system to now include information that allows for direct tracking of the nutritional situation of children in Ethiopia, where as previously, it was primarily agricultural and food security focused, and particularly in vulnerable areas. / The project helped to ensure a more effective humanitarian response – one that is now, to degrees, more evidence-based and prioritised. In turn this delivered a more cost-effective humanitarian response and reduced levels of malnutrition-related mortality. This project has been successful in improving relationships among the key stakeholders working on nutrition. The agreement to go ahead with nutritional surveys in sensitive areas is an indicator of this. Even with the identification of high levels of malnutrition, government has released the information and acted upon it by providing support themselves and by asking NGO partners to assist. This can likely be attributed to a sense of ownership of the system by the government. The success of the system is that it is fully coordinated and implemented by the Government, allowing for fast approval and dissemination of results. / In order to capitalise on the successes of this progress and in light of continued external resources to embed the benefits achieved, the Nutrition Surveillance activities will continue for four years ( 2014-2017), with additional support from DFID under the Accelerating Reductions in Undernutrition project. The new multi-year Nutrition project will provide technical assistance to the MoH and Emergency Nutrition Coordination Unit (ENCU) to strengthen the collection, analysis and collation of nutrition data across the sectors and will be an opportunity for exploring the possibility again of creating a central depository for multi-sectoral and multi-programmatic nutrition data within government systems.
[3] ¡ Population Projection (2010) according to the Ethiopia Census 2007. Central Statistics Agency. ¡¡Ethiopian Demographic Health Survey 2011, Federal Ministry of Health, Ethiopia. ¡¡¡ Population Projection (2010) according to the Ethiopia Census 2007. Central Statistics Agency. LIST OF ACRONYMS CBN	Community-based Nutrition Programme CHD	Community Health Days	NGO	Non-governmental Organization NNP	National Nutrition Programme CMAM	Community Management of Acute Malnutrition	NSP	Nutrition Surveillance Program DFID	Department for International Development	OTP	Outpatient Therapeutic Program DPPB	Disaster Prevention and Preparedness Bureau	PIM	Project Implementation Manual DRM	Disaster Risk Management	RENCU	Regional Emergency Nutrition Coordination Units DRMFSS	Disaster Risk Management and Food Security Sector	RHB	Regional Health bureau DHS	Demographic and Health Survey	SAM	Severe Acute Malnutrition ENCU	Emergency Nutrition Coordination Unit	SMART	Standardized Monitoring and Assessment of Relief and Transition EOS	Extended Outreach Strategy	SNNPR	Southern Nations, Nationalities and People's Region FAO	Food and Agriculture Organization	TFP	Therapeutic Feeding Programme FMoH	Federal Ministry of Health	TFU	Therapeutic Feeding Unit GAM	Global Acute Malnutrition	TSF	Targeted Supplementary Feeding GMP	Growth Monitoring and Promotion	UK	United Kingdom HDA	Health Development Army	UNICEF	United Nations Children’s Fund HEP	Health Extension Programme	VfM	Value for Money HEW	Health Extension Worker	WFP	World Food Program HRD	Humanitarian Requirement Document IMC	International Medical Corps MANTF	Multi-Agency Nutrition Task Force MAR	Multilateral Aid Review MOFED	Ministry of Finance and Economic Development

## Section A: Detailed Output Scoring

Output 1: Timely availability of Nutrition indicators from existing Theraputic Feeding Program (TFP) Community Based Nutrition Program (CBN)/ Expanded Outreach Strategy (EOS)/Child Health Day (CHD) data systems to feed into early warning system
Output 1: final score and performance description: / Overall score B: Output moderately did not met expectation. / Output 1 has three indicators: / Indicator 1: Five agreed indicators on CBN and TFP consistently reported - Score: A / Indicator 2: Number of weeks from collection to availability of data - Score: B / Indicator 3: Availability of new technology – database – Score : B / Table 1: Progress of output 1 against expected milestones: / Baseline (2010) Target (November 2013) At completion of project / Plan Achieved / Indicator 1: Three agreed indicators on CBN (1. Coverage, 2. Underweight and 3. Severe underweight) two indicators on TFP (1 Reporting Rate Out patient Theraputc Program (OTP); 2. New admissions OTP) consistently reported Poor reporting rate 100% of districts reporting all five agreed indicators CBN: Achieved for Coverage, under waight and severe under weight / TFP: Achieved for Reporting Rate and new admissions / Indicator 2: Number of weeks from collection to availability of data Delay up to 8 weeks Reducing delays to 4 weeks CBN: Partially achieved (not consistent) / TFP: Achieved / Indicator 3: Availability of new technology - database NA In Place Not fully achieved – but progressing / Performance description / Data obtained through the Therapeutic Feeding Programme (TFP), Severe Acute Malnutrition (SAM) data has consistently achieved 85% national reporting rate or higher from 2011 to 2013 ( see figure 1 below), The data includes the number of new admissions, reporting rate and the performance indicators (cure rate, death rate, defaulter rate). The reporting timeframe of the TFP data has been consistently maintained to within 3-4 weeks of the government deadline for reporting. As of October 2013, there are 12,410 expected reports (total sites supporting the management of severe acute malnutrition) in approximately 600 woredas. The admission as well as performance rates are consistently reported in all federal and regional early warning monthly and/or quarterly bulletins, as well as through the cluster forums. The availability of the data is most useful to the federal and regional Governments and other stakeholders in planning for supplies and other essential commodities related to the SAM programme and necessary for responding to the surge in case load and for enabling timely referral as needed for additional care for complicated cases. / The consistently high reporting rate and timeliness of reporting from such a large coverage of Ethiopia continues to highlight the success of the system and validate its usefulness in providing nutrition trend information for early warning. The usefulness of the TFP data has been instrumental for early warning on the nutritional status of children and also for confirming periods where the nutritional status of children is optimal. For instance, in 2011, increasing SAM admissions in Ethiopia was picked up and reported by March/April, whereas for the rest of the Horn of Africa, a drought emergency was only detected and declared in July. The robustness of the data management system in Ethiopia served to prevent increased case loads and death amongst the most vulnerable children at this time. In addition during the 2012 ‘Belg’ failure in Southern Nations, Nationalities and People's Region (SNNPR), the data management system began to depict increasing SAM in January the same year and enabled forward planning to minimize the negative consequences on children. First and foremost, the govornment Communit Management of Acute Malnutrition (CMAM) programme played key role to the success of the project by generating the TFP raw data. Another factor which was crucial in the success of the information system is the strong nutrition cluster mechanism in Ethiopia. Currently this is managed by the Emergency Nutrition Coordination Unit (ENCU), but is comprised of all nutrition partners. The information collection and reporting is strongly supported in some areas by NGO’s, particularly in Afar, and Somali. Note that UNICEF is the cluster lead for nutrition, but in Ethiopia, this support is provided through the ENCU. The ENCU was supported partially with DFID funding. / CBN routine growth monitoring data is consistently reported within 4-8 weeks from all programme woredas (currently there are 328 woredas implementing CBN out of 600 woredas throughout the country), including participation rate, underweight and severe underweight, disaggregated by gender. SNNP region consistently reports within 4-6 weeks, but the other regions are less consistent. The information is reported within 8 weeks, but this is internal, ie, government and UNICEF (and other partners, such as World Bank (WB), if requested). It is not reported within the early warning mechanisms, due to the limitations discussed. / There remains a limitation to utilizing this information for early warning, which is the coverage of the programme (participation rate). This has remained on average around 40-45 per cent from the four regions of SNNP, Amhara, Tigray and Oromia. SNNPR has done significantly better as a region, reaching a participation rate of 78 per cent. Overall, this level of coverage makes it difficult to interpret the situation for early warning purposes. Therefore, the CBN data currently cannot be included in monthly early warning reports. Participation rates would need to reach levels of around 80 per cent, such as with TFP, for the interpretation of the overall situation to be accurate and useful for nutrition surveillance and early warning objectives. The stakeholders involved in supporting the Federal Ministry of Health (FMoH) and Regional Health Bureaus (RHBs) in the implementation of the CBN program are working to resolve the low participation rates. With the introduction of the revised National Nutrition Program (NNP), and roll-out sensitization workshops to regions, increasing participation will be stressed as a priority. / Community health days(CHD)/Expanded outreach services (EOS) and Mid-Upper Arm Circumference( MUAC) screening data for children and Pregnant and Lactating Women remains a challenge, primarily due to the time it takes to process the information from the woreda, as well as the need to refer to population estimates per woreda in order to compute more accurate coverage. The approximate turnaround time to get the data is between 6-8 weeks, after data checking. This is too long to be used for early warning. However, when the data does become available, some regions report it in the early warning bulletins. In addition, there remains the uncertainty with inclusion error, since the screenings in priority 1 woredas are linked with Targeted Supplementary Food (TSF) distribution. While this data is useful for screening children into either Community Management of Acute Malnutrition (CMAM) or TSF programs, it is questionable as a population indicator. Also, the FMoH has now given the directive that all CHD woredas should shift to routine Health Extension Programme (HEP) services.This will add a layer of difficulty in getting the information, as it would then be generated monthly, requiring a different system for data collection and reporting. Should the FMoH nutrition information database (discussed below) be established, this may be facilitated. However, the timeframe for its establishment is still unknown. / Availability of new technology – database: This has not been fully achieved. However, there has been more significant progress in 2013 compared to previous years. During 2012, UNICEF sent out a Request For Proposal (RFP) for the development of a comprehensive nutrition information database, which would encompass each of the routine sources of information (TFP, CBN, and CHD) as well as nutrition survey data and some contextual data. However, after receiving the proposals, there was apprehension in the FMOH to move ahead and there were policy concerns about the management of the database, so the project was suspended. / During 2013, with the revised NNP, a new nutrition unit within the FMoH has been established. With the establishment of this unit, renewed demand has arisen for all nutrition information to be collated, and with this demand has also been a call for the development and establishment of a nutrition information database within the FMoH steering committee. This has now been established and several meetings have been held with a Terms of Reference developed for the group which began formally functioning with effect from October 2013. / UNICEF has indicated that it has been working internally on developing a comprehensive database (see screenshot below), but this has taken some time without dedicated project specific staff devoted to this task. UNICEF has shared this database with the FMoH and the newly established Steering Committee, which has proved useful as an advocacy tool for its further development within the FMoH. / Figure 2: Screen shot of database format / Recommendations: / The TFP SAM admission data is a well-established mechanism for nutrition early warning information. It is now widely reported by government and stakeholders, and is generally well understood in terms of interpreting the trends and overall situation combined with contextual data. / The CBN data depends in general on a much broader ownership by government of the programme. With the adoption of the revised NNP, the establishment of the nutrition unit within the FMoH, and the upcoming sensitization in the regions, it is anticipated that ownership will increase. There remains the question of whether or not the Health Extension Workers (HEWs) can maintain the same level of growth monitoring without the assistance of the Volunteer Health Workers (VHWs). Performance indicators for CBN including growth monitoring and reporting, if established for HEWs, would aid in programme implementation and reporting of the indicators. To increase the CBN participation rate the following actvites might help; 1. Strengthening the HEWs social mobilization outreach system to better inform mothers of the schedule of the CBN sessions and to encourage them to attend. It is also important to actively involve the Health Development Army (HDA) and community social mobilization groups (Afar/Benshangul Gumuz) to assist and strengthen the social mobilization. 2. Strengthen the capacity of the Supervisors to monitor the performance of the program and also provide support to the HEWs to strengthen outreach activities. Efforts should still be made and are being made to improve CBN/CHD participation and reporting. And of course, the factors mentioned to improve CBN participation are also supported with the new DFID funding. UNICEF has been advocating with FMOH to stress the importance of timely reporting and to push for an improvement. / In addition, if the nutrition database is established within the FMoH, and decentralized to the woreda level, the tracking of indicators will be better facilitated. If this development moves ahead, however, it will likely take a couple years to decentralize. Advocacy should continue with FMoH for this approach, as well as commitment to support development and provision of technical support based upon internal experience with attempts to establish a basic comprehensive database. The FMoH has committed to this, but there are other pressing priorities right now, such as the NNP rollout and regional sensitization.
Impact Weighting (%): 50% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 2: Timely availability and quality of bi-annual nutrition survey indicators
Output 2: final score and performance description: / Overall score: A - Output met expectation / Output 2 has three indicators. / Indicator 1: Number of surveys implemented on seasonal calander: Score: Score: A+ / Indicator 2: Number of survey reports endorsed within two weeks of release of reports: Score: A / Indicator 3: E-learning training modules developed for improved capacity development: Score: C / Table 2: Progress of output 2 against expected milestones: / Baseline (2010) Target (November 2013) At completion of project / Plan Achieved / Indicator 1: Number of surveys implemented on seasonal calander Delay in approval 100% of 40 to 46 surveys implemented in 20 to 23 woredas according to seasonal calendar Achieved 50 surveys in 25 weredas (The achieved number of surveys slightly exceeded the target number at completion of the project) / Indicator 2: Number of survey reports endorsed within two weeks of release of reports Delay in endorsement 100% of survey reports endorsed within two weeks Nearly achieved. Nutrition indicators calculated and reported on within two weeks. Survey reports took longer than two weeks to draft, so were not endorsed within 2 weeks. / Indicator 3: E-learning training modules developed for improved capacity development NA 100% of e-learning training modules developed for use by nutrition staff Not achieved / Performance description / There have now been four complete rounds of bi-annual nutrition surveys, December 2011, May/June 2012, December 2012 and May/June 2013. The fourth round achieved more than 100% implementation of 50 nutrition surveys in 25 woredas slightly exceeding the target number of surveys (40 to 46) at completion of the project in 20 to 23 woredas. The system is ongoing with the fifth round of surveys having begun in December 2013. At the time of preparing this report the data from the December 2013 round was not finalised. / Nutrition indicators were analysed and reported within two weeks of the end of the survey’s data collection and this is the most important factor to note in scoring this indicator. However, endorsement of the nutrition survey reports within two weeks was not achieved, as it physically took longer than 2 weeks for the reports to be drafted. Therefore, it is considered that the indicator is nearly achieved since the information was made available for resonse although the survey reports were not ready and endorsed, thus fulfilling the purpose as improving the availability of timely nutrition data to inform humanitarian response. / A key achievement in 2012 has been that the bi-annual nutrition surveys are recognized as a system within the government, and there is demand for the information not only from international/ national humanitarian partner stakeholders, but from the government as well. Findings of nutrition survey data previously generated from Non Governmental Organizations (NGOs) in Ethiopia were often controversial with the government. By supporting a system embedded in government, and strengthening the capacity of government staff, the information generated through internal systems (rather than external NGO reports) has witnessed faster turn-around times for release. / As part of the capacity development, it was planned that this project supports the development of a series of e-learning modules on nutrition data analysis. This was based on the observation that whilst there was some capacity for basic data analysis using the Standardized Monitoring and Assessment for Relief and Transition (SMART) methodology and software, capacity for analysis related to underlying causes of malnutrition such as infant and young child feeding was lacking. Therefore, with support from this project, e-learning modules were going to be developed for further nutrition data analysis skills. A consultant was hired to carry out this activity and developed outlines for the modules and submitted four basic modules out of 11 proposed. However, due to ill health of the consultant not all the remaining outputs were received as scheduled. Subsequently the contract with the consultant was cancelled and the outputs under this indicator were not delivered. The risk was managed through linking payment to receipt of outputs. See Recommendations below for further discussion. / Recommendations: / Woreda level nutrition surveys take a considerable amount of time, not only for data collection, but for analysis and report writing. Moving into 2014, lessons learned and relevant considerations need to be discussed among those involved in the system, primarily UNICEF and ENCU staff. These considerations are as follows: / For SNNP and Oromia, consider reducing the number of surveys to 4. This will reduce the cost and time required for a significant number of staff to be in the field. / Change the methodology to that of a standard SMART survey. The demand for information from stakeholders has largely been for the nutrition indicators. Food security and other contextual data is derived from the early warning system, World Food Program (WFP), Food and Agriculture Organization (FAO) and other partner organisations and can be gathered as secondary data. This does not need to be included in the field data collection. This will reduce the amount of time in the field which also reduces the cost. / As the bi-annual survey system has further support planned from DFID under the new and larger nutrition program, the recommendations to improve the timeliness and efficiency of data collection have a higher chance of being implemented e.g. shifting to SMART survey methodology. / Given that it is likely that the standard SMART methodology for surveys will be adopted, the emphasis on creating learning materials for higher level analysis (e-learning modules) will no longer be needed. Existing standard modules for SMART training will, therefore, be used in future trainings.
Impact Weighting (%):40% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 3: Increased knowledge and guidance on nutrition data collection and interpretation in pastoral areas
Output 3: final score and performance description: / Overall score: A output met expectation. / Indicator 1: Operational research conducted in pastoral areas - Score: A+ / Indicator 2: Best practice document available - Score: B / Table 3: Progress of output 3 against expected milestones: / Baseline (2010) Target (November 2013) At completion of project / Plan Achieved / Indicator 1 Operational research conducted in pastoral areas Operational research completed in Afar and Somali Achieved (in SNNP and Oromia as well) / Indicator 2 Best practice document available Partially Achieved / Performance description / A consulting firm was contracted to carry out the study for “Improving Nutrition Monitoring in Pastoralist Areas of Afar and Somali.”A steering committee was developed, consisting of government, UN and NGO members of the Multi-Agency Nutrition Task Force (MANTF). After some subsequent meetings of the steering committee, the project expanded to encompass pastoralist areas of SNNP and Oromia as well. The study was completed and a final report was submitted to the Steering Committee. UNICEF reviewed the report and approved it for completeness and attention to the TORs and required output. Achievment of indicator 1 of output 3 moderately exceeded expectation as the operational research was expanded to include pastoralist areas of SNNPR and Oromia. / Subsequent to receipt of the final report, the consultants met with the Steering Committee and presented the findings. Following this, the Steering Committee has met a couple times to discuss the findings. The recent establishment of the Nutrition Unit has meant that different persons from the FMoH are now involved and they have requested additional time to review the report. Once the FMoH has reviewed the report (which is lengthy), the Steering Committee will reconvene and work towards identifying the key issues and recommendations made in the report and discuss potential actions. UNICEF and DFID will follow-up and ensure that the FMoH review and approve the report which will then be followed by the release of the best practice document in 2014. / Some key recommendations highlighted in the report: / Improved coordination between HEWs and the Health Development Army (where established): as they play a major role in mobilizing the communities / Ensuring birth registration / Strengthening Growth Monitoring and Promotion (GMP) sessions / Strengthening the Micro-planning processes for CHDs / Improved convergence of Health and Disaster Risk Management and Food Security Sector (DRMFSS) structures – particularly the HEWs and Development Agents (DAs) / Capacity building, especially at lower levels / Increased involvement of clan leaders / Pro-active involvement of Kebele administration / Improved ownership / Revision of formats for inclusion of migration details / Selection of women HEWs from the communities / Addressing Turnover issues / The Steering Committee aims to review these recommendations and identify strategies for implementation as appropriate. Indicator 2 is considered to be partially achieved. / Recommendations: / Continue to follow up with FMoH on the review of the report and ensure that the Steering Committee reconvenes to identify key lessons learned and to decide actions as appropriate.
Impact Weighting (%): 10% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? No / 1.2 Final Output score and description: / Final output score: A / Based on the weighted scoring of the three outputs scores of B, A and A. This scoring is mainly based on the critical success of the programme in making timely nutrition information available to influence the humanitarian response. In particular the regular TFP data showing increasing trends in admittances to feeding programmes, combined with the nutrition surveys that provided solid technical data on the locality and severity of the humanitarian situation, were instrumental in influencing and prioritising the humanitarian response during 2011 to 2013. As a result of the availability of this information, levels of assistance were increased in a timely manner and a worse humanitarian situation was mitigated. This has undoubtedly contributed to saving the lives of many Ethiopians. The importance of this contribution of the programme should not be under-estimated. / However, a key challenge of the programme was to fully internalise nutrition data systems within Government’s own early warning systems in the timeframes set out in the logframe. The fact that the NSP was dependent on the performance of other existing programs (CBN, CHD, EOS) for data generation has negatively affected its achievement due to their limitations in terms of poor quality of the data, low coverage and the inherent bias in beneficiary selection. These programs in their current form, do not provide data which is of high enough quality to be used for nutrition surveillance purposes. / As regards the bi-annual nutrition surveys, all stages of the data management system including data gathering was part of the Nutrition Surveillanc Program (NSP) activities which led to a remarkable performance. Full achievement of the NSP was clearly dependent on the performance of other programs, a set of processes and commitments that are at least partly outside the control of this programme. The programme score is therefore, to an extent, a victim of some overambitious timeframes in the logframe target setting process and expectations that the existing programs could fully achieve their own targets. / As the project scored B at the last annual review, a Project Improvement Plan (PIP) was prepared to closely monitor and improve performance before the Project Completion Review (PCR). The PIP has drawn on the lessons from previous years and the recommendations of the last annual review which were based on the review’s assessment of challenges and lessons. Monthly joint DFID/UNICEF review meetingis were held to assess progress against the set targets, follow-up actions from the March 2013 Annual Review and incorporate additional feedback from beneficiaries. A joint field level assessment was also undertaken as part of the PIP. It is very encouraging to note that the PIP made a significant contribution to both the improved achievements of the NSP to date, and the decision to continue to invest in the nutrition information system in DFID’s new nutrition programme.
Direct feedback from beneficiaries / The direct beneficiaries of this programme are Government and the international humanitarian community, who are able to make use of the improved timeliness and availability of nutrition data for decision making regarding humanitarian response. / A) Federal DRMFSS / Interviews with concerned staff at federal DRMFSS indicated that the bi-annual surveys provide trend analysis over time in selected vulnerable woredas are used to triangulate with other sources of nutrition information in order to have better understanding of the evolving situation in the respective woredas. Moreover, The bi-annual surveys are used for decision making of initiating, phasing out or close monitoring of the situation. They are also used in “hotspot” classification; a means of identifying high risk areas for priority humanitarian assistance. They contribute in building/strengthening early warning information system within the DRMFSS. The DFID support has enhanced timely nutrition data collection, analysis and information flow from woreda to regional and finally to federal level. / The federal DRMFSS mentioned that a number of people have been trained on emergency nutrition assessments based on SMART methodology which has improved the capacity of the regions. Now government staff in the regions especially, Oromiya, Tigray, Somali, Amhara and SNNPR are no longer mere participants but they can plan and conduct the surveys themselves as team leaders or leading the survey at woreda level. / With regard to ownership, the NSP activities are planned, integrated within the DRMFSS annual work plan, implemented and monitored by the DRMFSS staff. / The NSP was appreciated by the central government for helping to support their negotiations with donors and other agencies for humanitarian support resources. / B) Oromiya Regional Early Warning Bureau / During a recent DFID monitoring field visit to East Harerghe zone of Oromia region, the Federal DRMFSS, Oromia DRMFSS bureau and East Harerge zone DPPB confirmed their appreciation for the financial and technical support provided by the nutrition surveillance programme including DFID’s substantial investment. DRMFSS staff in Oromia region and East Harerghe zone also indicated that government capacity was built on data collection as bi-annual training was provided at district level where government staff were trained per sentinel site. It was, however, pointed out that the capacity building in SMART software including data analysis was not adequate for government staff who are supposed to takeover the programme management role. They expressed their interest and commitment to assume the overall management and supervisory role once the necessary capacity building in all stages of the NSP (data collection, analysis and report preparation) has been completed. They also gave some examples where the NSP alerted government and agencies to a deteriorating nutrition or food security situation and this triggered a response which undoubtedly contributed to saving the lives of many Ethiopians. The DFID mission was informed that the survey information was being utilized for decision making such as initiating, terminating and extending humanitarian emergency interventions. For example, Oromia Regional ENCU/Federal ENCU/regional EW decieded to extend International Medical Corps (IMC) exit plan from Midega Tola woreda in June 2013 when the nutrition situation was classified as serious. IMC also continued supporting the woreda instead of withdrawing based on its initial exit plan. The surveillance information is used in hotspot classifications, triggering rapid responses and close monitoring of the situation/trend analysis. / Disaster Prevention and Preparedness Bureau (DPPB) staff of Oromia region and East Hararge Zone were of the impression that the Nutrition Surveillance Programme is owned by the DRMFSS at all levels and only use government structures for data collection. They also rasied their concern regarding the sustainability of the programme in the absence of financial support which the ENCU of DRMFSS was getting as well as due to inadequate capacity at national, regional, zonal and district levels. / Athough the woreda and regional officials were informally notified (through email) of the survey results after completion of the survey and actions are taken, they revealed that formal reports were delayed for months or never received . They requested that the reports be sent regularly and without delay to concerned government offices at various levels. / C) GOAL (NGO) – Ethiopia / The capacity of the government to conduct survey has been built through training and partners support. The NSP has helped the government officials understand the nutrition situation in their areas in terms of Global Acute Malnutrition (GAM) and SAM; this was not the case before. Based on the survey results, the woreda, zonal and regional officials are now able to put forward recommendations on the actions that should be taken. Moreover, the government owns the results of the survey and therefore there is no denial of the nutrition situation reported in bi-annual surveys. / GOAL has positively the coordination of emergency nutrition activities at national level. The coordination has helped to avoid resource duplication and strengthened the partners quick and timely emergency nutrition responses. / Weak linkages between the federal and regional coordination forums in terms of sharing and acting on issues from both sides was mentioned as a weakness of the NSP. / The improved capacity of government officals following the SMART training enabled them to conduct the bi-annual surveys themselves with minimal support in some woredas/regions. GOAL has been one of the partners engaged by the ENCU in providing technical support for the SMART training in a number of regions. / D) Concern (NGO) - Ethiopia / The NSP has helped the government and partners to understand the nutrition situation in nearby woredas. Moreover, the NSP has helped strengthening the government early warning system at zonal, regional and federal levels. Since the surveys are conducted and owned by the regional early warning bureaus, it has built the technical capacity of the regional staff. The NSP has helped partners like Concern focus more on implementation of interventions instead of conducting assessments, as the NSP fill that gap. Concern also expressed its satisfaction with the NSP information updates provided by the ENCU on the DRMFSS website. / Concern has been involved in several SMART trainings organized by the ENCU. The SMART training has strengthened the capacities of the government in the regions such that they can now conduct the bi-annual surveys by themselves with minimal support. / Concern staff noted that there is little practical experiences during the SMART training particularly in the actual implementation of emergency surveys. Concern recommend that “ the ENCU should organize practical surveys for the trainees after the workshop to provide the trainees with hands on experience on survey implementation”.

1.4 Outcome: Timely availability of nutrition indicators from existing CBN/TFP/CHD data systems to feed into early warning system. Overall outcome score and description: / The Outcome has two indicators. They both scored A. / Overall score for this outcome is A. / Indicator 1: % of bi-annual survey woredas providing timely nutrition reports: Score: A / Indicator 2: % of priority 1 woredas reporting all agreed monthly nutrition indicators: Score: A / Table 4: Progress against target milestones: / Baseline (2010) Target (November 2013) At completion of project / Plan Achieved / Indicator 1: % of bi-annual survey woredas providing timely nutrition reports Delay by 2-3 months Nutrition survey report available within 4 weeks for 100% of the woredas Achieved / Indicator 2: % of priority 1 woredas reporting all agreed monthly nutrition indicators Poor reporting rate >85% reporting all agreed nutrition indicators Achieved / Performance description / As mentioned in the Output reporting, the bi-annual nutrition survey system has largely been successful. Round 4 in May 2013 saw full implementation in all 25 woredas, with the data being reviewed and approved for release by government within approximately 2 weeks’ time. The reports were drafted in general within 4 weeks, with regional variability in duration. Despite the dlays in production of final documents, the most important factor for consideration is that the nutrition information itself was made available quickly and ahead of release of final reports, and thus fulfilled the purpose of assisting in the piroritisation and timeliness of humanitarian assistance. In previous years before the system, the only survey data available was from NGOs. This was from ad-hoc woredas and often contentious with government, likely due to the lack of communication, transparency from NGOs and lack of government ownership. This has all changed with a system owned and implemented by government. In addition, there is frequent support from NGOs to provide capacity and assistance with implementation, so in general, government attitude and sensitivity towards nutrition surveys and information has greatly improved. / Early warning reports and bulletins produced by government consistently report on TFP SAM monthly admissions, as well as the results of bi-annual nutrition surveys. Data from both systems is greatly relied upon, and is even used in making calculations and predictions for the Humanitarian Requirment Document (HRD). / Although all implementing woredas are reporting, the CHD/EOS data is not utilized to the required level. Compiling the report takes 6-8 weeks which is a constraining factor. CBN data is also being reported consistently from all woredas, but again, takes more time to report. In addition, the low participation rates (around 40-45%), as previously discussed under output 1, prevent it from being a viable source for early warning indicators. It will take some significant programmatic changes to improve upon this. Until this happens, the CBN data cannot be used for early warning but rather as part of data screening on malnutrition from the implementing woredas. / 1.5 Impact and Sustainability / At the impact level the nutrition surveillance project was expected to improve the timeliness, targeting and coverage of humanitarian response. / Based on the milestone table below, it was documented at the beginning of the programme (2010) that humanitarian response was delayed by 4-6 months. This is no longer the case. The combination of strengthened information systems, as well as a functioning coordination mechanism that actively tracks the information and advocates for response has led to a much shorter analysis to response time. / Based on indicators which UNICEF tracks separately, from the 127 “priority one” woredas identified in September 2013, 94.5% were covered with Outpatient Therapeutic Programme (OTP) services, 82% with Theraputic Feeding Programme (TFU) services and 62% with Targeted Supplementary Feeding (TSF) services, all within 4 weeks of release of the priority ranking. From the May/June 2013 priority woreda release with 113 priority 1 woredas, 98% were covered with OTP, 86% with TFP and 91% with TSF. This is the result of a consistent information system which contributes data to the priority classification system, as well as strong coordination mechanism with the ENCU which then advocates for NGO/UN response in the priority 1 woredas. / Over the past two years, this coordinated system has identified and responded at critical times of stress that were negatively impacting on child nutrition status, or that had the potential to. Examples are the Horn of Africa crisis (2011), the Belg failure in SNNP (2012), the drought in Afar (early 2013) and the worsening situation in East Hararghe (mid-2013) where the situation was identified and responded to appropriately with a sufficient amount of supplies and health system capacity support and strengthening by NGOs. / Table 5: Progress against target milestones: / Baseline (2010) Target (November 2013) At completion of project / Plan Achieved / Indicator 1: % of timely response to the crisis in priority 1 woredas Response delayed by 4-6 months Timely warning and appropriate response ensured by the end of two years Achieved / Indicator 2: % response in priority 1 woredas that used the monthly nutrition trends Lack of trend data 100% of priority 1 woredas used the monthly nutrition trends for decision making and response Achieved / 1.6 Sustainability and Challenges: The TFP programme is now integrated into the Child Case Management programme, meaning it will be scaled up nationally. The use of the monthly SAM admission data and analysing the trends is now commonly accepted by government and other stakeholders and highly valued, with the data even being presented by the State Minister in national and international forums. However, the consistent reporting for early warning is mainly due to the presence of the Emergency Nutrition Coordination Unit. With staff at both federal and regional level, including a data analyst, the data reporting is followed up closely every month. This is done in partnership with the RHB, but without the ENCU and the mechanism for reporting through the cluster, it is unclear how this would be facilitated, or if the RHB would continue this function. The TFP data is now included as a part of the Health Management Information System (HMIS), but this is not a system for early warning, as timely and efficient turnaround is improbable. / Therefore, the sustainability of the use of the information for early warning is currently dependent on the existence and full functionality of ENCU. There is speculation that the sustainability of the ENCU may be somehow affected by the adoption of the new Disaster Risk Management (DRM) policy which now implies that early warning and data systems would be managed across sectors and coordinated through the office of the Prime Minister. To date these changes have not yet been fully effected. Both the Federal Ministries of Agriculture and Health would need to discuss and define how data for early warning and response purposes would be collected in the future should the ENCU role be changed. / The components of CBN are now fully integrated into HEP with the revised NNP, so program sustainability is positive. If the FMoH progresses with the development of a comprehensive nutrition information database, as has been discussed over the previous few months, then it is likely they will also support the data collection and quality assurance related to growth monitoring and promotion. This would need to be coupled with the required programmatic improvements in order to increase the participation rates. / Even with the success of the bi-annual nutrition survey system and the demand for the information, it is unlikely to be sustainable without continued donor support due to the overall cost of carrying out nutrition surveys. Also, the ENCU is responsible for coordinating and implementing the system, so even with donor funding, the current system is dependent on the continuation of the ENCU. Recently, the Regional ENCU staff were put on government contracts and incorporated into the government system, which is a positive step. However, they are still entirely supported with donor funding, including DFID via UNICEF. UNICEF (and other partners including DFID) have been and will continue to allocate budget to government, particularly around training of HEWs/supervisors for improved monitoring and on the job supervision, and improve HDAs capacity for community mobilization. / DFID has allocated around £2million under the new nutrition business case to strengthen the nutrition information system in Ethiopia. We believe that with the recent launch of the revised National Nutrition Programme and Ethiopia’s signing up to the SUN, the government’s appetite for more comprehensive nutrition data is growing. Our new programme will provide technical assistance to the MoH to strengthen the collection, analysis and collation of nutrition data across the sectors and will be an opportunity for exploring the possibility again of creating a central depository with the government. As an interim step technical assistance could be hired to develop a database for the TFP, CBN, CHD and survey data that would be managed by the ENCU. This would would attempt to triangulate data from different sources into a national report. At the same time we are strongly advocating that the Health Management Information System be revised to capture all essential nutrition data which could be used for planning, monitoring and early warning.
2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / The development of the e-learning modules for nutrition data analysis was not achieved. This however, did not have an overall negative effect on the project, results or the VFM. In fact, as stated in the recommendations, it is likely that the data collection for the bi-annual nutrition surveys will be simplified to that of SMART nutrition surveys, reducing the time and cost of the system in the future, and eliminating the need for capacity for more advanced analysis skills. / As can be seen from table 6 and 8 below, major budget line items of the project were completed as planned in the project logframe. The actual cost for output 1, output 2 and output 3 is USD 1,105,336.5, 1,616,771.5 and 177,484, respectively which is more or less similar to those predictive costs presented in the DFID logframe as USD 1,006,466, 1,695,434 and 210,000. However there was an additional amount of funds remaining towards the end of the project. This is likely due to two factors, the first being that the original scope of the project included activities centred on the “fast track” concept, which ultimately was not accepted by the government. This led to a change in the project from the original proposal and ultimately a change in the budget utilization. This change in the project was well documented in previous reviews. In addition, the timeline of the bi-annual surveys was altered due to late implementation, also well documented in previous reviews, and led to a no-cost extension grant for one additional year. / The current round of bi-annual nutrition surveys that commenced in December 2013 is still underway with results anticipated shortly. Due to UNICEF mechanisms for transferring funds to government coinciding with the closure of the DFID grant and the need to ensure expenditure, some regions were not able to request the DFID funds for the bi-annual nutrition surveys in the time frame required, and therefore used complementing funds from other sources. In summary, the activities are proceeding as planned, but there were additional funds remaining under this grant. / Based on the request from UNICEF, permission was granted from DFID to use $95,000 to support the National Micronutrient Survey which is underway during 2013/14. This additional use of the funds will not detract from the results of this project or the VFM. In fact, it should be considered as adding to the Value for Money, as the micronutrient status of Ethiopians has not been assessed since 2005, and it fits under the umbrella of nutrition surveillance. The data on the micronutrient survey will be of great value in serving as baseline information ahead of the implementation of the national food fortification programme for Ethiopia. / The 2011 Multilateral Aid Review (MAR) identified that UNICEF has strong financial management systems in place that comply with international best practice. According to a central level assurance assessment recently conducted by United Nations Commonwealth Department (UNCD) in DFID on UNICEF’s fiduciary systems, the overall fiduciary risk of the programme is assessed as low, with UNICEF’s credible programme of financial management in place. / 2.2 Key cost drivers / Table 6 of the VfM section below (section 5.1), show how the overall costs were distributed across the programme. The key cost drivers of this project are costs applied for undertaking the bi-annual nutrition surveys, an activity that takes majority of the funds (53%) of the project. This is mainly driven by costs for employing enumerators and hiring vehicles. Second to this is the cost of specialist human resources (13%), specifically within the Emergency Nutrition Coordination Unit (ENCU) and regional UNICEF staff who are responsible for coordinating the bi-annual surveys, and collecting and processing the routine nutrition information. / Information obtained from UNICEF shows that the basic costs of implementing the surveys have not changed significantly since the start of the bi-annual nutrition surveys in November 2011. The cost of enumerators’ Daily Subsistence Allowances has remained at ETB 165/day in compliance with the agreed rates between UNICEF and Government under the Programme Implementation Manual (except for Afar where it is ETB 200/day). The average cost of renting a vehicle also remained between ETB 2000-2,300/day (including fuel and driver costs). / 2.3 Is the project on-track against original timescale: No / As reported in previous reviews, there was late implementation due to government approval of the mechanism for the bi-annual nutrition survey system being delayed. This did not, however, affect the overall cost of the project. It only delayed implementation by one year, which was addressed by the approval of a one year no-cost extension.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / There are no significant changes in evidence since the start of the project that should alter the implementation of the project. However there were slight modifications introduced as outlined below to accommodate programme level guidances from the government side. / The initial programme proposal included the “fast-track” concept, whereby woreda health officials would phone key indicators (TFP/CBN/CHD) vertically to regional officials as part of early warning. Ultimately, this concept was not accepted by government. Also, as part of this concept, woredas would compile a monthly “score-card”, where woreda health officials track the trends for each of the monthly routine nutrition indicators and analyse this trend along with other contextual factors. This also proved to be difficult to provide supportive supervision and monitor, particularly due to lack of government commitment. After the first year of slow implementation due to lengthy but fruitless negotiation with government to approve the approach, discussions were held with DFID and the concept of “fast-track” was dropped from the project. / In the proposal, it was planned to have surveys implemented by livelihood type. When this was developed and presented to government, they did not approve.They insisted on only having woreda level surveys, so that the results could be interpreted within administrative boundaries. The new methodology was developed based on this and has been successfully implemented across five rounds of surveys.

3.2 Set out what plans are in place for an evaluation.

There are no plans for a separate evaluation of this project. The gains need to be consolidated and strengthened and scaled up. However, some areas like sustainability, timely monitoring and tracking of data especially of CBN/CHD and robust capacity building of government staff are some of the major areas that require further support. The new DFID support to the Accelerating reductions in undernutrition programme will contribute to address these important elements through the different components of the Business Case.

4. Risk
4.1 Risk Rating (overall project risk): Medium / 4.2 Assessment of risk level / The risk rating remained unchanged over the life of the project. / From the proposal and logframe, the following risks were identified. / Government ownership and consensus: This risk was a factor at the beginning of the project and manifested in two ways. / First, in the initial program proposal, there was the “fast-track” concept. As discussed previously, this was not accepted by government and was subsequently dropped from the project. / The second instance, also previously discussed, was the bi-annual nutrition survey system methodology. Significant time was spent developing methodologies that the government finally approved, although different from the original proposal. The new methodology has now been implemented across 5 rounds and has been consistently included in regional Annual Work Plans. The bi-annual survey methodology was developed by a multi-agency team including government. It was reveiwed by both Ministry of Health and Agriculture and finally approved. Since then, it has been implemented every 6 months, and included in the government work plans with UNICEF. The risk was mitigated and government ownership is now strong. For the routine indicators, they are captured under the government programs and systems, and ownership is strong, particularly of CMAM. / System credibility / Since implementation, with four rounds complete, the credibility of the system has improved, with survey findings being reported in government updates, as well as key stakeholder meetings. It is a reliable source of malnutrition prevalence data which formerly did not exist. Section 5.1 below, under the Effectiveness sub-section elaborates how routine data (TFP/CHD) and the bi-annual nutrition survey results, are presented, reported and utilized which highlights how the information is widely used, and strongly indicate the systems credibility. / System sustainability / System sustainability has been addressed in the previous section’s discussion. The bi-annual nutrition survey system, will not be sustainable without external funding. The cost of nutrition surveys is high. So while the information is valuable, external commitment will be necessary for this information system to continue. As CMAM/CHD/CBN programs are now an integral component of the National Nutrition Program (NNP), with continued donors support including from DFID, sustainability is likely. / Political and security risks / Security risks in Somali region delayed implementation during one round of surveys, but in general these have not had a significant impact on implementation or attainment of results. This risk might continue in areas such as the Somali region. / Risk funds not used for purposes intended- Minimal / The UK National Audit Office (NAO) reviewed the project’s financial and accounting procedures and gave a clean and positive audit report. The conclusion of the report released on December 2012 expressed Auditors’ view for the project and its expenditure that they did not observe any instances of funds being applied to purposes outside the objectives and targets of the Department. / A due diligence assessment report carried out in August 2013 also concluded that UNICEF’s financial control and anti-corruption safeguards are robust enough to give sufficient level of assurance for DFID funds being used for the intended purpose. / There have been no significant irregularities identified by DFID programme officers after reviewing regular annual financial statements and external audit reports. / Climate and environmental risk / None – the programme was classified as having no environmental issues in the original appraisal. No new activities that would have environmental impact were introduced.

5. Value for Money
5.1 Performance of value for money measures / Economy - The total programmable amount received by UNICEF is USD 2,904,803. UNICEF reported a balance of USD 5,210.00 unspent remaining at the time this report was prepared. As can be seen from the table below, the biannual nutrition surveys made up the biggest share of UNICEF Nutrition Surveillance Programme costs (53% of the total cost in 2011, 2012 and 2013). The two major cost drivers of implementing the Bi-annual nutrition surveys are the cost of enumerators and the cost of renting vehicles. The other major cost component for the programme was the cost of specialist human resources, specifically within the Emergency Nutrition Coordination Unit (ENCU) and regional UNICEF staff who are responsible for coordinating the bi-annual surveys, and collecting and processing the routine nutrition information. / The 7% UNICEF Head Quarter Recovery Cost is centrally set and therefore beyond the scope of this programme to address. UNICEF Ethiopia also budgets for its management and in-country support costs for every grant it seeks. These management support costs vary from 5-10% depending on the programme/project. The overhead cost for the nutrition surveillance programme was 5%. / If the overall thrust of the project to embed nutrition survey and surveillance systems fully within government structures were achieved, these costs to the project would likely be reduced as government would meet them through routine departmental and local administrative expenditure. This review demonstrates that there is some way to go in terms of political prioritisation, capacity building and coordination for nutrition surveillance within Government structures before Government are likely to internally and effectively dedicate resources to carry out the surveys that are currently produced by this project. / Table 6: Cost in USD by category for the Nutrition Surveillance project (2011-2013) / Output 1: Direct Cost Timely availability and quality of monthly indicators from CBN/CHD/TFP 294,791 10% / Output 2: Direct Cost Timely availability and quality of semi-annual indicators from nutrition surveys 1,548,342 53% / Output 3: Direct Cost Nutrition surveillance in pastoralist areas 177,484 6% / Regional ENCU Cost 382,606 13% / Supply Support 121,418 4% / Technical Assistance (salary support, travel/monitoring) 238,092 8% / Operating Costs 136,859 5% / Table 7: The trend in unit cost (USD) of the key cost drivers of Nutrition Surveillance Programme / Key cost drivers 2010 2011 2012 2013 Average Remark / Staff cost/person/month (contract staff) NA 1500/person/month / (RENCU) Same Same 1500/person/month / Survey cost/district/round (average) NA 16,600* 12,240 12,500 13,780 / Cost/Training: From SMART training in Oromia region NA 4890 5000 6200 5363 / * This average is higher because in November 2011, only the bigger regions implemented whose costs were higher due to more woredas surveyed, greater distances travelled, more enumerators, etc. This drives up the average cost. / Efficiency - As can be seen from the table below, the actual cost per output is more or less comparable to those presented in the project logframe. The DFID logframe has all indicative costs spread across the outputs, including the operating costs. Therefore, these costs are applied to the outputs in the table below. Based on the 2010 UNICEF proposal, all human resource/travel related costs (ENCU, technical assistance) are to be applied to Output 1. These costs are broken down in table 6 above. The Operating Costs are divided evenly across Output 1 and 2. / Table 8: Cost per outputs of the Nutrition Surveillance program / Type of Output Indicative Costs / (taken from revised log-frame) Actual Costs / USD % USD % / Output 1 Timely availability and quality of monthly indicators from CBN/CHD/TFP 1,006,466 35 1,105,336.5 38 / Output 2 Timely availability and quality of semi-annual indicators from nutrition surveys 1,695,434 58 1,616,771.5 56 / Output 3 Nutrition surveillance in pastoralist areas 210,000 7 177,484 6 / Total 2,911,900 100 2,899,592 100 / With regard to output 1, compiled data from all CBN/TFP/CHD woredas and project sites were sent to the federal ENCU about 65,408 times over the last three years. This is on average estimated at $17 per compiled data sent to the center which is a reasonable amount considering the technical and material inputs involved in the process. / A total of 117 surveys were conducted over the last three years making the average cost per survey $13,780. Comparing the cost of implementing this project through UNICEF with other alternatives has proved to be difficult. Nutrition surveys conducted in Ethiopia by NGOs are ad-hoc, and conducted usually in response to an emergency or sharp deterioration, providing a one-off “snapshot” of the situation. In contrast the Bi-annual surveys under this programme are implemented in the same districts over time allowing for an analysis of trends and comparison between similar points in different years. / According to the information acquired from UNICEF, a standalone, NGO-led nutrition survey costs around ETB 270,000-350,000 per district. When compared with the bi-annual survey implemented via UNICEF (circa ETB 270,000) the cost is comparable or more expensive, while the benefits of trend monitoring or annual comparisons are limited or non-existent. / Although the operational research conducted in pastoral areas of Afar, Somali, SNNP and Oromia exceeded targets interms of geographical coverage, the actual total cost ($ 177,484) was lower than the expected cost indicated on the project logframe ($210,000). / Building the capacity of government is a core aim of the nutrition surveillance programme. Prior to the bi-annual nutrition survey system, there was little to no capacity for nutrition surveys within the government structures, with nutrition surveys being implemented by NGOs. In addition, capacity on nutrition information in general was weak. The Nutrition Surveillance program has done a great deal in strengthening institutional capacity. Training on the nutrition survey methodology (SMART) was facilitated in every region implementing the programme prior to each round. Since the bi-annual nutrition surveys system has been built within the government system, the main persons taking part as supervisors and enumerators are government staff. Therefore, it is the government staff that have been consistently capacitated. In addition to the training, key government staff have acted in the roles of supervisors, planners, and other roles, so have also been capacitated on-the-job. / The establishment of the bi-annual nutrition survey system within government systems, and strengthening their capacity to implement has been one of the key contributing factors to ensuring that results have been achieved. Prior to this system, only NGOs were carrying out nutrition surveys, and results were often delayed by months in getting approval from government. Since the government has taken ownership of the system, results are now even approved for release prior to full reports, increasing the efficiency of the information and effectiveness of the advocacy. / Effectiveness - The effectiveness of the project is measured against the milestones set for this period and shows that the targets have largely been achieved. The outcome of this project is timely availability and quality of nutrition reports linked to agro-economic baseline data and early warning data. / There are two outcome level targets set for this review period: The first target is that nutrition reports are available within 2 - 4 weeks of data collection in 90% of targeted districts. The timeliness of TFP data availability was consistently within 3-4 weeks of data collection. This target has been met. The CBN and CHD were reported within 4-6 weeks of data collection throughout the reporting period, which shows that this target has been partially achieved. / The second target is more than 85% of districts reporting on all agreed nutrition indicators. Of the 3 existing nutrition programme data systems that should have provided information to the early warning system, only the TFP did so in full accordance with the targets of reporting while the CBN and CHD programmes marginally missed these targets. The TFP reporting rate was maintained at an average of 87 per cent. / The project undoubtedly contributed to saving many lives where it was acted upon. Quantifying the level of impact of the NSP on lives saved is not possible. In terms of benefits, nutrition data - particularly that provided by the Bi-annual surveys and TFP monitoring under this project - do have a multiplier effect in terms of leveraging wider humanitarian expenditure, which totals £200 - £400 million annually in humanitarian response. Explicitly, the nutrition data has been shown to help ensure that these larger resources are targeted to where they are needed most. There are examples where the nutrition surveillance data alerted government and agencies to a deteriorating nutrition or food security situation and this provoked a response. This was the case in SNNPR during 2010/11 when the results of nutritional surveys combined with TFP data found higher than average levels of Global Acute Malnutrition (GAM) and admittances to therapeutic feeding programmes. The data achieved through this project was instrumental in identifying early the onset of the 2011 drought, indicating which areas were most affected and facilitating improved emergency coordination of partners, supplies and resources to affected areas. The increased assistance based on availability of data likely mitigated what would otherwise have been a far worse humanitarian situation. / The information that has been generated, compiled and analysed under this Nutrition Surveillance project has provided much needed early warning information to all relevant stakeholders and decision-makers allowing for an understanding of the nutritional situation of children during crises as well as periods of stability. There are various mechanisms where the information, the routine data (TFP/CHD) and the bi-annual nutrition survey results, are now presented, reported and utilized. Some examples below indicate the effectivness that the nutrition surveillance project had during 2011 - 2013. / Federal (MANTF) and Regional Cluster Coordination Mechanisms: The Federal level MANTF meeting is held monthly, and during times of crises, more frequently. Every month, the Federal ENCU prepares a summary of available nutrition information and circulates this to all partners by email prior to the meeting, as well as disseminating within the meetings. This includes the TFP SAM admission trend data (national, regional and exceptional woredas), CHD/EOS data, bi-annual nutrition survey results and NGO ad-hoc nutrition survey results. During this meeting, the information is discussed, checked for accuracy and focuses on urgent areas in need of attention. In addition, the TFP and bi-annual nutrition survey data are used to help guide NGO proposals for Humanitarian Requirement Funding, as well coordinate response so duplication is avoided and the most affected areas are responded to. / This coordination meeting is also facilitated in 6 regions, with the support of the Regional ENCU, RHB and Disaster Prevention and Prepardness Bureau (DPPB). Here, the region specific information is presented and discussed with subsequent coordination plans made as required. / Monthly Early Warning Bulletins: This is a mechanism where the nutrition surveillance information is reported and published by government. Again, this is published both at the Federal and Regional levels. / Humanitarian Requirement Document (HRD): Due to the now consistent reporting rate and wide coverage of the TFP SAM admissions data, consistent trends have been established for several years. The trend data provides information on what happens with admissions during hunger seasons, as well as during times of crises and normal periods. Because of this, the TFP trend data is now the critical component in estimating the upcoming year’s estimates within the HRD. This is also necessary for supply pipeline requirement estimation. / Ethiopia Humanitarian Country Team (EHCT) Bulletins: In 2013, UNICEF initiated a joint Food Security and Nutrition Analysis Bulletin, prepared in partnership with FAO and WFP. There have been three bulletins produced to date, SNNPR Update (May 27, 2013), East Hararghe Update (September 18, 2013) and a National Update (October 16, 2013). The NSP data (TFP, bi-annual nutrition survey) has been an important section of the bulletins along with food security and agricultural data to provide a more comprehensive analysis of the situation. / There is some difficulty in reporting on the Impact, as there are many factors involved when it comes to assessing timeliness of humanitarian response that are not in control of UNICEF, DFID or the Nutrition Surveillance project. However, as stated in the report text, UNICEF does track indicators that monitor the presence of nutrition actions in priority woredas within 4 weeks’ time, which gives a good indication. For instance, as of September 2013, out of the 127 priority one woredas, 94.5per cent were covered with OTP, 81.9 per cent with TFU, and 62.2 per cent with TSF. / Research was conducted on how to improve nutrition monitoring in pastoralist areas, with a final report produced and shared with all stakeholders. The report identifies key lessons learned from existing systems and makes recommendations. However, as the FMoH is a key partner, with the routine nutrition information generated from their own systems, they need to be an integral in the decision making. Since the new nutrition unit was established in the FMoH several months ago, and post report production, there has been a challenge with identifying a key person for reviewing the report and participating in the Steering Committee. DRMFSS has drafted a letter requesting their support and this is currently in process.Therefore at this time, the relevance/benefit of the research on informing programme/policy is unclear. / Cost-effectiveness - It is not possible to assess the cost effectiveness of the NSP as ‘effectiveness’ cannot be measured in this case. The impact of the NSP cannot be assessed and therefore, cannot be calculated in financial terms. It is an information system that informs at administrative , woreda/zonal/regional and federal levels. / We know that the NSP was successful in prompting a response. As the main use of NSP data was to advocate for humanitarian support, the cost of the NSP could be compared to the cost of donors investment in humanitarian assistance which is £200 - £400 million annually. The cost of the NSP was absolutely minimal when compared with the value of humanitarian support given by donors including DFID. / Please note that the Project Memorandum was drafted in 2010 prior to the current Business Case format that specifies VfM measures explicitly. However, the project considered VfM issues throughout its implementation. / 5.2 Commercial improvement and value for money / Once payments are received, the UNICEF country office channeled most of the resources to the GoE working in the programme areas through a direct cash transfer modality. Over the last year responsibility for implementation of the Bi-annual Surveys under this project has been gradually shifting to the Government of Ethiopia, although significant initiative, technical and financial support is still required from UNICEF to ensure that surveys happen on time and to sufficient quality. Implementing the project through Government systems has meant low (and in many cases lower) comparative costs of undertaking the activities than compared to the most prevalent alternative model of individual NGO-led surveys (see VFM section above). In other words, although there has not been a commercial improvement during this reporting period, the costs of conducting bi-annual surveys have not increased compared with previous years. / UNICEF uses national systems for auditing whilst the agreed programme implementation procedures between the UN system in Ethiopia and Ministry of Finance and Economic Development (MoFED) will guide procurement, accounting, and reporting procedures. In addition, the UNICEF internal control systems which are globally fixed for all procurement purposes are fully utilized to ensure that funds are used for the intended purpose. / UNICEF Ethiopia mainly uses competitive bidding processes in direct procurement of fixed term programme staff and short term technical assistance. The bids are assessed based on the selection criteria in terms of the quality of the product as well as delivery time and value for money. UNICEF also adheres to the UN rules as well as the relevant rules relating to procurement outlined in the Programme Implementation Manual (PIM) for UN-Assisted Programmes in Ethiopia, to ensure the bidding process is transparent, fair and accountable. / 5.3 Role of project partners / DFID provided support under this project for the Emergency Nutrition Coordination Unit (ENCU), both for Federal and Regional staff. ENCU members are responsible for collecting TFP data from RHBs, assuring data quality and reporting the findings. They are also responsible for coordinating bi-annual surveys, carrying out analysis and reporting, and coordinating emergency nutrition response. DFID plays a key role in lobbying for greater access for UN and NGOs for nutritional surveys. / Government at all levels and NGOs are integral to the success of this project. On partnerships, while the government has shown ownership of the project, it is still clearly understood that the bi-annual nutrition survey component is the result of the partnership UNICEF/DFID have with the government. This is a strong partnership and has been fostered particularly over the past few years with support from DFID funding in strengthening the early warning system, especially in the regions. As indicated in the value for Money/effectivness section above there are various mechanisms and forums where the information, the routine data (TFP/CHD) and the bi-annual nutrition survey results, are presented, reported and utilized. / 5.4 Did the project represent Value for Money - Yes / This judgement is based on four premises: / The cost of the NSP was absolutely minimal when compared with the value of humanitarian investment by donors including DFID without counting the potential cost savings in terms of averted illness and deaths. / The unit cost of the key cost drivers hasn’t changed during the reporting period. / The costs of conducting nutrition surveys through Government systems are equal to or less expensive than the alternative mechanism of NGO-led studies, while also incurring benefits of monitoring trends and comparing nutrition status over time. / The outcome level targets for this project have largely been achieved.

6. Conditionality
There is no conditionality attached to this project.
7. Conclusions
Before the initiation of the NSP there was a gap between ad-hoc and routine surveillance of the nutrition situation with limited coverage of coordinated nutrition surveys. Official approval of ad-hoc Non-Governmental Organization (NGO) surveys and endorsement of findings have been difficult in some regions, causing delays in emergency response. Furthermore, this lack of a focused NSP previously hindered trend analysis and contributed to the lack of credible and reliable information which could inform management decisions. / DFID provided £2,000,000 to UNICEF from October 2010 to November 2012 to support nutrition surveillance in Ethiopia to improve the timely availability and quality of nutritional data. Originally intended to be completed within 2 years, the programme was extended for a 3rd year (until November 2013) – within the original budget - due to lengthy delays in start-up. The key intervention areas of the project were: 1) building on the existing data sources generated from routine nutrition programmes, namely Therapeutic Feeding Programme (TFP), Child Health Days (CHD) and Community based Nutrition (CBN), to make them useful for timely warning, trends analysis and provision of inputs for programme planning; 2) developing a system of bi-annual nutrition surveys that complements the routine nutrition information with trend data on nutrition prevalence in chronically vulnerable areas; and 3) improving the knowledge of nutrition in pastoralist communities through operational research, particularly for information systems. / The major achievements of the NSP included: / Bi-annual nutrition surveys in selected 25 districts are recognized as a system within the government, and there is demand for the information not only from international/ national humanitarian partner stakeholders, but from the government as well. / Government capacity was built on nutritional status data collection as bi-annual training was provided at various levels. / Data obtained through the Therapeutic Feeding Programme (TFP), has consistently reached national reporting rate or higher from 2011 to 2013. / Community Based Nutrition program routine growth monitoring data is consistently reported within 4-8 weeks from all program woredas (currently there are 328 woredas implementing CBN out of 600 woredas throughout the country), / A nutrition database was designed and shared with the FMOH. / A study for “Improving Nutrition Monitoring in Pastoralist Areas of Afar , Somali, SNNPR and Oromia regions” was completed and a final report was submitted to the government / The improved availability of nutrition data provided through this project played a key role in informing the humanitarian response during the critical period from late 2011 through 2013 in Ethiopia. / The integration of TFP SAM admission data into the early warning analysis is systematized. It has become the principal indicator for tracking nutrition trends. This is in part to the wide coverage (600 woredas and expanding) and consistent reporting within 4 weeks. Currently, the information is channelled vertically through the health system to the regional level, where the RENCU compiles it in a database and reports through the early warning system. Both the regional ENCU and the early warning system are within the DPPB/Ministry of Agriculture system. The future of this structure is unclear in the new DRM policy framework as is thed future of the new nutrition unit within the FMOH. For now, UNICEF is committed to supporting the ENCU. / CBN and CHD/EOS data have been problematic for inclusion into early warning. CBN has low coverage though it is expected to expand nationally, and also has poor participation rate. With a poor participation rate, woreda level estimates of underweight cannot be made. A centralized nutrition information database within the FMOH and decentralized to woredas would help facilitate the information, but first, programmatically, the participation needs to increase to at least 80%. The CHD/EOS data is late in reporting, typically taking 6-8 weeks. Numerous attempts have been made to improve upon this with no success. Additionally, the quality of the screening data is questionable, with frequent inclusion error, due to linking the screening in priority 1 woredas to the TSF programme and food. If the CHD woredas shift to routine services, then reporting will again be different, as it would then be monthly and requiring a different system. The challenges faced in using the CBN and CHD/EOS data for early warning reflected that the project initially put ambitious targets in terms of timing for systemic change within government systems. Under the new DFID supported program, efforts need to continue to increase the participation rate and timely reporting of the CBN/CHD data along with using the data for monitoring and early warning purposes. / For now, support to the scale up of TFP to all woredas should be provided and capacitate government on the monitoring aspects should be built, particularly at woreda/zone and regional levels. At the Federal level, the FMOH should be supported to implement the comprehensive database and advocate for decentralization to woreda level. / The bi-annual nutrition survey system will continue through 2014-2015 with support from DFID under the Accelerating Reduction in Undernutrition programme. Complementary funding can be used by UNICEF to support implementation. In order to reduce costs, both financially and for field implementation time, it is recommended that the system use standard SMART survey methodology. This would allow for quicker report generation with standardized reporting formats. It is also recommended to consider reducing the number of woredas surveyed in SNNP and Oromia to 4, instead of the current system which is 6, to reduce the cost and time. Support beyond these additional two years will need to be assessed, particularly based on progress with a new comprehensive database in the FMOH, status of the ENCU and also status of the FMOH taking ownership of nutrition information and establishing a database. / The ENCU has been instrumental to the implementation of the bi-annual nutrition survey system, as well as ensuring that nutrition is systematized within the early warning system. Support for ENCU needs to continue. Regional ENCU positions have recently been placed on government contracts, but funding will continue to be externally supported. The new DFID grant will support 6 Regional ENCU positions for 2 years. The other 5 (2 currently vacant) positions will be funded with other grants or UNICEF resources. Where there still remains a gap is the Federal ENCU positions. This is normally met with emergency funding, however, emergency funding in 2014 is much less than previous years. / Lessons were learned on results not achieved, particularly on the e-learning nutrition analysis materials, although this was a small part of the overall project. For projects like this, the size and scope of the project needs to be better understood from the beginning. This should then inform whether the project should be assigned to an individual consultant, or sent out as request for proposal for bidding by companies and institutions. For this particular project, it should likely have been a company that was recruited. This way, the outputs would not have been dependent on one person. Additionally, there are very different skill sets required to developing the material, and to produce the e-learning materials. This is where a company would have been better suited to facilitate. / For the nutrition information database, progress is just beginning. However, the fact that there is now a dedicated nutrition unit within FMoH, and that they have initiated the discussion on establishing the database is a great leap forward. Ownership of data and information is the best solution for sustainability. UNICEF will move ahead with refining the database and will continue to work with the FMoH on capacity building and advocacy for a system that will be decentralized and potentially online, allowing all stakeholders access to information in a real-time format.

8. Review Process
The Project Completion Review was undertaken by the DFID Ethiopia Livelihoods and Humanitarian Team. The review process was carried out in a participatory manner. DFID’s Nutrition and Humanitarian Advisers, Deputy Program Manager and Program Officer consulted relevant staff from UNICEF in the compilation of progress report, comments and suggestions. Review meetings and frequent e-mail communications were also part of the review process that helped to collect and clarify information explained in this report. Reference was also made to the programme documents, technical reports of the programme and annual review for 2012.