Type of Review: Project Completion Review

Project Title: Enhancing Nigerian Advocacy for a Better Business Environment [ENABLE]

Date started: 1 October 2008	Date review undertaken: February 2014

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The UK provided £12m from October 2008 to March 2014 to improve the business environment for small and microenterprises in Nigeria. / The original 2006 programme memorandum envisaged that support of £7.5m would be provided through a challenge fund mechanism over a period of three years. The programme was changed to a Making Markets Work for the Poor (M4P) approach during the inception phase when it became evident that stakeholders responsible for triggering business environment reform in Nigeria were too weak to either submit applications for a challenge fund or implement projects on their own. / The programme worked with business membership organisations (BMOs), media houses, research institutions and government agencies - to build their capacity to advocate for changes within the business environment. This could lead to stronger organisations able to continue implementing changes beyond the duration of the programme. As it became evident that this would take longer and require more sustained engagement, the programme’s budget was increased to £12m and extended to 5.5 years.

What were the expected results?
The impact that ENABLE sought to achieve was to “improve the policy and regulatory environment for doing business” in Nigeria. Four indicators were used to measure this impact: (i) improvement in Nigeria’s World Bank Doing Business ranking, (ii) improvement in the index of business leaders’ perception of doing business, (iii) the cumulative number of policy, regulatory and legislative improvements to the business environment made, and (iv) the cumulative number of entrepreneurs and workers benefiting from these improvements. / The purpose of the programme was “to raise the level and quality of private sector advocacy and the effectiveness of public private dialogue in Kaduna, Kano, Lagos and at the federal level”. This was measured through the number of additional dialogues held each year. A distinction was made between media and non-media dialogues. A second indicator measured the percentage of business leaders that reported satisfaction with public private dialogue on business issues.

What was the context in which UK support was provided?
To achieve the MDGs in Nigeria, the country will require broad-based and sustained growth in the non-oil sector which provides livelihoods for the vast majority of Nigerians. Strong oil revenues have fuelled the growth of a largely unproductive, dysfunctional and unaccountable public sector that has failed to create the conditions for markets to operate efficiently and benefit the poor. The business environment for micro and small enterprises is particularly weak with these businesses being subject, amongst others, to nuisance taxes, much red tape and high costs of business registration, poor infrastructure and supply of electricity, no access to finance and long-term capital, etc. / Global experience shows that the most effective way for governments to improve the business environment is through strong dialogue with the private sector. BMOs and the media, supported by good evidence, can be influential agents of change to assist government to prioritise, sequence and implement reforms. They can also keep government accountable to see reforms through. However, there are many obstacles to effective public private dialogue (PPD) in Nigeria, especially relating to issues affecting small businesses. BMOs are weak or non-existent and they have no skills or experience in public private dialogue. The media provides limited coverage of business environment issues, and often do so only if they are paid. The research institutions are neither geared nor equipped to undertake research that can back up demands for business environment reform or show the best options for such reform. / There are also challenges to PPD on the government side. Most government agencies had never engaged in dialogue with the private sector and did not see the need for such interaction. Moreover, many of the issues affecting small and microbusinesses were dealt with at state rather than federal level, so multiple agencies spread out across the country were involved.

## Section A: Detailed Output Scoring

Output 1: Business Membership Organizations demonstrate competence to engage in effective advocacy
Output 1: final score and performance description: A
Final results: / This was ENABLE’s anchor output, covering its support to BMOs to improve their competence to engage in business advocacy and public private dialogue. ENABLE worked with a wide spectrum of organisations and its support varied from basic institution-building to assisting them to improve their relationship with their members. Three indicators were used to track performance: / Indicator 1 measured improvement in a composite advocacy competence index for the business organizations supported by ENABLE. The diagnostic assessment tool measured various dimensions of advocacy competence and was developed for ENABLE and administered by its staff. The target was an average improvement of 20%. The recorded improvement was 24%. / Indicator 2 measured the number of BMOs who achieved a sustained improvement in their advocacy competence score. The target was 20, but only 13 were achieved and final evaluations could only be done on 11, although 19 organisations implemented some form of practice change. / Sustained improvements in business advocacy are difficult to achieve in Nigerian business organisations for a number of reasons. Advocacy is seen by many small businesses as a public good. Even where value is recognised, the willingness to pay might still be lacking. BMOs with mostly smaller or micro members thus struggle to establish a sustainable revenue base, also because members tend to be informal and scattered. The other problem is that business environment reforms are not always consistently implemented administratively. Small businesses may therefore not experience the benefits immediately or even within 2 - 3 years. The best results were achieved with BMOs that had larger commercial members as well as small enterprise members, such as the Lagos Chamber of Commerce and Industry. Unfortunately, there are not too many of these in the states in which the programme worked. / Indicator 3 measured the percentage of programme-supported BMOs reporting satisfaction with the advocacy performance of their organisation. This was measured through a programme members’ survey. No target was set. The actual result was 49%. / Impact Weighting (%): 28% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Media proactively investigates and airs public policy and regulatory issues affecting private sector
Output 2: final score and performance description: A+
Final results: / The media component of ENABLE focused on supporting dialogue and initiating the public reform process by providing research-based, investigative and analytic reporting on business issues. This component is arguably the most successful of ENABLE’s four outputs, with clear incentives for partners to continue reporting on the business environment for small enterprises. Four strong media partnerships emerged from this component. Performance was tracked against three indicators: / Indicator 1 measured the “media quality” of project-supported business media products using a composite media quality index calculated from the ENABLE Media Quality Scorecard. The target for this indicator was 20% and the actual recorded improvement was 29%. / Indicator 2 measured the total number of business media products (either directly assisted by ENABLE or known cases of replication) that achieved a sustained improvement in its media quality score. Media products are scored on a scale of 1 to 5, using the ENABLE Media Quality Scorecard, according to three quality criteria: content & analysis, accessibility, and interactivity. The definition for sustained improvement is an increase in the score compared to a previous measurement. The target was 20 business media products showing a sustained improvement. The actual recorded number of business media products that showed a sustained improvement was 10, although 20 media houses introduced new business media products over the lifetime of ENABLE. / Even though the commercial incentives to partner with ENABLE were strong in the case of media houses, capacity to engage in advocacy for all partners was low to begin with, and organisational buy-in and transformation therefore required additional time. Moreover, it took time to discover which media partners were the most likely to implement change. In general, commercially owned media proved more likely to implement business advocacy than government owned media institutions. ENABLE also made a decision to only focus on the four strong partners due to the quality of these partnerships, but also because of the potential for scale in terms of audience and sustainability. The four main media partners ENABLE partnered with had some of the biggest audience and listenership figures in Nigeria. Indicator 2 for the media component could therefore have been too high, but would also have been more appropriate if it took the scale of impact of media products into account. / Indicator 3 measured the audience satisfaction rating of project-assisted business media products. The rating was measured through an independent media audience satisfaction survey which included a focus group discussion with representative audience members. The target was 60% and the actual recorded rating was 68%. / Impact Weighting (%): 24% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Ministries, Departments & Agencies (MDAs) demonstrate willingness and capacity to engage with private sector
Output 3: final score and performance description: A
Final results: / The objective of the MDA output was to strengthen the willingness and capacity of the public sector to engage in effective dialogue with the private sector. ENABLE’s approach was to demonstrate the concrete value of public private dialogue to MDAs and to build skills and understanding necessary to conduct productive dialogue sessions without ENABLE’s support. They provided internal capacity training combined with sensitising workshops on public private dialogues, before facilitating initial dialogues and bringing government and BMOs together. The performance of this output was measured against three indicators: / Indicator 1 measured the improvement in the composite ‘dialogue capacity’ index for project-supported MDAs. The index was calculated using a MDA Diagnostic Toolkit developed and administered by ENABLE. The target for improvement as measured by the index was 20% and the actual improvement was 30%. / Indicator 2 measured the total number of MDAs (either directly assisted or known cases of replication) that have achieved a sustained improvement in dialogue capacity as measured by the ENABLE MDA Diagnostic Toolkit and using a dialogue capacity score on a scale of 0 to 10. The target was 10 MDAs showing a sustained improvement and the actual achieved result was 7 MDAs showing a sustained improvement, although 8 MDAs implemented practice changes after partnering with ENABLE. / The MDA component emerged later in the programme and although it was successful at the state level, significant challenges facing this component remained. The biggest of these were transitions in leadership due to outcome of elections/politics, which may significantly undermine progress of reforms and implementation. Another was the relationship between state and local authorities. There was also a limited number of MDAs to work with as not all government agencies are required to deal with the private sector directly. / Indicator 3 measured the percentage of BMOs reporting an improvement in the dialogue capacity and openness of MDAs over a 12 month period. The indicator used a survey conducted by ENABLE on business organisations who attended different MDA consultation events and public private dialogues. No target was set for this indicator and the actual achieved result was 66% of business organisations reporting an improvement. / Impact Weighting (%): 28% / Revised since last Annual Review? N. / Risk: Medium / Revised since last Annual Review? N

Output 4: Effective and affordable support services (especially research provision) are available to business membership organisations and MDAs on a sustainable basis
Output 4: final score and performance description: A / Final results: / Output 4 aimed to stimulate the availability of effective and affordable support services (especially research provision in the form of relevant and useable information on the business environment) to BMOS and MDAs on a sustainable basis. Notably, interaction between media and research was not included in the logframe. This output was measured against three indicators: / Indicator 1 measured the number of BMOs and MDAs obtaining business research from project-supported research institutions or known cases of replication, using project surveys conducted by ENABLE. The review team interpreted this indicator as being cumulative. The target for this indicator therefore was 20, but only 12 BMOs and MDAs reported obtaining business research from project supported research houses or know replications. If the media was included in this indicator, the result would be 15.
The number of BMOs or MDAs using business research depended on the ability of the BMOs and MDAs to pay for research. The biggest obstacle was that business organisations had limited ability to pay for research (outside Lagos state it may be close to zero) and their internal structure made it difficult to engage with research houses as they are still not organised and structured. The review team concludes that the business organisation component remains the weak link in ENABLEs business environment reform system because their incentives to participate only accrue after policy changes have been implemented, which takes time. For this reason the actual 12 business organisations and MDAs obtaining business research was a significant achievement. / Indicator 2 measured the percentage of BMOs reporting satisfaction with the availability and quality of business research in Nigeria as calculated using the ENABLE Business leaders’ perception survey. No target was set for this indicator, and 26% of business organisations reported satisfaction. / Indicator 3 measured the number of BMOs and MDAs obtaining support services from project-supported providers or known cases of replication, using project surveys conducted by ENABLE. The target for this indicator was 20 and the actual achieved result was 24. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Achievement and Results
1.1 Has the logframe been changed since the last review? No / 1.2 Final Output score and description: A (Outcome met expectations)
Direct feedback from beneficiaries / The review team met with 20 ENABLE partner organisations in Lagos, Kano, Kaduna and Abuja. These included 8 BMOs, 4 media houses, 3 research institutions and 5 government agencies. The team did not meet with representatives from any failed partnerships. / The feedback from partners indicated strong brand recognition for ENABLE, as well as numerous personal relationships between partner organisation staff and ENABLE staff; which is essential to the success of a M4P programme that relies on facilitation and personal interaction to trigger change. Partners universally acknowledged ENABLE’s contribution as well as its expertise and professionalism. There was strong appreciation for ENABLE’s ability to bring in good and sometimes world class consultants, their ability to connect partners with the right people, and to open doors and new markets for them. In most cases, the organisations had never engaged in public private dialogue before and they had to be trained up in an entirely new set of activities and skills. / Although some partners requested direct monetary assistance from the programme, the review team was convinced that ENABLE’s approach of not providing any direct monetary assistance to partners was a strong reason for its success. The policy of not giving money quickly separated organisations who simply wanted to tap into donor money from those who were serious about change. / Several interviews with successful partners revealed that the relentless engagement with partners and continually applied pressure were responsible for getting partners to stay the course and continue with suggested changes, even if they did not initially realise the value. Athough a number of partners have not yet experienced the impact of their advocacy, they expect impact and intend to stay the course.
1.4 Overall Outcome score and description: A+ / The outcome targeted by ENABLE was to raise the level and quality of private sector advocacy and the effectiveness of public private dialogue in Kaduna, Kano, Lagos and at the federal level. The primary outcome indicator was the number of additional dialogues held per year, which ENABLE met easily across the life of the programme with 82 dialogues versus a target of 30. A secondary indicator measured the percentage of business leaders reporting satisfaction with public private dialogue on business issues. Although no target was set for this indicator, the achievement was 36%. / The fact that a dialogue took place gives limited indication of whether the process of dialogue between the partners involved will continue. This is particularly so since most of the early dialogues were extensively supported by ENABLE. A better indicator therefore would be the number of active or functional institutionalised dialogue platforms catalysed by the programme. At the outset of the programme only one such platform existed in Nigeria. As a result of the interventions of the programme a total of 14 platforms now exist, at least half of which address multiple issues and involve multiple organisations. / The programme did succeed to make some advances in gender inclusiveness of business advocacy by working with three women-led business organisations in Kano, Kaduna and Kwara, all located in Northern Nigeria where women entrepreneurs have a lower level of participation in business organisations. As a result two public private dialogue platforms, both called “Gender and Business” were established. Both pursue key business issues facing women entrepreneurs in their states. / 1.5 Impact and Sustainability / The impact ENABLE sought was to improve the policy and regulatory environment for doing business. It used four indicators to track progress: The first indicator was Nigeria’s ranking in the World Bank Doing Business index. In 2009 the ranking was 125 and the target was 119, but by 2013, the ranking was 138. Nigeria’s ranking thus deteriorated during the course of the programme. This indicator was retained despite annual review recommendations that it should be dropped on the grounds that the indicator has little relevance for micro and small businesses and the programme can have very little impact on Nigeria’s overall performance. / The second indicator measured business leaders’ perception of the difficulty of doing business through the annual Business Leaders Perception Survey where 5 indicates a poor perception and 1 a good perception. In the most recent 2013 survey, the index stood at 1.73 against a programme target of 2.0. / The third indicator measured the number of policy, regulatory or legislative improvements in the business environment. The target was 8 and a total of 13 changes were achieved as a result of the interventions of the programme. However, at the time of the review, only 5 of the changes have both been implemented and translated into broad impact on the poor, whilst some others are in progress. / The fourth indicator tracked the number of entrepreneurs and workers benefiting from the improvements mentioned in the previous paragraph. ENABLE significantly exceeded the target of 1m - 1,819,768 beneficiaries, of which 542 558 (29.8%) are female. / The impact recorded above is likely to be sustained, since they result from only three policy changes which have already been implemented and impact assessment conducted. These policy changes are unlikely to be reversed. As the implementation of these policy or regulatory changes is strengthened and other changes are implemented, the impact is likely to grow. / As an M4P programme, ENABLE targeted not only specific business environment changes, but an overall change in the system of business advocacy that would continue to yield business environment improvements beyond the lifespan of the programme. Although ENABLE made substantial progress in establishing a culture and practice of business advocacy in Nigeria, it would be premature to say that the culture is sustainable. The practice of government accountability to business, especially micro and small businesses still has some way to go. / ENABLE tended to be more successful where: / It engaged with state-level government agencies rather than with federal agencies. At state level the political link between the small businesses and the political leaders making the decision on the business environment reform seems closer and the effectiveness of public private dialogue therefore increases. / It worked with business organisations that had both large commercial members as well as small enterprise members. The large commercial members were more prepared to pay for business advocacy than smaller enterprises, making it more sustainable. / It worked with organisations that did not demand money, but were prepared to work with ENABLE and its service providers to improve their organisational capacity and advocacy competence. / It worked with all the parties involved in business advocacy - business organisations, media houses, research institutions and the government. / It tackled revenue-based issues relating to fees and impositions, for example nuisance taxes, imposed by state-level governments on enterprises, rather than where governments had to spend money. A number of successful interventions related to multiple taxation, lead to a dramatic increase in internally generated revenue in Lagos state.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / 2.2 Key cost drivers / ENABLE was originally conceived as a challenge fund, with a management fee of 10% and the balance issued in grants to partners. With the change to an M4P programme, the cost structure changed. At the heart of the M4P approach is facilitation, skills transfer and communication. These services trigger direct support to partners; all of these have to be done by people with the requisite skills. / The cost at which ENABLE could secure the services of persons with the necessary technical skills was therefore its primary cost driver. These costs were in turn driven by what proportion of the skills could be secured from within Nigeria and internationally. / The final composition of costs divided between direct spend on partners, including consultant costs, the cost of ENABLE’s technical staff, and overheads are reflected in the table below. These in turn are divided between the four output areas. Overheads constituted 35.5% of ENABLE’s total expenditure. / Component Direct costs on partners Direct staff/Springfield costs allocated to partners [Overheads] Total spent since inception Total programme spend / BMO £1 597 725 £814 346 £1 213 027 £3 625 098 / Media £1 293 517 £804 217 £1 213 027 £3 310 761 / Government £979 371 £429 143 £858 034 £2 266 547 / Research £568 204 £284 908 £715 028 £1 568 139 / Inception spend £505 363 / Total £4 438 816 £2 332 613 £3 999 117 £10 770 546 £11 275 909 / 2.3 Was the project completed within the expected timescale: No / The programme was extended to 5.5 years from an initial 3 years as a consequence of its restructuring from a challenge fund to an M4P approach requiring more time and dedication to deliver results.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / The original programme memorandum did not contain a specific theory of change. This was revised in the inception phase, when the programme was recast to adopt a market-based view of advocacy following the M4P approach. This approach postulated a transactional relationship between the private sector and government in relation to public policy. It characterised the business advocacy environment as a demand and supply function. The demand side is made up of BMOs, media and other groups who advocate for policy change. The supply side is the Government of Nigeria who is responsible for business environment improvements. The original concept was that most of the support had to be given to organisations on the demand-side, with limited support for the supply-side or government agencies. / During the course of the programme it became clear that government agencies needed as much support to effectively participate in public-private dialogue and a separate output was included to provide such support. / ENABLE proved that the M4P approach can be applied to trigger systemic change in the “market” for business environment reforms. The conditions for such success seem to be (i) that there is no way round building the basic capacity of institutions to engage in business advocacy if they do not have the capacity and skills; (ii) the incentives of business organisations, media houses, research institutions and government agencies to participate in business environment reform differ and must be very well understood and managed; and (iii) that sustainability is limited by the ability of participating parties to convert their public private dialogue activities into cash, particularly where their conduct of those activities are dependent on cash being generated. For example, a government agency, for whose staff the salaries are already paid from the government budget, can continue with advocacy whether they receive income from advocacy or not, but a research institution cannot continue with business environment orientated research if they are not funded or are not able to generate income out of it. / 3.2 Set out what plans are in place for an evaluation. / No impact evaluation for the entire programme was done. However, two impact assessments were conducted for two business environment changes contributed to by the programme (Cashless Nigeria and Multiple Taxation) and a monitoring report exists for a third business environment change (Growth Enhancement Support Scheme). While all three of these policy changes were considered to be strong, being both implemented and having broad based impact, only one impact assessment was considered to be strong. The monitoring report was not intended to provide a full impact assessment. The findings are included in the value for money assessment below, and indicated that 1.8 million enterprises experienced income increases as a result of the specific interventions.

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? No / 4.2 Risk funds not used for purposes intended / A financial audit was done in 2010 which did not raise any concerns that the funds were not used for their intended purpose. / 4.3 Climate and Environment Impact / The original programme memorandum did not anticipate any direct impact on the environment. Neither was any impact identified during annual reviews or during the PCR.

5. Value for Money
5.1 Performance on VfM measures / The programme memorandum was developed before VfM indicators were introduced. The programme therefore developed VfM indicators during its duration. / The nature of VfM in the context of a M4P programme differs to some extent from other programs. The M4P approach requires a longer lead time from intervention to impact, as it focuses on implementing system changes which in turn deliver impact, rather than delivering impact directly. In addition, whereas a direct intervention approach delivers impact only for those outputs and outcomes directly worked on by the programme, the M4P approach is designed to keep generating targeted outputs and outcomes beyond the direct intervention of the programme. VfM in the impact area for M4P programmes should thus always be an understatement if the programme is truly successful in generating sustainable system change. / VFM Indicator Performance / Economy Percentage of total consultant days performed by local consultants 71.20% / Average fee rate £340 / Overheads as percentage of total expenditure 35.50% / Efficiency Conversion rate (Partners demonstrating sustainable practice change as percentage of total partnerships) 40.30% / Average total direct spend per partner demonstrating sustainable practice change £218,433 / Partner investment for every £1 of direct expenditure by ENABLE 0.46 pence / Partner time contribution for every 1 day spent by ENABLE 1.47 days / Effectiveness and cost effectiveness Outreach 1,819768 / Percentage of outreach that is female 29.80% / Net income increase £107,286,379 / Percentage of income increase that is female 38.70% / Cost per beneficiary £6.20 / Net income increase per Pound spend by ENABLE £9.51 / The total outreach for the three interventions mentioned in section 3.2 above, is estimated at 1,819,768 while the income impact is £107,286,379. This translates into a cost per beneficiary of £6.20 and an income to cost ratio of £9.51, which represents good value for money. The proportion of outreach that is female is 29.8% while the female proportion of the income impact is 38.7%. / The review team adjusted VfM calculations to make reasonable allowance for the quality of impact assessments as well as questions of attribution. / 5.2 Commercial Improvement and Value for Money / ENABLE followed standard DFID procurement protocols with a specific focus on VfM and accessibility to indigenous Nigerian firms and individuals. Its procurement processes and procedures for consultants were reviewed by the 2010 independent Financial Audit and found to be in accordance with the procedures as laid down in its governance framework. A second financial audit has been conducted and a final report is due. The programme secured some cost savings due to collaboration with other DFID programmes, for example sharing a Security Advisor with NIAF and GEMS3. / ENABLE was able to reduce costs by sourcing a large proportion of consultants locally. Its ratio of local days used as a proportion of total days spent over the course of the programme (1 April 2009 to November 30 2013) is 71.2% and its average daily fee rate over the course of the programme is £340. Furthermore, it managed to decrease the average fee rate consistently over the course of the programme, bringing it down from £367 in 2009 to about £310 by 2013. / 5.3 Role of project partners / In total ENABLE engaged with 77 partners over the duration of the programme. Of these, 45 demonstrated practice change, of which 32 are considered to demonstrate sustainable practice change. This represents a conversion rate of 40.3%. The average total direct spend per partner demonstrating sustainable practice change (including direct component staff costs) is £218,322. Partners invested 0.46 pence for every £1 of direct expenditure by ENABLE, including ENABLE’s direct staff cost on partners. Partners contributed 1.47 days for every 1 day spent by ENABLE staff. / ENABLE has evolved its partner selection and exit approaches over the course of the programme, which allowed their partner relations to become more focused. / 5.4 Did the project represent Value for Money : Yes / Overall the programme did deliver good value for money. In terms of economy it has an average daily fee rate well below comparable DFID programmes in Nigeria, and managed to decrease this rate continuously over the course of the programme. Although there is no benchmark available for its conversion rate, the review team deems this as well as its average cost per partner that demonstrated a sustainable practice change as good, especially given the “pilot” nature of the programme. ENABLE was also able to effectively leverage partner resources - although time more so than money. ENABLE’s effectiveness and cost effectiveness seem to offer good value for money and the figures included here are expected to be an underestimation given that only 3 of the 13 regulatory interventions were evaluated and that other business environment changes will be triggered in due course.

6. Conditionality
6.1 Update on specific conditions / No conditions applied.

7. Conclusions
The performance of ENABLE vindicated the conversion of the original challenge fund into a market-based M4P approach. It was the first programme in the DFID portfolio to apply the M4P approach to trigger business environment reforms, and in the very difficult Nigerian environment where public accountability has always been limited is deemed to be successful. / Partners: The programme proved that it is necessary to work with all four categories of institutions that play a role in business environment reform - business organisations, the media, research institutions that generate research on the business environment, and the various public agencies responsible for delivering business environment reform. However, the M4P approach cannot simply be applied as it would in a commercial market environment. These categories of institutions have very different incentives for participating in business advocacy and their benefits accrue at different times. In evaluating the effectiveness of the media output, the quality of partners showing improvement should be considered as well as their potential for engaging in policy changes that would result in widespread impact. / For example, micro and small businesses benefit from business environment reforms only when those are implemented. This can be delayed for years if the public administration is weak or corrupt. Media houses, on the other hand, can see their ratings improve from the moment they start to report on public discontent with business environment conditions. A programme of this nature therefore needs to track the different timelines and incentives to make sure that reform that brings actual benefits to the poor is ultimately delivered. / Management: ENABLE was successful in assembling a team of staff members committed to what they were doing. This was essential for their success, due to the key role of facilitation to bring about systemic change. Staff turnover was low and the majority of staff were Nigerian. In any future phase of ENABLE the contractor should give particular attention to the quality and commitment of its staff. / Logframe: For most of the programme’s duration the logframe was particularly weak. The final logframe was only relevant for the last two years and even then it had four indicators without targets and some indicators that could not reflect the impact of the programme. In the project completion narrative report a number of recommendations are made on the structure of a logframe. It would assist the targeting of programme activities and achievement of VfM to have clear impact indicators including Donor Committee for Enterprises Development indicators dealing with numbers of people impacted, increase in income and new jobs created. At the outcome level measures of public private dialogue, the quality of the dialogue and the number of business environment reforms triggered should be adequate. / Impact evaluations: Policy and regulatory changes take time to come to fruition. ENABLE could therefore only do impact evaluations towards the end of the programme period. It would assist the design of results chains and targeting of activities if more impact evaluations could be done during the course of the next phase of the programme. / State vs federal engagement: ENABLE had the flexibility to engage both state and federal level government agencies and tackle issues at both levels. In future it should have a state-level bias since engagements at that level proved more successful. / Not giving grants: ENABLE developed an enviable reputation amongst partners for not providing grants. This was one of the strengths of the programme and a foundation for its success. It should not be compromised. / Keeping a watching brief: Public private dialogue as a primary strategy to improve the business environment in Nigeria is still in its infancy. ENABLE II should therefore keep a close watch on public private dialogue platforms established as part of ENABLE and be prepared to provide support to ensure that momentum is maintained. ENABLE has done ground-breaking work in a very tough environment and gains can be easily reversed. There is therefore much to be said for continuing to work with partners rather than exiting before new approaches have been truly embedded.

8. Review Process
The review was undertaken during 10 days in-country during January and February 2014 and included interviews with DFID (ENABLE programme advisor and State representative), ENABLE staff and twenty of ENABLE’s partners including BMOs, MDAs, media and research partners in Lagos, Kaduna, Kano and the Federal Capital Territory, Abuja. Multiple documents recording the activities and performance of the programme were reviewed and detailed interrogation on value for money indicators was conducted.