Type of Review: Annual Review

Project Title: Support to Malaria Control in the democratic Republic of Congo

Date started:	08/05/2013	Date review undertaken: April 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is supporting the delivery of 4.4 million long-lasting insecticide-treated bed nets (LLINs) to Kasai Occidental province in the Democratic Republic of Congo through a mass campaign. In addition, the UK will support key objectives of DRC’s National Malaria Control Programme (PNLP) which address some of the major constraints to improved malaria control in the country such as information and capacity for planning and availability of ACT medication (Artemesinin-based combination therapy). / This project is made up of two components / The total budget for this “design and build” programme is £39.5 million over six years (2012/13-2017/18). The project is made up of two main components / Component 1 (£20.2 million over 2 years) – the distribution of between 3.5 to 4 million bed nets in the DRC. This allows DFID to achieve results through lower risk - but less sustainable interventions with less impact on key partners including government. / Component 2 (£15.9 million over six years): Supporting the objectives of the DRC National Malaria Control Programme (PNLP) to (i) improve information systems and (ii) enhance the provision of first-line quality artemisinin-based combination therapies (ACTs) and improvement of management information. This is higher risk but offers an opportunity to influence how the government of DRC and donors engage in this sector, delivering more transformational and sustainable results allowing for a reduction in DFID’s investment over time and eventual exit. / The value of the current contract signed between DFID and PSI is £36.1m GBP. They have not been contracted for the full value of the business case in order to ensure that DFID could respond flexibly to needs/ as they arose during the life of the programme. The contract for this programme took longer than expected to procure following approval of the business case in September 2012. PSI (Population Services International) won the OJEU standard international competitive tender process and the contract was signed in late September 2013. Therefore, this annual review assesses the first six months of this “design and build” contract only. / During the six month period covered by this annual review, the project has mainly been in the design phase. The project was set up with separate design phase components, which have progressed at different rates. The design work for component 1 (bed nets) was approved internally within DFID DRC in December 2013. Therefore, for this component, this annual review covers the design phase plus three months of implementation work. Design work for component two has been extended until the end of May 2014. The design document for this requires Director level approval. DFID is currently arranging a design phase contract amendment for PSI through until September 2014 to allow the subcontract for institutional support to PNLP to be able to continue pending finalisation of approval and contracting procedures.

What are the expected results?
The programme will result in the distribution of approximately 4.4 million bed nets, which will protect more than 6 million people from Malaria. In turn, the programme is expected to have the following impact in targeted areas: / The prevalence of malaria infection will fall by about 13%, / The number of cases of uncomplicated malaria will fall by about 50%, resulting in about 2.5 million fewer episodes of malaria amongst children under five per year, / The lives of approximately 4,500 children under five will be saved per year. / We expect this reduction in the burden of malaria will in turn lead to wider socio-economic benefits and economic growth in the targeted areas, for example due to increased educational performance, reduced absenteeism from work and school, and savings in healthcare spending. / Additional results will be achieved through support to the PNLP (the National Malaria Control Programme), by strengthening the governance, effectiveness and accountability of malaria control in DRC, improving malaria case management, and reducing the risk of emergence of drug resistance.

What is the context in which UK support is provided?
WHO has recently identified DRC as having the second highest burden of Malaria in the world. The recent UK Public Accounts Committee report noted that since half of the total Malaria cases worldwide are in Nigeria and the Democratic Republic of Congo, it recommended that DFID improve its prioritisation of funding between countries, to target its resources on those countries where the need is greatest and expenditure is most effective. / Malaria is one of the most important public health and socio-economic challenges facing the DRC. 97% of the population live in areas experiencing high and stable malaria transmission, and in some parts of the country, the prevalence of malaria is as high as 80%. As a result, Malaria is responsible for about a third of all deaths in DRC. Malaria also imposes a great strain on the country’s fragile health system, and economically has been described by the Government of DRC as a ‘brake upon development’. / Within this broad context, three specific needs have been identified, which this programme will address: / Maintaining and increasing the availability and use of bed nets, which are a fundamental element of malaria control: this project will distribute 4.4 m bed nets in Kasai Occidental province according to the PNLP plan of mass distribution campaigns. / Improving the availability and accessibility of quality-assured ACTs in the private sector: The private sector accounts for the bulk of anti-malarials dispensed in DRC, but only a small proportion of these are first-line quality-assured ACTs. This means that a large number of people are receiving treatment that is partially or completely ineffective, and also has the potential to drive the emergence and spread of Artemesinin resistance. / Improving the availability and use of information for Malaria control in DRC: There is a lack of information on the epidemiology of Malaria in DRC, on the availability and effectiveness of key interventions in the country, and on the best mechanisms for delivering these. This is a key constraint to the effectiveness of malaria control in DRC, and hinders the PNLP in fulfilling its strategic leadership function.

## Section A: Detailed Output Scoring

Output 1: Improved procurement and equitable distribution of LLINs
Output 1 score and performance description: / A - Output met expectation
Progress against expected results: / In terms of design work for this component, the deliverables required at the end of the design phase were submitted on time and were approved. The breakpoint to proceed to implementation on this component was approved in December 2013. / In the subsequent first three months of implementation of this component that the annual review covers, the LLIN procurement was tendered and contracted by PSI Headquarters. The LLIN manufacturer will start production in early 2014 and the first batch will be ready for international testing in the second quarter of 2014. The bed nets are expected to reach the country by August 2014, in time for the mass campaign which is due to be conducted between November and December 2014. PSI conducted a visit with authorities and other local stakeholders in Kasai Occidental to begin the planning process for the mass distribution and are in the process of recruiting staff and securing office accommodation. / Recommendations: / DFID should continue to monitor closely the budget for both commodities and distribution costs (in terms of cost per net). / In 8 health zones in Kasai Occidental a British NGO Against Malaria Foundation has donated nets to the DFID funded ASSP project to do a “hang-up campaign”. This is a hybrid approach between a mass net distribution and follow on routine distributions through health facilities. DFID should monitor closely the results of this pilot both in terms of (a) utilisation of nets 6 months after distribution and (b) cost per net distributed and compare with the results of the conventional mass distribution approach. (NB: It may not be necessary for PSI to do a mass distribution in these zones and therefore nets which will not be required may be used for routine distribution in Kasai Occidental). / PSI should disseminate to PNLP and DFID the findings of their lessons learnt review of the previous mass distribution in Equateur and ensure that findings from this are included in the fiduciary risk management plan for the mass distribution in November. / Impact Weighting (%): 65% / Revised since last Annual Review? Not applicable / Risk: Medium / Revised since last Annual Review? Not applicable

Output 2: Enhanced provision of ACTs in the private sector
Output 2 score and performance description: / B - Output moderately did not meet expectation
Progress against expected results: / This component is still in design phase so we could not expect at this stage that it would be delivering directly against the output. However we can comment on progress made in design against what we would have expected. / PSI has conducted initial discussions with PNLP and the 3ieme Direction (relevant directorate within the Ministry of Health) on regulation, capacity building and improvement of functioning of the quality approved ACT supply chain in the private sector. The project team conducted a desk review on regulation and experiences of ACT distribution in the private sector in DRC and elsewhere to support the planning phase. Outcomes of the desk review were fed into the on-going “ACTs in private sector” situation analysis, risk matrix, and other project documents and used as working documents for a workshop held in January 2014. The objective of the workshop was to consult stakeholders on the work and to plan the best approach for implementation. The workshop of 70 attendees demonstrated that all the stakeholders (donors , MOH, civil society organisations and key partners involved in malaria in DRC) are supportive of this project, particularly for the innovative approach that will be used to make ACTs available in the private sector. PSI has successfully gained approval from the Global Fund (who now run the AMFm facility) to use the Green Leaf logo of quality assurance in DRC for ACTs subsidised by DFID. / The design document for this component was expected by the end of December 2013. DFID has agreed an extension for the submission of this report until mid-May 2014. We acknowledge that DFID under-estimated both the time and complexity/depth of analysis required for the design of this component. However, DFID is also aware that PSI was slow to start this analysis and to recruit/position appropriately skilled personnel for this work. At the time of writing (early April 2014), PSI has yet to assign a consultant/member of staff with appropriate economics skills to conduct market analysis – something which is essential before considering putting subsidies in place in the private sector. To date, the majority of work has been desk based reviews and we would have anticipated that more research on the ground and engagement of key stakeholders in the private sector would have taken place by now. / Recommendations: / This is the most innovative component of the project with greatest risk and therefore we recommend that its risk rating is increased from medium to high. It is also of vital importance in terms of controlling malaria in DRC. Almost no support exists to improve access to ACTs in the private sector and this remains the main way people access treatment. Whilst there is significant learning from the experience of the Affordable Medicines Facility – malaria (AMFm) which is now part of the Global Fund, DRC will be one of the first countries to attempt subsidisation of ACTs outside of this mechanism. There is therefore great interest in this component of the project both from PNLP (in terms of whether the pilot can be rolled out further using Global Fund/domestic resources) and also other high prevalence countries in Africa who may be considering this approach. / PSI should incorporate the lessons learnt from AMFm and other country pilots of ACT subsidy into the design of this project. (DFID has shared findings from its support in this area in Nigeria). / PSI should ensure in depth consultation with the main stakeholders in the private sector to test scenarios/assumptions prior to implementation. / PSI should establish a working group to discuss the outstanding issues of this component: scaling up of the approach, guidance and steps to use to introduce RDT (Rapid Diagnostic Tests) in the private sector and issues of taxes, tariffs and regulation. / See comment in section on overall progress on the break point for this component and options on the way forward if DFID does not approve the design work on this component. / Impact Weighting (%): 20% / Revised since last Annual Review? Not applicable / Risk: Medium (revised to high following this annual review) / Revised since last Annual Review? Not applicable

Output 3: Increased support to the PNLP (National Malaria Control Programme)
Output 3 score and performance description: / A - Output met expectation
Progress against expected results: / This component is managed by Swiss Tropical Institute of Public Health (STIPH). The subcontract for this was signed in November 2013 and this component is still in the design phase. It appears PNLP is keen to engage on this institutional strengthening collaboration with STIPH and design work for this appears to be progressing well. The design work for this component forms part of the component two design report, the deadline for which has been extended to mid-May 2014. / STIPH have had at least one member of their team based in Kinshasa and they have been working closely with PNLP. STIPH has also set several meetings with other donors (PMI/USAID, GF/SANRU) supporting the capacity building of PNLP (National Malaria Control Programme) in order to create synergies between programmes and avoid duplication of efforts (as other donors also support the institutional strengthening of PNLP). STIPH is awaiting the results of the PNLP‘s institutional assessment carried out by PMI/USAID, which is expected before the end of April 2014. / Recommendations: / DFID has discussed with PSI that it is important that this work should continue despite the delay in development of the design report for the ACT work under the component two. DFID has requested PSI to submit a proposal for an extension for the design phase to September rather than May when the design report will be submitted. This would ensure continuity of the subcontract through the period June to August, in which approval will be sought at Director level and contractual procedures on the break point will be completed by DFID’s Procurement Group. Currently, due to the strong engagement by PNLP, DFID DRC is not anticipating that this element of component two would be at risk in a scenario in which the design work on ACTs was not approved. / Impact Weighting (%): 15% / Revised since last Annual Review? Not applicable / Risk: Medium / Revised since last Annual Review? Not applicable

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the log frame been updated since last review? / This is the first review. The log-frame has been revised during the design phase. / 1.2 Overall Output Score and Description: / A - Outputs met expectation / 1.3 Direct feedback from beneficiaries / For component one, during the design phase, the PSI design team met and consulted with a wide range of authorities at national and provincial level ( the Governor of Kasai Occidental, Provincial Ministry of Health, Deputy head of Provincial Assembly, the Mayor of Tshikapa, Congolese Chamber of Commerce (FEC) Kasai occidental , health zones management teams and civil society representatives. During the meetings with Kasai Occidental provincial authorities, the MOH clearly voiced their concerns regarding mismanagement of campaign resources by civil servants in the province during the previous campaign in 2011 (funded by another donor) and expressed their commitment for improved management of the coming campaign. The feedback from the Director of PNLP has been very positive on the approach used for the project design. He commented that, “this is the first time a partner project is not only having regular meetings to discuss project issues but also sharing the project chronogram with us. This is exactly what we are expecting from partners to help coordinate malaria interventions in the country.” No direct feedback from beneficiaries is yet available for this first annual review as the distribution of bed nets is not scheduled until November. / For component two, DFID has received positive feedback on the proposed institutional strengthening work from PNLP. For the ACT work, DFID met with a range of stakeholders as part of the planning workshop in January 2014. This is an innovative approach and government officials needed detailed explanations and time for them to understand what is being proposed. Private sector stakeholders seemed enthusiastic about the proposals. However, further consultation with them is required as at that stage detailed plans were not available.
1.4 Summary of overall progress / Two of the three main work-streams (bed nets and institutional strengthening of the National Malaria Control Programme) have met expectations in terms of progress expected after six months. / The other work-stream (access to ACTs) is currently delayed and DFID has some concerns that PSI appears to have left it quite late to begin some of the detailed analysis and planning work (even with an extension agreed from end of December 2013 to mid-May 2014). / Providing subsidies for ACTs in the private sector is innovative outside of the Affordable Medicines Facility – malaria (AMFm) and therefore there is a lot of attention on DRC and DFID on whether this pilot can be made to work. A poor outcome would be one where the pilot fails due to lack of planning/weak implementation rather than failure of the approach itself. For this reason, DFID will need to be very confident that the design work completed by PSI is robust, based on strong in-depth analysis and has tested key assumptions and scenarios. DFID remains committed to improving access to ACTs in the private sector since this is a key component of Malaria control in the country and it has no support from other donors. / In the event that the design report for component two is not approved, DFID DRC may consider a number of options on the way forward; / Option A: Restructure component two to focus on only the institutional strengthening of PNLP work (i.e. output three) and scale down the budget accordingly / Option B: Approve output three separately but invite PSI to resubmit a proposal for social marketing of ACTs in the private sector. / Option C: Proceed only with component one i.e. access to bed nets and scale down the project budget accordingly. / NB: DFID is currently exploring a contract amendment for component one (access to bed-nets) which would enable PSI to accept a donation of up to $12 million USD of bed-nets from the British NGO Against Malaria Foundation for a mass distribution in five out of seven districts in Equateur Province in 2015. The contract amendment would enable DFID to support the distribution costs of this mass distribution. These discussions have needed to happen before the outcome of the breakpoint is known in mid 2014 in order for DFID to give PNLP adequate notice to seek an alternative donor for this distribution (which needs to take place by November 2015).
1.5 Key challenges / Key personnel: The design phase has suffered from not having appropriately skilled staff to lead on the ACT component in the right place at the right time; / PSI work through their local counterpart in DRC ASF. Whilst PSI has experience in the regional office of engagement on ACT subsidies, the ASF office does not. PSI may need to increase the level of support/technical assistance it gives to ASF to ensure that component two is approved and subsequently delivers. / ASF has experienced difficulty allocating appropriately skilled personnel to this project. DFID notes that one member of ASF staff identified as “key personnel” in this contract was moved off the project without notifying DFID until after the event. The contract requires that PSI seek DFID approval in writing to change key personnel. / Communications: During the first six months of the project, DFID DRC could have improved communication with PSI in terms of (a) the difference in expectations from DFID on partners delivering work based on a commercial contract basis rather than an accountable grant and (b) the degree to which it regards the ACT component as innovative/risky and resulting expectations on the quality of the design document as specified in the terms of reference. DFID DRC could also have been clearer with PSI that the break point requires Director level approval and therefore provision needed to be made in respect of sub-contracted partner(s) during this approval/contracting process which is likely to take three months. / Logistics: Transport of LLINs through the various layers of the supply chain is a significant challenge. PSI is exploring the possibility to transport the nets by train and if this can work, it will contribute to decrease the unit cost. Train is more risky in terms of potential delay however. / Fiduciary risk of working with government partners: this is a known risk when operating in remote areas with little access to the formal banking system and irregular supervision from provincial and national authorities. The key element of managing this risk has been securing the early involvement of provincial authorities. This was the purpose of PSI’s advocacy visits to the Governor, the provincial MOH and other local authorities. Signing an MOU with heads of health zones and involving community members in key activities will also reduce risks. / The lack of regulation and the weak capacity of the 3rd Directorate of the Ministry of Health to oversee and supervise the distribution of quality assured ACTs in the private sector. It was noticeable that government officials involved in the planning workshop in January lacked understanding and experience of working with the private sector. The project will provide resources to strengthen regulation and supervisory capacity of the MOH to undertake their duties and build capacity in the private sector’s supply chain. / Institutional reform of the Ministry of Health: The MoH is in the process of institutional reform of the various directorates and this is likely to directly impact PNLP. The Secretary General of the Ministry of Health has indicated that the Ministry is seeking to evolve into a more integrated institution rather than one with many directorates based on vertical disease control programmes.
1.6 Annual Outcome Assessment / A – Moderately meets expectation

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / DFID has contracted £36,053,684 to PSI for this project out of £39,500,000 approved under the overall programme business case. The balance of funds has yet to be contracted. / £6,927,799 has been spent to date, representing 19%. The bulk of this has been commodity procurement (bed-nets). Costs for the first three months of design were as expected and PSI has made the large procurement of bed-nets as expected. / The extension of the design phase is likely to slow expenditure rate within the project going forward. / 2.2 Key cost drivers / Commodity costs: From the price of £2.19 for the purchase of LLINs in 2012, provisional unit cost has dropped to an estimated £1.70 for the current order. Final unit cost will be assessed when the procurement process is completed. DFID will continue to monitor both unit costs for both the nets themselves and distribution costs. / Transport costs: A key cost driver going forward will be in country transportation and whether PSI decides to use rail transport rather than air freight. At the time of writing, DFID does not have detailed information on cost of planned ACT subsidies from PSI. / 2.3 Is the project on-track against original timescale: / No – the design document for component two which was due late December 2013 has been delayed until mid-May 2014. DFID under-estimated the length of time the design work on ACTs would need to take, considering the depth and scope of analysis it expected. Six months should have been allocated for this work. Also, DFID DRC did not take into consideration the likely additional three months that will be required following submission of the first draft of the design document to cover commenting, finalisation of the report, approval from Head of Office and the Director and issue of notice to proceed to implementation from Procurement Group. This will mean that the project is likely to be running approximately nine to twelve months behind schedule by the next annual review.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Last month, Clinton Health Access Initiative published findings of a systematic review of 40 studies on the impact of price subsidies on the use of ACTs in the private sector[1]. This provides good evidence on the likely effectiveness of the ACT component of this project. The reviewed studies found a substantial increase in private sector ACT use following the introduction of a subsidy. Overall, each $1 decrease in price was linked to a 24 percentage point increase in the fraction of suspected malaria cases purchasing ACTs. These findings suggest that ACT price reductions can increase their use for suspected malaria, even within poorer, more remote populations that may be most at risk of malaria mortality. They commented that whether a subsidy is appropriate will depend upon local context, including treatment-seeking behaviours and malaria prevalence. This research emphasises the importance of ensuring adequate contextual analysis in the design phase of this component. / 3.2 Where an evaluation is planned what progress has been made? / For component 1, no formal evaluation has been planned but a mixed team (DFID- PSI and PNLP) will make an assessment of the key activities of the project and follow-up checks on utilisation of nets after the distribution. / DFID has requested that the Swiss Tropical Institute of Public Health include an evaluation of the ACT component in their work plan and terms of reference will be updated accordingly with further specifications for this. DFID will use the SEQAS service for quality assurance of this research.
[1] Morris A, Ward A, Moonen B et al (2014) Price subsidies increase the use of private sector ACTs: evidence from a systematic review. Health Policy and Planning Health Policy and Planning 2014;1–9 doi:10.1093/heapol/czu013

4. Risk
4.1 Output Risk Rating: / Medium – overall output rating. / Assessment of the risk level / Output 1: Risk level: Medium / Delay in the procurement and transportation of LLINs: this is monitored each month by PSI through the implementation plan: procurement activities planned during the period covered this review were implemented as planned. Contracts with manufacturers were signed on time and samples for testing are planned for the end of March/beginning of April 2014. / Political or institutional change at provincial level: There is a planned restructuring of provincial health system that may have an impact on provincial malaria programme coordination. The expected local elections may also have an impact. / Output 2: Risk level: High (NB: this output was originally assessed as medium in the business case but will now been increased) / Providing subsidies in the private sector is innovative outside of the Affordable Medicines Facility – malaria (AMFm). / Engaging with the private sector in DRC is complex and assumptions need to be properly tested / It is unclear whether the planned number of outlets (approximately fifty) will be adequate to shift behaviour of consumers in the market (i.e. stimulate demand) in order to sustain a price reduction long term. / Output 3: Risk level: Medium / The on-going institutional review of PNLP and wider institutional reform of the Ministry of Health are likely to make institutional strengthening work more challenging in the short term. However, these may result in a potentially stronger more effective national control programme in the long term. / There are a number of other partners and donors currently supporting the PNLP so it is important this work is carefully coordinated and planned.
Risk of funds not being used as intended / DRC is a high risk environment to operate in and this project works both through government partners and will additionally engage in the private sector. However, DFID DRC has been working with PSI for a number of years. DFID is currently undertaking a formal Due Diligence Assessment of PSI and to date no significant concerns have been raised. PSI is developing a detailed mitigation plan of all the risks linked to the project including fiduciary risk. / 4.4 Climate and Environment Risk / The main risk to the climate and environment posed by the project is linked to the increased risk of environmental contamination by insecticide. PSI will procure nets according to WHOPES standard which are designed to maintain their biological efficacy against vector mosquitoes for at least three years in the field under recommended conditions of use, obviating the need for regular insecticide treatment which reduces environmental contamination risks.

5. Value for Money
5.1 Performance on VfM measures / See section on key cost drivers which outlines commodity unit costs for nets. Transportation costs will vary according to whether air or rail transportation is used. For the two other outputs (ACT and support to PNLP) further information is awaited in the design document. / 5.2 Commercial Improvement and Value for Money / There was a strong response to the call for tenders for the contract under which this programme will be implemented with evidence of competition on costs. DFID will continue to monitor unit costs of nets in particular within the life of the project and also findings on VFM on the alternative “hang-up campaign” approach pilot by another NGO. / 5.3 Role of project partners / This project is managed by a consortium of three organisations: / PSI consortium lead : PSI/ASF leads two components : delivery of bed nest distributions and increasing access to ACT in the private sector / Swiss Tropical Public Health Institute : leads on the capacity building of PNLP / Green Mash: has a consultancy agreement with PSI and will work on collection and analysis of data collected at sentinel sites through mHealth solutions. Their role will be determined by the end of the design phase. / This project is implemented under the leadership of PNLP and will contribute to the achievement of their objectives. During the implementation phase, the project will also work with local NGOs, commercial transporters, radio and TV stations, drug manufacturers, first line buyers and local pharmacies in Kinshasa. / 5.4 Does the project still represent Value for Money : / Yes. Early indications from the procurement of nets indicate that the bed-net component represents good value. It is too early to comment on VFM of the other components. / 5.5 If not, what action will you take? / DFID DRC will be looking for strong evidence of VFM for the ACT work in the design document for component two before giving approval for implementation.

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
So far two of the three outputs of this project are on track and their performance in the first six months appears to be satisfactory. / The implementation of the distribution of bed nets (impact weighting 65% in the log-frame) has been approved, the procurement of bed nets underway , macro planning process held in Kasai Occidental in February 2014 and distribution planned in November 2014. / There are positive early indications of a good engagement with PNLP for output 3 (although the design document for this is awaited). / Output two (access to ACTs in the private sector) is considered the highest risk component of the project. Progress on design has been slower than expected and the design report is now expected mid May 2014. The design phase of the contract is being extended until September 2014 to allow for approvals/contract procedures. Section 1.6 outlines the options DFID DRC will consider in the event that approval is not given for output two (ACTs).

8. Review Process
The review process draws on analysis of the projects reports and discussions with PNLP, project consortium members, and key malaria stakeholders in DRC.