Business Case and Intervention Summary

Intervention Summary
## Title: Humanitarian Emergency Procurement Programme
What support will the UK provide?
The UK will provide up to £7.25 million over a three year period to ensure non-food items can be delivered to those in need, rapidly in sudden onset emergencies. Complementary specialist logistics and supply chain management support will be provided through the on-going Humanitarian Emergency Operations Support Services programme. Following an interim review of UK government humanitarian stockholdings in November 2012 it was agreed that there should be an immediate uplift of £4 million to enhance the range of emergency supplies held in UK stocks and increase official deployment capability. An evaluation after two years of the programme will consider an extension of support at a similar level for a further two years.

Why is UK support required?
The UK government’s humanitarian policy ‘Saving lives, preventing suffering and building resilience’ recognised that humanitarian need is likely to continue to grow.[1] One of the seven goals it set for improving the effectiveness of UK humanitarian support was to reinforce the British Government’s own capacity to respond to humanitarian crises. In doing so it recognised that carefully targeted bilateral support provided a valuable contribution to the international response and that the UK has a strong reputation for its humanitarian work in rapid-onset disasters and in fragile and conflict-affected states. / As part of the toolkit needed to ensure an effective direct bilateral response to a sudden onset or emerging slow onset emergency it is vital DFID is able to access life saving and essential shelter materials and other specialist non-food items (NFIs) that can be quickly and effectively deployed. It is equally important for DFID to be able to access, and use, high quality and effective equipment and materials to support the deployment of our own field teams and, where common support platforms have been agreed, our partners’ specialist teams where we support their deployment. / As our stockpile forms part of a wider international humanitarian system it is equally important that the international community (including national governments, donors, the UN, NGOs and other operational organisations) is able to access and deploy life saving equipment and materials as part of future humanitarian responses. To do so effective systems are needed that; / ensure “hard to access” specialist equipment and materials, as well as generically required NFIs, held by individual organisations in the international humanitarian community or private sector can be quickly identified; / implement minimum acceptable standards for NFIs provided in response to emergencies which can be monitored and for which providers can be held accountable; and / enable innovations in NFIs to be developed and assessed and, where appropriate, brought into standard practice by both the UK and the international humanitarian community.
[1] http://www.dfid.gov.uk/Documents/publications1/The%20UK%20Government's%20Humanitarian%20Policy%20-%20September%202011%20-%20Final.pdf

What are the expected results?
The results of this investment will ensure we can respond quickly, effectively and appropriately to a broad range of humanitarian crises (including urban crises), drawing on equipment and materials that enable us to meet the needs of affected communities, and will ensure we can support the field deployment of DFID and key partners for up to three simultaneous events. This investment will also inform our current and future engagement with the wider international humanitarian procurement system.

Business Case

Strategic Case

A. Context and need for a DFID intervention / The UK government’s humanitarian policy ’Saving lives, preventing suffering and building resilience’ recognised that humanitarian need is likely to continue to grow.[2] One of the seven goals it set for improving the effectiveness of UK humanitarian support was to reinforce the British Government’s own capacity to respond to humanitarian crises. In doing so it recognised that carefully targeted bilateral support provided a valuable contribution to the international response and that the UK has a strong reputation for its humanitarian work in rapid-onset disasters and in fragile and conflict-affected states. / As part of the toolkit needed to ensure an effective direct bilateral response to a sudden onset or emerging slow onset emergency it is vital that DFID holds or is able to rapidly access life saving and essential shelter materials and other specialist non-food items (NFIs) that can be quickly and effectively deployed to meet the immediate humanitarian needs of affected communities. It is equally important that we are able to access, and use, high quality and effective equipment and materials to support the deployment of our own field teams and, where common support platforms have been agreed, our partners’ specialist teams where we support their deployment. / In order to meet these needs DFID has established UK Government humanitarian stockpiles, currently mainly located in Dubai and Kemble, of materials and equipment that can be drawn on in a response. DFID has also developed a network of suppliers, including an awareness of their production capacities and stockholdings, who can supplement these resources as needed; which has been particularly important in enabling us to meet more specialist or less predictable needs. The humanitarian stockpile works in parallel with a similar Stabilisation Unit (SU) support package and shares warehousing, labour and maintenance services. To meet future challenges we need to maintain these resources while undertaking an on-going process that reviews needs and the performance of the materials we hold or procure and the locations of our stockpiles, and ensures the UK takes advantage of innovation and new technology. Additional items may be procured where they are necessary or desirable, or to support innovations in the humanitarian response. / In addition to the materials held for an immediate response the stockpile(s) currently include field bespoke modules, based on the UNDAC Basic Module designed by OCHA, to support the deployment of DFID (CHASE and CHASE-OT) field staff. / There are two main elements in the current stockpile(s): / Emergency Relief Non-Food Items (including shelter materials) / Deployment Support Equipment (including vehicles) / UK stocks are stored in various locations for flexibility and rapid response time. Stocks are currently split geographically with warehouse space in Kemble (UK), the Cayman Islands and Dubai. A list of the stocks held in the 3 locations as at 31 December 2012 is at Annex 1. A small stock of emergency response module equipment and other frequent use items are held in London. The value of the stocks at 31 December 2012 is estimated at £3m. / CHASE is responsible for managing humanitarian response operations for the UK Government and for supporting those of other humanitarian partners, in particular the UN. The UK stockpile, first established in 1994, has been an essential element in CHASE’s response portfolio and has been drawn on for a wide range of humanitarian responses. / The stockpiles of non-food relief goods have enabled the UK to provide practical support to beneficiaries and partners by providing immediate initial stocks of shelter materials for use in both sudden onset disasters and complex emergencies, most recently in the UK's response to the 2011 earthquake in Turkey where it enabled provision of winterised tents for some 5,000 people. / The range of items in the existing stockpiles has been developed in the light of extensive experience and is currently limited to those items (tents, blankets, plastic sheeting, and buckets) that are proven to have been most urgently and frequently required in disasters and which are cost-effective to store and transport; items have been added if they provide a worthwhile increase in capability and deleted if they no longer serve a useful purpose. Current stock levels are based on providing shelter for approximately 5,000 families. Deployed stocks are usually replaced from programme funds specific to the emergency response which draws them down. All equipment and materials in our stocks meet, or exceed, the quality specifications of the major aid agencies. / In addition to items contained within current stockholdings, UK government is also able to draw on supplementary items provided by the network of Rapid Response Facility suppliers. Where the UK wants assured provision of difficult to obtain materials that would not be appropriate to hold in the UK stockpiles (e.g. due to short expiry date, rapid innovation in the sector, high value, high maintenance costs etc) agreements have been put in place to enable rapid access to these materials. / Following an interim review, in November 2012, of the current holdings of emergency relief items it was proposed that an immediate uplift of £4 million be added to the humanitarian response capability. This uplift will enable the UK Government to meet the needs of 38,750 people, an increase of 21,250 over the original stockpile capability, and increase the range of non-food items that can be delivered during an emergency response. The uplift will also improve the quality of UK government response by enabling us to provide support which meets the wider needs of disaster affected populations. The uplift also extends the ability of field teams to rapidly deploy by increasing the range of mission critical equipment at our disposal and by improving our logistical capability to move field teams and equipment at short notice. / In 2010, 263 million people were affected by disasters – 110 million more than in 2004, the year of the Asian tsunami. All trends suggest that more people – particularly in developing countries – will be affected by humanitarian emergencies in the coming decades. The HERR makes it clear that this trend will only grow with climate change, population growth and greater urbanisation. Against this background there is a clear and continuing need for the UK government to maintain and extend its capacity to respond directly to a wide range of humanitarian crises, to be able to provide carefully targeted bilateral support and to be able to adapt and innovate to ensure it can respond to a wider range of humanitarian crises. / The planned intervention will ensure that existing UK stocks, and our access to stocks held by others, will be maintained and refreshed and increased to meet the basic shelter and emergency survival needs (excluding food) for affected communities across a wider range of humanitarian crises. The intervention will also ensure that innovations and emerging technology in essential humanitarian equipment and materials are properly assessed and, where appropriate, brought into standard stock holdings. It will also ensure the UK Government is able to effectively support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of emergency environments, including insecure/conflict affected environments, for up to three simultaneous deployments. / As our stockpiles form part of a wider international humanitarian system it is equally important the international community (including national governments, donors, the UN, NGOs and other operational organisations) is able to effectively access and deploy life saving equipment and materials as part of future humanitarian responses. Experience has proved that immediately available global stocks are invariably inadequate to deal with a major emergency, that manufacturing capacity is often unable to meet the surge of demand typical in such situations and that some suppliers have used shortages to inflate their prices. To improve the current situation effective systems are needed that; / ensure “hard to access” specialist equipment and materials, as well as generically required NFIs, held by individual organisations in the international humanitarian community or the private sector can be quickly identified and accessed; / enforce minimum acceptable standards for NFIs provided in response to emergencies, which are monitored and for which providers can be held accountable; and / enable innovations in NFIs to be developed and assessed and, where appropriate, brought into standard practice by both the UK and the international humanitarian community. / There are a range of existing international systems that have been established to meet these needs (e.g. the OCHA Central Register and Global Mapping of Emergency Stockpiles System) but little evidence is currently available to indicate whether they have had the expected impact. The planned intervention will enable us to review their impact and, subject to the findings of the review, to consider whether and where we might work with the UN and other stakeholders to help develop and improve the systems so they can meet future challenges.
B. Impact and Outcome that we expect to achieve / The expected outcomes from this investment are that; / UK stockpiles (quality, content, volume) are sufficient to enable us to provide direct, bilateral ‘in-kind’ support to meet the basic shelter and emergency survival needs (excluding food) for affected communities across a wider range of humanitarian crises. / UK stockpiles (quality, content, volume) are sufficient to support the simultaneous deployment of DFID staff (and/or those of partners’ specialist teams) into a range of emergency environments, including insecure/conflict affected environments, for up to three simultaneous deployments. The deployment platform should include the full range of essential equipment, including but not limited to; shelter and personal kit; communications and office equipment; vehicles and other field requirements and will require on-going maintenance support. / Where the UK wants assured provision for NFIs/complex equipment/difficult to obtain materials that would not be appropriate to hold in the UK stockpiles (e.g. due to short expiry date, rapid innovation in the sector, high value, high maintenance costs etc) agreements will be put in place to enable rapid access to materials on this list (eg through mechanisms including Vendor Managed Inventory; production agreements; partnerships with manufacturers and suppliers of key NFIs etc). Agreements established as part of this process will be reflected by the inclusion of the suppliers of such specialist equipment/materials on the Rapid Response Facility (RRF) which provides the umbrella framework for our immediate response toolkit. / Innovations and emerging technology in essential humanitarian equipment and materials are properly assessed and, where appropriate, brought into standard stock holdings. The findings of the review and testing process are routinely made available to inform best practice in the wider humanitarian community. / UK stockpiles are located appropriately to maximise the UK Government’s capability to respond effectively on a global basis and are linked with global logistics/transport providers (including the DFID air service provider) operations to ensure a seamless supply/deployment process. / Existing international systems (eg OCHA Central Register and Global Mapping of Emergency Stockpiles System) for stockpile monitoring, reporting, inventory management, quality control etc have been reviewed and assessed. Subject to the outcomes of this review, and where appropriate, support will be provided to help develop and improve these systems, and will help inform where the UK might cover critical gaps or change its stock profile to minimise duplication. / Subject to the outcome of a review of existing international standards used for key NFIs and the systems used to (i) disseminate details of such standards and (ii) ensure/monitor compliance we will consider what, if any, further work is needed to drive improvements in their observance and, working with other key stakeholders, how this might be delivered. / Theory of Change / Inputs / Activities / Outputs / Outcome / Impact / Inputs / Process / Outputs / Outcome / Impact / UK Government stocks can meet the basic shelter and emergency survival needs (excluding food) for affected communities across a wider range of humanitarian crises. / Agreements in place to provide rapid access to essential materials and equipment held outside the stockpile. / DFID Stockpile(s) appropriately located. / Implementation of agreed recommendations to support, improve and replace etc existing international systems. / Implementation of agreed recommendations on standards and dissemination and compliance. / Up to £7.25 million over 3 years. / Support from within the on-going Humanitarian and Emergency Operations and Support Service contract. / Review undertaken to ensure UK stocks are able to meet the basic shelter and emergency survival needs (excluding food) for affected communities across a wider range of humanitarian crises. / Review undertaken to establish range of materials that would not be appropriate for the DFID held stockpile but where we would want assured provision. / Review undertaken of UK stockpiles to establish siting needs and explore the options to add/subtract regional locations. / Review undertaken to ascertain whether existing international systems (eg OCHA Central Register and Global Mapping of Emergency Stockpiles System) are fit for purpose. / Review undertaken to establish current standards used for shelter materials and other key NFIs and the existing systems used to (i) disseminate details of such standards and (ii) ensure/monitor compliance with such standards. / UK Government humanitarian stocks enable a quick, effective and appropriate response to humanitarian crises. / International system better prepared to respond quickly, effectively and appropriately to humanitarian crises and their changing nature and scale. / Innovations in shelter materials and NFIs assessed properly and brought into routine use as part of the humanitarian response. / Early and effective response saves lives and reduces suffering. / Inputs / Activities / Outputs / Outcome / Impact / Inputs / Process / Outputs / Outcome / Impact / On-going review and testing of innovations and emerging technology in essential shelter and NFI sectors to ensure they are properly assessed. / Review ensures DFID held stockpiles are sufficient to support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of environments for up to three simultaneous deployments. / Innovative new products and technologies brought into standard stock holdings by DFID as appropriate. Results of assessments shared with wider humanitarian community. / DFID held stocks support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of environments for up to three simultaneous deployments. / Assumptions: DFID wants to be able to directly deploy support in response to humanitarian emergencies. / The
[2] http://www.dfid.gov.uk/Documents/publications1/The%20UK%20Government's%20Humanitarian%20Policy%20-%20September%202011%20-%20Final.pdf

Appraisal Case

What are the feasible options that address the need set out in the Strategic case? / Option 1: DFID continues to maintain the UK government’s independent humanitarian stocks with the mix and locations of stocks broadly unchanged. / Option 1a: DFID continues with the current arrangements of managing the UK government’s independent humanitarian stocks and extends and enhances the stocks subject to a review of its content, quality and volume. / Option 2: The preferred option. DFID continues to manage and maintain the UK government’s independent stocks and commissions reviews on its content, quality and volume. In addition DFID directly commissions a series of reviews of the international humanitarian system to identify where additional support may be required, the demand for such support and the prospects of a successful intervention. / Option 2a: DFID continues to manage and maintain the UK government’s independent stocks and commissions reviews on its content, quality and volume. Subject to discussions with key stakeholders on need and demand support is provided directly to the UN system to enable it to further develop the Central Register and Global Mapping of Emergency Stockpiles Systems. / Option 1: This option, essentially maintaining the status quo, has been discounted as it would not allow us to respond to the increasing challenges and the changing nature of humanitarian responses. / Option 1a: The status quo plus option. Subject a review allows for an expansion and change in the mix of the current stockpile to meet expected increases in the humanitarian caseload, to enable us to respond in a wider set of circumstances (e.g. urban crises) and to bring innovative new products and equipment into use. Indicative budgets for the expansion of the current stocks are included in the budget but these will be considered further subject to the outcome of the reviews. / Option 1a also reflects the need to establish (i) a more regular and routine process to review and assess new and emerging innovations in humanitarian equipment and materials and to consider their inclusion in UK stocks and (ii) to allow us to work directly with innovators to ensure they have a robust understanding of on-the-ground humanitarian needs and requirements to help inform the development of new products. These costs are not currently included in the logistics/procurement support offered under the Humanitarian Emergency Operations Support Services contract. / Under Options 1 and 1a the costs of maintaining the current UK government stockpile largely comprises warehouse rents and utilities, warehouse labour and materials and the maintenance of the equipment and materials we hold. The total annual cost of these three core elements are £476,000. Additionally under Option 1a the proposed budget allows for a series of reviews to inform the expansion of the existing stocks and to bring in new and innovative products to enhance our capability in mounting a direct response. The benefits of ensuring DFID has access to wider response capability are that it allows us to deliver a more holistic response for affected communities, that it enables us to respond effectively in a wider set of situations and that it ensures we have rapid access to equipment and materials we may not wish/need to hold on a permanent basis in our stocks. / Option 2 – DFID continues to manage and maintain the UK government’s independent stocks to: / i) enable a direct, bilateral, in-kind contribution to be made subject to our assessment of needs, and; / ii) enable the rapid deployment of DFID staff/teams into the field. / This is supported by wider direct engagement with the international system to drive up standards and practice in humanitarian procurement and to seek to bring innovation – both in products and practices – through to the humanitarian response. There would be no need to re-tender, and management costs would be covered by the existing CHASE OT contract. / Recognising the UK stocks sit within a wider humanitarian procurement context the proposed programme of support under Option 2 draws on existing in-house supply chain management expertise to undertake a fundamental review of the international system, and the standards currently used for NFIs, to identify its strengths and weaknesses and to consider where UK support might drive improvements. The costs of the reviews reflect the need for additional skills to be brought in to support the in-house team deliver a comprehensive review process while, at this point, the cost of any implementation package is indicative and would be subject a design process following agreement to any of the review recommendations. / Option 2+ - Following an interim review of UK independent stocks in November 2012 a need was identified for an immediate £4 million uplift in stockholdings to enhance the range of UK emergency supplies held in stocks and increase official deployment capacity. Subject to the approval of this uplift, Option 2 will become Option 2+, the preferred option. / Option 2a - DFID continues to manage and maintain its own independent stocks to (i) enable a direct, bilateral, in-kind contribution to be made subject to our assessment of needs, (ii) enable the rapid deployment of DFID staff/teams into the field. / Unlike option 2 – where reviews of the international system are commissioned in house – this option provides for the development of a programme of support for OCHA to undertake a review UN procurement systems and practices, to improve and develop the Central Register and Global Mapping of Emergency Stockpiles System (which maps capacities and resources of humanitarian actors to respond to the needs of affected populations in case of emergency, with the aim of a more coordinated response) and to allow it to provide direct support to its partners. / The costs for the management of the UK independent stocks would be the same as in option 1a and 2 but, as the proposed reviews of and support for improvements in the international system would not draw on our existing in-house supply chain management expertise, we would anticipate that if OCHA were willing to take them forward the costs would be significantly higher, that any recommendations arising from the reviews would need to be spun off it a separate programme of support with the involvement of a wider group of stakeholders and that we would need to carefully manage expectations of continued UK support for an externally designed programme.
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 Strong / 1a Strong / 2 Medium / 2a Limited / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 1a C C / 2 C C / 2a C C
C. What are the costs and benefits of each feasible option? / The cost of Option 1 is approximately £476,000 per annum. This sum provides for maintenance of the existing stockpile, which would be refreshed on a like-for-like basis as stocks were drawn down in specific responses. Option 1a, the status quo plus, will incur additional costs of £32,000 per year to (i) assess and new and emerging technologies and consider the case for their inclusion in the stockpile and (ii) to work with innovators to help them reflect on-the-ground humanitarian needs and requirements in the development of new technologies. / Options 2 and 2a both continue with the activities/provision of Option 1a, and have additional activities/provisions on top of this. As such, it is the costs and benefits of these additional activities/provisions that are relevant to the assessments of Options 2 and 2a. / Costs / The additional (undiscounted) costs of Options 1a, 2 and 2a have common elements of £0.17m for conducting reviews relating to the UK stockpile. For Option 2+ an indicative figure of £5m is suggested for procuring and warehousing new products, materials and equipment to enhance the stockpile (rows 6-10 in the Financial Case table below). Under Option 2 there is also £0.7m for reviews and follow up of the international system, to be conducted or contracted by CHASE OT (rows 11-14). Under Option 2a, the same reviews would be conducted or contracted by the UN at a cost estimated at £0.75m. The difference is due to the UN levying a 7% management fee – this is thought to be a conservative estimate since higher UN salary rates could drive the cost even higher. / Beyond the 5 year period of the contract, Options 2 and 2a may have on-going implications for warehousing costs. At this stage it is not clear whether warehousing costs will rise or fall (or by how much), for reasons including the uncertain extent to which vendor managed inventory will be employed. / Benefits / On top of the benefits from the status quo (Option 1), which are realised under all of the subsequent options, a number of additional benefits are anticipated for Options 1a, 2 and 2a: / the ability to make a larger direct, bilateral, in-kind contribution, subject to our assessment of needs (international contributions are usually insufficient to meet need, so this would be additional, all else being equal); / improved quality and appropriateness of response due to greater breadth and depth in the stockpile, improving the ability of the stockpile to meet survival needs; / improved speed of response; / lower transport costs, through increased regional and local sourcing and stockpiling of NFIs; / the financial value of the expanded stockpile – which (undiscounted) is equal to value of the additional products, materials, equipment procured (i.e. £1m less warehousing costs); / improved quality of NFIs used by both DFID and other humanitarian actors, due to innovation; and, / higher standards and practice in humanitarian procurement, stockpiling and coordination in the international system. / While there are expected to be some financial benefits as a result of Options 2 and 2a compared to Option 1a, most of their benefits are expected to be in terms of speed, quality and appropriateness of response. Quantifying these benefits would be difficult and require arbitrary and subjective assumptions, producing results that lack robustness. As such, the work required to do a cost-benefit analysis is deemed as being disproportionate to the size of the programme. However a partial analysis has been done. On the costs side, this looking just at the procurement of products, materials, equipment and the reviews of the current stockpile and possible new NFIs (row 4-9 in the Financial Case table below). On the benefits side, this considers just the financial value of the expanded stockpile. / Assessed for the five year project period, and assuming a conservative 10% discount rate (which is often used in development project appraisals) and nil additional warehousing costs, costs exceed benefits by £185k. With a discount rate of 3.5% (the HMG Green Book rate), costs exceed benefits by £116k. It is thought highly likely that the value of the other benefits identified will substantially exceed these amounts, and so Option 1 is rejected. The additional costs of warehousing associated with Option 2+ will be taken from within the total £4 million uplift, and will not necessitate drawing on additional funds. The costs of the procurement work needed to increase the stockpile and provide on-going management support can be met from within current resources within the CHASE-OT logistics team. / Options 2 and 2a are very similar. Option 2 is preferred as it is thought to be the lower cost option. Under CHASE-OT’s contract, procurement services will be provided on a direct cost basis with no mark up. Under Option 2a, a management fee/mark-up would be charged by the UN, conservatively estimated to cost an additional £0.75m. This assessment is based on the assumptions that (i) the quality and (ii) the impact of the review work is the same under both options. / Procurement and warehousing management services are provided by Crown Agents under the CHASE-OT contract. Confidence that this arrangement offers value for money comes from the fact that Crown Agents won the contract through a competitive tender process.
D. What measures can be used to assess Value for Money for the intervention? / Beamon and Balcik (2008) divide performance metrics in humanitarian relief chains into three categories: resource performance; output performance; and flexibility performance. An indicator will be employed for the latter two categories: / Output performance: time from date of request to delivery at first point of distribution. / Flexibility performance: number of different types of items held in stock or subject to a manufacturer framework agreement (precise indicator to be developed following the reviews of the NFI and deployment stockpiles and the establishment of the agreements for rapid access to goods, equipment and materials that we will not hold directly). / Additional quantitative indicators will be developed to measure the quality of the Central Register and Global Mapping of Emergency Stockpiles System as part of the review process and in the design of any programme to follow up agreed recommendations. / Going further, an addition outcomes metric will be employed, which indicates the benefits received by the recipient (capturing appropriateness, quality and timeliness): Recipient satisfaction, measured by a survey 6 months after the intervention (precise indicator to be developed as part of the evaluation process for individual humanitarian responses).
E. Summary Value for Money Statement for the preferred option / Option 2+ is the preferred option. Value for Money is delivered by utilising the services of the CHASE OT Procurement Team to deliver both the core stockpile management and deployment services under the Humanitarian Emergency Operations Support Services project (which was subject to a fully competitive procurement process) and the additional series of reviews, for which individual Terms of Reference will be agreed in each case with the Humanitarian Response Group in CHASE. / Each of the reviews will lead to a series of recommendations for the CHASE Humanitarian Response Group. Subject to agreement to any recommendations a programme of follow up work will be designed but all future procurement will be subject to public procurement rules and will meet best practice standards.

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / This programme will draw on, the existing relationship with CHASE-OT for the delivery and management of the services and activities needed to deliver the proposed interventions (e.g. for procuring and maintaining stocks, managing warehousing and undertaking the defined reviews and supporting any follow up work needed). Many of the inputs needed to deliver the intervention are already in place as a part of the existing Humanitarian Emergency Operations Support Services contract which was let following a competitive tender exercise (i.e. the HEOSS includes a comprehensive logistics/procurement team with plans to develop new arrangements for the DFID stocks, humanitarian advisers and a full management and accounts package). / The existing logistics/procurement team in the UK Government’s CHASE Operations Team has a proven track record of delivering complex and robust support for the delivery of ‘in-kind’ humanitarian support and for providing extremely effective support for the deployment of and support to DFID teams in the field.
B. How does the intervention design use competition to drive commercial advantage for DFID? / Competition driven through the establishment – following open competition as per public procurement rules and best practice – of relationships with suppliers (eg for VMI etc) will be mediated through the CHASE OT and through open procurement for materials and supplies that are held in the stockpile. Suppliers identified through the Rapid Response Facility process will be invited to participate in these procurement processes to formalise any agreements that need to extend beyond the EU Procurement Directive thresholds.
C. How do we expect the market place will respond to this opportunity? / The primary opportunity that will be open to the market will be for the additional items that we want/need to bring into our stockholding or where we want to establish alternative, guaranteed, arrangements with suppliers. Through outreach, as part of the development of the Rapid Response Facility, it is clear there is a strong appetite from the potential suppliers of humanitarian NFIs to see their products held in DFID stocks and/or to develop alternative supply chain arrangements.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The key cost elements that affect the overall cost of the programme are (i) the cost of warehousing and maintaining the DFID stockpiles and (ii) the indicative cost of the additional materials that will be added to the existing stocks following the reviews of needs and new and innovative products and technologies. Both elements have been and, where a refresh is needed, will be subject to open competition that follows public procurement rules and best practice. Costs will be passed on to DFID without any additional procurement/management fees beyond those already included in the Humanitarian Emergency Operations Support Services (HEOSS) contract. Value is added by the procurement process being delivered through CHASE-OT by an experienced and tested logistics team that is subject, through the HEOSS contract process, to on-going review following individual responses and a robust annual review process managed by the Humanitarian Response Group in CHASE. / In addition to the significant costs of managing, maintaining and extending the DFID humanitarian stocks there will be a number of low value reviews that will be delivered through the CHASE-OT team. The Terms of Reference, scope and specific cost of each of these reviews will be agreed with CHASE-OT prior to commencement.
E. What is the intended Procurement Process to support contract award? / The programme will not require separate contract award. The services needed to deliver the project inputs will be delivered through the existing agreements and resources in the contract with Crown Agents for the provision of CHASE-OT services. As part of that contract CHASE-OT will manage the key elements of this programme (eg warehousing, direct procurement of equipment and materials and the development of a range of agreements for the supply of equipment and materials (eg through Vendor Managed Inventory, supplier and production agreements etc) following open competition that follows public procurement rules and best practice.
F. How will contract & supplier performance be managed through the life of the intervention? / The contract performance will be managed as a core component of the Humanitarian Emergency Operations Support Services (HEOSS) contract. As part of the management arrangement for that contract a Partnership Board has been established to oversee the ongoing management of the CHASE-OT contract including the work of the supply chain management/logistics team. This Partnership Board will meet on a quarterly basis to discuss progress, performance and any other issues arising. The Board will comprise the SU and CHASE Senior Responsible Owners (SROs) for the contract, the Crown Agents Commercial Director and Crown Agent’s Project Director. / Additionally the Crown Agents Project Director will convene a leadership meeting with the CHASE SRO and SU SRO separately, on a monthly basis. The Crown Agents Commercial Director will be available to attend these meetings on a regular basis as required. Weekly meeting of the Humanitarian Response Group and CHASE-OT leadership groups will discuss and resolve any day to day issues. / The performance of the project will be subject to an Annual Review process led by the CHASE Humanitarian Response Group with a formal review after 30 months that will also consider the case for an extension beyond the initial 3 years based on an analysis of performance by the CHASE-OT team. The Annual Review and 30 month review will also be informed by Project Completion Reports produced for individual humanitarian interventions undertaken during the project period.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / N/A
B. Value for money through procurement / N/A

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The costs of the programme are detailed in the table below, with indicative budget provided for years 4-5. The budget profile reflects the financial year breakdown (with Budget Year 1 covering the period 1 September 2012-31 March 2013). Costs have been derived from the existing and known costs of warehousing, maintenance and warehouse labour and materials under a previous programme and in line with existing contractual commitments. Accurate forecasting of these elements will be delivered through on-going engagement with the CHASE-OT team delivering the on-going and predicable elements of the programme. / The cost of purchasing additional equipment, materials and supplies to enhance the capability and coverage of the stockpile are indicative and will be subject to the reviews in budget lines 4, 5 and 6. / The costs of implementing any follow up programme to improve the international system (budget lines 12 and 14) will need to be revised and re-profiled in the light of recommendations agreed following the reviews. Accurate forecasting of these elements is not possible at this stage but the indicative figures included in the budget reflect current expectations of absorptive capacity and potential appetite for engagement by external partners. / Input Budget Year 1 Budget Year 2 Budget Year 3 Indicative Budget Year 4 Indicative Budget Year 5 Comments / 1 Warehouse rent(s) and utilities 150,000 274,000 274,000 274,000 274,000 Current UK and UAE locations. / 2 Maintenance of equipment and supplies 30,000 50,000 50,000 50,000 50,000 Vehicles and Comms/I.T. / 3 Warehouse labour and materials 140,000 208,000 208,000 208,000 208,000 Inc. supplier management, regulatory costs and training. / 4 Review of current DFID NFI stockpiles and refresh of stocks 0 0 0 0 0 Costs already contained in CHASE-OT contract / 5 Review of current DFID deployment support stockpiles and refresh of stocks 0 0 0 0 0 Costs already contained in CHASE-OT contract / 6 On going reviews of NFI products and deployment support equipment (with recommendations for inclusion of new/additional materials in stockpile). 12,000 12,000 12,000 15,000 15,000 Establishment of routine review process for new NFI and deployment support process. / 7 Purchase of additional products, materials, equipment for enhanced stockpile(s) 258,000 2,206,000 2,086,000 350,000 350,000 Indicative cost only. Will be subject to agreed recommendations of reviews at 4, 5 and 6. / 8 Establishment of agreements to enable rapid access to goods, equipment, materials not held in DFID stockpiles (eg Vendor Managed Inventory agreements) 0 0 0 0 0 Costs already contained in CHASE-OT contract / 9 Review of stock location with options to add or subtract regional locations 0 0 0 0 0 Costs already contained in CHASE-OT contract / 10 Support to NFI innovators to promote understanding of humanitarian needs 20,000 20,000 20,000 20,000 20,000 Provision of advisory service for innovators to help inform the design and development of new products for humanitarian use. / 11 Review of international stockpile monitoring systems (e.g. OCHA) 0 30,000 0 20,000 0 / 12 Support to improve international stockpile monitoring systems 0 150,000 150,000 150,000 150,000 Indicative figure only. Subject to outcome of review in budget line 11 and agreement to any recommendations / 13 Review of current standards (and current levels of compliance with them) for shelter materials and other NFIs. 0 30,000 0 20,000 0 / 14 Support to improve current standards for shelter and NFIs and compliance systems 0 100,000 100,000 100,000 100,000 Indicative figure only. Subject to outcome of review in budget line 13 and agreement to any recommendations. / Sub-total Total 610,000 3,080,000 2,900,000 1,151,000 1,111,000 / 15 Contingency @ approximately 10% 61,000 309,000 290,000 115,100 111,100 / Total 671,000 3,389,000 3,190,000 1,266,100 1,222,100
B. How will it be funded: capital/programme/admin? / Programme; associated costs of the existing CHASE-OT contract not included in the programme will also come from programme costs and will be separately managed by CHASE HRG.
C. How will funds be paid out? / Funds will be paid out in arrears through the same mechanism used for the Humanitarian Emergency Operations Support Services (HEOSS) contract.
D. What is the assessment of financial risk and fraud? / The risk is considered very low. Crown Agents are one of DFID’s three approved procurement agents and have in place stringent anti-corruption and anti-bribery policies and practices; a statement of Crown Agents policies in these areas is at http://www.crownagents.com/Corporate-Social-Responsibility.aspx. The provision of the services being supplied under the Humanitarian Emergency Operations Support Services contract, which will provide the bulk of the resources needed to implement the Humanitarian Emergency Procurement Project, were subject to competition and will be overseen through a comprehensive process described in section F of the Commercial case.
E. How will expenditure be monitored, reported, and accounted for? / Expenditure will be monitored through the submission of invoices submitted by CHASE-OT through the HEOSS contract. Invoices are submitted monthly in arrears and are subject to review by the CHASE Humanitarian Response Group. An annual summary of expenditure under the programme, which will also include details of stockpile replenishment paid for as part of individual humanitarian responses, will be produced to inform the Annual Review process.

Management Case

A. What are the Management Arrangements for implementing the intervention? / The intervention will be managed by the Humanitarian Response Group in CHASE. The CHASE-Operations Team (OT), a service provided by Crown Agents, will deliver the core aspects of the programme: broadly the on-going rental of the stockpile warehousing (including labour costs); maintenance costs and a series of relatively low-value review activities without it going to wider competition. This approach has been discussed and agreed with DFID Procurement Group. / The reasoning behind this decision is that the CHASE-OT contract has already been subject to competition; it would be impossible to sensibly separate the warehousing and labour costs from the management of the stockpile (already included in the CHASE-OT contract); and, the cost of individual reviews could be delivered through the systems in place under the CHASE-OT contract for drawing on external specialist support.
B. What are the risks and how these will be managed? / There are limited risks around the management and delivery of the UK stockpiles (which comprise the most significant expenditures under the intervention). The current intervention follows a series of previous projects (Stockpile projects 1 through 5) which maintained the high quality stocks of UK NFIs and support equipment deployed into a range of humanitarian emergency operations using the CHASE-OT supply management and logistics team. Although innovative approaches to alternative procurement processes, such as Vendor Managed Inventories, have not been extensively used in previous stockpile projects they are a standard industry practice and CHASE OT will initially pursue a conservative approach to ensure these approaches meet our needs. / The scale of ambition to drive up the quality of procurement in the overall humanitarian system necessitates a larger risk appetite. Success is contingent on the UK’s ability to influence OCHA, cluster leads and other partners. Partners may not be committed to delivering real change. / The appetite of OCHA and other international partners for changes in the international procurement process have not been tested at this point. Anecdotal evidence suggests that there is scope and appetite for a well designed intervention but the risk will be mitigated by thorough investigation as part of the review process. For each of the low value reviews detailed Terms of Reference will be agreed in advance between CHASE-HRG and CHASE-OT. The recommendations of each review will be agreed by CHASE-HRG before further resources are committed.
C. What conditions apply (for financial aid only)? / N/A.
D. How will progress and results be monitored, measured and evaluated? / Given there is a strong evidence base for the approach DFID is taking – the focus of evaluation will be on the success of the utilisation of the UK stocks. There will be an internal review of the programme after 30 months. Specific indicators for the progress against interventions undertaken following reviews of the UN procurement process will be developed and agreed as part of the process of agreeing next steps. / The use and impact of stocks drawn down from the stockpile will be reviewed as part of the Project Completion Review process for individual humanitarian responses. Ongoing monitoring will be undertaken through the existing CHASE-HRG and CHASE-OT partnership as defined in the contract for the Humanitarian Emergency Operations Support Services contract and in the monthly meetings of the combined management teams.
Lograme / Quest No of logframe for this intervention: 3658871

Annex 1

UK Stockpile Holdings as at 31 December 2012

Stocks held in Dubai

Items	Quantity
50% wool blankets – pressed	8900
High Thermal Blankets	21000
50% wool blankets – raised	36000
Buckets	24000
Shelter Kits	14992
Knives	21150
Pole sets	15002
Tents	3499

Stocks held in the Cayman Islands (Managed by CIRC)

Items	Quantity
Shelter Kits	2620
Knives	4000
Aqua Tabs	9600
Office Tents	3
Plastic funnels	200
Jerry cans	10656

Stocks held in the UK (Kemble)

Items	Quantity
Armoured Vehicles	11
Soft Skin Vehicles	12
UK Road Vehicles	4
Boats	4
Mechanic and Engineering Workshop Equipment	1 pack
10 Person Module	1
+ 10 Person Module	1
Medical Support Module	1
Preparedness Module	1
5 Person Module	1
2 Person Module	1
Comms Stock	1 pack
ICT Stock	1 pack
Personal Response Equipment	1 pack