Business Case and Intervention Summary

ClimAA

Africa-Brazil partnership on
climate-smart agriculture and food security: new tools and new approaches

DFID Brazil, March 2012
CONTENTS

Intervention Summary	4

Business Case

Strategic Case
A. Context and need for DFID intervention	7
B. Impact and Outcome	that we expect to achieve	21

Appraisal Case
A. Generating feasible options	22
B. Evidence Base for the feasible Options	26
C. What are the costs and benefits of each feasible option?	26
D. Measures used to assess value for money	33
E. Summary Value for Money Statement for the preferred option	34

Commercial Case
Indirect procurement
A. Justification of proposed funding mechanism	35
B. Value for money through procurement	35
Direct Procurement
A. Procurement/commercial requirements for intervention	36
B. How competition will drive commercial advantage for DFID	36
C. How we expect the market place to respond to this opportunity	36
D. Key cost elements and how value is added and measured	37
E. Intended Procurement Process to support contract award	37
F. Management of contract and supplier performance	37

Financial Case
A. How much it will cost	38
B. How it will be funded: capital/programme/admin	39
C. How funds will be paid out	39
D Assessment of Financial Risk and Fraud	40
E. How expenditure will be monitored, reported, and accounted for	40

Management Case
A. Management Arrangements for Implementation	41
B. Risks and how they will be managed	42
C. Conditionality	42
D. How Progress and Results will be Monitored, measured and Evaluated	42

References	44
Abbreviations

ABC	Brazilian Agency for Development Cooperation
AIM	Agricultural Innovation Marketplace process
AU	African Union
BBSRC	Biotechnology and Biological Sciences Research Council, UK
BRICS	Development compact linking Brazil, Russia, India, China, South Africa
CAADP	Comprehensive African Agricultural Development Programme
CAISAN	Interministerial Chamber for Food and Nutritional Security, Brazil
CECAT	Centre for Strategic Studies and Capacity Building, Embrapa, Brazil
CGFOME	General Coordination of International Action to Fight Hunger, Ministry of Foreign Affairs, Government of Brazil
CGIAR	Consultative Group on International Agricultural Research
ClimAA	DFID Africa-Brazil partnership on climate-smart agriculture and food security (Clima, Agricultura e Alimentos)
CONSEA	National Council for Food and Nutritional Security, Brazil
DFID	UK Department For International Development
Embrapa	Brazilian Federal Agricultural Research Corporation
FAO	United Nations Food and Agricultural Organisation
FUNARBE	Fundaçao Arthur Bernardes
G20	The Group of Twenty Finance Ministers and Central Bank Governors
GDP	Gross Domestic Product
GDPP	Global Development Partnership Programme
GOB	Government of Brazil
GPD	Global Partnerships Department, DFID
IBGE	Brazilian Institute of Geography and Statistics
IBSA	Development compact linking India, Brazil and South Africa
IDS	Institute of Development Studies, UK
IFAD	International Fund for Agricultural Development, Rome
IFPRI	International Food Policy Research Institute
IICA	Inter-American Institute for Cooperation on Agriculture
IMF	International Monetary Fund
INCRA	National Institute of Colonisation and Agrarian Reform, Brazil
IPCC	Intergovernmental Panel on Climate Change
IPEA	Institute for Applied Economic Research, Brazil
LAC	Latin America and the Caribbean
M&E	Monitoring and Evaluation
MAR	DFID’s 2011 Multilateral Aid Review
MDGs	Millennium Development Goals
MoU	Memorandum of Understanding
NEPAD	New Partnership for Africa’s Development.
ODI	Overseas Development Institute, UK
OECD	Organisation for Economic Co-operation and Development
P4P	Purchase for Progress programme of WFP
PAA	Food Purchase Programme, Brazil
TRU	Technology Reference Unit
UN	United Nations
UNDP	United Nations Development Programme
WDR	World Development Report of the World Bank
WFP	United Nations World Food Programme
WRS	Warehouse Receipting System
Intervention Summary

## Title: Africa-Brazil partnership on climate-smart agriculture and food security: new tools and new approaches (ClimAA)

What support will the UK provide?
How much funding does the UK expect to provide? / Total: £10.8 million / Period of funding / Three years funded activity. Based on continuous monitoring of progress and an evaluation at the end of that period, further support could be requested for an additional three years.

Why is UK support required?
What need are we trying to address? / Agricultural growth has stagnated in many African countries; hunger remains unacceptably high; and these problems are compounded by climate risks. These three inter-related challenges threaten progress on poverty reduction in Africa: / i. The agricultural productivity challenge: some 75% of the world’s poor are rural, and agriculture remains fundamental for feeding a growing population, reducing poverty, driving growth and ensuring environmental sustainability. Yet global annual growth rates in yields of major grains have declined from 3% in 1980 to 1% today (WDR, 2008). Problems are particularly acute in Africa, affecting growth, livelihoods and food security. / ii. The food and nutrition security challenge: alongside the need to boost food supply, improved access to food is essential to deliver food security and adequate nutrition. Worldwide, one in seven people are undernourished – a quarter of whom are in Sub-Saharan Africa (FAO, 2010) – and by 2050 there will be one third (2.3 billion) more people to feed than today (UN, 2008). Demand for food will increase at a time when competing land uses are growing rapidly, and water scarcity is increasing. / iii. The climate challenge: vulnerable and food insecure people in developing countries are the most exposed and most likely to be seriously affected by climate change and shorter term variability. Higher temperatures, extreme events and changing rainfall patterns will worsen existing challenges of productivity and food security. / What will we do to tackle this problem? / New tools and innovative approaches are needed to respond to these challenges at the pace and scale required. Testing approaches proven in emerging powers like Brazil is one such approach. Brazil has demonstrated that change is possible by transforming its agriculture sector and tackling hunger faster than most countries, e.g. / boosting crop production by 270%, while expanding harvested area only by 45%; and increasing beef exports tenfold in a decade; / extending sustainable, climate-smart techniques like zero-till farming for over 50% of grain production; and using integrated forest-agriculture-livestock systems to reclaim and improve productivity on formerly degraded pasture lands; / harnessing smaller scale ‘family farming’ to supply 50-80% of Brazil’s domestic food staples, and provide three quarters of rural jobs; / providing an assured market for small farmers by channeling the products of family farming to feed nearly 50 million people through schools, public utilities and businesses; / halving child malnutrition in ten years; reducing malnutrition among children under the age of two by two thirds; and halving overall malnutrition in Brazil’s poorest region (the North East). / Many poor countries believe that the experience of emerging powers is more relevant to them than those of developed countries. The remarkable results that Brazil has achieved in agriculture are particularly relevant for Africa, since they took place on poor savanna soils once considered unfit for farming, and in savanna to more arid ecosystems - similar to those found in many African countries. Support for small-scale farming (the dominant production system in Africa) is an integral part of Brazil’s domestic supply strategy and food security model. And Brazil has expertise on crops that matter to poor people, like maize, cassava and sorghum. / Brazil is politically committed to international development, particularly partnerships with Africa, where Brazil has historical and cultural ties. This is reflected in Brazil’s participation in fora such as the G20, UN, BRICS and IBSA. Brazil promotes a distinctive south-south cooperation model, which offers different and complementary tools and partnership opportunities than those provided by traditional donors. / Demand from African countries for Brazilian support on agriculture and food security is high, and Brazil has responded with a political commitment to support Africa and a range of agreements with individual countries. Brazil’s agricultural institutions are well organised, and recent laws (Dec 2010) enable these to function internationally. But Brazilian cooperation is still in its early stages, and would benefit from DFID’s partnership. / DFID has already established policy dialogue and initial activities with Brazil in support of this south-south agenda. Building on successes achieved to date, Government ministries and technical agencies in Brazil wish to deepen their partnership with DFID, where our key contribution would be to: / accelerate and refine implementation so that Brazil is better able to respond to the growing demand from African countries; / sharpen the focus on climate-smart-development; / extend Brazil’s development reach through our flexible funding instruments which will enable Brazil to kick-start and scale up activities; / strengthen the focus on results and learning through monitoring and evaluation; / create strong knowledge and learning tools, to harness and disseminate lessons emerging from the programme, and to use evidence to guide strategy. / Who will be implementing the support we provide? / Our support will be channelled primarily through grants to the Brazilian federal agriculture research corporation, Embrapa; to the World Food Programme’s (WFP) Centre for Excellence on Hunger; and to the International Food Policy Research Institute (IFPRI). These institutions will manage DFID’s funds and involve a broader range of partners including the Brazilian Ministry of External Relations, the Ministry of Social Development and Fight against Hunger, and the UN Food and Agricultural Organisation (FAO). A broader group of actors responsible for carrying out specific activities will be defined in the opening phase of the programme. Recognising that DFID partnership with emerging power nations is innovative, independent analysis of evidence and continuous monitoring will take place throughout the programme. Learning will inform DFID’s broader work with emerging powers. To maintain southern leadership and ensure harmonisation, activities under the initiative will focus on implementing existing agreements between Brazil and individual African countries, and support AU/NEPAD’s Comprehensive African Agricultural Development Programme (CAADP).

What are the expected results?
What will change as a result of our support? / Success in selected countries would be for Brazil’s approaches to actively inform more effective, climate-smart approaches to build food security and reduce poverty through: / more productive, sustainable and resilient agricultural systems, particularly for smallholders, that improve yields and incomes as well as helping reduce volatility around food prices; / better systems for enabling smallholder access to domestic markets and poor people’s access to food. / The programme will generate new joint Africa-Brazil collaborations, lead to new evidence (what may work, where and for whom), and validate and adapt a range of Brazilian innovations in specific contexts. This will strengthen systems and capacity in participating African countries to deliver benefits to small farmers and food insecure populations. It will also generate new tools and new approaches for broader application. / What are the planned Outputs as a result of UK support? / 1. Productivity and Food Security / At least 30 new joint research partnerships linking Brazil with partners in Africa and the LAC region, to generate and inform useful smallholder-targeted products for improving productivity and food security in Africa, supported by capacity strengthening and knowledge exchange processes. / Lesson learning and strategy development on Brazilian systems of local food production and procurement for feeding programmes informing piloting in Mozambique, Malawi, Ethiopia, Senegal and Niger. / 2. Climate-smart development / Climate smart-approaches mainstreamed into 1 above and 3 below. / Climate-smart agriculture approaches being tested in dedicated units in Ghana, Mozambique and Tanzania. / Additional capacity building/training on climate-smart agriculture provided for at least 180 African professionals. / 3. Knowledge management / Robust evidence and practical decision making tools generated to help Brazil’s prospective development partners assess the feasibility of Brazilian innovations in their own contexts. / Flexible support for convening debate and supporting knowledge generating products (e.g. seminars, workshops etc) upon demand. / How will we determine whether the expected results have been achieved? / Continuous, independent monitoring and evaluation of the overall package of support, as well as of individual elements, will be used to refine project activities and measure progress against outputs and outcomes.

Business Case

Strategic Case

A. Context and need for a DFID intervention / 1. Tackling three important development challenges / The intervention recognises that agriculture has stagnated and needs to become more productive in order to reduce poverty; that hunger remains unacceptably high and more food needs to be accessible by poor people; and that these problems are compounded by pressures from climate change and variability. These three inter-related challenges are pressing problems that threaten progress on poverty reduction in Africa. / i. The agricultural productivity challenge / Approximately 70% of the developing world’s 1.4 billion extremely poor people live in rural areas (IFAD, 2011). Rural poverty is particularly high in Sub-Saharan Africa, where nearly a third of the world’s extremely poor rural people live. Of all Africans who are poor, nearly two-thirds live in rural areas (IFAD, 2011). For the foreseeable future therefore, reducing poverty in Africa will need to include action to stimulate rural growth (World Bank 2009). / Evidence shows that the roots of industrial growth lie in pro-poor agricultural and rural development (World Bank 2008), suggesting that pro-poor agricultural development, not export-oriented industrialisation, should be a priority for African states seeking to achieve sustained growth and poverty reduction (Henley, 2012). / Agricultural growth remains a particularly powerful engine of rural growth, with potential to stimulate broader, economy-wide benefits (DFID, 2005; OECD, 2006; World Bank 2008). This is because agriculture has important forward and backward linkages to the local economy on both the production and consumption sides. These links mean that a thriving agriculture sector also supports many urban dwellers – those in precarious informal jobs or who are unemployed – who continue to depend on extended, agriculture-based family networks in rural areas as a safety net (Shepherd, 2010). / Agricultural growth is particularly effective at reaching poor people, particularly women who supply 43% of the agricultural labour force in developing countries (FAO, 2010). Even in today’s rapidly urbanising world, overall GDP growth originating in agriculture is up to four times as effective in raising incomes of the poor as growth generated in non-agricultural sectors, regardless of the setting (Litchfield, 2010; World Bank 2008). Countries that have successfully reduced poverty in recent years initially emphasized support to agriculture and related food security (Action Aid, 2010). / There is extensive evidence that agricultural technology and improved farming systems can provide huge increases in yield growth (World Bank 2008; Evenson and Gollin 2003) and generate positive internal rates of return – an average of 43% in 700 Research and Development projects evaluated in developing countries (Alston et al. 2000), and an average of 55% in sub-Saharan Africa (Alene and Coulibaly, 2009). / The potential exists in sub-Saharan Africa for a step change in agricultural productivity (Beddington, 2010) to drive development. However, this potential engine of growth and poverty reduction has stagnated in many African countries (Markwei et al, 2008). Global annual growth rates in yields of major grains have declined from around 3% in 1980 to 1% today (World Bank, 2008). The difference between the prevailing historical trend and the required higher rate represents a substantial productivity gap. To close this gap, the rate of growth must be 25% faster than the recent trend rate. In Sub-Saharan Africa where grain productivity is the lowest in the world, the rate of growth is 0.85% a year, creating a substantial yield gap (Global Harvest Initiative, 2011; Foresight, 2011). / In the absence of significant investment in developing country agriculture, production increases are largely achieved through increasing the area of land cultivated – rather than intensification on existing planted area. This can cause environmental degradation that undermines long term food security, as farming is pushed into fragile ecological zones (Foresight, 2011). Without the means to sustainably intensify production, the resource base upon which poor people depend is undermined. / Recognising this productivity challenge, AU/NEPAD has set a stretching target of 6% annual growth in agriculture through the Comprehensive Africa Agriculture Development Programme (CAADP). This framework hopes to make Africa a strategic player in agricultural science and technology; and instill a culture of environmentally sound and sustainably managed agriculture in Africa. But despite a pan-African political commitment to this agenda, the CAADP targets for agricultural growth remain elusive for many countries. / ii. The food security and nutrition challenge / Worldwide, close to 1 billion people (1 in 7) are undernourished – around a quarter of these are in Sub-Saharan Africa. A further 1 billion are micro-nutrient deficient (World Bank, 2008; FAO, 2010). Only 58 out of 118 countries are likely to achieve the MDG 1 hunger target and 20 countries have made no progress at all. Undernutrition is estimated to cost developing countries up to 3% of their annual gross domestic product (World Bank, 2008). The impacts of food insecurity are intergenerational. Under-nutrition in infancy has permanent consequences and affects capacity for work in adulthood, reducing future earning capacity by up to 10%. Food insecurity is linked to many other challenges facing Africa, including high prevalence levels of HIV and infectious disease, gender inequalities and some of the worst global impacts of climate change. / Food and nutritional security only exists when people have access to food and can afford food (Wiggins et al, 2010). Many agriculture-dependent, food insecure countries are landlocked and/or have high trade-related costs. Investment in food production where local consumers are is often the most economical way to boost access to food and build sustainable long-term food security (FAO, 2010). This is particularly the case for Sub-Saharan Africa where 80% of the population is fed by local agriculture (Gueye et al, 2007), and where farmers are able to compete successfully with food imports (World Bank 2010). Hence, NEPAD’s strategy is to increase both the amount and quality of locally produced food as a route to strengthening food security. / By 2050 there will be an estimated 2.3 billion more people to feed - one third more than today (UN, 2008). Population growth is highest in sub-Saharan Africa. Demand for food will increase at a time when competing land uses are growing rapidly, and water scarcity is increasing. These trends place upward pressure on food prices and on further deforestation to expand crop area (Foresight, 2011). / iii. The global climate challenge / The backdrop against which the first two challenges are played out is one of existing climate variability and risk, expected to worsen as global temperatures rise. Populations in the developing world, which are already vulnerable and food insecure, are amongst the most exposed to climate risks and those likely to be the most seriously affected. The substantial increase in food production that will be required to meet global demand must therefore be achieved through a significant transformation in agriculture while responding to climate change. / Agriculture is extremely vulnerable to climate change and shorter term variability, particularly in developing countries in the tropics. Climate change is expected to bring higher average and peak temperatures, more severe and frequent extreme weather events, changes in rainfall distribution and shorter growing seasons in many areas (IPCC, 2007). Such changes have the potential to significantly reduce both long-term productivity of crops upon which poor people depend, and the likelihood of short-run crop instability and failure (Cline, 2007; Nelson et al, 2009; Lipper et al 2010). Countries in Sub-Saharan Africa are likely to experience yield losses of between 5 and 20% by 2050; lose up to 9% per cent of potential agricultural land by 2080; experience more than 40% increase in food insecurity; and have amongst the lowest capacities to adapt (Fischer et al 2002; Lobell et al 2008; Müller et al, 2009). This will expose more people, more frequently and for longer periods to threats to their livelihoods and their food security (FAO, 2005; World Bank, 2009a). / Agriculture is also a major contributor to climate change, responsible for around 10–12% of emissions excluding the impact of deforestation associated with land use change (IPCC, 2007). There is considerable scope to reduce emissions from agriculture by changing farming practices and using new technologies (Beddington, 2010). Analysis at a global level suggests that 60% of emissions in the sector could be eliminated (Khan and Zaks, 2009). / Agriculture’s role as both a cause and a victim of climate change therefore requires a response that includes concerted efforts both to mitigate climate change through reduced agricultural emissions, and to adapt to continued and inevitable climate risks (Stern, 2007). Both are possible through ‘climate smart’ approaches to agriculture (World Bank, 2009b). / A DFID review of evidence shows that environmentally sustainable and climate-resilient smallholder farming practices have demonstrated significant benefits, (e.g. carbon sequestration, reduced flooding and siltation and reduced expensive and damaging famine events and emergency responses), providing ‘a strong economic justification’ for supporting their promotion (Whiteside, 2011). Some, but not all, of this evidence is described as robust, and there is a need for more independent collection and assessment of evidence. / The review concludes that DFID should support such approaches, carry out robust monitoring and evaluation of the results within different contexts and identify approaches that appear most effective at encouraging agricultural transformation (Whiteside 2011). ClimAA aims to respond to this agenda. / Effective climate-smart practices already exist and are recommended for developing country agricultural systems. But new initiatives are needed to enable smallholders to make the transition to climate-smart agriculture, fill data and knowledge gaps, develop locally appropriate technologies and methodologies, and strengthen institutional capacity to improve dissemination of climate-smart information and coordinate farmers (Lipper et al 2010). / 2. Small scale family farming as a focus for change / Evidence suggests that small scale family farming offers a natural focus for solutions to address the challenges above and to act as agents for change. Small mixed farms continue to feed most of the world’s people (Herreo et al, 2010), and solutions that work at a small scale will offer potential for larger-scale applications. / Support for small scale farmers was endorsed by world leaders at the 2010 UN MDG Summit, who recommitted to “Supporting small-scale producers … to increase production of crops and livestock; and “Increasing the sustainable production and augmenting the availability and quality of food …for developing countries.” / The objective is not to ‘trap’ small farmers in agriculture, particularly in more marginal areas. Rather, the aim is to climate-proof farmers against risk and vulnerability and to avoid subsistence traps. This builds on evidence that small farms show a comparative advantage in: / enhancing productivity: small farms can produce more output per unit of land than large farms (Litchfield 2010), particularly in scenarios with large imperfections in land and labour markets (World Bank, 2008), such as those prevailing in many African countries; / providing incomes and food security and reducing poverty for large numbers of people in the absence of sufficient non-farm job creation in rural and/or urban areas (Von Grebmer et al, 2009); / readily adapting to changing environmental conditions, avoiding ‘lock-in’ to carbon dependent inputs and supply chains, and adapting effectively to the increasing effects of climate change (World Bank, 2008; Herreo et al, 2010). / A systematic review of evidence (Whiteside 2011) highlights a range of benefits delivered by environmentally sustainable and climate-resilient smallholder farming practices, and recommends that DFID support, test and promote these in different settings. Development of such technologies and farming systems offers a potential triple win on the three challenges of productivity, food security and climate change set out above. / 3. Brazil’s potential to support progress on climate-smart agriculture and food security in Africa / DFID already works directly with African countries on the inter-related challenges set out above. But new tools and innovative approaches are needed to achieve results at the pace and scale required. Crucial to this effort, is working with ‘emerging power’ nations such as Brazil, India, South Africa and China. These countries are transforming prospects for development in terms of: / their experiences, that many developing countries believe are more relevant than those of developed nations; / the scale and growth of their financial flows to developing countries; / their impact on global issues like climate change and their influence on the international system. / The Global Development Partnerships Programme (GDPP) is DFID’s first systematic engagement with emerging powers and aims to harness positive development outcomes from their engagement with developing countries. As part of this, DFID is working to strengthen Brazil’s south-south partnerships, to / enable African countries to adapt promising new tools and approaches proven in Brazil to their own contexts. / Brazil is an obvious source of learning for African countries, having achieved impressive results on tackling its own domestic development issues, including: / Growth with less poverty and inequality - Brazil is the only country among the BRIC nations that is managing economic growth while decreasing social inequality. Poverty was reduced by 12 million over 5 years (IPEASTAT, 2011). Moreover, Brazil’s per capita income grew an average of 1.8% faster than its GDP in 2003–09 (World Bank/IPEA, 2011). / Increased agricultural productivity for both large and small farmers – in less than 30 years, Brazil has transformed itself from a net food importer into an agricultural superpower with little government subsidy: / since 1976, crop production has increased by 270% from around 40 to 145 million tons (2010), while harvested area has expanded only by 45%; / the value of Brazil’s crops grew 365% between 1996 and 2006. Brazil increased its beef exports tenfold in a decade (Albuquerque and Da Silva, 2008). Also see Box 3. / Climate-smart techniques that reduce emissions from agriculture and improve the resilience of crops and farming systems. This includes sustainably intensifying land use through integrated forest-agriculture-livestock systems; recovery of degraded pasture lands; biological nitrogen fixation; treatment of animal wastes; and expansion of zero-till agriculture (today, Brazilian farmers use zero-till farming for over 50% of grain production). / Lower hunger and better nutrition - hunger has been tackled faster than in many countries (Box 4). In ten years, child malnutrition in Brazil halved from 13% to 7%, malnutrition among 0-2 year olds reduced by two thirds, and overall malnutrition halved in the North East - Brazil’s poorest region (CONSEA, 2009). / These results show particular benefits for small farmers. From 2002 to 2008, Brazil’s family farming support programmes helped to reduce poverty of smallholder farmers by 37%, boost average incomes by 30% through better access to staple grains markets, and improve access to food for at-risk populations (CONSEA, 2009; UN, 2011). Evidence of impact of Brazil’s local procurement approach (PAA) is well documented, e.g: / increase in cultivated area, product diversification, and market use of previously non-traded products; / increased employment for rural farm workers; / investments in product quality and in productivity-enhancing technologies; / better prices for producers with limited bargaining capacity and market access; / better farmer management of risk, and protection from price and demand volatility; / community participation in associated health, nutrition and education services; and / stronger farmer organisations and production systems, and stronger institutional and social ties between State, farmers and communities at risk of food insecurity. / (Barrett, 2007; Consea, 2009; da Silva et al, 2010; Chmielewska and Souza, 2010; CAISAN, 2011). / As a result of this success, demand by African countries for Brazil’s support is high. The successful transformation of savanna soils; the inclusion of expertise on African staples like cassava and sorghum; the focus on integrating small farmers into domestic markets; and the use of family farming to drive Brazil’s food security model all present highly credible and relevant sources of learning for Africa. Strong historic and cultural links and similar eco-climatic conditions mean that Brazilian technology is considered to be easily adapted to African settings. / Brazil has made a clear political commitment to an international development role, particularly in Africa. Brazil promotes a distinctive south-south cooperation model, which offers different and complementary tools and partnership opportunities than those provided by traditional donors. This political commitment to development is clearly expressed in Brazil’s participation in international fora such as the G20 and UN. Brazil’s specific commitments to support African agriculture and food security[1] and to strengthen south-south cooperation are reflected in development compacts such as BRICS and IBSA. / In 2010, almost 60% of Brazilian cooperation was directed at African countries (World Bank/IPEA, 2011). Brazilian development cooperation is presented as different from other emerging power nations like China because it aims to leave ‘a legacy to Africa’ in the form of technology transfer, manpower training, and social programmes (World Bank/IPEA, 2011). Brazil prides itself on taking a demand-based approach that responds to partners’ needs, rather than applying a top-down strategy. / On agriculture, Embrapa is the key implementing agent for Brazil, channelling some 70-80% of Brazilian development assistance (Embrapa 2011, pers.comm). Embrapa supports African agriculture through: / ‘structuring projects’ in countries like Mali and Senegal on improving cotton and rice production; and in Mozambique on strengthening the national agriculture research system, building institutional capacity and validating and adapting agricultural technology originally intended for savanna-type conditions in Brazil (with support from Japan and USA); / an Agricultural Innovation Marketplace process to develop new Africa-Brazil research collaborations, co-designed and co-funded by DFID (See p14); / technical training in Brazilian systems delivered through Embrapa’s Centre for Capacity Building and Strategic Studies (CECAT) in Brasilia, launched in 2010. This delivered training to 224 technicians from 60 countries in 2011 (Embrapa, pers.comm). / On food security, UN agencies endorse Brazil as a partner for developing countries. WFP based their Purchase for Progress (P4P) programme on Brazil’s PAA local procurement system, and chose to launch a new Centre of Excellence on Hunger in Brazil in 2011 to help other developing countries learn from and adapt Brazil’s approach. FAO has formally certified Brazilian food and nutritional security programs at the international level as successful experiences to be shared within the scope of emergency and humanitarian programs. / The Brazilian Government (GoB) has signed an MOU with the UN to implement its initiatives through FAO and WFP. Based on Brazil’s PAA food purchase programme, the GoB has developed a new ‘PAAfrica’ (Purchase from Africans for Africa) initiative to pursue joint learning and piloting with Mozambique, Malawi, Ethiopia, Senegal and Niger, based on their formal agreements with Brazil for cooperation. They all have high levels of poverty (from 44% in Ethiopia to 70% in Malawi) and food insecurity (from 17% in Senegal to 41% in Ethiopia) according to IFAD. PAAfrica will also involve Haiti as a learning partner, with whom Brazil has piloted a range of development support on agriculture and food security. / PAAfrica will fund improved local smallholder production systems to supply food assistance programmes (particularly school feeding). Based on Brazil’s model, the assured market of PAA-type systems aims to provide sufficient income for farmers to improve their production networks and overcome entry barriers to staple grains markets (e.g. Barrett, 2007). The Program aims to develop small-scale projects and assess local capacity to scale these up in partnership with FAO and WFP. To build sustainability and lasting impact, multi-stakeholder dialogue will seek to implement a strategy to ensure continuity of food supplies to at-risk groups. / 4. DFID’s comparative advantage in supporting Africa-Brazil cooperation / The Brazilian Government still faces big challenges in absorbing high levels of demand from Africa. Brazil’s footprint is less developed outside its traditional Lusophone country partners, where language differences affect the ease of deploying technical assistance. Brazil’s international cooperation agency (ABC) also lacks the capacity and autonomy of longer-standing development agencies, and can experience difficulties in accessing flexible funding to implement programmes that will make an impact on development at the pace and scale needed in African countries. / DFID is well-placed to help Brazil improve its development impact. DFID acknowledges that Brazil has its own model of development and ‘horizontal’ ways of working, based on south-south cooperation, and existing commitments to partner with specific African countries. The Brazilian government and technical institutions in turn recognise UK (governmental and non-governmental) expertise in development, and DFID’s offer of genuine partnership in which ideas are developed on an equal footing. / Brazil’s agencies are already partnering with DFID to provide technical assistance to Africa in the fields of social protection, deforestation monitoring and smallholder agriculture (Figure 1). This includes the co-design and funding of an Africa-Brazil Agricultural Innovation Marketplace process to competitively fund collaborative projects between African And Brazilian institutions, launched in 2010 (Box 5). Our work with Brazil feeds into and informs DFID’s broader work with other ‘emerging power’ countries, and provides lessons on the potential for delivering development impact through support to South-South partnerships. / Figure 1: DFID’s existing support to 2011 / Building on successes achieved to date, Government ministries and technical agencies in Brazil wish to deepen DFID’s partnership engagement through an expanded set of Africa-Brazil initiatives addressing integrated agriculture, food security and climate change challenges. These include adding value to existing/planned programmes (e.g. PAAfrica), and setting up new initiatives. In all cases, initiatives have been developed by Brazilian institutions, based on demand expressed from Brazil’s African cooperation partners, and incorporating advice from DFID. The approach is therefore strongly rooted in southern leadership. / In supporting Brazil’s south-south cooperation effort, Brazilian partners identify DFID’s added value as: / facilitating learning with Brazil’s identified partners (e.g. funding study missions and learning events) to inform approaches; / offering international experience and lessons learned as inputs to programme design; / helping Brazil’s African partners to assess the feasibility of Brazilian approaches in their context, pilot approaches and adapt locally-suitable solutions; / strengthening African capacity to deliver joint partnerships with Brazil; / applying flexible funding instruments to kickstart and boost south-south processes; / sharpening the focus on climate-smart development approaches; / building the evidence base of what may work where and for whom, to guide Brazil’s strategy; / advising on monitoring and evaluation (M&E) to strengthen the focus on results; and / enabling dissemination of Brazilian approaches to a wider audience. / The political and institutional framework for a deeper UK-Brazil partnership is set out in a Memorandum of Understanding (MoU) on Global Development signed by Brazil and the UK in June 2011. This partnership aims to draw on Brazil’s assets to (a) deliver impact in low income countries; (b) influence the international system and; (c) strengthen global public goods. The proposed programme on climate-smart agriculture and food security (ClimAA[2]) aims to contribute primarily to areas (a) and, to a lesser extent, (c) of this framework. / 5. Our proposed approach / Working with African countries that Brazil has identified as cooperation partners for climate-smart agriculture and food security (Figure 2; Table 1), ClimAA seeks an outcome in which uptake of Brazil-influenced approaches enhances food security by boosting productivity, improving access to food and encouraging a climate-smart approach to development. / The heart of the programme’s approach is to build a strong partnership that recognises and maximises the respective strengths of Brazil’s agencies and DFID. The outcome of this partnership should be a programme that has greater impact than similar programmes carried out by either DFID or Brazil alone- hence mutual learning is central and built into the design of the programme (principally through output 3 below and M&E). / Figure 2: Map of Brazil’s six main African cooperation partners for ClimAA / Table 1: Profile of Brazil’s six main* African cooperation partners for ClimAA / 1. Niger 2. Ethiopia / Poverty[3]: 65.9% / Climate change: annual rainfall has declined since the 1960s. Climate risks are already one of the biggest challenges to agricultural development, and a change in long-term weather conditions would lead to recurrent crises and food insecurity. / Agriculture: accounts for 40% GDP and 80% employment (IFAD, 2011). Drought has hit agriculture hard and climate change threatens to increase impacts. Some communities have responded by returning to traditional conservation agriculture practices to reclaim formerly degraded lands, with positive results. There are now more than 4.8 million hectares of millet and sorghum being grown in agro-forestry systems. / Food security: Undernourishment stands at 28%; 54.8% of under-fives are stunted (IFAD, 2011). Climate shocks have had large impacts on food security, weakened traditional social coping structures and stimulated cross-border migration. Poverty: 39% / Climate change: drought, a key cause of transient poverty, affected more than half of the population between 1999 and 2004. Agriculture is considered the most vulnerable sector, with climate change projected to reduce staple wheat yields by 33%. The livelihoods of small-scale rain-fed subsistence farmers and pastoralists are the most affected by climate change. (Government of Ethiopia, 2007). / Agriculture: accounts for nearly 43% of GDP and employs more than half the workforce (IFAD, 2011). Ethiopia is highly dependent on the sector for income and food security, and therefore highly vulnerable to climate variability and change. / Food security: Undernourishment stands at 44%; half of Ethiopian under-fives are stunted (IFAD, 2011). Recognising that climate change is likely to exacerbate risks for vulnerable populations, realising food security is a focus of Ethiopia’s National Adaptation Plan. / 3. Senegal: partner in Brazil’s PAAfrica programme 4. Tanzania: partner for climate-smart Units / Poverty: 33.5% / Climate change: Rainfall is unpredictable and serious drought is a regular occurrence, with impacts on the rural majority, particularly in the semi-arid interior. / Agriculture: Senegal is the only partner in the group considered to be ‘transforming’ rather than ‘agriculture-dependent’ (World Bank, 2008). But agricultural production and job creation is lagging with resultant impacts on poor small-scale farmers who comprise 75% of the rural majority. / Food security: A quarter of Senegalese are undernourished; 20.1% of under-fives are stunted (IFAD, 2011). Senegal was hit hard by food price spikes in 2007-08 owing to reliance on imports for 60% of its food needs. This triggered massive investment in agriculture and a single-minded drive for self-sufficiency. Unusually good rain led to a doubling of yields in 2008-09. But gains were localised in the fertile Senegal River Valley, and subsequent climatic variability exposed Senegal’s continued vulnerability to food insecurity (80% of planted area remains rainfed). Poor households throughout Senegal are affected by low yields and high prices (One World, 2012). Poverty: 34% / Climate change: a large proportion of Tanzania’s economy relies on climate-sensitive agriculture. Recent drought and flood events have had major social and economic impacts, with future climate impacts projected to reduce GDP by 2% per year by 2030 and prevent Tanzania achieving poverty reduction targets and its planned timetable for achieving middle income status. Establishing a climate-resilient and sustainable growth model is therefore a priority (Watkiss et al, 2011). / Agriculture: accounted for 24% of GDP in 2010 and employs 74% of the labour force. The government aims to improve productivity and access to markets (Government of Tanzania, 2011). In the absence of climate-smart approaches, this strategy could be undermined by climate change, with maize yields dropping by a million tonnes per year by 2030 in some projections. / Food security: 23% of all households in rural mainland Tanzania are food-insecure (WFP, 2010); 44% of under-fives are stunted (IFAD, 2011). 3% of rural households consumed only one meal a day, compared with 2% of urban households (Government of Tanzania, 2011). / Mozambique Ghana / Poverty: 55-75% / Climate change: Mozambique is the 3rd most vulnerable country to climate change in Africa, with extreme risk linked principally to drought, plus coastal flooding and cyclones. The frequency of climate events is accelerating, with 29 million people affected in the last 10 years (DFID, 2012). Increasing household resilience to climatic shocks is a priority for poverty reduction. / Agriculture: continues to be the largest driver of GDP growth (23%). More than 75% of the labour force is employed in agriculture, mostly through small-scale subsistence farming. Despite high overall GDP growth over the past decade, this has not translated into poverty reduction. Raising agricultural productivity represents the best bet for large scale poverty reduction (DFID, 2012), based on evidence that rehabilitation in agriculture accounted for 75% of poverty reduction achieved between 1996-2003 (World Bank, 2008a). / Food security: Undernourishment stands at 37%; 47% of under-fives are stunted /chronically malnourished (IFAD, 2012), with little change since records began in 1996. Poverty and hunger shows distinct regional patterns, largely due to disparities in access to food and public services (DFID, 2012). Poverty: 30% / Climate change: “Brazil is Ghana’s number one preferred partner on climate change” (DFID Ghana, pers. comm.) / Many key economic assets – the coastal zone, agriculture and water resources – are considered to be affected by climate change, which is a threat to economic output, livelihoods and poverty reduction. Failing to respond to climate change in Ghana could lead to a 3.3 percent decline in real GDP by 2050 relative to the base scenario. Agricultural GDP is projected to decline in the range of 1 and 6.5 percent per year by 2050, with an annual decline in cocoa output (a major economic driver) of 26-39 percent (World Bank, 2010a). 80% of disasters are considered to be climate-related. Ghana’s vision is to ‘ensure a climate resilient and climate compatible economy while achieving sustainable development and equitable low carbon economic growth’ (Government of Ghana, 2010). / Agriculture: contributes 33% GDP and employs nearly half the labour force (IFAD, 2011). Small-scale farmers account for 80% of production and are vulnerable to the impacts of climate change. The improvement of land management practices could ensure the greatest benefits for the poorest smallholders, removing the incentives for deforestation and improving household food security (Government of Ghana, 2010). Some 200,000-300,000 farmers have turned to conservation agriculture practices with positive results (IFAD, 2011), providing good scope for partnership with Brazil. / Food security: Undernourishment has fallen to 8%, but 18% of extremely poor Ghanaians remain chronically food insecure. 28% of under-fives are stunted and 18% are underweight (IFAD, 2011). The potential impact of climate change on the agricultural sector is a major cause for concern for a country that needs a productive population to achieve middle income status. / * NOTE: while these six countries provide the focus for Brazil’s PAAfrica programme (p13) and climate-smart Units (described below), the Agricultural Innovation Marketplace process (p14) will continue to invite competitive bids from all African countries. / Malawi / Poverty: 73.9% / Climate change: Malawi has experienced increasing frequency and intensity of drought and flooding over the last 40 years (Government of Malawi, 2006), with impacts to the exposed and vulnerable rural majority, most of whom depend on agriculture for livelihoods. Growing seasons have shortened in many years and assets eroded by recurrent disasters, threatening yields and food security. / Agriculture: accounts for some 34% of GDP, nearly 90% of total export value, and 68% of employment (IFAD, 2011). Following severe disasters in 2005 that left half the country needing food aid, Malawi has turned its agricultural performance around, based on a central policy of food input subsidy for fertiliser and hybrid maize seed. But maize is intolerant to climatic stresses, and unrelenting cycles of maize have negative impacts on soil fertility and fertiliser dependency (One World, 2011). / Food security: Although overall hunger has fallen from 24 to 15% over the last decade, undernourishment still stands at 29% and more than half under-fives are stunted (IFAD, 2011). This is due in part to the unvarying focus on maize. / Adapting to context / Brazil’s agricultural and food security cooperation systems are still in their early stages. Brazilian institutions recognise that their models cannot be adopted wholesale in Africa: despite facing many similar challenges and demonstrating commonalities listed above, there are inevitably differences in resource availability, social systems, and institutional capacity, e.g. / Size matters: the average family farming[4] unit size in Brazil is calculated as around 18 ha (the 2009 census lists 4,367,902 establishments covering a total of 80 million ha - IBGE, 2009) – compared with <2 ha per smallholder in Sub-Saharan Africa. / Political economy matters: strong leadership drove transformational change in agriculture and food security in Brazil. Change was underpinned by a strong rights-based approach, redefined institutions and multi-stakeholder participation. / With these differences in mind, careful analysis of the success factors that enabled Brazil’s transformation is needed, to inform a proper feasibility assessment of Brazilian innovations in African contexts. The characteristics of particular African farming systems need to be well understood in order to judge where Brazilian approaches are appropriate, what kinds of adaptations are needed, and which approaches are unlikely to work. Brazilian development interventions need to include strategies to overcome blockages, including on political economy issues. / Table 2: Planned Components of DFID support under ClimAA / Component Description / Productivity and Access (to food and to markets) / Output 1i and 2i The Agricultural Innovation Marketplace process described above requires additional funds to: / scale up reach and impact; / engage a broader range of learning from the LAC region to benefit Africa; / introduce a stronger focus on climate-smart innovations; / address capacity gaps in African institutions to help them form effective joint partnerships. / Capacity building activities would occur around annual Marketplace Forum events planned within the existing Marketplace process, which convenes partners for peer learning and proposal development. Benefits to participants would extend beyond Marketplace activities. / Output 1ii Brazil’s PAAfrica initiative described above requires support to enable cross-learning and exchange based on technical visits, meetings, seminars and contributions from civil society (farming associations, cooperatives and social councils). Funds are also needed to strengthen the capacity of government staff to support farmer-led production initiatives. There is a risk that PAAfrica will fail if these learning, adaptation and capacity strengthening elements are not included. / Climate-smart development / Output 2ii Embrapa has requested funds to establish Technology Reference Units (TRUs) in three African countries. Piloting improved crop varieties and farming/livestock systems through the TRU model has been proven to be highly effective in Brazil. Similar well-resourced agricultural research testing stations have also delivered proven results in a range of settings. The proposed TRUs will validate and adapt Brazilian technologies in three different African contexts. The focus would be on developing products for smallholder systems, but approaches tested by TRUs would also have potential for application at scale in larger private sector enterprises. / Output 2iii Embrapa’s new state of the art capacity building facility (CECAT) has begun in the last two years to train developing country professionals on Brazil’s policy approaches and technical agronomic systems. So far the learning packages offered by CECAT have not applied an explicit focus on climate-smart agriculture. Embrapa welcomes DFID’ support in developing a portfolio of training in this area, which would offer synergies with other DFID-supported activities planned above. Support for development outreach and capacity building by Brazil-based institutions is a deliverable under the Whitehall strategy for Brazil. / Knowledge and learning / Output 3i and 3ii Robust evidence and practical decision making tools generated to help Brazil’s prospective development partners to assess the feasibility of Brazilian innovations in their own contexts. This component would also support broader knowledge management, debate and dialogue on Brazil’s development role; and cross learning to inform DFID’s engagement with other emerging powers and support for south-south processes. / Scope to add or extend components / There is scope to continue ClimAA or its constituent elements further than the period covered by this Business Case. Based on results and broader dialogue within the initial three year funding period, DFID will consider options for extending or scaling up promising approaches in existing or new partner countries. If this results in any major changes in the results chain, the logframe will be rewritten accordingly. / In parallel, DFID will continue to scope additional, complementary areas for future collaboration with ClimAA partners. This includes the option for a future joint UK-Brazil (Embrapa) research call on agriculture to benefit Africa which would be the focus of a separate Business Case informed by DFID’s Research and Evidence Division, using similar initiatives such as the UK-India-Gates Foundation partnership launched in 2011 as a reference point. / Delivery Partners / The recommended components are built around budgeted proposals co-developed with the intended implementing partners, who have a proven track record of delivery: / Embrapa is a large organisation widely credited with driving the transformation of Brazil’s agriculture sector. Its approach and achievements are well documented (e.g. Alburquerque and Da Silva, 2008; Bientema et al, 2010), and it has rigorous systems and results for impact evaluation (e.g. Avila et al, 2008; Avila et al, 2010; Avila and Evenson, 2010). Embrapa has strong science partnerships with UK (e.g. BBSRC) and its international division has delivered a well-regarded collaboration with DFID. / WFP scored positively in DFID’s Multilateral Aid Review (2011). WFP based their Purchase for Progress (P4P) programme on Brazil’s PAA local procurement system, and chose to launch a new Centre of Excellence on Hunger in Brazil in 2011 to help other developing countries learn from and adapt Brazil’s approach. WFP offers partnership instruments that help Brazil to consolidate an operational network between countries and apply the experience of UN agencies in Africa. / IFPRI is a leading policy research institution that would bring rigour and independence to analysis and feasibility assessment of Brazilian innovations. / 6. Links to HMG/DFID strategic priorities / ClimAA will help to implement: / DFID’s strategy for partnering with emerging powers for impact in developing countries and on global public goods; / international development elements of our Whitehall strategy for partnership with Brazil, and the UK-Brazil MoU on international development; / action on priority themes for DFID support’s to Africa-Brazil partnerships (agriculture, food security, climate change); / DFID’s strategic priorities to strengthen food and agriculture systems (MDG1) in the context of climate change; / disbursal of UK climate finance; / DFID’s commitment to build resilience in vulnerable countries in order to improve and avoid future crises, and to help people to cope with shocks and maintain a path out of poverty; / broader DFID/UK support to Africa, including regional programmes like the forthcoming Africa-based Centre for Excellence on Climate-Smart Agriculture, and pan-African support for AU-NEPAD’s CAADP; / DFID’s commitment to strengthen partnerships for development (multilateral agencies, national governments, civil society, local stakeholders); / constructive UK engagement with UN agencies (WFP, FAO) on improving effectiveness and impact; / DFID’s country-led approach to development by placing southern partners in the lead; / ongoing work in the G20 on food security involving both developed countries and emerging powers. / Box 1: The agricultural sector In Sub-Saharan Africa: / - employs nearly two thirds of the population, particularly women, and accounts for 20-30% of GDP (World Bank 2008; Oxfam, 2009); / - accounts for 12% of growth, even with low investments in the sector (McKinsey, 2010); / - generates incomes that stimulate rural economies, generates demand for goods and services, leads to improved nutrition, better health, and increased investment in education (Green, 2008). / Box 2: Agriculture-led poverty reduction / - In China, growth in smallholder agriculture had four times the impact on poverty alleviation as growth in other sectors (Fan et al 2010; Godoy 2010); / - In Rwanda, government support to smallholders has led to a 15% rise in agricultural production in 2008 and 2009, and a doubling of maize yields (Obbodo, 2009; Burwell, 2010); / - Ghana will achieve MDG 1 before 2015, where investment in agriculture over the last thirty years has driven an average annual agricultural growth rate of over 5%, an 80% increase in food production per capita and a 50% reduction in child malnutrition (ODI, 2010). / “Food security exists when all people, at all times, have physical and economic access to sufficient, safe and nutritious food to meet their dietary needs and food preferences for an active and healthy life.” / Rome Declaration on World / Food Security, 1996 / “Climate-smart agriculture is agriculture that sustainably increases productivity and resilience, reduces or removes green house gases and helps achieve national food security and development goals.” / (FAO, 2010) / Box 4: How Brazil has tackled hunger / Brazil’s ‘Zero Hunger’ model rests on two main pillars: / 1. measures to increase food supply through family farming, which accounts for 38% of production value (US$32bn), three quarters of rural jobs and some 50-80% of domestic food staples (e.g. cassava, beans, corn, milk, pork and poultry). Farmers receive rural credit (some US$7bn/yr), technical assistance, water supplies in semi-arid areas, and an assured market through: / 2. measures to increase access to food for at-risk populations. Income transfers to around 50 million people are complemented by a Food Purchase Programme (PAA) that channels the products of family farming to feeding programmes: / - school feeding delivers meals to 35 million 0-14 year olds in day-care and schools, and an additional 12 million through youth and adult education programmes; / - public utilities like subsidised canteens serve 100,000 per day; food banks serve 700,000 people; and community kitchens serve 70,000 people; / - a Workers Food Programme delivered by companies, benefits 12 million workers (CONSEA 2009). / Box 3: How Brazil transformed its agriculture / What makes Brazil’s farming revolution remarkable is that it took place in the remote, landlocked Cerrado region on poor soils and in savanna-type and more arid systems similar to those prevailing in many African countries. Once considered unfit for farming by Dr. Norman Borlaug (the ‘father of the Green Revolution’), the Cerrado now accounts for a massive 70% of Brazil’s farm output (The Economist, 2010). / Change was driven by investing 1.66% of Brazil’s agricultural GDP in agricultural research, to develop Brazil’s world class tropical agriculture research agency, Embrapa (Global Harvest Initiative, 2011). Soils were improved at scale, and higher yielding and more resilient varieties successfully developed. / Brazil’s distinctive agriculture model takes a twin-track approach that supports both large agri-businesses (for export markets) and smaller-scale ‘family farming’ (for domestic markets). Brazil’s success supports the conclusion that a combined contribution from both large and small scale farming is optimal for achieving growth, poverty reduction and food security (e.g. Collier and Dercon 2009; Dercon et al 2009). / Box 5: Existing DFID partnership on agriculture / Working with Embrapa and the World Bank, DFID co-designed and funded a ‘Marketplace’ initiative to develop pro-poor, smallholder-based innovations by competitively funding collaborative projects between African institutions and Embrapa Centres. / Within the first year of operation (2010-11), ten Africa-Brazil collaborations were funded, benefiting nine African countries: / - Burkina Faso: using tree species for food security under climate change. / - Kenya: integrated pest management for smallholder cotton farms; low impact grazing to rehabilitate degraded rangeland; ethanol production from sorghum. / - Ethiopia: improved forage grass for smallholder dairy herds; honey production for food security. / - Togo: tackling pesticide contamination of groundwater in vegetable farms. / - Ghana: improved cowpea production for applications in Nigeria, Mozambique, Angola. / - Tanzania: better cotton varieties and pest management. / - Mozambique: better integrated natural resource management.
B. Impact and Outcome that we expect to achieve / Baselines / Baselines will be developed for individual elements of ClimAA. Working with experts in partner countries, Embrapa, WFP and FAO will gather key information on agricultural productivity and food security, as well as climatic vulnerability and impact of farming in partner countries within the scope of funded initiatives. / Embrapa (agriculture lead) and CGFOME (General Coordination of International Action to Fight Hunger, Brazilian Ministry of Foreign Affairs – food security lead) will supply baseline information on their support to Africa on agriculture and on food security. Embrapa currently provides technical cooperation to a range of African countries, and trained 240 technicians from 60 countries in 2011. In 2010, the Brazilian government provided some £60m of humanitarian assistance to around 35 countries. Brazilian development assistance to Africa is in its early stages and accordingly there is not a coherent body of information on real impacts in terms of development indicators. Monitoring and evaluation systems require strengthening, as does understanding of outcomes and results achieved. Through its partnership with DFID, which has strengths in these areas, ClimAA should help Brazil address this evidence gap and provide lesson-learning opportunities for Brazilian agencies so they can strengthen the capacity of internal M&E systems for the future. / Problem / Low agricultural productivity / Vulnerability to climate change / Poor access to food and agricultural markets / Impact / Reduction in poverty manifested through improved food security in participating African countries. / Outcome / Increased uptake of Brazil-influenced approaches, including climate-smart practices, reduce food insecurity by: improving agricultural productivity, improved access to domestic agricultural markets for smallholder farmers, and through better access to food for at-risk populations. / Outputs / 1. Productivity and Food Security / At least 30 new joint research partnerships with Brazil generating useful smallholder-targeted products for improving productivity and food security, supported by capacity strengthening and knowledge exchange processes. / Lesson learning and strategy development on Brazilian systems of local food production and procurement for feeding programmes informing piloting in five African countries. / 2. Climate-smart development / Climate smart-approaches mainstreamed into 1 above and 3 below. / Brazilian climate-smart agriculture approaches being piloted in three African countries through dedicated units. / Additional capacity building and practical training on climate-smart agriculture provided for at least 180 African technicians. / 3. Knowledge management / Robust evidence and practical decision making tools generated to help Brazil’s prospective development partners assess the feasibility of Brazilian innovations in their own contexts. / Flexible support for convening debate and supporting knowledge generating products (e.g. seminars, workshops etc) upon demand.
[1] Declaration of the Brazil-Africa Dialogue on Food Security, Fighting Hunger and Rural Development, Brasilia, May, 2010.
[2] ClimaAA – ‘Clima, Agricultura e Alimentos’ (Climate, Agriculture and Food)
[3] Population living under US$1.25 (Purchasing Power Parity) a day. World Bank data, most recent year available during period 2000-2007; gaps filled with national data (e.g. Tanzania, Mozambique). Debate over the quality and validity of national poverty statistics is acknowledged.
[4] ‘Family farming’ in Brazil is defined according to a range of criteria related to the structure and characteristics of production (INCRA, 1980), whereas ‘smallholders’ in Africa are defined solely in terms of the size of holding.

Appraisal Case

A. Generating feasible options / Theory of Change / The theory of change underpinning this intervention is that populations at risk of food-insecurity in Africa can benefit from collaborations with Brazil. As a development partner, Brazil is in a strong position to assist African countries, given the eco-climatic similarities between the Cerrado region and many African countries, as well as its successful record at increasing food production and reducing food insecurity in a way that incorporates elements of climate-smart agriculture. / The three broad channels through which ClimAA seeks to address food security concerns are around food productivity, access and resilience. Figure 3 below shows how the challenges of productivity and access will be addressed, while Figure 4 sets out how climate-smart measures will be used to strengthen farmers’ resilience to shocks. / Figure 3: Productivity and Food Security Results Chain / Input Output Outcomes Impact / Figure 4: Climate-Smart Development Results Chain / Input Output Outcomes Impact / *Thickness of arrow indicates strength of DFID attribution / Assumptions / Declining agricultural productivity is an important driver of food insecurity: 75% of the world’s poor are rural, and agriculture remains fundamental for feeding a growing population and reducing poverty. Yet global annual growth rates in yields of major grains have declined from 3% in 1980 to 1% today (World Bank, 2008). Through a combination of capacity building and research outputs, ClimAA will aim to bolster local production in participating African countries so that there is a greater and more stable local supply of food. / Access to food and smallholder access to markets: access to food can become very precarious for a number of reasons, some of which are related to local supply. For instance shocks to income or a sudden global price hike can tip vulnerable groups into food insecurity as they can no longer afford to buy essential food. ClimAA will target at risk-groups through feeding programmes, with food procured through small scale farming in order to simultaneously incentivise local production. / Resilience to climatic shocks: exposure of local agriculture to adverse climatic shocks is expected to have serious repercussions on the level, growth and stability of agricultural supply, although the severity will vary by crop and geography. Current projections are that higher temperatures and lower rainfall in parts of Africa, combined with doubling of the population, will lead to a 43% increase in food insecurity. ClimAA will help to bolster farmers’ capacity to deal with such shocks and to employ climate-smart practices, by piloting these in 3 countries as well as training 180 African technicians. The aim is to start building the systems and knowledge at the smallholder level to enable farming to better withstand negative external shocks. / Assumption to move from outcome to impact is that improved evidence and successful piloting will lead to farmer adoption of new approaches and leverage of further investment. Use of new approaches will enhance food security and trigger wider adoption of innovations. / Assumption to move from outputs to outcome is that learning, testing and capacity building leads to uptake and longer term spread of new approaches and innovations. / Problem statement / Food security is caused by combined failures in assuring (1) the supply of food and (2) access to food by at-risk populations. / Assumptions about how Brazilian experiences can help to address the problem: / The supply of food can be increased and made less volatile by improving productivity and better managing climate risks through the adoption of innovations proven in Brazil. / Access to markets for smallholders and access to food by at-risk populations in Africa can be improved by adopting local procurement and feeding programmes demonstrated successfully in Brazil. / These assumptions are supported by evidence of Brazil’s achievements and of the potential to apply lessons successfully in Africa presented in section A.3 of the Strategic Case. / Criteria for generating options / The premise of this business case is that Brazil’s experiences in the areas of agriculture, food security and management of climate risks are likely to be relevant and applicable to African countries. Section A.3 of the Strategic Case provides the evidence for this; the Theory of Change above sets out the expected results chain. To maximise the potential development impact of Brazil’s work in this area for Africa, successful options will be those that meet the following four criteria: / Learning approach - through introducing a pre-programme learning phase into the PAAfrica initiative, as well as knowledge building tools throughout the programme lifecycle. / Flexibility - flexibility in range of tools or outputs and the ability to allocate funding between these as evidence of performance becomes available. / Scale - DFID financing should allow successful interventions to be scaled up to generate a tangible impact and thus create demonstration effects. / Climate-smart – sustainable agricultural production should be based on climate-smart practices where resilience and effective resource management is central. / There are potentially three feasible options which are set out below. In terms of other options that were considered but rejected in the process of generating these feasible options, these included: / a) Providing more direct resources to African countries. This was rejected on the basis that it would not implement DFID’s strategy to engage emerging powers like Brazil as development actors. Emerging powers are already having an impact in other developing countries, especially in Africa, and this impact will only grow in the future. This would also mean that there would be a missed opportunity to bring new tools, approaches and relationships to bear on the tough development challenges facing Africa. / b) Sharing Brazil’s lessons using a different partner whilst trying to achieve the same outcome. Under this approach, DFID would invest directly in African countries, with the choice and scope of the programme determined by DFID itself. The difference between this and business as usual DFID interventions in Africa, is that DFID would try to harness the positive lessons it believes Brazilian approaches have generated in the areas of food security and climate-smart agriculture. DFID would use a multilateral partner, such as UNDP, to co-design and implement the programme. UNDP already has good working relations and experience of implementing Brazilian development programmes. Despite some possible advantages in terms of simpler bureaucracy, this option was rejected on the basis that sharing Brazil’s experience would not be practically possible or politically feasible without engaging the Brazilian Government and its agencies. Moreover, without the endorsement of the Brazilian Government, such a programme would have less impact and questionable legitimacy amongst recipient countries. / Description of feasible Options / Option 1: Do nothing more than DFID is already doing / Option 1 aims to demonstrate the absolute additionality of the programme compared to a baseline of what DFID is currently doing. In this scenario: / Embrapa would continue to implement Agricultural Innovation Marketplace processes, but with less resources for funding joint partnerships (30 less partnerships funded), and no dedicated resources for running training and capacity building activities; / Embrapa would not implement a dedicated portfolio of climate-smart-agriculture training through its CECAT centre; / Embrapa would not create new Technology Reference Units in Tanzania, Mozambique and Ghana; / the Government of Brazil would not include a phase of lesson learning (seminars, courses and field visits) in its PAAfrica programme with Mozambique, Malawi, Ethiopia, Senegal and Niger; / IFPRI would not carry out analysis of Brazil’s approach, nor develop decision making tools for African decision makers; and / broader debate and dissemination of findings on Brazilian innovations would not be implemented. / DFID would maintain its current dialogue with partners, but without accompanying partnership to make this meaningful or impactful. Engagement by Brazil would be likely to decrease in the absence of practical partnership support. / Option 2: Scale up investment to existing Agricultural Innovation Marketplace initiatives / Option 2 aims to present a low ambition option of support to an existing programme. The Africa-Brazil Agricultural Innovation Marketplace initiative was originally co-designed and co-funded by DFID in partnership with Embrapa and the World Bank, and subsequently generated a second Marketplace linking Brazil with the Latin America and Caribbean (LAC) region. This initiative is described in Strategic Case A.3 and A.4. / In this scenario, DFID would provide additional resources to fund 30 additional partnerships through the two linked Marketplace processes, and provide additional funds for running training and capacity building activities to improve the ability of African participants to form effective partnerships with Embrapa counterparts. One practical consideration is that Embrapa has stipulated that the funding mechanism previously used by DFID to channel its support via the World Bank would not be viable for any new funding. New funds would need to be channelled through FUNARBE (Fundaçao Arthur Bernardes), which is Embrapa’s system for receiving Marketplace funds from other partners (World Bank, Gates Foundation, etc.). This Option is therefore not simply business as usual in terms of contracting arrangements. / This Option would generate some additional benefits for improving agricultural productivity, and DFID’s funding could be preferentially targeted towards initiatives that were ‘climate-smart’. This would be a supply-side intervention targeted at agricultural production, and would not harness Brazil’s experience in improving access to agricultural markets or access to food by at-risk populations. In this sense it would only address one of the two commonly-agreed pillars for ensuring food security (supply and access) and would therefore not achieve all desired outcomes and impact as set out in the results chain. / The following initiatives would not be implemented by Brazil in this scenario: / a dedicated portfolio of climate-smart-agriculture training through CECAT; / Technology Reference Units in Tanzania, Mozambique and Ghana; / a phase of lesson learning (seminars, courses and field visits) in the Government of Brazil’s PAAfrica programme with Mozambique, Malawi, Ethiopia, Senegal and Niger; / analysis of Brazil’s approach and development of decision making tools for African decision makers; / broader debate and dissemination of findings on Brazilian innovations and cooperation approaches. / Option 3. Comprehensive package of support with Brazil as a lead partner / This option includes a blend of interventions designed to address both the issues around supply of food as well as access to food and agricultural markets. Mainstreaming climate-smart agricultural practices will also be a critical element under this approach. Key elements of the proposed package are set out in section A.5 of the Strategic Case. These are: / Three new Units to test Brazilian climate-smart approaches to agriculture in Tanzania, Mozambique and Ghana. / Scaled up support for the Agricultural Innovation Marketplace process outlined in Option 2. / Capacity strengthening of developing country participants to deliver Agricultural Innovation Marketplace partnerships with Brazil, as outlined in Option 2. / Training for African professionals in Brazilian climate-smart approaches through CECAT. / Support for Brazil’s PAAfrica initiative through a programme of lesson learning and exchange to inform piloting of Brazilian systems of local procurement and feeding programmes in Mozambique, Malawi, Ethiopia, Senegal and Niger. / Support for analysis, feasibility studies, decision tools, guidance on piloting, dialogue and debate on Brazilian innovations and cooperation approaches. / Increased productivity leading to higher yields. / Higher, more stable incomes / Lower, more stable food prices / 30 new research partnerships focusing on improving food security and productivity amongst smallholders. / Improvement in food security and decrease in poverty. / DFID funding / Lesson learning & strategy development on food production and procurement for feeding programmes. / Improved access to domestic markets for smallholders / improved access to food for at-risk populations / Analysis and decision tools on Brazilian approaches for African decision makers / Brazilian climate-smart approaches tested in 3 African countries. / 180 African professionals given practical training & support on climate-smart agricultural practices. / Minimise adverse impacts of climate change on productivity and predictability of yields and income. / Minimise adverse impacts on food prices and access to food. / Build new cadre of professionals to promote and implement climate-smart approaches. / Avoid increase in food insecurity and poverty as a result of adverse impacts of climate change. / DFID funding
B. Assessing the strength of the evidence base for each feasible option / Table 3 below sets out: / feasible options that address the need set out in the Strategic Case; / the quality of evidence for each option, rated as either Strong, Medium or Limited. / The likely impact (positive and negative) for each feasible option on climate change and environment. / Table 3: Quality of evidence for each feasible Option, and likely impact on climate change and environment / Option Description Evidence rating Climate/environment / risk opportunity / Option 1 / (counterfactual) No further support to Brazil’s development cooperation on agriculture and food security. Medium C C / Option 2 Scaled up support to existing Agricultural Innovation Marketplace Processes Medium B C / Option 3 Comprehensive support with the Government of Brazil as a lead partner Medium B A / A - high potential risk/opportunity / B - medium/manageable potential risk/opportunity / C - low/no risk/opportunity).
C. What are the costs and benefits of each feasible option? / The economic rationale for the intervention is set out below, followed by a summary of evidence and known analysis, including where possible estimates of costs and benefits of the various types of intervention. / 1. Economic rationale for intervention / It has been argued that the persistence of food insecurity in many African countries, arises as a result of: / low agricultural productivity and yields; / i) uncertain access to food, especially during times of scarcity; / ii) poor smallholder access to markets; / lack of resilience to adverse climatic shocks / The economic impact of these factors is significant, and is set out in the following sections. While these impacts affect both large scale and smallholder agriculture in several African countries (World Bank, 2009), evidence indicates that the severity and pervasiveness of impacts is particularly acute for small scale farmers, who are poorer and have fewer assets with which to boost production or to provide a buffer against shocks. It therefore follows that the main focus of ClimAA will be on smallholders, as a way of addressing supply side constraints. / Economic impact of low productivity / Sub-Saharan Africa has the lowest average agricultural grain yields and the highest population growth in the world (FAO, 2008). At national level, this leads to undersupply to the domestic market, with demand often having to be met through imports (or, where populations lack financial means, through food aid). This is an example of large scale market failure. / As a result, since the 1970s, most African countries have become net food importers with escalating food import bills. For those African countries lacking revenues from oil and minerals, paying for this growing current account deficit is becoming a serious challenge. With reserves often already at precariously low levels, a single exogenous shock such as a season of drought or flooding, can be enough to cause serious damage to agricultural systems, causing depletion of reserves and preventing a country from paying for vital food imports. The frequency of emergency food aid programmes in recent years provides evidence of the growing scale of this problem, as domestic agricultural production in several African countries fails to keep pace with population growth. / The high and growing import dependency common across many African countries, coupled with low crop yields, is evidence that food production in Africa is generally price inelastic, meaning that high demand reflected in price signals, often fails to have the desired impact on production levels. At the sub-national level, the situation can be even more serious. High transport costs often lead to segmentation of local markets, making local communities very vulnerable to the vagaries of local agricultural production and leading to severe incidence of food insecurity in particular hotspots. / Small-scale producers, often farming on less than 2 hectares generate over 90% of Africa’s agricultural produce (IFPRI, 2004). Many of these smallholders are likely to focus largely on subsistence production. A significant share of these smallholders will have limited and in some cases non-existent access to finance, coupled with insecure land tenure, lack of collateral and poor access to markets. These precarious conditions mean that farmers often lack the means and incentives to invest in their farms. The net effect of these supply side failures is twofold: / a quantity or supply effect, with weak supply leading to a ‘rationing’ effect thereby directly causing food scarcity and insecurity; and / a price effect, which becomes particularly pronounced during times of scarcity, leading to sharp price hikes which mean that poor populations are simply priced out and can no longer buy food. / The structural economic issues that underlie the low productivity of many African agricultural markets include: / risk averse behaviour by farmers based on rational risk assessment leading to unwillingness or inability to make productive investments in their farms – for reasons including: / informational asymmetries preventing farmers from getting access to finance and insurance; / liquidity constraints faced by smallholders, most notably poor access to finance; and / segmentation of markets as a result of high transport costs isolating and fragmenting local markets. / Impact of poor access to food / Food insecurity is a reality for around 290 million Africans or a quarter of Africa’s population (FAO, 2010). This problem is compounded by: / high global food prices, which are projected to continue increasing in the long-term; / the lowest agricultural yields and highest population growth in the world; and / the projected net impacts of climate change - expected to be negative for most African countries. / Food insecurity has several adverse economic impacts. At the individual/household level, the nutritional impact of inadequate food intake affects an individual’s overall welfare and economic prospects through: / direct loss of productivity for adults; and reduced learning and cognitive performance for children leading to lower educational attainment and diminished job prospects as adults; / higher incidence of illness and disease, leading to greater healthcare costs and loss of income due to time off work; diminished learning ability for children; / reduced lifespan leading to loss of earning potential; / intergenerational impacts from maternal malnutrition leading to greater probability of offspring being stunted and/or suffering from cognitive deficiencies, with resultant increased dependency burden on family income earners. / At the macro/societal level, food insecurity can create costs that have macroeconomic impacts: / populations suffering from prolonged food insecurity can often become internally displaced people or cross-border refugees – the latter placing heavy demands on resources in receiving areas; / heightened food insecurity is often a cause of conflict as well as being a consequence of it. War is predicted to reduce GDP per capita by as much as 63% (IMF, 2007)[5]. A conservative estimate of impact suggests that a year of conflict reduces a country’s growth rate by 2.2%.[6] / food shortages can also have direct impacts on government budgets and on the magnitude of current account deficits. Where governments try to procure emergency food stocks or subsidise food staples, there can be a very significant impact on budget deficits and the current account, often leading to depletion of reserves. / While there are various triggers that can cause food insecurity such as, conflict, weather/climatic shocks, other natural disasters, crop or livestock diseases, fires etc, these should not be confused with propagation channels through which these shocks lead to food insecurity. Correctly understood, these propagation channels can also become mitigation mechanisms through which appropriate interventions can be designed in order to reduce vulnerability of at-risk populations. There are four broad and inter-linked economic transmission mechanisms through which external shocks can lead to food insecurity. There is usually more than one pathway involved leading from an initial shock to a situation of food insecurity, with consumption nearly always being the effect of one or more of the other channels: / Productivity and crop yields - depressed production reduces the availability of food and likelihood of crop surpluses. During these bumper harvests, emergency stocks are often accumulated, which are then drawn down during times of scarcity. / Income - loss of earning power for at risk groups can mean that it is no longer affordable to have an adequately healthy diet. At risk populations may end up replacing foods in their usual diet with cheaper substitutes which do not meet their dietary needs. / Consumption - impaired health and unsanitary conditions as a result of prolonged malnutrition can mean it is not possible to fully utilise the nutritional value of what little food is available. / Food prices - during times of scarcity, the shortage in supply of food is often accompanied by sharp price increases that effectively cut off access for the poor. / Impact of poor access to agricultural markets / Barriers that prevent smallholders from getting their produce to markets and from accessing agricultural inputs are a significant factor behind low crop yields. These barriers include: / poor or no storage facilities; / poor rural infrastructure, leading to high transport costs and times; / poor information about market prices and demand; / high cost of agricultural inputs like fertiliser, seeds and irrigation pumps; / poor access to finance to invest in production. / The outcome is that much of Africa is characterised by small, segmented, inefficient and isolated local markets, where limited demand means that prices drop sharply in response to increases in supply during surplus production seasons. This provides very weak commercial incentives and leads to risk-averse behaviour in which farmers curtail production at a level enough to satisfy local demand. This makes food security of the community very susceptible to local supply shocks. / This is a clear case of market failure, where the equilibrium situation deters investment and expansion of agricultural supply to the detriment of both consumers and producers. / It is possible to reverse this trend. Evidence suggests that where opportunities to access markets and make profits exist, a significant number of farmers are willing to invest in production and increase supply to markets, an example of this is the success of market literacy initiatives, including warehouse receipting. / Impact of weak agricultural resilience to climatic shocks / Climate change impacts are difficult to predict with certainty at the local level, but the net effect on the African agricultural sector is expected to be negative. It has been estimated that on average agriculture yields could fall by as much as 50% by 2050 in parts of Africa, with most countries in the region likely to experience yield losses of between 5 and 20% (Müller et al, 2009). Current projections are that higher temperatures and lower precipitation in parts of Africa, coupled with doubling of the population, will cause a 43% increase in food insecurity. In turn this will lead to a 60% increase in food aid expenditures during the next two decades (Funk and Brown, 2009). Adaptation costs for the agricultural sector as a percentage of GDP are also projected to be the greatest for any region. This is due to low current and projected levels of GDP in Sub-Saharan Africa, combined with high dependence on risky rainfed agriculture (96% of agricultural production relies on rainfall). / Figure 5 below provides a stylised depiction of the impact of detrimental climate shocks on agricultural production in the absence of any climate smart agricultural changes. In diagram a), the curve yc, shows the decrease in output after climate shocks. There are two notable impacts of climate change: / 1) the supply curve yc is lower than the original production curve y; i.e there is a level effect on agricultural production as a result of climate change / 2) the slope of the curve yc also has a lower gradient than the original production curve - this implies that there is also a growth effect, whereby agricultural production grows slower after the onset of climatic shocks. / In Figure 5.b, the dashed curve yA shows the reduction in losses as a result of adaptation measures. However, it is worth noting that yA still remains below the “no climate change” scenario, y – this wedge between curves y and yA represents the residual damages caused by climatic events that cannot be adapted to in the long-term. The kinds of climate smart agricultural measures envisaged here under ∆A would be based on conservation agriculture principles, involving both adaptation measures that increase resilience to drought, reduce erosion and maintain soil fertility as well as practises to better manage natural resources and sequester carbon. / Figure 5: Impact of climatic shocks on agricultural production / a) without climate smart agriculture b) with climate smart agriculture / Output y Output y / residual damages / yA / ∆C C ∆A / yc y c / Time Time / 2. Cost-Benefit Ratios / Table 4 below provides some indicative cost-benefit ratios of various types of intervention designed to address the four sets of issues: / Table 4: Cost-benefit ratios for interventions addressing key market failures / Market Failure Types of activities/interventions Cost-Benefit Ratios / 1. Low agricultural productivity and yields Agricultural research Range from 1:2-17 / Based on survey of research commissioned by Consultative Group on International Agricultural Research (CGIAR, 2006) / 2. Uncertain access to food, especially during times of scarcity Feeding programmes 1:4 / Based on economic analysis of school feeding program done by Boston Consulting Group / 3. Poor smallholder access to markets Warehouse Receipt Systems (WRS) / General “market literacy” initiatives 1:3 (assumes no production constraints) / Based on Common Fund for Commodities WRS programme in Zambia (2002) / 4. Lack of resilience to adverse climatic shocks Climate Smart Agricultural practices based on Conservation Agriculture approach 1:1.4 / Based on estimate derived from DFID business case: ‘ClimateSmart – Scaling-up Climate Smart Agriculture in Eastern and Southern Africa’ / Both the activities and estimates are meant to be indicative. The Government of Brazil (GoB) is likely to decide the exact nature and scope of the interventions on a country by country basis during the inception phase of the program. The cost-benefit ratios are positive in all cases, but refer to particular types of activities. It would be advisable for DFID to appraise and monitor the performance of the activities that are eventually implemented in order to generate an evidence base – ideally cost-benefit ratios - to help the GoB and recipient countries assess the effectiveness of different interventions. / 3. Economic Appraisal of Options / There is insufficient evidence by which to conduct a formal cost-benefit analysis of the three options, however the ratios above provide best estimates of economic return. These ratios should represent an understatement of the actual benefits across all three options as they are based only on the direct impacts on poverty through agricultural measures and do not capture the efficiency gains both to the GoB or DFID as a result of partnership and mutual learning. Therefore, these cost-benefit estimates are supplemented by a qualitative assessment of the relative efficacy of the three approaches in order to better weigh up the entirety of the relative benefits under each option. / Option 1: Do nothing more than DFID is already doing / *Predicted cost-benefit ratio- 1:2 / Under this scenario: / The GoB would continue to implement Agricultural Innovation Marketplace (AIM) processes, but with less resources for funding joint partnerships (30 less partnerships funded). / However, the following elements would not be implemented: climate-smart agriculture training through its CECAT centre; Technology Reference Units in Tanzania, Mozambique and Ghana, a lesson learning phase, IFPRI analysis and tool for African decision makers, broader dissemination and debate. / Efforts to address the market failures outlined in section 1, require complimentary sets of activities. While AIM may produce some partnerships that have localised impacts, the modest scale at which these will be implemented is likely to prevent them from having any systemic effect. Analysis done on CGIAR’s extensive agricultural research has shown that the rates of return on agricultural research are seriously affected when complimentary infrastructure is not in place (Alene and Coulibaly, 2009). Option 1 presents a very similar situation: there is a complex chain of causality from the activities proposed under AIM and the eventual impact on poverty reduction and food security. Addressing the vulnerabilities that lead to food security thus requires a set of complimentary, mutually reinforcing interventions that can collectively cause systemic level change. Such change is by definition complex and is unlikely to be addressed through a modest scale single intervention. For this reason the most conservative estimates of cost-benefit for agricultural research activities have been used as the closest available indicator of the possible economic value of this option. However it must be noted, that as DFID is not investing in this, DFID cannot claim attribution to the benefits- the BC ratios are therefore indicative of the return the GoB can expect. / In terms of leveraging aid efficiency gains, the potential for harnessing mutual institutional learning for both DFID and Embrapa would also be lost. For the GoB, it is very likely it would fail to instigate measures to increase the efficiency and effectiveness of its activities as well as failing to realise the benefits of a learning phase for its subsequent activities. Similarly the UK would lose out on the opportunity to learn first hand from the novel and different approaches to food security pioneered by Brazil. Thus effectiveness gains to both partners would not materialise and African countries would not benefit fully from the potential impacts of well designed and comprehensive programmes. / Option 2: Scale up investment to existing Agricultural Innovation Marketplace initiatives / Predicted cost-benefit ratio - 1:>2-3 / This option seeks to extend on the limited AIM initiative in option 1 to include 30 new partnerships in Africa. The focus of this option would be squarely on addressing agricultural productivity issues. Many of the complimentary measures absent in option 1 would also be missing here. The critical difference with option 1 is that under this option UK funding goes to scaling up the AIM initiatives so they have greater impact in Africa and there may be a greater emphasis on climate-smart agriculture. For this reason the cost-benefit ratio (given as a range here) is considerably higher than that for option 1, lying between 1:>2-3. / In terms of anticipated economic benefits, the scale effect of bolstering the AIM partnerships is much more likely to create demonstration effects and leverage some level of change. However the lack of lesson learning and partnership is expected to constrain the effectiveness of this option. Indeed this option is predicated more on the basis of co-funding than genuine partnership with the GoB. Potentially valuable insights and learning opportunities for both DFID and Embrapa would not be realised under this scenario, potentially reducing the level of the programme’s overall impact. / Option 3. Comprehensive package of support with Brazil as a lead partner / Predicted cost-benefit ratio- 1:>3-4 / This option involves partnership with Embrapa across a suite of complimentary activities that collectively address the issues around agricultural productivity, access to food and markets as well as resilience to climatic shocks. While the costs under this option are higher, the spectrum of issues addressed and the larger scale of intervention is expected to generate more substantial benefits than under either options 1 or 2. / Weaknesses / From an economic perspective, the potential weakness of this approach is that the multiplicity of instruments, may risk doing too many activities in some cases whilst failing to adequately tackle the binding constraints. E.g in a given country a lot of funding could be invested in softer activities around knowledge dissemination and discussion, when the key problem could be lack of access to appropriate agricultural inputs which are seriously depressing production and causing local food shortages. There is therefore a potential risk to the allocative efficiency of this option relative to the others. However the portfolio nature of this option also means that there is the potential to reduce this risk and to increase the programme’s allocative efficiency by reallocating funding across the 6 output areas as evidence emerges of each intervention’s relative effectiveness. / Another possible weakness of this option relates to a potential loss of operational efficiency, at least in the early stages as both Embrapa and DFID get accustomed to the partnership arrangement. There is thus a learning phase within the partnership itself, where progress is slow. However, as the programme progresses, it is expected that this initial phase lays the foundation for more productive partnership which becomes evident over the programme’s life cycle. / Strengths & Benefits / Beside addressing additional issues around access and climate-smart agriculture, there are two further benefits that we would expect to arise from this option which are not captured under the cost-benefit estimate: / 1. Helping Brazil realise its potential as a development partner / One way of seeing Brazil’s current position as a donor is to use the analogy of the infant industry case of a new firm that is entering the market. There is a school of thought that in the marketplace “infant industries” who incur high costs by virtue of being new but who can potentially become very efficient, justify government support. Otherwise encumbent firms dominate the market, simply as a result of first-mover advantage and the market becomes uncontestable, i.e. no new entrants are able to enter and establish themselves. While the analogy to the GoB is meant to illustrate a principle around ‘dynamic efficiency gains’ (efficiency gains that occur over time due to factors such as innovation, R&D etc), it also serves to strengthen the case for DFID partnering with the GoB more than in the market scenario. Unlike a market situation where firms are often rivals competing over finite market share, in the aid industry, the beneficiaries are the millions of the world’s poor. Demand in this case far outstrips the ability of governments and aid organisations to address it. Thus, Brazil as a more effective donor is a win-win situation for all. / 2. Mutual learning and innovation / Econometric evidence tells us that whether we are looking at countries, cities or firms, those that are more exposed to new ideas and people tend to grow faster and be more successful and resilient than those that remain closed. The world’s most successful firms and economic areas, such as Silicon Valley are characterised by this constant appetite for engaging with new ideas and people from across the world, while the world’s most vibrant and productive economies, from New York to Shanghai are similarly characterised by very high degrees of openness and change (measured across various indices such as trade, mobility of labour force, firm entry and exit etc). While the analogy to openness among donors and the UK-Brazil partnership in particular is only illustrative, it helps to contextualise the reasons for the emphasis economists and policy makers place on knowledge exchange and lesson learning from outside. This learning can have very deep impacts and across various channels. For instance there can be efficiency gains as a result of either or both DFID and the GoB learning to do existing activities in a more efficient way. However, exposure to new approaches and ideas can occasionally also lead to innovations, i.e. these are not just about doing things in a different way but are fundamentally about doing new things altogether. In economic terms this is about moving onto a higher production frontier. / In our case, the success of Brazil’s Bolsa Familia (social welfare cash transfer) model is just one example of its potential capacity to generate innovative new approaches. The success of Bolsa Familia, coupled with a similar programme in Mexico, has caused a shift across the global aid industry over the last decade, and led to the development of conditional cash transfer schemes that are now widely accepted and used amongst Western donors. While genuine innovation cannot be engineered, and by nature is difficult to predict, there are nevertheless conditions and environments that are more conducive to such change. A universal condition is openness to outside influences and ideas. / It therefore follows that the programme design under this option should pay careful consideration to how the partnership works, in particular the channels for knowledge and lesson sharing in order to harness mutual benefits. / Summary / Option 3 appears to be the approach that is likely to generate the highest returns. Although it is not without risks, these should be manageable through appropriate mitigation measures. On the other hand, the benefits especially in the medium term are likely to be significant and enduring and would not be realised under options 1 and 2.
D. What measures can be used to assess Value for Money (VfM) for the intervention? / Monitoring and evaluation will aim to track the following VfM measures: / 1. Costs / a. cost per beneficiary reached; or total admin/programme ratio; / b. costs of different types of activity; / c. how indicators for a. and c. progress over programme lifecycle; / d. non-administrative procurement costs. / 2. Benefits / In all cases a suitable base case/or baseline will be critical- examples include the indictors before the inception of the programme, or indicators in another African country or sub-region that has not benefited and which is facing similar food security challenges. / a. Net benefits to recipients- there are two potential approaches: / i) monetise the value of the additional food that beneficiaries are able to access per day multiplied by the number of beneficiaries and the total number of days over which they are food secure compared to base case. / ii) assign monetary values to improvement in nutritional wellbeing of recipients, e.g. through reduction in DALYs, improvement in health proxied by reduction in medical costs etc. Such welfare improvements would be multiplied by the total number of recipients to derive an estimate of the total (net) effect of the programme. / b. Net benefits of increased production- monetise value (or use prevailing market prices) of increased yields to capture effect on productivity and supply as a result of programme compared to base case. / Trigger point: the innovative nature of the ClimAA programme as a test case of working with an emerging power partner needs to be weighed against VfM considerations. Continuous monitoring in years 1-3 will be used to assess and guide the programme strategy and activity mix in order to optimise VfM. We anticipate a lag between initial investments and evidence of impact of up to three years. Therefore, we do not recommend a trigger point for exit within the initial three year timeframe on the basis of monetisable benefits. At the end of three years, evaluation will guide decisions on whether to extend the ClimAA programme for a further three years in order to realise greater impact. If at this time costs remain higher than the quantifiable benefits and an improved results trajectory is not predicted on the basis of available evidence, an exit strategy should be considered.
E. Summary Value for Money Statement for the preferred option / Option 1: Do nothing more than DFID is already doing / * Predicted cost-benefit ratio – 1:2 (applies to GoB only) / Costs incurred: £0 / Option 2: Scale up investment to existing Agricultural Innovation Marketplace initiatives / Predicted cost-benefit ratio – 1:>2-3 / Costs incurred: £2.2m / Option 3. Comprehensive package of support with Brazil as a lead partner / Predicted cost-benefit ratio – 1:>3-4 / Costs incurred: £10.8m / While option 3 involves a significant level of investment from DFID over the course of the 3 years, the returns are expected to be very significant and higher than the benefits expected under the other options.
[5] Average GDP per capita: $1839 for conflict countries, $2997 for non-conflict countries. Data is PPP, averaged from 1990-2006. Source: International Monetary Fund, World Economic Outlook Database, April 2007
[6] Paul Collier at: http://users.ox.ac.uk/~econpco/research/conflict.htm

Commercial Case

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The complexity of the proposed package of support makes it unfeasible for DFID to manage the numerous contracts for inputs of goods and services that this would require. But more fundamentally, DFID’s role is to support south-south leadership of ClimAA, which removes the option for DFID to deliver the interventions directly. / ClimAA will be delivered through the following mechanisms and not-for profit organisations: / Outputs 1i, 2ii and 2iii will be delivered by Embrapa, via an accountable grant from DFID to FUNARBE; / Output 1ii will be delivered by FAO and WFP, via an annex to DFID’s existing core Framework Agreement with WFP, paid into WFP’s Trust Fund for Brazil. This is a fast funding modality that can be taken up by WFP’s Centre for Excellence Against Hunger in Brazil; / Output 3i will be delivered by IFPRI, via an accountable grant from DFID. / Output 3ii will be delivered by organisations to be defined during programme implementation, upon demand. / Consideration was given to the idea of delivering ClimAA through a management consultant, or through a multilateral partner. Despite some possible advantages in terms of less bureaucracy, there are significant constraints to this approach: / there is a risk that international consultants may not fully internalise the political sensitivities and environment the programme needs to operate in and consequently find it difficult to build productive relationships. This would hamper the pace of implementation and not be cost effective in the long term; / a commercial company would incorporate an element of overheads (normally 10-15%) to fee rates as well as a management fee (typically 5-7%) for funding interventions upfront. Overheads associated with the preferred mechanisms are lower – e.g. WFP 7% - which will help to deliver better VfM; / In addition to these factors, the recommended option works through partners approved and trusted by GoB, which is an important part of DFID’s relationship building process.
B. Value for money through procurement / Value for money will be achieved by delivery institutions using a combination of competitive and non-competitive processes. / Where non-competitive processes are used, a negotiated and agreed schedule of prices and rigorous expectation of results will also ensure VfM. / DFID’s 2011 Multilateral Aid Review concluded that WFP demonstrated “a strong corporate emphasis on costs/efficiencies coupled with business model improvements… Drives cost control with delivery partners; and it seeks value for money through local procurement and cost-efficient delivery tools” / IFPRI is regularly subjected to external audit and review. External audit in 2010 found IFPRI to be in full compliance with financial performance standards set by the Consultative Group on International Agricultural Research (CGIAR). DFID is a major core contributor to CGIAR and has confidence in its systems. / A number of additional factors are important for ensuring VfM of support to Embrapa, which constitutes the main investment under ClimAA: / Existing experience of partnership work with Embrapa shows that it manages fiduciary risk to a high level. Embrapa shares the commitment of their donor partners to efficiency and effectiveness. / Following DFID’s support to the Marketplace initiative, other donors such as the World Bank and the Gates Foundation have come on board, demonstrating confidence in Embrapa’s ability to manage resources and deliver results. / Embrapa’s systems have a high level of transparency, with easy access to financial information about donor investments, making VfM easier to assess. / Embrapa’s delivery of Output 1i (Agricultural Innovation Marketplace processes) will use a competitive process through annual Calls for Proposals to identify high quality partnerships between Embrapa and African institutions that will qualify for research grants. Based on DFID’s existing experience as a funder and Steering Committee member of the Marketplace process, a range of organisations are expected to respond to research Calls, and a two stage process will be used to assess quality: (1) initial expressions of interest, followed by (2) full proposal development by shortlisted bidders. This assessment process will use an established scoring system already tested by the Marketplace Steering Committee using experts within each of its member organisations. Scores are combined and reviewed by the Steering Committee, with additional qualitative assessment used to complement quantitative scoring. This process and rigorous grant management will drive Value for Money (VfM). / Continuous independent monitoring and evaluation will be a critical way of identifying risks that could potentially undermine the VfM of ClimAA. As part of this process we will consider commissioning within the second year of implementation a VfM study including recommendations to enhance VfM.

Direct Procurement

A. Clearly state the procurement/commercial requirements for intervention / While DFID will use indirect procurement to deliver all key outputs as set out above, DFID will use competition to directly contract a supplier to carry out independent monitoring and evaluation (M&E) of the overall ClimAA programme. This will drive up quality and drive down costs, and support lesson learning.
B. How does the intervention design use competition to drive commercial advantage for DFID? / The service provider will be selected through competition advertised in the Official Journal of the European Union (OJEU) in accordance with EU Public Procurement Directives. Terms of reference will be clear on the evaluation criteria, balancing quality and cost, and focusing on results and VfM. A standard 80/20 weighting for quality/cost will be applied.
C. How do we expect the market place will respond to this opportunity? / There are a range of organisations supplying M&E services, including those that have global networks and experience relevant for assessing this Africa-Brazil programme. Development programmes working with emerging powers like Brazil and focusing on South-South processes are innovative and popular, providing an attractive option for organisations looking to expand their portfolios into this area. The competition will not affect the market for this type of programme, because the organisations that will express interest in M&E will have a different skill set from those engaged in programme activity on climate, agriculture and food security.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Services will be largely desk-based, focusing on assessment of written material backed up by interviewing. The key cost elements are therefore time and travel, plus overheads. Quality and value will be added by focusing on effective practices and outputs of the M&E service. Travel costs will be controlled through forward planning and good practice guidelines (e.g. negotiation with airlines and hotel groups). / The contracting process will ensure that financial limits are set and the management process will report regularly on performance against Terms of Reference and evaluation criteria.
E. What is the intended Procurement Process to support contract award? / The procurement process will be managed by the Procurement Department of the Finance and Corporate Performance Division of DFID, following standard procedures.
F. How will contract & supplier performance be managed through the life of the intervention? / The contract and supplier performance will be managed through contract design based on: / clear Terms of Reference with measurable outputs and performance indicators; / an agreed delivery plan and a cancellation clause in the event of poor supplier performance; / quarterly planning and reporting process to mitigate and manage poor supplier performance.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The expected cost of ClimAA is £10.8 million over 3 years. If progress is promising DFID could consider additional funding to ClimAA, with necessary revisions to the business case and logframe. As set out in the Strategic Case A.5 (p.19), the design of ClimAA makes it possible to extend funding or add complementary components relatively easy. Equally, M&E should be able to identify any issues that could lead to cost escalation or poor results within the programme lifecycle that warrant a re-evaluation or, in the worst case, an exit from the programme. / As set out in Appraisal Case D2, an evaluation in Year 3 will assess opportunities to extend ClimAA for a further three years, or whether an exit strategy should be followed to terminate at the end of year 3. / Table 5 shows the approximate breakdown of costs by year, which will be revisited once ClimAA begins. / Table 5: Approximate cost profile by year / Cost (£m) 2011/12 2012/13 2013/14 2014/15 / £10.8 0.35 4.15 3.35 2.95 / Table 6 below shows the approximate allocation of funds to individual components of ClimAA, with a description of how funds would be used. / Table 6: Approximate allocation of funds to individual components of ClimAA / Component Description Cost and use of funds % appr / Output 1i and 2i: At least 30 new joint research partnerships linking Brazil with partners in Africa and the LAC region, generating and informing useful smallholder-targeted products for improving productivity and food security in Africa, supported by capacity strengthening and knowledge exchange processes. £2.2m over 3 years: / US$500,000 per Marketplace process per year used to support 5 additional joint Africa-Brazil and 5 LAC-Brazil projects per year, at US$80,000 per project. / US$320,000 to support additional capacity strengthening activities immediately before or after annual Marketplace Forum events. / Balance used to foster knowledge exchange via the Marketplace Forum, support monitoring and evaluation activities, and fund support for program implementation. 20% / Output 1ii: Programme of lesson learning and strategy development on Brazilian systems of local food production and procurement for feeding programmes informing piloting in five African countries. £0.6m over 2 years. To fund: / two seminars (experience exchange, capacity building, lessons and outputs); / two short courses on sustainable production and local purchase systems; / four technical visits to Brazilian projects; / five visits to African initiatives (one per partner country) 5% / Output 2ii: Brazilian climate-smart agriculture approaches being tested in three African countries through new 'Technology Reference Units' (TRUs). £5m over 3 years. To fund: / pre-appraisal and impact assessment / establishment of TRUs at 3 sites; / delivery of technical training; / administrative and communications systems and products; / monitoring and evaluation. 46% / Output 2iii: Additional capacity building and practical training on climate-smart agriculture provided for at least 180 African technicians. £1m over three years. / To fund 2 courses a year for 3 years for 30 participants per course of 2-week duration. 10% / Output 3i and 3ii: Programme to support analysis, feasibility studies, decision tools, guidance on piloting, dialogue and debate on Brazilian innovations and cooperation approaches. £1.5m over 3 years: / US$1.86m grant to IFPRI over 2 years. / Balance used to identify and support dialogue and debate on Brazil’s south-south approach through other partners (e.g. ABC, IDS). 14% / Independent Monitoring and Evaluation of ClimAA. £0.5m over 3 years. To monitor results and VfM, and derive lessons learned. 5% / Total: £10.8m 100% / We judge that ClimAA represents good value of money in terms of the anticipated direct benefits, and in terms of the additional benefits to invest in Brazil as a long term development partner.
B. How will it be funded: capital/programme/admin? / DFID programme funds from the Global Development Partnership Programme will be disbursed by the Global Partnerships Department (GPD). ClimAA will require oversight by a 0.5 FTE A2 adviser and 0.1 Policy Officer in DFID Brazil, supported by GPD administrative and financial staff based in Brasilia and DFID HQ, London.
C. How will funds be paid out? / Funds will be paid to the Government of Brazil and its agencies, international agencies (including WFP and FAO), policy research and civil society organisations, consultants and companies providing services. / The majority of funds will be channelled via: / Embrapa: suggested channel for funds is via an accountable grant to FUNARBE. (Fundaçao Arthur Bernardes); / WFP via their Centre of Excellence Against Hunger, Brasilia. DFID’s existing core Framework Agreement with WFP provides the financial mechanism for the purpose of transferring DFID’s funds; / IFPRI, through an accountable grant. / Payments will normally be made quarterly to the main implementing agents, who will be responsible for further disbursements according to work plan, progress reports, programme management manual and agreements/contracts. Payments will be made on the basis of justified requests, i.e. annual work plan and progress reports. Advance payments may be disbursed to implementing partners that demonstrate a proven need, e.g. to cover start-up costs. The principle, however, will be payment in arrears for provision of agreed services, as per Blue Book principles. Payments will be made on the basis of self-declaration, supported by annual external audit.
D. What is the assessment of financial risk and fraud? / All partners will be informed of DFID’s zero tolerance approach to corruption and fraud. / Table 7: Suggested strategies for mitigating against financial risk and fraud / Risk Analysis and Mitigation / Financial mismanagement or fraud within Embrapa/FUNARBE This would be extremely serious since three quarters of programme funds will pass through FUNARBE to Embrapa. However the risk is considered low. Embrapa currently manages annual funds of US$1bn. FUNARBE’s fiduciary systems channel significant international funds, and meet the requirements of agencies like the World Bank and the Gates Foundation, who will be scrutinising performance as part of their co-funding of Marketplace initiatives under output 1i. / Financial mismanagement or fraud within WFP This is a low risk: based on a good track record, DFID delivers more humanitarian assistance (36% of our 2008-09 spend) through WFP than any other agency, demonstrating DFID’s confidence in WFP’s systems. WFP meets all of DFID’s fiduciary risk requirements. DFID’s Multilateral Aid Review concluded that “WFP has strong financial management systems and is addressing areas of weakness”. WFP systems and auditing will mitigate against any potential risk of financial mismanagement or fraud. / Financial mismanagement or Fraud within IFPRI IFPRI has a track record of managing DFID funds, and meet CGIAR stndards. Under ClimAA, IFPRI will be submitting annual audited statements. These reporting requirements should mitigate against any potential risks / Financial mismanagement or Fraud within the Monitoring and Evaluation service provider Acceptable fiduciary capacity will be part of the tender assessment process. Funds will be paid out in instalments against satisfactory progress and financial reporting. An audit may be requested. / Financial mismanagement or Fraud by projects funded through the Agricultural Innovation Marketplace processes Projects are capped at US$80,000 which limits and spreads exposure to risk. Grantees will be informed of a zero tolerance policy towards fraud. Financial capacity and track record will be part of the assessment process. Funds will be released in against clear expected outputs and financial reporting requirements. Funding will be terminated if any evidence of financial mismanagement or fraudulent activities is identified or if performance targets are not met. / Delays in approval and transfer of funds by DFID This is a risk with large consequences. In particular rainfed agricultural programmes need to be implemented on time or a whole year of results can be lost. Implementing partners will demand timely action from DFID. Donor performance will be on the ToR of the evaluations.
E. How will expenditure be monitored, reported, and accounted for? / Monitoring and evaluation programmed into each constituent element of ClimAA will be, supported by independent monitoring and evaluation of the results and net impact of the overall ClimAA programme. / All delivery institutions will be required to submit regular financial expenditure reports along with a report on progress. These reports will clearly show detailed expenditure against approved budget lines. DFID will reconcile expenditure reports against data on Aries and approved project plans and budget. Discrepancies will be raised with implementers and where required revisions to expenditure reports will be made. Through this process, we will ensure that no illegitimate or unapproved expenditure will be funded by DFID as well as ensuring that no further tranches will be made if the reports indicate unsatisfactory performance.

Management Case

A. What are the Management Arrangements for implementing the intervention? / ClimAA forms part of DFID’s engagement with emerging power nations through its Global Development Partnership Programme (GDPP). Oversight and strategic direction is provided by the GDPP Board, chaired by the Secretary of State for International Development, and by the GDPP Director’s Group, chaired by the Director General, Policy and International. DFID staff in Brasilia, reporting to DFID’s Global Partnerships Department (GPD) in London, will be the assigned coordinating officers for this business case. / ClimAA is a new partnership experience for DFID, so a learning approach will be taken and arrangements will be monitored and revised during implementation as required. The core management approach will use a set of executive committee structures comprising the lead Brazilian agency and their African counterpart (Figure 6). As well as overall coordination, DFID will provide advisory input through steering committee structures. / Figure 6: ClimAA management structure / As set out above, responsibility for outputs will be as follows: / Output 1i: Embrapa International Division, as part of an Executive Committee for each Agricultural Innovation Marketplace process: / for Africa-Brazil: Foundation for Agricultural Research in Africa (FARA); / for LAC-Brazil: Inter-American Institute for Cooperation on Agriculture (IICA) and FAO. / Each Marketplace process to be supported by a Steering Committee including DFID, World Bank, IFAD, Gates Foundation and Brazilian Cooperation Agency. Details of other partners and governance structure available at www.africa-brazil.org and www.lac-brazil.org). / Output 1ii: Programme Coordinator, to be appointed by WFP Centre for Excellence against Hunger, and based in Brazilian Ministry of Social Development and Fight Against Hunger (MDS), supported by an advisory committee including DFID, WFP, MDS and CGFOME (Ministry of External Relations). Implementation will take place in close coordination with the Secretariat of GoB’s PAAfrica programme, coordinated by CGFOME. Activities in participating African countries will be implemented by FAO Emergency Rehabilitation and Coordination Units and WFP local offices in close collaboration with host government ministries. / Output 2ii: Embrapa International Division, as part of an Executive Committee including representatives from each of the three participating African countries. The Executive Committee to be supported by an Advisory Committee comprised of representatives from DFID, Embrapa, African country representatives and NEPAD. / Output 2iii: Embrapa CECAT, with advisory input from DFID Brazil, in response to demand from African partners. / Output 3i: IFPRI, with advisory input from DFID and Brazilian institutions including Embrapa and CGFOME. / Output 3ii: by organisations to be appointed during implementation; / Monitoring and evaluation of ClimAA: independent organisation, to be appointed. / Use of advisers in DFID HQ and specialist service providers will be used to provide technical advice on aspects of ClimAA. This will include the use of DFID resource centres or equivalent as appropriate. These inputs will be managed by the DFID team on the basis of Terms of Reference and contracts, awarded and managed according to DFID’s normal operating procedures and standards. / DFID Brazil is fully integrated into the British Embassy in Brasilia, is an integral part of the implementation of the Whitehall UK-Brazil strategy, and consults closely across the Embassy team. DFID’s work under the GDPP will be regularly reported to the British Embassy senior management, to DFID HQ (including management lines and policy leads on agriculture, food security and climate change); and to relevant Africa programmes. DFID will make use of UK staff in the British Embassy and the UK to promote the GDPP agenda and support its implementation.
B. What are the risks and how these will be managed? / Table 8: The likely effect of risks and how to mitigate these / Risk Effect Probability Mitigation / Lack of commitment from partners by virtue of shifting political priorities Low impact on project objectives Low/Moderate Work with focal points in Government and forge partnerships with civil society / Resistance of partner Governments and international agencies in reviewing national policies, procedures and programmes to apply lessons and take up new approaches Difficulty in achieving medium-term outcomes Moderate Engage local leaders in all project planning and evaluation stages. Work with focal points in Government and forge partnerships with civil society. / Brazilian models not sufficiently adapted to context Difficulty in achieving impact and outcomes Moderate Processes of lesson learning, testing and multi-stakeholder dialogue built into or the primary focus of recommended components. / Insufficient ownership by African participants Difficulty in achieving impact and outcomes Low/moderate Lead partners build an effective multi-stakeholder network to build buy-in and capacity to engage / Capacity of developing country partners insufficient to engage effectively with Brazilian actors. Difficulty in achieving medium-term outcomes Low Capacity strengthening built into all main components of ClimAA. / Insufficient evidence base to measure results Difficulty in measuring impact and outcomes Low M&E element built into each component, supported by analysis and decision support commissioned under Output 3i and overall programme M&E.
C. What conditions apply (for financial aid only)? / N/A
D. How will progress and results be monitored, measured and evaluated? / Monitoring and evaluation (M&E) will be integrated across the programme at the earliest possible opportunity to ensure that: / the results outlined in the logframe are monitored; and / VfM indicators are tracked to ensure that the logframe results are achieved in an efficient way. / Recognising that DFID’s partnerships with emerging powers are still in their early stages, a comprehensive and independent M&E plan, including an impact evaluation is envisaged. To ensure that the programme is driven by a strategic focus and good internal management from the outset, implementing partners are expected wherever possible to track evidence of costs and impacts, to inform implementation on a continuous basis. The independent M&E will, at regular stages of the programme’s lifespan, provide an external assessment of whether these objectives are being met. / The impact evaluation and M&E are two complimentary but logically distinct exercises. The role and purpose of each can be set out in relation to overall outcome and impact: / Gross Outcome/Impact = A) Intervention + B) Exogenous Factors + C) Error / (net outcome) (other causal factors) (random and measurement error) / Impact evaluation seeks to appraise what change there has been at the impact level of the logframe (the left hand side of the equation above) between an initial (baseline) assessment and a final assessment after the end of the programme. The impact evaluation alone does not provide information about causality or attribution of impact. It merely provides evidence of correlation between impact level changes and the programme. / M&E will provide continuous evidence on what results the programme itself has delivered according to the logframe (part A of the equation above). A robust M&E should also ensure that error in measurement of results (part C) is minimised. An effective ex post evaluation at the end of the programme will provide evidence for how much of the observed, gross outcome is due to the programme, and will also explain other exogenous factors that may be driving the outcome. E.g. improved rainfall or greater budgetary support to domestic farmers may help to reduce food insecurity, but happen entirely independently of the programme. / The section below outlines the key issues and processes related to evaluation (M&E and impact evaluation): / Purpose and target audience - evaluation products will provide an objective evidence base by which to appraise the performance of the programme’s constituent components. This evidence should play a central part in the management of the programme, hence the executive and advisory/steering committees and their implementers outlined in section A of the Management Case should be key users of the evaluation. Findings should also be shared with representatives from the beneficiary groups in order to check whether they resonate with their experience of the programme. / Timing - a baseline survey will be done as soon as feasible after the programme is approved. After that, annual evaluations will be conducted, with the final evaluation appraising the programme’s overall performance. / Methodology - the key questions underpinning the M&E will include those raised in the Appraisal Case and VfM sections in particular. The exact nature of the methodology will be developed in consultation with implementing partners, managing agents and the organisation appointed to carry out the M&E. / Evidence base - evaluation should provide reliable first hand data on the programme activities. These should include cost-benefit ratios where possible, which can be used by DFID and its partners in the development of future agricultural/food security interventions. The evaluation will have a broader relevance in informing DFID’s engagement with emerging power nations and in support of south-south programmes. It will also be a resource for the GoB and its existing and prospective future partners in examining Brazilian international cooperation in this field. / Communication – evaluation products should be published and actively shared with key stakeholders in the GoB and amongst beneficiaries, as well as providing a general public good to those interested in Brazil’s international cooperation. / Process for contracting - the team to carry our impact evaluation and M&E will be selected through an open tender procurement process in order to ensure transparency and value for money, as set out in the Procurement Case (p36). The successful bidder will be selected on the basis of how well they meet the specification set out in the Terms of Reference (to be established in due course in collaboration with partners).
Quest No of Logframe for this intervention: to be supplied

References Cited

Action Aid (September 2010), Hunger Score Card 2010. Action Aid, UK.
Albuqerque, ACS; Da Silva AG (Ed.) (2008). Agricultura Tropical: quatro décadas de inovações institucionais e políticas. Embrapa Informação Tecnológica, Brasília, DF.
Alene AD, Coulibaly O (2009) The impact of agricultural research on productivity and poverty in sub-Saharan Africa. Food Policy Volume 34, Issue 2. Elsevier Ltd, pp. 198-209
Avila AFD et al (2008) Avaliacao dos impactos de tecnologias geradas pela Embrapa: metogologia de referencia. Embrapa Informaçãoo Tecnológica, Brasilia, Brazil.
Avila AFD, Evenson RE (2010) Total Factor Productivity Growth in Agriculture: The Role of Technological Capital. In Handbook of Agricultural Economics, Burlington: Academic Press, 2010, pp. 3769-3822.
Avila AFD, Luis Romano, Fernando Garagorry (2010) Agricultural Productivity in Latin America and the Caribbean and Sources of Growth. In Handbook of Agricultural Economics, Burlington: Academic Press, 2010, pp. 3713-3768.
Barrett CB (2007) Smallholder market participation: Concepts and evidence from Eastern and Southern Africa. Food Policy 33 (2008) 299–317. Available at: https://entwicklungspolitik.uni-hohenheim.de/uploads/media/SMALLHOLDER_MARKET_PARTCIPATION.pdf

Beddington J (2010) Food security: contributions from science to a new and greener revolution. Philosophical Transactions of the Royal Society. 12 January 2010, vol. 365 no. 1537, pp. 61-71
Bientema (2010) Brazil: new developments in the organisation and funding of agricultural research. Country Note, October 2010. Agricultural Science and Technology Indicators. Embrapa
Burwell SM (2010) Big action for small farmers. Huffington Post, 25 June 2010. Available at: http://www.huffingtonpost.com/sylvia-mathews-burwell/big-action-for-small-farm_b_625754.html
CAISAN (2011) Plano Nacional de Segurança Alimentar e Nutricional: 2012/2015. Câmara Interministerial de Segurança Alimentar e Nutricional; Ministério do Desenvolvimento Social e Combate à Fome; Conselho Nacional de Segurança Alimentar e Nutricional. Brasília, DF.
Chmielewska D, Souza D (2010) Market alternatives for smallholder farmers in food security initiatives: lessons from the Brazilian Food Acquisition Programme. Working Paper 64, International Policy Centre for Inclusive Growth, UNDP. Brasilia, Brazil
Cline WR (2007) Global warming and agriculture: impact estimates by country. Peterson Institute. Washington DC.
Collier P, Dercon S (2009), African Agriculture in 50 Years: smallholders in a rapidly changing world. Expert Meeting on How to Feed the World in 2050, FAO, Rome.
CONSEA (2009) Building up the National Policy and System for Food and Nutrition Security: The Brazilian Experience. Report by Brazil’s National Council on Food and Nutrition Security. Government of Brazil.
DFID (2011) Multilateral Aid Review: Ensuring maximum value for money for UK aid through multilateral organisations. DFID, London, UK
DFID (2012) Growth strategy for Mozambique (draft, unpubl). DFID, Maputo, Mozambique.
Dercon S, Vargas Hill R, Zeitin A (2009), In Search of a Strategy: Rethinking Agriculture-led Growth in Ethiopia. Oxford University. Available at: http://www.economics.ox.ac.uk/members/stefan.dercon/policy_ethiopiaagriculturework.htm
The Economist (2010) The miracle of the cerrado. The Economist August 26, 2010. Available at: http://www.economist.com/node/16886442?story_ id=16886442&fsrc=rss.
Fan S, Nestorova B, Olofinbiyi T (2010), China’s Agricultural and Rural Development: Implications for Africa. IFPRI, Washington DC.
FAO (2005) Special event on impact of climate change, pests and diseases on food security and poverty reduction. Background document. In 31st session of the Committee on World Food Security. Rome, Italy: FAO. Available at: ftp://ftp.fao.org/docrep/fao/meeting/009/j5411e.pdf
FAO (2006) State of Food Security in the World 2006: Eradicating world hunger – taking stock ten years after the World Food Summit. FAO, Rome.
FAO (2008) FAOSTAT database. Production: crops. Available:  http://faostat/fao.org/site/567/default.aspx.  Accessed 18 December 2008 in Garrity et al.

FAO (2010) The State of Food and Agriculture 2010-11: Women in agriculture: closing the gender gap for development. FAO, Rome
Foresight (2011) The Future of Food and Farming: Final Project Report. The Government Office for Science, London.
Funk CC and Brown ME (2009). Declining global per capita agricultural production and warming oceans threaten food security.  Food Security 1: pp. 271-289

Global Harvest Initiative (2011) Global Agricultural Productivity Report 2011: measuring global productivity. Available at: http://www.globalharvestinitiative.org/index.php/2011-gap-report/
Godoy, J (2010), Africa Should Take Lessons from China, IPS News http://ipsnews.net/news.asp?idnews=51590
Government of Ethiopia (2007) Climate Change National Adaptation Programme of Action (NAPA) of Ethiopia. MoWR and NMA, Government of Ethiopia, Addis Ababa.
Government of Ghana (2010) Ghana goes for green growth: national engagement on climate change. Discussion document, Ministry of Environment, Science and Technology, Republic of Ghana, Accra.
Government of Malawi (2006) Malawi’s National Adaptation Programmes of Action (NAPA) Under The United Nations Framework Convention On Climate Change (UNFCCC). Environmental Affairs Department, Government of Malawi, Lilongwe.
Government of Tanzania (2011) Poverty and human development report 2011. Research and Analysis Working Group, MKUKUTA Monitoring System, Ministry of Finance and Economic Affairs, United Republic of Tanzania, Dar es Salaam.
Green D (2008) From Poverty to Power: How Active Citizens and Effective States Can Change the World. Oxfam International, Oxford.
Gueye B, Petersen P, Ugas R, van Walsum E, Gopal KS (2007), Opinion: Family Farming First: any future needs family farming. The Broker, 27 September 2009. Available at: http://www.thebrokeronline.eu/en/Magazine/articles/Opinion-Family-farming-first
Henley D (2012) The Agrarian Roots of Industrial Growth: Rural Development in South-East Asia and sub-Saharan Africa. Development Policy Review Special Issue: Tracking Development in South-East Asia and sub-Saharan Africa. Vol 30 Issue Supplement 1, pp. 25-47. Available at: http://onlinelibrary.wiley.com/doi/10.1111/j.1467-7679.2012.00564.x/abstract
Herrero M, Thornton PK, Notenbaert AM, Wood S, Msangi S, Freeman HA, Bossio D, Dixon J, Peters M, Van De Steeg J, Lynam J, Parthasarathy Rao P, Macmillan S, Gerard B, Mcdermott J, Seré C, Rosegrant M (2010). Smart Investments in Sustainable Food Production: Revisiting Mixed Crop-Livestock Systems. Science, 12 February 2010: Vol. 327. no. 5967, pp. 822 - 825
IFAD (2010). Rural Poverty Report 2011: New realities, new challenges: new opportunities for a new generation. Rome: IFAD.
IFAD (2011) Rural Poverty Report. IFAD, Rome.
IFPRI (2004) Ending hunger in Africa: prospects for the small scale farmer. IFPRI, Washington DC
IBGE (2009). Censo Agropecuário 2006. Rio de Janeiro,Brazil.
IMF (2007) World Economic Outlook Database, April 2007. International Monetary Fund, Washington, USA
INCRA (1980). ‘Instrução Especial/INCRA/Nº. 20, de 28 de Maio de 1980’. Published in the Diário Oficial.
Khan BM, Zaks D (2009) Investing in agriculture: far-reaching challenge, significant opportunity. Deutsch Bank Climate Change Advisors. Frankfurt, Germany.
Lipper L, Mann W, Meybeck A (2010) 'Climate-Smart' agriculture: policies, practices and financing for food security, adaptation, and mitigation. Food and Agriculture Organization of the United Nations. FAO, Rome. Available at: http://www.eldis.org/cf/rdr/?doc=58933
Litchfield, J (2010) Report for DFID: Agriculture and Growth Theme Reviews
Markwei C, Ndlovu L, Robinson E, Shah W (2008) Sub Saharan Africa summary for decision makers. International Assessment of Agricultural Knowledge, Science and Technology for Development (IAASTD). Available at: http://www.agassessment.org
McKinsey (2010) Roadmap for Achievement of the New Vision for Agriculture. Presentation to World Economic Forum, September 2010.

Müller, C., A. Bondeau, A. Popp, K. Waha, and M. Fader. 2009. “Climate Change Impacts on Agricultural Yields.” Background note for the WDR2010.

Nelson GC, Rosegrant MW, Koo J, Robertson R, Sulser, T, Zhu T, Ringler C, Msangi S, Palazzo A, Batka M, Magalhaes M, Valmonte-Santos R, Ewing M, Lee D (2009) Climate change: Impact on agriculture and costs of adaptation. IFPRI, Washington DC.

Oboodo K (2009) Rwanda’s agriculture up despite global crisis. The Independent, 10 November 2009. Available at: http://www.independent.co.ug/index.php/news/regional-news/78-regional-news/2091-rwandas-agriculture-up-despite-global-crisis

OECD (2006) Promoting Pro-poor Growth: agriculture. DAC guidelines and reference series. OECD, Paris.
One World (2011) Food security in Malawi. One World Briefing, last updated September 2011. Available at: http://uk.oneworld.net/guides/malawi/food_security
One World (2012) Food security in Senegal. One World Briefing, last updated February 2012. Available at: http://uk.oneworld.net/guides/senegal/food_security
Oxfam (2009) Harnessing Agriculture for Development. International Research Report (September 2009). Oxfam, Oxford.
Shepherd A (2010) Agriculture and Escaping Rural Poverty: an Analysis of Movements and Markets. Paper presented at the Chronic Poverty Research Centre Poverty Conference, 8-10 Sept. 2010, Manchester UK.
da Silva JG, Del Grossi ME, de França CG [eds] (2010) Fome Zero: a experiência brasileira. Ministério do Desenvolvimento Agrário, Brasília, DF, Brazil.
UN (2008) World Population Prospects. The 2008 Revision. UN, New York
UN (2011) “Procurement and the Millennium Development Goals - Supplement to the 2010 Annual Statistical Report on United Nations Procurement” [7]
[7] http://www.unops.org/SiteCollectionDocuments/ASR/2010-supplement.pdf

Von Grebmer K, Nestorova B, Quisumbing A, Fertziger R, Fritschel H, Pandya-Lorch R, Yohannes Y (2009) The Challenge of Hunger: Focus on Financial Crisis and Gender Inequality. In Global Hunger Index 2009. IFPRI, Washington DC.
Watkiss P, Downing T, Dyszynski J, Pye S et al (2011). The Economics of Climate Change in the United Republic of Tanzania. Report to Development Partners Group and the UK Department for International Development. Available at: http://economics-of-cc-in-tanzania.org/
WFP (2010) (2010). United Republic of Tanzania 2009/10 Comprehensive Food Security and Vulnerability Analysis. World Food Programme, Dar es Salaam.
World Bank/IPEA (2011) Brazil-Sub-Saharan Africa relations. World Bank, Washington DC
Wiggins S, Clay EJ, Keats S. (2010) Briefing: food crisis in Niger 2010. Overseas Development Institute (ODI), London, draft, September 2010.
World Bank (2008) World Development Report 2008: Agriculture For Development. World Bank, Washington DC
World Bank (2008a) Beating the odds: Sustaining inclusion in Mozambique’s growing economy. Poverty, Gender and Social Assessment for Mozambique. January 2008. The World Bank, Washington DC
World Bank (2009a) World Development Report 2010: Development and Climate Change. World Bank, Washington DC.
World Bank (2009b) Implementing agriculture for development. World Bank, Washington DC.
World Bank (2010) Briefing Note: Awakening Africa’s Sleeping Giant. Agriculture and Rural Development Notes. World Bank, Washington DC
World Bank (2010a) Economics of Adaptation to Climate Change: Ghana. World Bank, Washington DC