Project Completion Review – post April 2018

Title: Business in the Community: Private Sector Engagement Programme
Final Programme Value £ (full life): £736,311	Review Date: 10/12/2018
Programme Code: 203417	Start Date: 15th July 2013	Final End Date: 15th October 2018

Summary of Programme Performance

Year	2014	2015	2016	2017	2018	2018
Programme Score	A	A+	A+	A+	A	A
Risk Rating	Low	Low	Minor	Minor	Minor	Minor

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Log Frame

A. Summary and Overview (1-2 pages)

Description of programme and what it has achieved
The UK Provided a total of £736,311 over a five-year period (2013 – 2018) to Business in the Community (BITC) to help improve the coordination and effectiveness of the UK private sector’s response to humanitarian emergencies.

At the time of the original business case, there had been a growing sense within the humanitarian sector that, beyond monetary donations, there was insufficient guidance, support, and regulation to guarantee quality humanitarian support from businesses. Moreover, a lack of mutual understanding and communication between humanitarian and commercial actors meant that access to the opportunities which humanitarian-business partnerships represent had been inhibited. This project was designed to help address this problem, and through it BITC have produced guidance and provided training to business in the delivery of humanitarian and emergency aid. They used their extensive networks and convening power to deliver this work and bring business and non-government organisations (NGO) together.

Through the project, BITC also arranged and delivered the International Disaster Relief and Resilience Award category at the annual Responsible Business Awards which showcases the best efforts of business’ in humanitarian response over the year and works to continually promote business engagement. The changing nature of the private sector’s engagement throughout the time of the project was analysed by a series of publications Business’ Unique Contribution (BUC) I, II and III.

After the last annual review a three-month time only extension was granted to this project to deliver a few additional outputs. These are reviewed in this project completion report. The last annual review was completed five months ago and contains more detail about the performance of this project over the last year. As the time period for this review only covers three additional months, the output scoring section is smaller than in previous annual reviews. More detail on previous years can be found on the Development Tracker website.

Summary of overall performance against outputs

Over the course of the programme BITC has scored well on meeting its indicators and has scored As and A+s over its lifetime.

Output one of the project has concerned engaging business in disaster relief activities through the International Disaster Relief and Resilience Awards, providing case studies to showcase the work of business in international disaster relief, providing guidance to businesses and evaluating the higher-level changes to business engagement through the Business Unique Contribution research. The project has tended to score well against this output, and has produced a range of blogs, opinion pieces and other articles on various disaster relief related topics such as: ‘Silent Disasters’, ‘Relief Resistance and Redesign’, ‘World Humanitarian Day’, ‘and The Refugee Crisis’. It has also consistently promoted case studies from award nominations and produced the 3 BUC reports.

As the project developed it could be seen that the submissions for entry into the International Disaster Relief and Resilience Award category were increasing in sophistication. The number of entries had increased over most years during the project but did see quite a considerable reduction during the 2018 awards. It was thought that, given the strong field of entries in previous years, some businesses did not believe that their disaster relief work was strong enough to win an award. Also, as the work of some businesses could potentially have been entered under a range of award categories, some may have submitted their entries for other responsible business awards.

Output two of the project has concerned creating partnerships between NGOs and businesses through BITC arranging networking events, which is one of their key strengths, and also the development of an online ‘matching tool’, called the Hub, to match businesses offers and NGO requirements for any specific disaster response.

While the technological development and launch of the Hub was successful, and considerable effort was put in by BITC to encourage its use, it was discovered early on after its launch that it was not going to deliver the anticipated matches between businesses and NGOs. BITC were quick to acknowledge that the use of the Hub was not likely to produce the intended effect, and kept DFID updated as results of use and efforts to increase use unfolded. DFID and BITC were then able to come to a timely decision to reorient the project to other activities that would yield better results.

While the Hub may not have had the intended success that it was hoped to have, it is believed that it helped to bring businesses and NGOs together, and facilitate useful conversations and sharing of information which is a higher-level goal of the project. The BUCIII research indicates that there has been a fourfold increase in partnerships since the beginning of the project in 2014.

Output three of the project concerned raising awareness amongst business and NGOs of the importance and effectiveness of the private sector in disaster response.

In addition to the events held during the development of the Hub, BITC have organised and attended several relevant events to raise awareness of the private sector’s role in disaster response. For example, the BITC International Campaign Team participated in the World Humanitarian Summit global consultation in Geneva, and in partnership with other business groups, hosted a side event, Public-Private Partnerships for Resilience and Localised Response, at the World Humanitarian Summit.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Increased insight and understanding for business on how they can best assist during humanitarian emergencies
Output number per LF		1	Output Score	A
Impact weighting (%)?		30	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Numbers of best practice case studies identified	Publish 15 case studies from awards finalists and BUC III research	Achieved. Case study publication achieved in principle, plus additional communications produced. BUC III produced.
Publications referencing the business case for business engagement in disaster relief.	50 site visits to Business Unique Contribution III during the first few months after its launch	Data not available

Provide supporting narrative for the score

By the time the call for entries for the last International Disaster Relief and Resilience award process closed, 11 businesses had started the application form and 3 award entries had been made. The 3 case studies for the award entries have been published and are available online. These are the entries for the two runners up Airbnb, Pearson, and the winner Arup.

In addition to these, over the last 3 months of the project, BITC has been involved in producing several other publications relevant to international disaster relief.

On 20th July 2018 a blog entitled, ‘Harnessing digital technology to reduce natural disaster damage’ was published on BITC’s website. This case study highlighted a partnership that Fujitsu had developed between the UN Development Programme and the Tohoku University in Japan to use digital technology to reduce damage caused by natural disasters.
On 17th August 2018, in preparation for World Humanitarian Day 2018, BITC’s Global Goals and Sector Director wrote an article focusing on the human perspective of humanitarian disasters. This highlighted the work that BITC has been doing in this space and the role of the Sustainable Development Goals in supporting the international disaster relief agenda.
Under the project BITC also arranged and published Business’ Unique Contribution III (BUC III), the final piece of research on business’ changing approach to engagement in international disaster relief. This is based on research by Bean Research, an external research consultancy. Quantitative and qualitative data through an online questionnaire and in-depth phone interviews were conducted and the perspectives of both NGOs and businesses were obtained. 66 businesses completed quantitative research for BUCIII, with an additional nine in-depth one-to-one interviews. As the BUC reports provide a useful insight into the wider changes that the private sector is making in disaster response, a summary of relevant key findings is provided in the theory of change section below.

This final instalment of the series on Business’ Unique Contribution reports was launched on 5th November. The launch was slightly behind schedule due to unexpected staffing changes. As such, data on number of downloads in the first few months is not available. While the publication of the report was delayed beyond the project end date, DFID was not charged for any project activity beyond the formal grant agreement date. As reported in the last annual review, since the baseline year, the number of downloads for the previous two BUC publications has grown by 56%, so we would expect a similarly a strong rate of use for BUCIII.

Output Title	Partnerships between NGOs and businesses are created
Output number per LF		2	Output Score	A
Impact weighting (%)?		40	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of fora and increase in dialogue around importance of engagement and partnership between NGOs and businesses.	Plan one event on International Disaster Relief	Achieved

Provide supporting narrative for the score

Marsh funded and provided accommodation for a CEO networking dinner organised by BITC under this oputput to discuss International Disaster Relief and Resilience on 17th May 2018. The event was attended by 17 participants, 13 of whom were from business and four from academia. During the presentations there was a focus on the need for business to focus on all four stages of a disaster: preparation, response, recovery and mitigation. Some of the highlights of the BUC III research were highlighted during the evening.
BITC report that discussion at the dinner focussed on Businesses role in disaster relief and resilience and taking ownership for progressing BITC’s work in this area. It is felt that the private sector has the expertise, means and desire to step up, and that it is important for them to use their core expertise and experience, regardless if they are a large or small business.
Points were made around building resilience in cities and the need for business coordination to ensure complementarity in work and not to duplicate. It was questioned whether there was a role for the new BITC Pride of Place strategy to be taken global.

Output Title	Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response
Output number per LF		3	Output Score	A
Impact weighting (%)?		30	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Capacity building for businesses to identify their unique contribution and better understand how it can be used	Start planning BITC blueprint for once the DFID programme ends	Continued work for this agenda is planned

Provide supporting narrative for the score

BITC plan to continue their engagement in the private sector’s role in disaster response under their wider Global Goals activities.
While this project has come to a close, BITC plan to continue to disseminate information based on the learning from this project. They plan to use this to support questions on their new online Responsible Business Tracker® which is due to be fully launched in 2019. BITC’s webpages provide more information on the Responsible Business Tracker®
BITC’s new Global Goal’s Director is due to attend the event ‘Working Together for Disaster Relief’. A conference being co-convened by Catholic Relief Services and BRE. A further BITC event is planned to be held in early 2019 on the International Disaster Relief agenda, and BITC will consider opportunities to work with its internal team the Business Emergency Resilience Group to further its work on disaster relief in the international arena to enable it to offer more tailored advisory work to companies.
BITC willcontinue to recognise businesses supporting disaster resilience work through the Barclays Developing Resilience Award which is now open for international businesses.

BITC have also confirmed that they will seek follow up on areas for improvement that were identified in the BUCIII research.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The outcome for the project is: The private sector operating in the UK demonstrates stronger engagement in disaster response at a corporate level.

The impact is: The private sector is better harnessed to reduce human suffering in humanitarian disasters

As indicated in BUC III changes in these directions do appear to have been happening over the life of the project. Amongst other things the research indicates:

- Business partnerships with non-government organisations (NGOs) are becoming more strategic, moving from ad hoc and donation-based activities to contributions of skills and expertise. For example, in 2014, 90% of businesses supported disasters through cash donations, but this has fallen to 67% in favour of other support.
- In 2014 the majority of businesses focussed on immediate, reactive response and recovery. In 2018, 2 in 5 businesses now address risk mitigation, preparedness and resilience consistently.
- Businesses are improving their understanding of how to utilise their core competencies, products and services to support; but NGOs still find businesses do not have enough awareness of how to use these most effectively.

Summarise the programme’s theory of change and major changes to it in the past year

The causal chain in the Business Case suggests that the creation of guidance for business, development of a matching tool to link businesses and NGOs, and the establishment of the disaster relief award category will lead to the following outputs:
- Increased insight and understanding for business on how they can best assist during humanitarian emergencies
- Formal partnerships between NGOs and businesses
- Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response.

The assumption underpinning the causal chain is that increased awareness amongst NGOs and businesses of the case for action and how to do it, as well as practical support and brokering, will scale up the level of private sector engagement.

There have been no major changes to the causal chain in the Business Case. While the Hub did not deliver as expected (as referenced above and in the 2018 Annual Review) the purpose behind the tool (to link business and NGOs together) remains a significant part of the causal chain, which BITC have delivered successfully on through other means.

Explain major changes to the logframe in the past year

For the additional 3 month time only extension a small number of additional milestones were added to the logframe. Other than those, the logframe has not changed.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme (1 page)

The value for money proposition in the original business case highlights BITC’s strategic position as a central source of advice and guidance for the private sector. Its wide network of members was noted as providing an opportunity to effect sector-wide change in humanitarian response, improving the private sector’s coordination during humanitarian emergencies and offering the potential to improve the quality and effectiveness of their responses. Making funding agencies and NGOs more aware of private sector resources was also highlighted as something that would enable smarter funding decisions.

BITC has continued to deliver against these VFM objectives. BITC uses a well-established and maintained database of over 800 business members. BITC continues to update the database through discussions with existing and target business, and uses this data to target guidance, research and events relating to emergency response.

In addition to the value for money proposition in the original business case, BITC presents good economic VFM through its ability to use pro-bono support from its members (including venue hire and printing costs).

The use of BITC’s database of business and its capacity to convene business around the programme’s agenda highlights the efficiency with which using an organisation such as BITC offers this programme. Through its core business activities BITC have demonstrated good ability to convene business to push the programme’s agenda.

E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

The risk, identified in the business case, of there being insufficient interest and commitment among business and humanitarian agencies to pursue this agenda has remained low. Last year there was a significant reduction in business interest in submitting applications to the International Disaster Relief and Resilience Award category at the annual Responsible Business Awards. This could have been seen as an indicator that this risk is being realised. However, the results from BUC III strongly indicate that the private sectors’ interest and engagement in disaster relief and preparedness is still high. This is demonstrated, for example, through the increasing use of longer-term and strategic partnerships and collaboration, rather than ad hoc and often donation based engagement.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

The programme finished with a £20,000 underspend against its original budget due to savings that were made by BITC.

One of the budget lines for the Global Goals and Sectors Director underspent due to a staff change during the project. A secondee from the Environment Agency took on this role in 2018 and as BITC did not pay his salary his time on the programme is was budgeted into the project costs.
The budget line for the Global Relief and Resilience Hub (The Hub) was also reduced because this was built pro-bono by PwC.

These savings also enabled the project to be extended by 3 months without additional charge.

BITC’s ability to leverage pro-bono support against this programme for things such as venue hire, publications and The Hub has been a strong driver in keeping project costs to a minimum.

Towards the end of the programme BITC has had a number of programme manager staff changes. While this had some impact on continuity of the programme, the programme did not suffer and kept generally on track. The programme has been managed well by BITC.

Date of last narrative financial report	22/11/2018
Date of last audited annual statement	22/12/2017

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring, Evidence and Learning

The research, BUC III, has provided the independent analysis of the changing approach of the private sector to disaster relief. It complements and builds on two previous research publications of the same name and is one of the significant outputs of this programme.

The research for ‘Business Unique Contribution I’ was carried out in spring 2014, at the beginning of the programme, to establish the level of business engagement in international disaster relief and resilience as well as expectations from both the business and NGO communities. The second iteration of research, ‘Business Unique Contribution II’ provided a midpoint review of the progression of business engagement in international disaster relief and resilience.