## PPG July 2016
PROJECT NAME | PRO POOR GROWTH PROGRAMME
IMPACT | Impact Indicator 1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016)
Reduce poverty through promotion of business growth, job creation and access to finance | GDP growth in Zimbabwe | Planned |  |  |  | 4% | 1.4%
|  | Achieved |  | 4.5% | 3.1% | 1.1%
Source: WB
| Impact Indicator 2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016)
| Per capita GDP (constant 2010 US$) | Planned | $800* | 817 | 841.51 | 883.5855 | 927.7648
Achieved
Source: 2014 GoZ Budget Statement / IMF SMP
* Source - DFIDZ results Adviser
OUTCOME | Outcome Indicator 1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016) | Assumptions
Improved access to financial and business development services for agricultural value chain actors, SM&MEs and entrepreneurs | Number of economic opportunities created | Planned | 0 | #REF! | #REF! | #REF! | #REF! | Business environment does not deteriorate. Political stability. Favourable policy environment.
|  | Achieved |  | #REF! | #REF! | 76133 | #REF!
|  |  | Source: | GWCVT results aggregation report
| Outcome Indicator 2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016)
| Average incremental income generated per new economic opportunity (US$ per annum) | Planned | 0 | #REF! | #REF! | #REF! | #REF!
|  | Achieved |  | #REF! | #REF! | AIZ$389, ZADT $1887 AECF$51 | AIZ $98, AECF $54
|  |  | Source | GWCVT results aggregation report
| Outcome Indicator 4 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016)
| Number of previously excluded beneficiaries with access to financial services | Planned | 0 | #REF! | #REF! | #REF! | #REF!
|  | Achieved |  | #REF! | #REF! | 23202 | #REF!
|  |  | Source | GWCVT results aggregation report
OUTPUT 1 | Output Indicator 2.1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016) | Assumptions
Appropriate financial products accessible to value chain actors | No. of financial products with attributes developed for and being used by target beneficiaries | Planned | 0 | 2 | 3 | 4 | 6 | Macro-economic environment is conducive for funds and beneficiaries to carry out their business activities in a profitable manner. Participating banks and MFIs continue to meet regulatory requirements. No negative policy shifts in fiscal policy.
|  | Achieved |  | 0 | 2 | 6 | ZADT 4, ZMF 5
|  | Source | ZMWF, ZADTs Plans and Reports
| Output Indicator 2.2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016)
| Operational self-sufficiency for both ZADT and ZMWF (total operational cost/total income) | Planned ZADT | 0 | 70% | 80% | 85% | 115%
|  | Planned ZMF | 0 | 30% | 70% | 100% | 120%
|  | Achieved ZADT |  | 207% | 40% | 90%
|  | Achieved ZMF |  | 23% | 65% | 65% | 118%
|  | Source | ZMWF, ZADTs Plans and Reports |  |  |  |  | RISK RATING: High
IMPACT WEIGHTING 30% | DFID (FTEs)
INPUTS (HR) | Econ Adviser 15%, Project Officer 15% and SRO 15%
|  | Planned | 0 | All 4 Implementing partners |  | All 4 Implementing partners | All 4 Implementing partners
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016) | Assumptions
Financial and technical support to business with innovative and inclusive business models | Number of businesses funded by PPG partners still operational 12 months post support | Planned: | 0 | 42 | 44 | 49 | 60 | Business environment does not deteriorate. Favourable agricultural policies prevail. The programme leverages additional funds from other donors.
|  | Achieved |  | 46 | 47 | 55 | 47 (AECF 3, ZADT 12, ZMF 15, AIZ 17)
|  | Source | AECF, ZADT. ZMWF and AIZ logframes
| Output Indicator 2.2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016)
| Days of technical assistance provided to agribusinesses | Planned | 0 | 840 | 1260 | 1680 | 1680
|  | Achieved |  | 1140 | 1560 | 1975 | 2980
|  | Source: | AIZ Project reports based on MIS data
| Output Indicator 2.3 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Milestone 4 (2016)
| % of AIZ clients reporting quality technical assistance | Planned (AIZ 1) | _ | _ | 30% | 45% | N/A
|  | Planned (AIZ 2) |  |  |  |  | 70%
|  | Achieved (AIZ 1) |  |  |  | data not available | N/A
|  | Achieved (AIZ 2) |  | _ |  | data not available
|  | Source: | AIZ Project reports based on MIS data |  |  |  |  | RISK RATING: Medium
IMPACT WEIGHTING 30%
INPUTS (HR) | Econ Adviser 20%, Project Officer 20% and SRO 20%
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (date) December 2016 | Assumptions
Enabling environment for business and microfinance | Number of regulations supporting growth of the MFI sector | Planned | Draft Microfinance Act | 1 | 1 | 1 | 2 | Global and national market conditions are no worse than baseline year. Political events do not negatively affect business performance. Conditions for doing business remain stable or improve.
|  | Achieved |  | 0 | 1 | 1
|  | Source: | The Ministry of Finance 2014 Budget statement
| Output Indicator 3.2 |  | Baseline (2012) | Milestone 1 (2013) | Milestone 2 (2014) | Milestone 3 (2015) | Target (date) December 2016
| No of MFIs borrowing from ZWMF that have attained operational self sustainability | Planned | 0 | Three (3) MFIs with OSS ratio above 85% | Four (4) MFIs with OSS ratio above 85% | Five (5) MFIs with OSS ratio above 90% | Five (5) MFIs with OSS ratio above 100%
|  | Achieved |  | 5 | 4 | 11 | 15
|  | Source: |  | ZMWFT Quarterly Monitoring Reports |  |  |  | RISK RATING: Medium
IMPACT WEIGHTING 15% | DFID (FTEs)
INPUTS (HR) | Econ Adviser 15%, Project Officer 15% and SRO 15%
OUTPUT 4 | Output Indicator 4.1 |  | 2012 | 2013 | Baseline (2014) | Milestone 1 (2015) | Target (date) December 2016 | Assumption
Effective 2013/14 annual review PPG course correction including i) effectively supported idea generation (ideation) process and ii) effective delivery of MFI skills and support to the MFI sector to enhance increased investment in ZMWF | number of new business ideas stage gated through AIZ ideation programme | Planned (T) | N/A | N/A | 0 | 21 | 14
|  | Planned (F) | N/A | N/A | 0 | 8 | 6
|  | Achieved (T) | N/A | N/A | 0 | 21 | 14
|  | Achieved (F) | N/A | N/A | 0 | 8 | 5
|  | Source | AIZ phase 2 programme records
| Output Indicator 4.2 |  | 2012 | 2013 | Baseline (2014) | Milestone 1 (2015) | Target (date) December 2016
| number of beneficiaries trained via ZAMFI skills training programme | Planned | N/A | N/A | 0 | 250 | 250
|  | Achieved | N/A | N/A |  | 330 | 372
|  | Source | ZMWF programme records
| Output Indicator 4.3 |  | 2012 | 2013 | Baseline (2014) | Milestone 1 (2015) | Target (date) December 2016
| % of participants that demonstrate improved knowledge immediately after training | Planned |  |  | 0% | 60% | 60%
|  | Achieved |  |  |  | 100% | 100%
|  | Source | ZMWF programme records
| Output Indicator 4.4 |  | 2012 | 2013 | Baseline (2014) | Milestone 1 (2015) | Target (date) December 2016
| number of MFI's using industry standard MIS rolled out by ZAMFI | Planned | N/A | N/A | 0 | 11 | 15
|  | Achieved | N/A | N/A |  | 8 | 15
|  | Source | ZMWF programme records
| Output Indicator 4.5 |  | 2012 | 2013 | Baseline (2014) | Milestone 1 (2015) | Target (date) December 2016
| Average management fee megotiated for programme extensions (ZMWF and AIZ) | Planned | N/A | N/A | 13.4% |  | N/A
|  | Achieved | N/A | N/A |  | 8.5% | N/A
|  | Source: | QUEST |  |  |  |  | RISK RATING Medium
IMPACT WEIGHTING 50% | DFID (FTEs)
INPUTS (HR) | Econ Adviser 50%, Project Officer 50% and SRO 50%