Annual Review

Sub-National Governance Programme
DFID Pakistan, April 2013 – September 2017

Date started:	08 April 2013
Date review undertaken:	February and March 2014

## Introduction and Context
What support is the UK providing?
DFID Pakistan’s Sub-National Governance programme, 2013-2017, (SNG) aims to contribute to more stable democracy in Pakistan. It does so by supporting the improvement of government service delivery in 12 districts, 6 each in Khyber Pakhtunkhwa (KP) and Punjab. / In its first year, there have been four areas of SNG programme activity: / Technical assistance on public financial management, planning and local governance at both provincial and sub-provincial levels / Challenge Funds in both provinces to pilot innovative service delivery interventions at sub-provincial levels / Conditional Grant work in KP / Work with the World Bank, primarily in Punjab, on three Externally-Financed Outputs (EFOs) on Information and Communication Technology (ICT); Right To Information legislation; and a Public Expenditure and Financial Accountability (PEFA) assessment of Pakistan’s Federally Administered Tribal Areas (FATA) / . / These will be complemented in coming years by support to a Special Monitoring Unit in Punjab, as well as Geographical Information System (GIS) support work in both provinces.

What are the expected results?
There are three programme outputs: / Decisions by sub-national governments are based on robust evidence, monitored against 3 indicators: / District budgets are based on evidence of people’s needs / Service improvement pilots are evaluated and successful pilots are adopted by provincial governments / Government uses GIS to monitor and plan quantity and quality of services / Sub-national government services are more responsive to people’s needs, monitored against 3 indicators: / Proportion of budget allocated to primary health and primary education at district level / Number of departments / districts using smart information communication technology / Accessibility by the public to budgetary information / Strengthened sub-national government capability to deliver basic services, monitored against 3 indicators: / Sub-national planning is more performance orientated (especially for health and education) / Percentage of budget reaching service delivery units / Increased provincial resources to finance services: number of activities delivered / The programme outcome is Poor people in Punjab and Khyber Pakhtunkhwa report that services are better meeting their needs, monitored against 2 indicators: / Household satisfaction with basic health and education services[1] / Access to improved health and education services:[2] / Gross Enrolment Rate for girls at government primary schools / Percentage of diarrhoea patients consulting Rural Health Centres (RHCs) / Basic Health Units (BHUs)
[1] This captures government and private sector facilities for education (primary, middle, and high), and basic health care
[2] This captures only government facilities for primary education, gross enrolment rate (GER) and diarrhoea treatment at Rural Health Centres / Basic Health Units (RHCs/BHUs)

What is the context in which UK support is provided?
Weak governance lies at the heart of Pakistan’s economic and social problems. Good governance requires the Government to deliver better services to its citizens, including poor people. SNG was designed to respond to this challenge in KP and Punjab – the two focus provinces across DFID Pakistan’s portfolio. The programme’s theory of change, as set out in the business case, is presented in the diagram below: / The programme was designed to recognise the differences in the institutional environments of the two provinces, and was built on lessons learned from previous DFID provincial reform programmes in both provinces. More broadly, SNG was specifically designed to complement other activity on education, health, accountability and the rule of law being undertaken by each provincial government, DFID and other donors. / The rationale behind the main components of SNG was that: / Technical assistance is closely aligned with governance programmes of the EU and World Bank. The SNG-funded EFOs in particular were designed to support the World Bank to initiate work whilst waiting for their funding to become available / Challenge funds should incubate new service delivery innovations at district level, demonstrate the value of devolved governance, and encourage provincial governments to replicate successful pilots / Conditional grants in KP should expand Output-Based Budgeting (OBB) to 6 districts, building on a successful baseline of 2 districts under the SNG predecessor programme, PRP (Provincial Reform Programme) / The business case was approved by DFID’s Secretary of State in August 2012. An official exchange of letters with Pakistan’s Economic Affairs Division (EAD) was signed in March 2013. Following a competitive tender under the Official Journal of the European Union (OJEU), a consortium led by Oxford Policy Management (OPM) and Coffey was contracted to manage the technical assistance and challenge fund components of SNG in both provinces. The programme started in April 2013 with a 6-month inception phase. This annual review covers the first 12 months of programming, April 2013 to March 2014. / Services better meet the needs of poor people in KP and Punjab / Increased government capability and responsiveness to deliver services / Improved state-society relations / more stable democracy in Pakistan / SNG Theory of Change

## Section A: Detailed Output Scoring

Output 1: Decisions by sub-national governments are based on robust evidence
Output 1 score and performance description: / A: Output met expectations / Indicator Targets for Year 2013-14 / (Punjab) Actuals for Year 2013-14 / (Punjab) Targets for Year 2013-14 / (Khyber Pakhtunkhwa) Actuals for Year 2013-14 / (Khyber Pakhtunkhwa) / Output Indicator 1.1: District budgets based on evidence of people’s needs 2 needs assessments done (one per district) with a focus on women and girls On track: Needs Assessments for Hafizabad and Bahawalnager 2 needs assessments done (one per district) with a focus on women and girls On track: / Needs Assessment successfully piloted in Nowshera district, on track in Karak and Haripur / Output Indicator 1.2: Service improvement pilots are evaluated and successful pilots are adopted by provincial governments Challenge Fund institutional arrangements agreed and Round 1 launched / Pilots identified and 2 supported with technical assistance in 2 districts Achieved: Round 1 launched / On Track: / only a few weeks behind schedule Challenge Fund institutional arrangements agreed and Round 1 launched / Pilots identified and 2 supported with technical assistance in 2 districts Achieved: / Round 1 launched / On Track: / only a few weeks behind schedule / Output Indicator 1.3: Government uses GIS to monitor and plan quantity and quality of services 2 pilot districts selected for GIS introduction Achieved: Vehari and Sheikhupura selected 2 pilot districts selected for GIS introduction Achieved: Karak and Haripur selected
Progress against expected results: / PUNJAB / Indicator 1.1 / Following piloting in KP, the work on needs assessment has started in Punjab. At the request of government, the health sector is being prioritised and needs assessments are being undertaken in two districts – Hafizabad and Bahawalnagar. A concept note, approved by the Government of Punjab (GoPb), focuses on generating evidence on primary healthcare accessibility, coverage and quality to inform district budgeting and planning. / The review team saw evidence of good buy-in from district administrations. However, impact is likely to be limited in the absence of the implementation of the 2013 Punjab Local Government Act, as districts have little space for expenditure re-prioritisation. This is beyond the control of SNG, but the programme will nonetheless advocate for local elections to take place in the coming year. / Indicator 1.2 / The SNG challenge fund is among very few initiatives in Pakistan which encourage organisations to develop improved service delivery models within the government system. The first round focuses on education, with an allocated budget of £500,000. During this first year of the programme, the design and governance arrangements of the challenge fund were finalised, and the fund was launched successfully. The review team found that the design of the challenge fund and the quality of communications have been very strong. The process has been rigorous and consultative, with strong demand and buy-in at both provincial and district levels. Over 200 expressions of interest were submitted. At the end of March 2014, fifteen had been shortlisted and invited to submit full applications. / Indicator 1.3 / The Geographical Information System (GIS) scoping mission, conducted during the SNG inception phase (April-October 2013) produced good analysis of the status of GIS knowledge and usage in Punjab, and proposed a low-cost GIS model for rollout in SNG districts. Two districts, Vehari and Sheikhupura have been identified and agreed with the Government of Punjab as pilots for this activity in 2014/15. The review team saw evidence of very strong demand from district officials for this work. A follow up mission is set to develop a detailed implementation plan for the establishment of GIS at district level during 2014. / KHYBER PAKHTUNKHWA / Indicator 1.1 / SNG successfully piloted a needs assessment in Nowshera, inspecting 67 government primary schools (of which 27 were girls’ schools) using mobile phones and spatial mapping. The exercise demonstrated the effectiveness of focus group discussions, Public Financial Management (PFM) analysis, as well as the use of EMIS (Education Management Information System) and spatial mapping data for policy work. The pilot provided important findings about both district planning and budgeting processes, as well as about the needs assessment process itself. / The terms of reference for two additional needs assessments (Haripur and Karak) have been agreed with the KP Elementary and Secondary Education Department (ESED). These assessments were conducted in March 2014, with reports to issue shortly. / Indicator 1.2 / The design and governance arrangements for the KP challenge fund were finalised. A working group has been notified and institutional arrangements for the challenge fund have been approved by the Government of KP (GoKP). A media and communications campaign to support the challenge fund launch was successfully undertaken alongside nine pre-launch orientation sessions held in Peshawar and all SNG districts. Over 160 expressions of interest were made to the challenge fund. At the end of March 2014, twelve had been shortlisted and invited to submit full applications. / Indicator 1.3 / Plans to support the development and expansion of GIS work in KP build heavily on the SNG inception phase mission. Two districts, Karak and Haripur, have been identified for pilot GIS activity in 2014/15, with the agreement of the Government of KP. The follow-up mission in March 2014 develop a detailed implementation plan, with a report due for submission in early April. / The Urban Unit facility in KP, in contrast to that of Punjab, is very basic; it is likely that SNG’s GIS work will concentrate on KP, possibly encouraging information sharing and training from Punjab’s Urban Unit. / SUMMARY OUTPUT 1 / In both Punjab and KP, this output has met expectations. There has been good overall progress in the first year of programming, particularly in terms of establishing and launching the challenge funds and pre-planning for future GIS support. The KP pilot needs assessment proved invaluable in terms of learning lessons on process, notably that it could be more participatory. Gender is already a key consideration but other exclusion dimensions such as children, minorities and the disabled could be focused on more, as relevant. OPM has worked effectively both in technical terms and in terms of building awareness of and interest in SNG at both provincial and district levels. / Recommendations: / Consider investing more in political engagement and influencing in both provinces to complement the set of technically robust interventions / If implementation of the local government acts in each province is delayed (i.e. local bodies are not in place by 01 July 2014) the programme will need to reconsider its workplans and priorities for 2014/15 / The programme will need to retain its flexibility of design to meet ongoing high demand from district offices for short-term technical assistance / Consider ways of consulting the public in district needs assessments to ensure that district plans are truly representative / Ensure that SNG challenge funds are closely coordinated with other similar challenge funds and initiatives, including those funded by DFID (Alif Ailaan/Ilm Ideas) / Ensure effective monitoring of challenge fund projects to assess how far excluded groups are being reached, and that all initiatives are implemented in a conflict sensitive manner / District GIS activity will need field testing and evaluating before going live / Impact Weighting: 30% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 2: Sub-national government services are more responsive to peoples' needs
Output 2 score and performance description: / A: Output met expectations / Indicator Targets for Year 2013-14 / (Punjab) Actuals for Year 2013-14 / (Punjab) Targets for Year 2013-14 / (Khyber Pakhtunkhwa) Actuals for Year 2013-14 / (Khyber Pakhtunkhwa) / Output Indicator 2.1: Proportion of budget allocated to primary health and primary education at district level Need-based transparent formula for devolution of resources to districts approved by PFC On Track: / Work ongoing to provide policy choices and is highly valued by GoPb Need-based transparent formula for devolution of resources to districts approved by PFC On Track: Work ongoing to provide policy choices and is highly valued by GoKP / Output Indicator 2.2: Number of departments / districts using smart information communication technology 1 (Education or Health); 2 Districts On Track: Ongoing support to Vehari and Sheikhupura; improved SNG/EFO integration needed NA NA / Output Indicator 2.3: Accessibility by the public to budgetary information Baseline established On Track Baseline established On Track
Progress against expected results: / PUNJAB / Indicator 2.1 / Following ratification of Punjab’s 2013 Local Government Act, establishing a Provincial Finance Commission (PFC) became a priority for GoPb. SNG has done well by responding to government needs by providing technical assistance to the PFC process. This transparent, formula-based, inter-governmental fiscal transfer system ensures predictable revenue transfers to local governments and, if done properly, will promote improved fiscal behaviour in the province. / The assistance provided has involved a huge data collecting exercise on district expenditure and revenue. To date, district-level indicators of development and proxies for local tax bases, population figures, and past performance on key service provision have been collected. This has been followed up with consultations with provincial departments and district officials, and providing options for the provincial formula. Detailed briefings have been given to government counterparts, presided over by Secretary Finance. The Government of Punjab has repeatedly expressed its appreciation to DFID for this support. During the review itself, Finance Department strongly welcomed it and articulated very high demand for this ‘essential’ support. / Both Government and SNG staff recognise that the impact of technical inputs to the PFC will depend on future political approval and implementation, both of which are beyond the control of the programme itself. There is concern amongst senior provincial officials about the loss of central control implied by an effective implementation of any PFC award. Political will for full fiscal decentralisation is therefore questionable in Punjab. The programme should remain aware, and focus advocacy efforts to try to mitigate this. / Indicator 2.2 / World Bank teams funded by SNG are providing a variety of support to districts on smart management, including support to mining data produced through a so-called ‘Citizen Feedback Model’ (CFM) whereby citizens using public services in Punjab are specifically requested for feedback on the quality of the service they receive. Data are being collected for public health services across all 36 districts in the province. The World Bank team are currently reviewing the data for 2 pilot districts, Vehari and Sheikhupura, and designing a monitoring tool for district administrations. / Additional experimental work by the World Bank under this component is highly innovative and exciting. Reporting this work (both on process and substantive achievements) has been patchy to date, and greater engagement between World Bank and SNG is required in 2014. In January 2014, World Bank and SNG teams agreed a 6-month workplan to improve coordination. / Indicator 2.3 / SNG is looking at a range of options to enhance transparency and public access to budgetary information. The team reviewed the Open Budget Index (OBI) methodology (the recognised international standard for accessibility and transparency of budget documentation) and assessed its suitability for sub-national application in Punjab. In consultation with Finance Department, a questionnaire has been prepared to prepare a baseline of fiscal transparency in Punjab using OBI methodology. This will provide the basis for targets in subsequent years. It is the first time the OBI methodology is being used at a sub-national level anywhere in the world. The work itself is not a high priority for Finance Department but they are happy with progress and see its potential benefits. As part of this work, the programme is also reviewing Punjab’s Right to Information Act 2013 and mapping its implications for budgetary accessibility. / KHYBER PAKHTUNKHWA / Indicator 2.1 / Following the passage of the 2013 KP Local Government Act, SNG agreed to provide support to the development of the KP Provincial Financial Commission (PFC) award. Terms of reference have been agreed and short-term technical assistance is being provided. As in Punjab, the SNG team in Peshawar have collected data on fiscal capacity and needs of district governments.[3] District as well as Tehsil Municipal Authority (TMA) level expenditure and revenue items have been identified, consistent with the structure of the new local governments. The SNG team has emphasised that reported data with no validation may not serve the needs of transfer formulas because they may be contested by local governments. Wherever possible, socio-economic data have been sex disaggregated with further disaggregation into relevant age groups for health and education, gender parity, and antenatal coverage. / Next steps include developing options for the PFC award formula by April 2014. It should be noted that overall progress towards achieving the milestone has been hampered by delays in the implementation of the Local Government Act. Given these, it is expected that only a partial PFC formula will be used for the 2014/15 budget in KP, with full PFC implementation anticipated from 2015/16. Overall the work being provided by SNG in support of the PFC has the potential to lead to far more responsive sub-national government services. / Indicator 2.3 / GoKP’s Strategic Development Partnership Framework (SDPF) identifies ‘improved transparency and accountability by adopting international standards of budgetary systems and strengthening anti-corruption activities’ as a key priority. SNG is assisting the working group on improved transparency to update the government’s Public Financial Management (PFM) and anti-corruption reform strategies as a first step to building awareness and consensus with the government on adopting the Open Budget Index methodology to assess budget transparency and establish a baseline. / SNG has finalised terms of reference and a workplan and is currently holding discussions with key government officials. This activity is slightly behind schedule against its milestone, with the baseline likely to be established in April 2014 (rather than end of March). However the groundwork currently being undertaken is important to build dialogue with the government. The workplan is promising and there should be stronger results by the time of the next annual review. / SUMMARY OUTPUT 2 / There has been good progress generally, with some very high quality work on the PFC in both provinces. The work on budget transparency is slightly behind schedule, but extremely promising work has been done to lay the foundations of what is clearly going to be a complicated process of making budgeting more transparent. / Recommendations: / DFID should consider a targeted advocacy strategy for Government of Punjab to ensure quality and integrity of PFC design is retained (transparent and rules-based leading to sufficient and predictable financing for new local government bodies) / Review the milestones for indicator 2.1 to assess the realism of the percentage increases in budget being directed to service delivery in a post-PFC award environment. Clear agreement is needed between the Government of KP and the programme on how these milestones will be calculated / Encourage closer integration between World Bank ICT EFO teams and SNG to enable effective practical application of pilots in districts. This should include field testing the mapping work currently being supported at the Lahore University of Management Sciences (LUMS) / Clarify OBI milestones which should refer to percentage (or index) points rather than simply percentage increases from baseline / Impact Weighting: 30% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No
[3] During the reporting period, extensive data on the fiscal capacity and service delivery needs of district governments were collected and reviewed for the design of the PFC award. Primary data on fiscal information, population, and key performance indicators on education and health was collected from Finance, Local Government & Rural Development Departments, the Provincial Bureau of Statistics, the Education Management Information System and the District Health Information System. Secondary sources of data to support the simulation model include the four rounds of PLSM survey since 2004-05, MICS 2008, Districts Indices of Multiple Deprivations for Pakistan 2011, Alif Ailaan Pakistan Districts Education Rankings 2013, and the report by the Social Policy & Development Centre on ‘Predicting Sub-National Poverty Incidence for Pakistan (2013)’.

Output 3: Strengthened sub-national government capability to deliver basic services
Output 3 score and performance description: / B: Output moderately did not meet expectations / Indicator Targets for Year 2013-14 / (Punjab) Actuals for Year 2013-14 / (Punjab) Targets for Year 2013-14 / (Khyber Pakhtunkhwa) Actuals for Year 2013-14 / (Khyber Pakhtunkhwa) / Output Indicator 3.1: Sub-national planning is more performance orientated (especially for health and education). Basis for delegation of Health and Education budgets to districts agreed On Track: / Good progress on DEAs, which may provide basis for future performance planning. No progress on DHAs. Explicit discussion of performance budgeting limited Basis for performance-oriented health and education budgets agreed Partially Achieved: / Key achievements are ensuring the linkage between the SDPF, PTI policy, the medium-term budget framework and the budget call circulars is strengthened and deepened / Output Indicator 3.2: Percentage of budget reaching service delivery units Expenditure tracking for basic health and primary education agreed in SNG districts and % of non-salary budget allocations reaching service delivery units in a timely fashion established Partially Achieved: / SNG is directly supporting QESDS by mapping fund flow Expenditure tracking for basic health and primary education agreed in SNG districts and % of non-salary budget allocations reaching service delivery units in a timely fashion established Partially Achieved: / Weak year on conditional grants. Improved controls now in place. Education delivering better than health. / Output Indicator 3.3: Increased provincial resources to finance services: number of activities delivered Plan agreed for SNG to support expenditure saving or revenue raising activities On Track: / Concept discussed and evidence of support from FD and ED very strong Plan agreed for SNG to support expenditure saving or revenue raising activities Achieved: Excellent support to revenue authority and Education payroll audit
Progress against expected results: / PUNJAB / Indicator 3.1 / In Punjab, District Health and Education Authorities (DHAs and DEAs), formed under the 2013 Local Government Act, have become the focus for improving service delivery at district and sub-district levels. The law indicates the general structure and functions of these authorities, but provides no framework for their operation. / SNG is assisting the School Education Department (SED) to develop institutional arrangements and rules for the operation of DEAs. The support provided has been high quality, timely and very well appreciated by stakeholders. This, in combination with PFC work and needs assessments, could form the basis of more performance-focused planning across the province. Nonetheless, success will require full implementation of the Local Government Act. There has not been any real progress on DHAs, though SNG has been very active in discussions with the Department of Health and the respective DFID sector programme. Stakeholders are aware that the programme stands ready to support as and when feasible. / The discussion of performance budgeting beyond DEAs is limited. There is no obvious interest at provincial level and delayed Local Government Act implementation is limiting interest at the district level. One of the next steps on this output will be to develop and agree a PFM strategy with the Government of Punjab. / Indicator 3.2 / One of the key challenges in Punjab is to track funds and expenditure at the level of service delivery unit (schools and Basic Health Units). At the moment, such information is available only at the district level and not beyond. The World Bank is leading a Public Expenditure Tracking Survey (PETS) in the education sector, with the SNG team fully engaged by supporting them on the development of a concept note on Quantitative Expenditure and Service Delivery Survey (QESDS). SNG’s contribution has been acknowledged in the official notification of the PETS by Finance Department. SNG work on DEAs will also feed into this. / Progress here is again limited by delays in the implementation of the Local Government Act, but SNG has moved sensibly forward where it can. SNG has prepared a draft report on fund flow mechanisms and benchmarking the tracking mechanisms, which will lead into forward work, including the development of provincial PFM strategy. / Indicator 3.3 / There has not been any major achievement on increased resources in Punjab. The programme was primarily engaged on two areas: (a) education payroll audit, and (b) process re-engineering of stamp duties. As a result of SNG engagement, the Finance and Education Departments committed to the payroll audit – no small achievement in itself. Given that more than 30% of the Government of Punjab workforce is in the Education Department, this work has the potential for significant savings efficiencies in the future. / KHYBER PAKHTUNKHWA / Indicator 3.1 / This milestone is rated as being partially achieved in KP. The review team considered that the 2014 target did not appropriately reflect the work and progress made by the programme, hampered by lack of progress to implement the 2013 Local Government Act. Once the act comes into effect, existing milestones for years 2 and 3 of SNG are likely to remain relevant and to be met. / Over the past year, the KP SNG team have played an instrumental role in improving the sub-national planning process to ensure that it is more performance-oriented in fiscal year 2014/15 than in any previous year. Key achievements are ensuring the linkage between the Government of KP’s Strategic Development Partnership Framework (SDPF), political party policy, the medium-term budgetary framework, and a strengthened budget call circular process. / The programme has supported various technical improvement to provincial budgeting, including improving Forward Budget Estimates (FBEs) 2014-17, improving the provincial Budget Strategy Paper (BSP), and setting indicative budget ceilings (agreed by Finance and Planning Departments). / At the district level, the SNG team has undertaken: / Consultative workshop for health department officials on conditional grants / Development of a toolkit for district health plans and training of district officials / Development of district health plans in the six SNG districts, all approved by Director General (DG) Health Services / Coordination with DFID’s Education Support programme in the province, KESP, to ensure a similar process for district education plans / This progress at the provincial level is to be commended and is part and parcel of achieving progress towards the overall indicator. There is a significant amount of work to prepare districts for a more performance-oriented budgeting process following the PFC award. Thus, whilst the milestone for the past year was only partially achieved, the review does not recommend changing the milestones for future years. They remain appropriate and relevant to the focus of the programme. / Indicator 3.2 / The SNG team has committed significant resources to supporting the provincial government to scale up the implementation of the conditional grants programme. These activities are reflected under this milestone, although this was not the sole intention of indicator 3.2. SNG has focused more on conditional grants over the past year than anticipated during programme design due to concerns raised by audit reports. Key corrective actions have now been put in place. These should be useful to both DFID and GoKP during the implementation of the PFC award. Specifically, the programme has: / Worked on support to the monitoring of conditional grants and timely follow-up in response to continuous audit findings – working with departments of Finance, Health and Elementary & Secondary Education (ESED). This has improved the identification of district-level budget execution challenges / Reviewed audit findings (with DG Health Services and the audit firm, Deloitte Pakistan) and provided advice to the Government of KP on appropriate corrective actions to be implemented at district level. This has started thinking on how to manage a conditional grants component of the PFC award in the future / More broadly, support has been provided to the Provincial Finance Controller to develop guidelines on how districts should access and manage funds once the 2013 Local Government Act is implemented. / Indicator 3.3 / A significant amount of progress has been made under this indicator. Specifically SNG has held discussions with government on priority areas for support to revenue generation. Three priority areas of support were agreed: / SNG contracted, managed and quality assured support provided through FEnD (a local consultancy firm) to establish a KP Provincial Revenue Authority (KP PRA). The work on the KP PRA alone has potentially doubled the provincial service tax take within the span of one fiscal year (from Rs 4.3 billion in fiscal year 2012/13 to Rs 3 billion in the first half of fiscal year 2013/14) / Information Technology (IT) payroll audit undertaken of ESED and scope for efficiency savings identified / Work with Secretary Excise and Taxation on a baseline survey of sales tax (currently underway) / Beyond the work on revenue generation, SNG has begun work on a comprehensive spending review, the SDPF (a key policy prioritisation exercise), and the integrated development strategy. These key policy documents should help to prioritise government spending and increase budget efficiency in future years. / SUMMARY OUTPUT 3 / SNG has made good progress on budgetary planning and resource savings. Further work is needed on expenditure tracking. The support to DEA institutional design in Punjab was described to the review team as ‘excellent’; this success is moderated by lack of progress on DHAs, although the team stands ready to respond to requests from government as necessary. Payroll audits in both provinces and the KP PRA are positive stories on resource savings. / On conditional grants, 2013 was a lost year. DFID, the SNG implementing team, and GoKP could all have done more to ensure more effective implementation as this component of the programme expanded. The impact that the May 2013 elections would have on this expansion was not fully anticipated by any stakeholder, and led to mismanagement and confusion amongst district level officials. The review team acknowledges the good work that all stakeholders are doing to put conditional grants back on course. / Overall the output best indicates the SNG team’s hard work and commitment to moving forward the key reforms that underlie the SNG programme. Continued commitment to reform across both governments, as well as improved collaboration between the Finance and Planning & Development Departments in both provinces will be key to the success of SNG. Finalisation of a PFM strategy in Punjab must be prioritised in early 2014. / Recommendations: / Revisit PFM reform priorities between now and end September 2014 to ensure continued government commitment to producing and implementing PFM strategies / Consider a specific advocacy strategy on local government implementation in both provinces (possibly with the UK Foreign & Commonwealth Office, FCO) / Consider how best to encourage design work on DHAs in Punjab, working closely with the DFID Health Team / Ensure all conditional grant and PFC work is undertaken in a conflict sensitive manner / Clarify the milestones towards increased provincial resources under indicators 3.1 and 3.3 / Impact Weighting: 40 % / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money

1. Progress and results
1.1 Has the logframe been updated since last review? Yes / The logframe was revised during the programme inception phase, as planned for and set out in the business case. This involved extensive consultation within DFID, OPM, the World Bank, and with government counterparts. / The review team recommends following revisions to the logframe: / Review where indicators can be sex disaggregated / Revisit the number of beneficiaries for output indicators 1.2 and 2.1 and clarify whether these figures represent the total population in each of the districts in which we are working or those in school and using health services over the period / Revisit the milestones for 2016 and 2017 under indicator 2.3 to reflect quality of use / Clarify the milestones for indicators 3.1 and 3.3 / 1.2 Overall Output Score and Description: A / Outputs 1 and 2 are reviewed as having met expectations. Output 3 moderately did not meet expectations. Given the respective weightings against each output, this annual review aggregates to an overall score of A in 2013/14. / 1.3 Direct feedback from beneficiaries / Various Punjab and Khyber Pakhtunkhwa government officials met during the review expressed strong support for the programme, and welcomed its various components and initiatives. Punjab’s Secretary Planning & Development expressed strong support for the management of SNG, and was complimentary about the quality and openness of the working relationship between DFID and GoPb. The District Coordination Officer (DCO) in Vehari (southern Punjab) echoed the ownership of the programme and requested flexible technical assistance for district planning and monitoring functions including capacity building of middle-tier district administrators. / Discussions with challenge fund applicants and others during the review suggested that the challenge fund has been well communicated and that applicants are comfortable and understand the process for applying. / The review recommends a regular beneficiary feedback and monitoring going forward. / 1.4 Summary of overall progress / As a predominantly technical assistance programme in a complex environment, SNG has done well to anchor itself as a key reform partner in both provinces. Outputs 1 and 2 have met expectations, although output 3 is assessed as moderately not meeting expectations. As designed, in its first year, the programme has both successfully established itself administratively (finding and setting up offices; recruiting staff) as well as initiated substantive technical work, based on government demand. The programme has achieved a number of substantive quick wins by supporting ground work on the PFC, DEAs and RTI legislation in Punjab and support to the KP PRA. The KP ESED payroll audit is a ground-breaking initiative in the province that will substantially contribute towards improved resource efficiency in future years. The Government of Punjab is not far behind on this, having committed to the first ever payroll audit in its own ESED. There is good ground work underway in both provinces on fiscal transparency, Medium-Term Budgetary Frameworks and expenditure tracking despite constraints due to limited fiscal space for districts. The needs assessments and GIS work through SNG are both valued inputs for district level planning. The design and launch of challenge funds have been robust and there is a clear buy-in and excitement amongst government counterparts. SNG has established an excellent platform on which to build itself in coming years. / Conditional Grants are less of a success story and there are important lessons to be learnt for DFID, OPM and GoKP. The work on putting them back on track is ongoing and will be closely followed up with technical assistance and regular dialogue with Government. / Some concerns about the sustainability and operationalisation of mobile governance innovations were raised by Government officials when reviewing the World Bank EFOs. The SNG Punjab team and World Bank colleagues must continue their dialogue on prioritisation and collaboration. / Overall, the review team found that the technical substance of SNG’s first year has been exceptional; the programme’s flexibility of approach and responsiveness to government demands have proven the logic of the original programme design. It will remain the case that SNG is vulnerable to political economy developments in each province, notably around devolution of government service delivery below the provincial level. All SNG stakeholders must remain aware of this reality and adjust activity and advocacy accordingly. / 1.5 Key challenges / Political ownership: Strong ownership of the SNG programme by government counterparts does not automatically translate into an ownership of reform or commitment to improved service delivery. The biggest challenge for SNG’s strong technical activity will continue to be promoting and achieving ongoing political commitment to SNG work. / Bureaucratic engagement: The technical assistance component of SNG includes several staff on special leave from Pakistan’s government service. This is a strength of the programme given the team benefits from their institutional knowledge and social capital and also builds their professional and technical capacity. Nonetheless, the programme must watch against this meaning that SNG reduces its specific challenge function to government counterparts. There is a related risk that SNG faces on potential turnover of programme staff, if their duties are requested back by the respective governments, in particular at short notice. This risk is considered manageable by the programme implementer. / Delay in Local Elections: In the absence of elected local governments, the programme may not deliver its outcomes related to fiscal devolution to the districts. The PFC awards and devolution of the development budget to the districts are clearly linked to the timeline of local government elections. The review recognises this political reality and recommends considering alternative activity in the event local elections are not held. / Programme coherence: SNG is made up of 6 distinct components (only 4 of which have been initiated in the first year of activity). It will be important to monitor that each component contributes to the broader programme outcome. The review found clear evidence that this is happening. Some caution was raised about coordination with the World Bank. In addition, the challenge fund implementation in the next two years of programming should be closely monitored to retain over-arching coherence and impact of this component of the programme. / Security: Access to KP remains a challenge for DFID and OPM staff. It is unlikely that DFID staff will ever be able to visit the SNG office in south KP. OPM staff have fewer access issues but they rely heavily on their security team for any movement on the ground. They must retain their regular engagement with British High Commission Security Section. / 1.6 Annual Outcome Assessment / Outcome indicators rely on the Pakistan Living Standards Measurement survey (PLSM). Data are not yet available. The review therefore cannot comment on specific levels of progress at outcome level. Nonetheless, it can be said that the programme has established a good basis on which to build, and a positive trajectory towards achieving the outcome over its lifetime.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / The first year of the programme experienced relatively slow spend mainly due to a design-heavy inception phase. Spend on the conditional grants component was also interrupted due to mismanagement issues. This led to a revision of the programme spending forecast in October 2013. Since then, the project has been on-track against financial forecasts. / 2.2 Key cost drivers / In its first year, the programme has spent £6,314,117 (up to March 2014): / Technical Assistance (via OPM): £2,534,117 / Financial Aid to KP (Conditional Grants): £2,500,000 / EFO Contributions to World Bank: £1,280,000 / 2.3 Is the project on-track against original timescale: Yes / Largely, SNG technical assistance has been provided according to the programme workplan. Timeframes of some components, such as awarding of challenge fund grants and approval of the PFC awards, have slipped into next year. It is correct to keep the programme’s design flexible to respond to emerging challenges, opportunities and requests from either partner government. It is recommended that DFID and OPM review the timescale and milestones once every quarter to reflect this. / The World Bank EFO component is also on track. Excellent progress has been made to establish, expand and update the Punjab Citizen Feedback Model. There are some concerns around prioritisation and targeting, and a consequent lack of impact. The workplan produced by World Bank, DFID and OPM should mitigate this. / The major concern on deliverables has been around the KP conditional grants. The programme has resolved the challenges adequately to ensure more effective progress and delivery in the second year of implementation. Progress on budget reform may mean that this component of the programme is combined into the KP budget in future years.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Local elections scheduled for 30 January 2014 in Punjab have been postponed with no new date set. In the programme’s next year of operation, this will likely affect progress on Outputs 2 and 3 on the degree of government responsiveness to people (more easily done with vibrant local democratic institutions in place). / Key senior vacancies in the Punjab health department may also affect programme effectiveness in that sector. / 3.2 Where an evaluation is planned what progress has been made? / The programme business case made a number of evaluation-related commitments for the first six months, including: / Confirming indicators with relevant stakeholders / Compiling an inventory of Monitoring and Evaluation (M&E) frameworks being implemented by DFID in Punjab and KP / Designing a detailed M&E framework with written guidelines/operating manual / Undertaking research, studies and surveys to establish missing baselines and fill gaps in the theory of change, as well as to measure the impact of the programme on corruption / Establishing a robust monitoring system for the programme / Most commitments were met during the past year. The review found that a very good monitoring system has been developed which is clearly very effective. / However, there has been limited progress on filling evidence gaps in the theory of change. More progress on written evaluation guidelines could also have been made. / The review raised a number of concerns over some logframe indicators; not least that progress against impact level indicators will not reflect provincial developments. Sex disaggregation of indicators also needs review. See Section B, 1.1. / The review also found that whilst M&E arrangements in place on the programme are sufficient, the programme to date has focused attention on monitoring and not evaluation. An evaluability assessment has been commissioned and will form an important element of the programme in future years. Evaluation arrangements for the challenge funds appear satisfactory at this stage with project staff working closely with the applicants to ensure that proposals are evaluable and later assessed. While for the majority of projects these relatively light touch arrangements are fine, any potential game-changing ideas to emerge from the challenge funds will need to be more thoroughly evaluated. This will be undertaken by the independent programme evaluator.

4. Risk
4.1 Output Risk Rating: High / On the basis of the complexity of the operating environment and political economy of reform in KP and Punjab, the original risk of the programme was rated high. The review team did not find any evidence to suggest the rating needs to be revisited. / 4.2 Assessment of the risk level / While there is no change in the risk level, the review team underlined the importance of the challenges facing the programme set out in Section 1.5 above. / Risk of funds not being used as intended / The technical assistance component has robust controls in place, including OPM’s own internal audit of its work on SNG, third-party audit of the conditional grants component, and robust programme management and delegated authority controls. There are plans in place to conduct due diligence for all the grantees under the challenge funds. DFID has received monthly financial reports and invoices. All long- and short-term technical assistance resources are approved by DFID before deployment. The robust M&E programme team ensures regular reporting against the workplans and logframe. All these good practices effectively reduce the risk of any misappropriation of DFID funds. / There is no formal financial reporting requirement for the World Bank EFO component, in line with normal EFO practice. Nonetheless, the World Bank in Pakistan has agreed to provide narrative reports for its work on SNG, and have agreed a forward workplan on the ICT EFO. A monthly EFO coordination group has also been put in place. More broadly, the World Bank’s internal controls are robust and were rated highly in DFID’s 2010 Multilateral Aid Review (MAR). For all these reasons, the review team is content that DFID has adequate assurance on the use of DFID funds in this component. / On the conditional grants component, DFID and GoKP receive monthly audit reports from the third-party auditors. In September 2013, concerns were raised around misappropriation of funds in conditional grants. These were mainly around non-compliance in procurement, non-availability of paper-work, and unauthorised transactions. This was immediately raised with DFID’s Counter Fraud Unit (CFU) (Quest no 4162622). DFID has since been in regular contact with all stakeholders (GoKP; OPM; CFU). The Government of KP has initiated an internal inquiry, as well as established a Conditional Grants Oversight Committee at provincial level to review progress. DFID is satisfied that all audit findings have now been addressed (Quest number: 4307550). Actions taken to support government officials’ increased understanding of the conditional grants process mean that the likelihood of similar findings in future years of the SNG programme have been substantially reduced. DFID will continue to work very closely on this component of the programme. / Climate and Environment Risk / The SNG programme, with its focus on governance and capacity building, is unlikely to have negative impacts on climate change or the environment. In its first year of programme implementation, SNG focus districts did not face any natural disaster or climate change and the programme activities therefore remained largely unaffected. The principal climate and environment risk implications for the programme are: / There are no technical assistance funds being directed into infrastructure development, or any other area that might be considered mal-adaptive. The review recommends using technical assistance to raise awareness in government about climate change issues and to undertake measures in this regard, e.g. introducing a climate lens in the planning and budgeting cycle / The GIS component of programme, together with the spatial mapping work conducted under the ICT EFO, provide an opportunity to enhance structures and systems for assessing climate vulnerability and risk in Pakistan / A large portion of funds under conditional grants are directed towards small infrastructure development such as classrooms and other facilities within primary schools and Basic Health Units (BHUs). During the conditional grants pilot (before SNG started), these construction plans were cleared by a government-contracted engineer. The review recommends reintroducing this protocol now that conditional grants have been expanded. SNG can also draw upon the technical assistance being provided under DFID’s education programme in KP, KESP, for school construction / The programme could also benefit from more regular inputs of an Environment and Climate Change expert

5. Value for Money
It was agreed between DFID and OPM that, for the first annual review of the programme, a Value For Money (VFM) assessment would only be based on economy indicators. There are insufficient data to make robust assessments of programme efficiency and effectiveness at this time. A methodology for assessing programme efficiency and effectiveness in years 2 and 3 of the programme is in place. / The diagram below shows the breakdown of total programme input costs and results achieved during the first year. / The key indicators of SNG economy, as presented in the VFM framework, are: / Average unit cost of different types of technical assistance (e.g. international, national) compared to contract benchmarks (monetary indicator) / Average unit cost of major reimbursable items (e.g. flights, daily subsistence allowance) compared to contract benchmarks (monetary indicator) / Supplier negotiation and contract management to ensure costs remain competitive (process indicator) / One-off cost savings on resources secured through negotiation (monetary indicator) / Based on these measures, the review team estimate that the SNG programme currently represents good value for money. / Efficiency and effectiveness indicators have also been identified for the programme to evaluate once sufficient data are available: / Percentage increase in proportion of district budget allocated to pro-poor expenditure / District budgets are increasingly based on evidence of needs / Number of challenge fund pilots assessed as successful and lessons disseminated / Trends in average cost of support to specific initiatives over the life of the programme / Provincial and district budgets reflect the extent to which SNG is achieving results / 5.2 Commercial Improvement and Value for Money / OPM was contracted through a competitive process, which included rigorous negotiation over financial costs for the entire programme timeframe. During this process, DFID achieved overall cost savings of £621,000. / The service provider team structure was analysed and reduced. Over the past year, the number of days worked by the permanent technical assistance team has been firmly monitored and rates for short-term technical assistance have been negotiated on a case by case basis. Similarly, reimbursable expenditures have been scrutinised each month. Standard policy on SNG procurement procedures was followed, i.e. requiring a minimum of three quotes from suppliers in order to maintain transparency and value for money. As a result, average international airfare costs over the past year have been £844, less than the contractual benchmark average unit cost of £1000. Similarly, the average unit cost of hotel accommodation has been £78 in comparison to the contractual benchmark average unit cost of £150. / The average unit cost of national technical assistance during the period has been £221/day compared to an average unit cost agreed over the full life of the programme of £264/day. This suggests that national technical assistance was obtained at an average fee rate some 12% below the benchmark. / 5.3 Role of project partners / The role of project partners in ensuring VFM can be demonstrated by the following examples: / The agreed outputs under the inception phase (April to October 2013) were delivered for about half the amount agreed in the inception budget, i.e. £1.3 million against £2.41 million. / The programme has also secured one-off cost savings on the major contracts negotiated during the period: / The initial proposal for support to the Khyber Pakhtunkhwa Revenue Authority totalled USD 209,000. The contract negotiated by OPM totalled USD 80,000 (£49,000), and included an additional input of 20 days from an external tax specialist / The KP PRA was successfully established in July 2013 and collected Rs. 2.2 billion (£12.9 million) General Sales Tax (GST) on services in the first four months of its establishment. SNG’s intervention fast tracked the process by at least six months, achieving a net benefit of at least £17.6 million for Khyber Pakhtunkhwa / The continuous audit of SNG’s conditional grants component was initially costed at Rs 31.5 million. OPM negotiated this to down to Rs 26 million, thus realising a saving of Rs 4.5 million, or £26,500. / 5.4 Does the project still represent Value for Money: Yes / The programme is clearly doing well on VFM when viewed from an economy perspective, and has successfully positioned itself as a reliable reform partner for both provincial governments. All the outputs are broadly on track. The theory of change of the programme (that improved government systems will contribute to improved service delivery in targeted districts) still holds. In the absence of either sustained results delivered to date or an impact evaluation, it is difficult to quantify value for money. Nonetheless, the trajectory of programme effectiveness is judged as positive. / Total Input / = £ 6.31 million / Technical Assistance / = £ 2.53 million / Establishment of Khyber Pakhtunkhwa Revenue Authority / Design of Pakistan’s inter-governmental fiscal transfer systems (PFC Awards) / Ensuring government services better meet the needs of poor people in Punjab and Khyber Pakhtunkhwa / Financial Aid / = £ 2.5 million / Externally Financed Outputs (EFOs) / = £ 1.28 million / Saving Punjab citizens Rs. 4000-5000 (£25-£32) per public service transaction as cost of corruption for property registration / Allowing citizens in Punjab to provide feedback on public service delivery. Over 3.6 million people have been contacted for feedback.

6. Conditionality
The only component of SNG where specific conditionality applies is on conditional grants in KP, provided through financial aid. The key conditions attached to this funding are: / Provision of an annual audit statements of accounts / Continuous audit and third party validation of the conditional grants funds, and / Actions taken to follow up the findings of the continuous audit reports / These conditions have largely been met over the past year. GoKP still needs to appoint a third party validator, but are likely to do so in the next quarter.

7. Conclusions and actions
This has been a good first year for SNG. The programme was designed to respond flexibly and responsively to partner government requests. In its first year of operation, it was anticipated that the programme should both set itself up (by finding offices; recruiting high-quality personnel; and agreeing governance arrangements) and start early technical support to the provinces of Khyber Pakhtunkhwa and Punjab. Both have been achieved. Indeed, despite the fluid political situation in both provinces following Pakistan’s May 2013 elections, SNG’s technical assistance has been described to the review team as exceptional; it is much appreciated by government counterparts in both provinces. The programme successfully completed its inception phase, on time and under-budget. The programme is in a good place to ensure broader activity and impact in the remaining 3.5 years of the programme timeframe. / Actions: / DFID needs to: / Consider investing more in political engagement and influencing in both provinces to complement the set of technically robust interventions / Consider a targeted advocacy strategy with the Government of Punjab to ensure quality and integrity of PFC design is retained (transparent and rules-based leading to sufficient and predictable financing for new local government bodies) / Encourage closer integration between World Bank ICT EFO teams and SNG to enable effective practical application of pilots in districts. This should include field testing the mapping work currently being supported at the Lahore University of Management Sciences (LUMS) / Consider a specific advocacy strategy on local government implementation in both provinces (possibly with the UK Foreign & Commonwealth Office, FCO) / Ensure regular inputs to the programme from a climate and environment expert / Ensure the independent evaluator is appointed / OPM needs to: / If implementation of local government acts is delayed, reconsider priorities for 2014/15 / Ensure that the programme retains its flexibility to enable short-term technical assistance to district offices / Consider ways of consulting the public in district needs assessments to ensure that district plans are truly representative / Ensure that SNG challenge funds are closely coordinated with other similar challenge funds and initiatives, including those funded by DFID (Alif Ailaan/Ilm Ideas) / Ensure effective monitoring of challenge fund projects to assess how far excluded groups are being reached, and that all challenge fund activity is undertaken in a conflict sensitive manner / Ensure field testing and evaluating for District GIS activity before it goes live / Review the milestones for indicator 2.1 to assess the realism of the percentage increases in budget being directed to service delivery in a post-PFC award environment. Clear agreement is needed between the Government of KP and the programme on how these milestones will be calculated / Clarify OBI milestones under indicator 2.3, which should refer to percentage (or index) points rather than simply percentage increases from baseline / Ensure that the construction work under conditional grants is cleared by an engineer. SNG can also draw upon the technical assistance being provided under KESP for school construction / Revisit PFM reform priorities between now and the end of September 2014 to ensure continued government commitment to producing and implementing PFM strategies / Consider how best to encourage design work on DHAs in Punjab working closely with the DFID Health Team / Ensure all conditional grant and PFC work is undertaken in a conflict sensitive manner / Clarify the milestones towards increased provincial resources under indicator 3.1 and 3.3 / Ensure regular beneficiary feedback and monitoring

8. Review Process
This annual review was led by DFID Pakistan’s SNG Deputy Programme Manager, alongside a core team of DFID Pakistan’s Evaluation Adviser and Social Development Adviser. In KP, they were joined by SNG’s KP Governance Adviser. In Punjab, they were joined by SNG’s Punjab Governance Adviser and a member of the Punjab Planning & Development department. The review was conducted during the week of 17-21 February 2014. The review included a desk-based review of relevant programme documentation and field visits to both KP and Punjab for face-to face interviews with key stakeholders and beneficiaries. A draft report was peer reviewed within DFID Pakistan by conflict, education, and infrastructure advisers, as well as a member of the British High Commission Political Section.