Type of Review: Annual Review

Project Title: Increasing coverage of Long lasting insecticide treated nets in Uganda

Date started: Dec. 2013	Date review undertaken: Dec 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe. / the detailed guidance (How to Note)- Reviewing and Scoring Projects. / the most recent annual review (where appropriate) and other related monitoring reports. / key data from ARIES, including the risk rating. / the separate project scoring calculation sheet (pending access to ARIES). / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing £19.9 million for two years through a delegated cooperation arrangement with the United States Agency for International Development (USAID) to support procurement and distribution of five million long lasting insecticidal nets (LLINs), as well as a behaviour change communication campaign designed to increase rational use of LLINs; and an evaluation that will seek to understand the impact of the campaign and what aspects worked well, to help other countries implement similar approaches. The original budget at approval of the project in November 2012 was £17 million; however following a request from Ministry of Health in late 2013 to cover a gap in the distribution budget, an additional investment of £2.9 million was approved on 20 November 2013. This cost extension was to enable DFID to support distribution of an additional 4.5 million LLINs, procured by the Global Fund to fight AIDS, Tuberculosis and Malaria (GFATM). Implementation of the project is through two existing USAID implementing partners, namely the Stop Malaria Project (SMP) and DELIVER (a private contractor) – various subcontractors, including the Malaria Consortium, are involved in distribution and communications. / The purpose of the project is increased use of LLINs among children under 5 years of age and pregnant women. The project has one component: procurement and distribution of LLINs in Uganda to achieve universal coverage of LLINs, contributing to the reduction of malaria related morbidity and mortality in Uganda. / The universal coverage campaign was launched on 10 May 2013 in Soroti District at an event presided over by His Excellency The President of the Republic of Uganda. It is a major initiative of the National Malaria Control Programme (NMCP) of the Government of Uganda (GoU) and its partners, to achieve universal coverage of LLINs in Uganda. As per the World Health Organization (WHO) recommendations, LLINs are distributed at no cost to all Ugandan households through a one-off mass distribution campaign, and routinely thereafter to all pregnant women and mothers of infants during ante-natal and immunisation visits. To carry out this initiative, Uganda needed at least 20 million LLINs for its estimated population of 33 million. The GFATM and the U.S. President’s Malaria Initiative (PMI) have committed to providing approximately 15 million LLINs; GoU requested that DFID supports procurement and distribution of the remaining five million LLINs. The mass distribution campaign is implemented by USAID with support from other funders, and overseen by NMCP. No financial resources are directed to GoU institutions.

What are the expected results?
The logframe was revised in November 2013, to reflect a cost and time extension to 31 December 2014. The expected impact and outcome did not change. / The expected impact of the project is: decrease in related malaria mortality and morbidity in Uganda. / The planned outcome is: increased use of LLINs among children under five years of age and pregnant women. / The outputs of the project attributable to DFID are: / Increased ownership of LLINs. / Proportion of households with at least one LLIN. / Number of LLINs procured and delivered through DFID support in 2013. / Increased awareness of the importance of using LLINs. / Awareness among women age 15 to 49 years about the benefits of using LLINs. / Percentage of villages covered through community sensitisation drive during mass LLIN campaign. / How will we know whether the results have been achieved? / The 2011 Uganda Demographic Health Survey (UDHS) will provide baseline values for LLIN awareness, coverage and utilisation. A Malaria Indicator Survey (MIS) will be carried out in November 2014, and with support from DFID the results will be analysed to allow a before-and-after analysis of LLIN awareness, coverage and use, enabling reporting on 1(a) and 2(a) above. In addition, a DFID-funded evaluation will examine what worked and did not work in the distribution of LLINs. The dataset from the 2014 MIS will be available in early 2015, so this result is unlikely to be rigorous by the end of the project in December 2014. However, we will either work to get hold of an early dataset from the survey and analyse it ourselves, or use project management data to estimate the household coverage rate in the meantime. / Results from survey data in 2014 will confirm the level of morbidity and mortality reduction in Uganda as a whole, and the DFID-funded evaluation will enable an assessment of the extent to which this is attributable to the universal campaign. / Indicators 1(b) and 2(b) above will be determined from project management information. / The logframe was revised in November 2013 to reflect the additional investment of £2.9 million for the distribution of the nets.

What is the context in which UK support is provided?
Malaria remains one of the greatest public health problems in Uganda. Uganda records one of the highest (45%) prevalence rates of malaria in children in the world; significantly higher than in neighboring countries. Uganda’s tropical climate and seven months of rainfall allows perennial malaria transmission across 95% of the country. The country records nearly 16,000[1] malaria related deaths per year; children account for the majority of these; and it has the highest number of ‘probable and confirmed’ malaria cases in the world, according to the UN. / Reducing the high levels of morbidity and mortality associated with malaria in Uganda will require sustained delivery of proven prevention and treatment strategies at scale. The three primary interventions recommended by WHO’s Global Malaria Project (GMP) to tackle malaria are: a) distribution of insecticide-treated nets (ITNs), more specifically LLINs, to achieve universal coverage; b) indoor residual spraying (IRS) of houses to reduce and eliminate malaria transmission; and, c) diagnosis of malaria cases and treatment with effective medicines. Uganda’s inability in the past to take these proven anti-malarial interventions to scale means that malaria prevalence and malaria related deaths have remained high. / If it achieves anything close to universal LLIN coverage, Uganda will not only be able to protect the large number of people sleeping under these nets but may also be able to protect other households in the vicinity not using nets. Universal coverage and high use of LLINs would be likely to significantly reduce the burden of malaria in Uganda over the next three years which in turn would lead to wider socio-economic benefits through increased educational performance, reduced absenteeism from work and school, savings in healthcare spending and lives saved.
[1] WHO World Malaria Report, 2012

## Section A: Detailed Output Scoring

Output 1: Increased ownership of LLINs
Output 1 score and performance description: A / Output 1 has two indicators of which one is not met since it has not been measured yet, and another largely met expectations.
Progress against expected results: / Indicator Baseline 2013 milestones 2013 status Dec / 1.1 Proportion of households with at least one LLIN. 59% (2011) Not set Data will be available after MIS 2014 survey scheduled for November 2014. / 1.2 Number of LLINs procured and delivered through DFID support in 2013 0 Not set 2,950,000. The initial commitment was for DFID to procure five million nets, but the actual cost of LLINs and their distribution at the procurement stage meant that 4.45 million were affordable, of which 2.95 million have arrived in country. All 4.45 million are procured. / Summary of activities: / The reporting from the implementing partner indicates that procurement orders were placed for the total of 4,450,000 nets in three shipments which are now delivered to Uganda. / Recommendations: / The implementing partners should continue monitoring the pipeline to ensure that the distribution process continues to be carried out according to plan. / Impact Weighting (%): 80 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Increased awareness of the importance of using LLINs
Output 2 score and performance description: A / Output 2 has two indicators. One is not met since it has not been measured yet, and another met expectation.
Progress against expected results: / Indicator Baseline 2013 milestones 2013 status (Dec) / 2.1 Awareness among women age 15 to 49 years about the benefits of using LLINs Not set. Data will be available after MIS 2014 survey scheduled for November 2014. / 2.2 Percentage of villages covered through community sensitisation drive during mass LLIN campaign 0% (2012) Not set. 90% of Village Health Teams have been trained in effective net use. However, independent data on the % of villages covered will not be available until the MIS survey is complete. / Summary of activities: / The campaign is being implemented in a phased approach on a regional basis that started with the eastern region (Wave I – III), Central (Wave IV - V), Western (Wave V – VII) and lastly Northern (Wave VII -VIII). Each Wave represents districts neighbouring each other or with similar characteristics. / Each Wave of distribution was preceded by an intensive phase of pre distribution activities which involved setting up district task forces and sub county task forces, training of the district, Sub County, parish and village teams, conducting household registration and allocation of nets. The pre-distribution activities were completed in waves IV and V. Details of numbers reached for pre-distribution activities in these waves are shown in table below. / Achievements for pre-distribution activities in waves IV and V / Category Targeted Actual Percentage Achieved / District leaders sensitized 930 835 89.8% / District Task Force Members trained 521 468 89.9% / Sub County Leaders Sensitized 8,251 7,819 95% / Sub County Trainers / Supervisors trained 858 827 96.3% / LC1 Chairpersons sensitized 16,273 14,265 87.6% / VHTs trained 29,879 26,933 90% / The operating guidelines of the campaign created three subcommittees to handle the operational details of the campaign and reporting to the National Coordination Committee (NCC), which is the managing body of the campaign. During this period, the logistics subcommittee met 4 times and operations subcommittees 3 times; a number of issues were discussed and presented to the NCC. Key among these was what to do with surplus nets that were still in districts that had been part of the distribution campaign. It was agreed that these nets be quantified, collected and distributed in subsequent Waves. A total of 91,000 nets were collected from the districts, added to balances at the central warehouse, and allocated to subsequent Waves. The NCC also endorsed the operations subcommittee proposal that all buffers be removed from the quantification. / The other key issue discussed in the operations subcommittee was how to implement the data management centre effectively to cope with the increasing amounts of data from the districts. Following this meeting, a team from the SMP and the Johns Hopkins University Centre for Communication Programmes, together with MoH, conducted interviews for staff to run the data centre: a total of 80 data entrants, 10 data receiving and archiving staff, 8 supervisors, 2 systems administrators, 4 data managers and support staff were hired. However due to operational challenges in the data centre, there was a delay in starting the data entry process. These have now been sorted out and the team started entry in January 2014. There has also been a change in the numbers hired from 80 to 120 data entrants, and 8 to 12 data supervisors. / Recommendations / Implementing partners should continue to monitor data management through the established and now functional data centre. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? Y / The original project duration was for one year. However, in November 2013, the project was approved for further cost and time extension until 31 December 2014. The logframe was updated in November 2013 to reflect results for the additional cost to the project to enable distribution of 4.5 million nets bought by GFATM. / 1.2 Overall Output Score and Description: A / The description of progress above indicates that the project has met expectations against the milestones defined in the logframe. However, progress has been much slower than expected. Assurances provided by the SMP in January that 100% of districts would have been covered by the campaign by end March 2014 have not been met, with 37% of districts representing some 20% of the population of the country still to be reached. / 1.3 Direct feedback from beneficiaries / Direct feedback from beneficiaries was collected through structured interviews carried out by the PMI team. For example, feedback was obtained from beneficiaries in the districts of Kabarole and Rubirizi during the distribution of nets in Wave V. This was during a joint mission comprised of John Hopkins University (JHU), Ministry of Health, PMI and GFATM officials that visited western Uganda from 3 – 6 January 2014. The team was keen to find out whether the community had been adequately made aware of the availability of the LLINs, and how to use them, including how to minimise adverse reactions from the pyrethrin in the nets. In both districts, effective use of nets was apparent and beneficiaries were positive about the campaign and the expected health benefits and convenience of using nets that did not need to be re-treated on a regular basis.
1.4 Summary of overall progress / The project is progressing well, and mainly according to plan, with minor delays in reaching the final wave of districts in the north of the country. / To date, distribution has been completed in 63% of districts (n=112); during the reporting period, three waves received nets: Wave II, III and IV; while pre-distribution activities were completed in 15 wave V districts in early January 2014.
1.5 Key challenges / One of the major challenges was the total cost of five million nets. Upon analysis in early 2013, it was realized that the £17.5 million allocated to DELIVER could procure 4,450,000 nets and not five million nets as earlier estimated. However, PMI used its own programme resources to procure an additional 550,000 nets in order to arrive at the five million net total requested by the NMCP and originally agreed with DFID. / The other major challenge was the delay in net delivery and distribution. The former was caused by an upsurge in global net orders, with the result that net manufacturers could not deliver as per earlier estimated timelines, and the latter was due to a delay in finalising the net distribution schedule and micro plan among major malaria stakeholders in the country. Reporting from DELIVER indicates that the procurement was carried out through 3 planned shipments. / In addition, in some parts of the country, bad weather and a poor road network contributed to delays in the arrival of nets to final distribution points. In some eastern Uganda districts such as Sironko and Kween, for example, a combination of rain and damaged seasonal roads contributed to the delay of net delivery to final beneficiaries by up to two weeks.
1.6 Annual Outcome Assessment / It is still too early to determine outcome until the MIS has been completed.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Due to the need to procure and distribute a significant order of LLINs in a single campaign, DFID made a one-off payment of £16.75m in December 2012 (as approved in the business case) so that letters of credit were available to enable the procurement of five million nets to be initiated and completed within the expected timeframe. / Out of the £16.75m disbursement, the following allocations were made to two implementing partners: / DELIVER - £10,781,173 ($17,500,000); / Stop Malaria Programme - £5,968,827 ($9,688,600). / USAID Partner Funds received (US$) Funds Spent (US$) as at 31 December 2013 Balance of Funds % of expenditure utilised / DELIVER 17,500,000 14,266,599 3,233,401 82 / SMP 9,688,600 6,206,382 3,482,218 64 / Total 27,188,600 20,472,981 6,715,619 75 / The project had a cost and time extension in November 2013 of £2,900,000 which was required to ensure continuation of activities and complete the distribution phase by 31 March 2014. USAID provided assurances that the distribution phase is on track to be completed by end of March 2014 – in reality, the final districts will not be reached until the end of April. This will be likely to have a small impact on the effectiveness of the campaign in those districts, since LLINs will not be in use by the time rains start and malaria risk begins to rise. / 2.2 Key cost drivers / Key cost drivers have been: / Procurement of nets and unit price of nets. / Distribution costs of nets. / Costs of supporting the communication campaign. / Management of these costs has been addressed through a competitive procurement process for all three inputs, alongside significant use of standing national capacity in the form of police and army staff stationed across the country. / Additional unforeseen costs are created by: / The operations subcommittee anticipates the LLINs procured may not quite cover the entire population, because national population estimates are proving to significantly under-estimate actual registration rates. In earlier distribution waves, the variance was as high as 14% from projected population. Approximately two million people (6% of population) will not receive nets from existing stock if this discrepancy continues and applies across the country. To address this challenge a number of proposals are being discussed, including capping net distribution for houses above a certain size, and reducing and redistributing the buffer stock into the mainstream distribution. / Mobile populations in the districts of Isingiro and Bundibugyo. Due to the political situation in the Great Lakes region, the influx of refugees is increasing: Isingiro district has a refugee camp with over 70,000 people that were not included in the official district level planning data. Bundibugyo has also faced a refugee influx. In Isingiro, the Ministry of Health decided that all permanent camps should be included in registration for LLIN distribution. In Bundibugyo, it was agreed that registration should be done in permanent settlement centres and not transition sites. Additional Village health teams (VHTs) were trained to verify and register the households in the camps so that they received nets during distribution. / 2.3 Is the project on-track against original timescale: N / The project had an original timescale of one year, to December 2013. However, procurement delays, due to a rise in global net orders, as well as delays in finalising a national malaria net distribution plan, ruined the original timescale. An extension to December 2014 to enable the distribution and evaluation of the project to take place has been agreed. The project now appears on track to meet its output targets by the revised timescale of 31 December 2014, but initial expectations that all districts in the country would have been completed by now have not been met, with 41 districts not yet covered.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Free LLINs continue to be one of the 3 main planks of the WHO recommended malaria control strategy and there is no change here. No new evidence is coming to light regarding the most appropriate distribution and communication approaches. However, national population estimates are proving to systematically underestimate demand for nets. / 3.2 Where an evaluation is planned what progress has been made? / A DFID funded evaluation will be undertaken in 2014 following the end of the distribution phase. DFID and PMI have finalised the evaluation methodology and USAID is now procuring the team through their evaluation framework arrangement (similar to DFID’s) to maximise the likelihood that the evaluation will be able to reveal the impact of the campaign on national LLIN usage rates and awareness of malaria prevention.

4. Risk

4.1 Output Risk Rating: Medium / The LLIN business case contains a set of risk categories against which the overall project risk can be determined and scored. An assessment of these risks to the delivery of expected results and an assessment of whether the mitigation actions directly address the identified risks is contained in the table below. / Output level risks indicated in the logframe / Risk Probability Impact Narrative / Financial fraud, corruption or misuse of funds / Channelling funds to USAID who then disburse funds to implementing partners exposes DFID funds to misuse and fraud/ Low Medium Regular monitoring with implementing partners throughout the remainder of the distribution phases. / Delays in disbursement of LLINs/funds by GFATM / Any significant delays in the disbursement of the anticipated 15 million nets will impede universal coverage of LLINs. This will have an effect on anticipated outcomes of the project. Medium High The LLINs were procured in three shipments however there were frequent changes in the pipeline. PMI team are awaiting confirmation of the remaining balance of DFID and GFATM nets. / Change in U.S. government priorities on health spending in developing countries The current US elections may result in a change in government that could lead to a shift in US priorities on malaria. Low High No change so far. Initial assessments suggest that Uganda’s introduction of the anti-homosexuality act will also have little impact on USAID malaria policy or spending in Uganda. / 4.2 Assessment of the risk level / The overall risk of the project remains at Medium.
Risk of funds not being used as intended / The LLIN project funds are managed through USAID’s robust financial procedures to the implementing partners. The close monitoring of funds by USAID and the various checks and balances minimise the risk of funds being misused. The implementing partners DELIVER and Stop Malaria Programme put in place systems to check spend and ensure accountability of the funds received. / 4.4 Climate and Environment Risk / The earlier distribution phases reported some incidences of skin irritations due to the chemicals in the nets however the village health Teams (VHTs) were provided with masks and gloves to mitigate the impact during distribution. / The key risk associated with insecticide treated nets in the past has occurred during washing and retreatment of the nets. The LLINs procured require fewer applications of pesticides during their lifetime and tend to release smaller amounts while being washed, reducing this problem. Pyrethrin, the pesticide used, is biodegradable and does not accumulate in the food chain like DDT. Being polymers, when discarded, LLINs will take some time to degrade and may block water sources and cause damage to wildlife.

5. Value for Money
5.1 Performance on VfM measures / DELIVER, the agency that handled the procurement of LLINs, estimated the unit cost as $3.00 for the first order and $2.85 for the subsequent two orders. / The first purchase order had a lot of 1,500,000 LLINs, delivered on December 15th. / The second purchase order of 1,450,000 was split into two lots of 700,000 LLINs each. The first shipment arrived in February and the second lot of 700,000 LLINs arrived in early March. / The final purchase order of 1,500,000 LLINs is currently in production and is to be delivered in mid April 2014. / It was reported that 160 LLINs were missing at the delivery of the first purchase order of nets. USAID obtained a credit note that was applied to the purchase order and DFID’s account was not charged for the missing LLINs. / 5.2 Commercial improvement and value for money / DFID signed a Memorandum of Understanding with USAID to implement this support through the PMI. By working with USAID, DFID has built on an existing successful malaria partnership between PMI and the NMCP. This arrangement promotes a harmonised approach to the control of malaria in Uganda. It avoids duplication of efforts and minimises fiduciary risk by using existing USAID procedures to manage DFID funds and deliver the expected results. / Although overall corruption risk is high in Uganda, DFID’s funding arrangement with USAID for this support mitigates against the risk of mismanagement and fraud. USAID has robust financial management and procurement procedures to ensure value-for-money and transparency. With DFID resources, USAID procured 4,450,000 LLINs through its existing global procurement mechanism and works closely with the NMCP to distribute these nets along with the 15 million LLINs provided by GFATM and others. USAID will also expand its existing behaviour change communication and demand creation activities to improve coverage and use of LLINs. No financial flows go to GoU institutions. / 5.3 Role of project partners / DELIVER: support the procurement of five million LLINs for the mass campaign. DELIVER was responsible for the procurement of the right quantity of nets according to agreed specifications, delivery, and clearance up to Kampala. DELIVER was also required to review importation requirements, and define roles and responsibilities for the different stakeholders in the net importation process in order to ensure timely net delivery to the country. / SMP: responsible for in-country storage and distribution of nets. In addition, SMP was responsible for facilitating dialogue and agreement among national and district level stakeholders during micro-planning and distribution to ensure smooth and timely delivery of nets to project beneficiaries. SMP was also responsible for supporting a net campaign data management centre at the Ministry of Health. SMP works with other partners namely: John Hopkins University / Centre for Communications Programme and Malaria Consortium in delivery of this component. / Government of Uganda: as part of its contribution to the universal coverage campaign, the Government of the Republic of Uganda has fully funded the participation of the security / uniformed forces in the exercise by making a provision of close to five billion shillings to the Health Sector Budget to facilitate the uniformed forces during the LLIN mass distribution campaign. The involvement of uniformed forces has brought numerous benefits to the campaign implementation process: in addition to providing transport and active participation in the distribution process, they have also been instrumental in ensuring security of the nets. For example, during distribution in Mukono district, a total of 39 bales were reported as missing or stolen. Using joint operations by the Uganda Police and UPDF, the missing nets were recovered and brought back to MOH stores. Other attempts to steal or grab nets during the distribution exercise in various parts of the country have been diffused or contained by the security personnel deployed during the distribution exercise. / 5.4 Does the project still represent Value for Money : Y / The prices achieved for LLINs and distribution are highly competitive. LLIN use in a country with as high a malaria burden as Uganda continues to be one of the five most cost-effective public health interventions available, alongside routine immunisation, promotion of breastfeeding, and intermittent presumptive treatment (for malaria) in pregnancy. / 5.5 If not, what action will you take? N/A

6. Conditionality
6.1 Update on specific conditions / There are no conditions set in this project as no funds have been provided directly to Government of Uganda from DFID.

7. Conclusions and actions
This is a broadly on-track programme to deliver one of the most cost-effective possible public health interventions possible to tackle one of Uganda’s most pressing public health concerns. Three main issues are identified as part of this review. First, slow distribution of LLINs. We will initiate an analysis of the root causes of the delays with USAID and the SMP to see whether they are amenable to DFID intervention. Second, the underestimation of demand by the NMCP based on underestimates of population by the Uganda Bureau of Statistics may mean undersupply of nets. A working group is already looking at potential solutions to this issue, including reallocation of national buffer stocks into the distribution effort and capping the maximum number of LLINs that large households can receive. Finally, there are concerns that the impact of the campaign on net use, malaria prevalence, morbidity and mortality may not be traceable from the November 2014 Malaria Indicator Survey. DFID has invested significant time and effort in USAID’s procurement of an evaluation to ensure that the MIS is designed in such a way as to make firm conclusions possible.

8. Review Process
As the project was initially approved for a one year period, an annual review was not identified as necessary, other than the project completion report. The project was approved in November 2013 for another year and therefore the annual review is a requirement. The review has been carried out in-house with DFID MDG Team staff as well as the PMI team. The review has drawn on reporting from the implementing partners: SMP and DELIVER. No external partners were interviewed through this process. / The documentation that formed background material for this desk review were: / The business case and submission, / The original logframe (Nov 2012) and the revised logframe (Nov 2013), / Request from Ministry of Health to enable distribution of additional 4.95 million nets procured by Global Fund, and submissions for the cost and time extension, / Universal Coverage LLINs Mass Campaign Distribution Progress Report December 2012 to September 2013 (Stop Malaria Program) / Universal Coverage LLINs Mass Campaign Distribution Progress Report October to December 2013 (Stop Malaria Program) / SMP Financial Report May to June 2013 / SMP Financial Report October to December 2013 / Interview with nets beneficiary in Rubirizi and Kabarole Districts / DELIVER Financial reports June 2013 – August 2013 which covers forecasts for September 2013 – February 2014 / DELIVER Financial reports: September 2013 - December 2013 which covers forecasts for January – March 2014 / Concept note for evaluation of the distribution of nets, and other related correspondence.