Type of Review: Annual Review

Project Title: State Partnership for Accountability, Responsiveness and Capability (SPARC)
Date started: August 2008
Date review undertaken: 25th November to 13th December 2013
ARIES Report submitted: January 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Glossary

AR	Annual Review
CGS	Conditional Grants Scheme
DFID	Department for International Development
ESSPIN	Education Sector Support in Nigeria
ExCo	Executive Committee (of State Government)
FCT	Federal Capital Territory
FGN	Federal Government of Nigeria
G&SI	Gender and Social Inclusion
GEMS	Growth and Employment in States Programme
HMG	Her Majesty’s Government (UK)
HoS	Head of Service
HR	Human Resources
HRM	Human Resource Management
IFMIS	Integrated Financial Management Information System
IMEP	Independent Monitoring and Evaluation Programme
LGA	Local Government Area
MDAs	Ministries, Departments and Agencies
MDG	Millennium Development Goal
MDGs CGS	Millennium Development Goals Conditional Grant Scheme
M&E	Monitoring and Evaluation
MoBP	Ministry of Budget and Planning
MoH	Ministry of Health
MTSS	Medium-Term Sector Strategy
NGF	Nigeria Governors Forum
NGO	Non-Governmental Organisation
OHCS	Office of the Head of the Civil Service
P&S	Policy and Strategy
PATHS2	Partnership for Transforming Health Systems Phase 2
PDG & STL	Programme Development Group & State Team Leaders (SPARC)
PEA	Political Economy Analysis
PEFA	Public Expenditure and Financial Accountability
PFM	Public Financial Management
PSM	Public Service Management
PSR	Public Sector Reform
SAVI	State Accountability and Voice Initiative Programme
SDP	State Development Plan
SEAT	State Evaluation and Assessment Tool
SHoA	State House of Assembly
SLP	State Level Programme
SPARC	State Partnership for Accountability, Responsiveness and Capability
SPoA	State Plan of Action
SPRM	State Peer Review Mechanism
SSAR	State Self Assessment Report
TA	Technical Assistance
ToC	Theory of Change
ToR	Terms of Reference
VFM	Value for Money
WB	World Bank

## Introduction and Context
What support is the UK providing?
How much funding does the UK expect to provide? / The UK is providing total funding of up to £60.4m to SPARC. / Period of funding / Funding is for 7 years, from 2008 to 2015. The scale up approved by DFID in 2012 increased the funding from £45.9m to £60.4m, and extended the duration of the programme by an additional year from 6 years to 7 years, with a new closing date of 2015.

What are the expected results?
The Impact of the intervention is expected to be Nigeria’s own resources used efficiently and effectively to achieve the Millennium Development Goals (MDGs). Expected key results include improvements in citizens’ access to, use of and satisfaction with basic services. Outcome is the efficiency and effectiveness of selected state governments’ use of public resources is enhanced. Expected key results include in at least 50% of the States: (a) the State Development Plan and MTSSs/sector plans of at least 75% of sectors are adequately reflected in the 2015-2017 budget (b) variance between 2015-2017 budget and medium-term revenue forecasts is less than 15% and (c) reorganisation has been completed in priority central MDAs. / The programme has four Outputs: / Output 1: Policy and strategy development, monitoring and evaluation improved. Expected key results include in at least 50% of the states at least 3 good standard processes being used in policy making and at least five good standard processes in sector strategy making being used in the majority of sectors adopting MTSS / Output 2: State public financial management improved. Expected key results include in at least 50% of the states that State Governments are using medium-term revenue forecasts and sector spending ceilings to prepare the 2015-2017 budget / Output 3: State civil service performance improved. Expected key results include, in at least 50% of the states: performance against service standards (including equity of access) is being measured and draft establishment plans and workforce plans are being developed / Output 4: Federal support to state governance improved. Expected key results include at least 18 states have submitted their State Peer Review Mechanism Self Assessment and Plan of Action, and SPARC state level lessons have been promoted to all non-SPARC states.

What is the context in which UK support is provided?
What need are we trying to address? / Nigeria is a large and diverse Federation. Of Nigeria’s 158 million people, 64% live in poverty. The poverty rate is 77% in northern Nigeria[1]. Nigeria’s poverty and underdevelopment are widely attributed to poor governance. Although limited public resources is an issue in Nigeria particularly in northern states, the ineffective use of resources is the biggest impediment to sustained improvement in public services, and ultimately in making progress towards achieving the country’s MDGs. Nigeria is rated in the bottom 25th percentile globally on indicators of government effectiveness and control of corruption (lower than the Sub-Saharan average). Key challenges stem from the combination of patronage politics and weak systems. Poor governance and the unequal distribution of oil revenues are key underlying reasons for the significant levels of instability and violent conflict that Nigeria is currently experiencing, particularly in the north of the country. / The situation in many states in Nigeria is characterised by low institutional capacities, including weak planning systems, poor budgeting and cash management, very poor human resource management, extensive corruption in procurement and very weak audit capacity. The states are also subject to limited oversight or accountability – by the Federal Government, State Houses of Assembly, civil society and the media. / SPARC’s remit / The SPARC programme is working with 10 selected Nigerian state governments (Anambra, Enugu, Jigawa, Kaduna, Kano, Katsina, Lagos, Niger, Yobe, and Zamfara) to help deliver improved (a) policies and strategies; (b) public financial management; and (c) state civil service performance. In addition, at the Federal level SPARC is assisting with Federal support to state governance.
[1] SPARC scale up business case, November 2012

## Section A: Detailed Output Scoring
Output 1: Appropriate state policies and strategies adopted, monitored and evaluated
Output 1 score and performance description: Score: A+ (output moderately exceeded expectation)
Narrative summary of progress / Indicator Achievements / 1.1 Extent to which policy and strategy making processes meet good practice standards. State specific MTSS guidelines have been adopted in Anambra, Kano, Niger, Yobe and Zamfara, whilst previously adopted MTSS guidelines have been formally issued to the majority of MDAs by the central planning agency in Enugu, Jigawa, Kaduna and Lagos. All guidelines are consistent with good practice standards. / State policy guides have been prepared and are in use in Anambra, Jigawa, Kaduna, Kano, Katsina and Yobe. / New strategy and policy making processes are being promoted by the central planning agency in Enugu and Lagos and are consistent with good practice standards. / 1.2 Quality and comprehensiveness of policies and strategies. State development plans have been formally approved and subsequently updated in Enugu, Kano, Jigawa, and Lagos, awaiting final approval in Yobe and under development in Katsina and Zamfara. Approved SDPs meet the required level of compliance with policy content standards. / 2014-2016 MTSSs have been prepared and are being finalized for all targeted priority sectors in Enugu, Jigawa, Kaduna, Kano, Lagos, Niger, Yobe and Zamfara. Where assessed, draft MTSSs meet the required level of compliance with strategy content standards. / 1.3 Extent to which results frameworks are comprehensive and measured. SDPs (where developed) and draft 2014-2016 MTSSs for targeted priority sectors include results frameworks with KPIs for the required proportion of sectors/programmes in Enugu, Jigawa, Kaduna, Katsina, Lagos, Niger and Yobe. / Baseline data required to measure the required proportion of results frameworks is available in Jigawa and Lagos and partially available in Kaduna. / 1.4 Extent to which performance management processes are being used. Performance Management Review/Reporting guidelines have been prepared in Anambra, Niger and Yobe whilst previously adopted guidelines have been updated and training/support in their use provided to MDAs by the central planning agency in Enugu, Jigawa, Kaduna, Kano and Lagos. / 1.5 Extent to which political commitment to governance reform is evident. Agreed Intervention Approaches have been prepared in Anambra, Katsina, Niger, Yobe and Zamfara but only formally adopted by Anambra and Katsina. / High level discussions around key governance reform issues have been held in Enugu and are underway in Kaduna. / In Lagos, the majority of central MDAs include governance reforms goals and objectives in their medium-term strategic plans and are in the process of being integrated within BEPD plans in Jigawa. / Progress in meeting milestones / Table 1: Assessment of achievements against 2013 milestones / Indicator and Progress by State Points[2] % Score / 1.1 Extent to which policy and strategy making processes meet good practice standards / Fully Achieved[3] : All ten states 10 100 A++ / 1.2 Quality and comprehensiveness of policies and strategies / Fully Achieved: Six states (Enugu, Kano, Katsina, Lagos, Niger, Zamfara) / Partly Achieved: Three states (Jigawa, Kaduna, Yobe) / Not Achieved: One state (Anambra) 6 / 0.75 68 A+ / 1.3 Extent to which results frameworks are comprehensive and measured / Fully Achieved: Five states (Enugu, Jigawa, Katsina, Niger, Yobe) / Partly Achieved: Three states (Kaduna, Kano, Lagos) / Not Achieved: Two states (Anambra, Zamfara) 5 / 0.75 58 A / 1.4 Extent to which performance management processes are being used / Fully Achieved: Five states (Anambra, Enugu, Kaduna, Lagos, Niger) / Partly Achieved: Two states (Jigawa, Yobe) / Not Achieved: One state (Kano) / Not Applied: Two states (Katsina, Zamfara) 5 / 0.5 69 A+ / 1.5 Extent to which political commitment to governance reform is evident / Fully Achieved: Four states (Anambra, Enugu, Katsina, Lagos) / Partly Achieved: Three states (Kano, Niger, Zamfara) / Not Achieved: Three states (Jigawa, Kaduna, Yobe) 4 / 0.75 48 B / Note: 2013 milestones for each indicator vary significantly between states and for brevity are not shown. The actual progress listed is a summary synthesis of progress reported against state logframes. For a detailed description of progress against state level logframes, including state specific milestones, see the SPARC Report: Progress Against 2013 Logframe Milestones. / Recommendation: / As several states are moving into the implementation of a second cycle of Medium Term Sector Strategies (MTSSs), within the context of new State Development Plans, monitoring and evaluation becomes an increasingly important function both in the sectors as well as in the central agencies. The options on how best SPARC is able to support these central agencies should be a focus of the programme’s efforts in the remaining period of the programme so that states can start to build the evidence base for measuring the effectiveness of their policy implementation. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No
[2] Points based on Fully Achieved (Green and Green/Amber) = 1.00 per state and Partly Achieved (Amber and Amber/Red) = 0.25 per state
[3] These categories map to the SPARC RAG system of reporting progress in the following way: Fully Achieved = Green and Amber/Green, Partly Achieved = Amber and Amber/Red, and Not Achieved = Red.

Output 2: State public financial management improved
Output 2 score and performance description: Score: A+ (output moderately exceeded expectation)
Narrative summary of progress / Indicator Achievements / 2.1 Extent to which the budget is credible and policy based. Budget call circulars which include aggregate and sector budget allocations based on revenue forecasts have been prepared in Anambra, Enugu, Jigawa, Kaduna, Lagos, Niger, Yobe and Zamfara. / A budget calendar has been prepared and formally adopted in Yobe and Zamfara and a budget policy statement has been prepared and used to guide revenue forecasts in Anambra and Enugu. / 2.2 Extent to which the budget is comprehensive and transparent. Budget manual has been prepared and formally adopted in Anambra and Enugu and budget documentation meets 6 out 9 PEFA standards in Kaduna. / The Budget Classification and Chart of Accounts (BC&COA) have been reviewed in Jigawa, Kaduna, Kano, Katsina, Lagos and successfully updated in Kaduna, Katsina and Lagos. / 2.3 Level of predictability and control in budget execution. Internally Generated Revenue (IGR) strategy has been prepared and submitted to government in Anambra, Niger and Lagos. / Procurement manuals/guidelines/training have been prepared in Anambra, Enugu, Jigawa, Kano and Lagos. / A cash forecasting model has been developed and is in use in Jigawa, Kano, Lagos and Niger whilst training on cash planning/profiling in selected sectors has been provided in Enugu, Kaduna and Yobe. / 2.4 Quality of accounting, recording and reporting. Proposals made for improving budget performance reporting have been prepared and submitted to government in Anambra, Lagos and Niger. / The bank reconciliation model has been upgraded in Kano and a mechanism for monitoring the quality of bank reconciliations has been implemented in Jigawa. / Debt management training has been provided to state government in Enugu and Kaduna. / An asset management register has been prepared and staff trained in its use in Enugu / 2.5 Extent and quality of external scrutiny and audit. Training on budget realism has been provided to the State Houses of Assembly (SHoAs) in Kano, Katsina and Yobe, in partnership with SAVI. Whilst not a specific logframe milestone, this training has also been conducted in all other SPARC states apart from Anambra. / Training and manuals for improved audit procedures have been delivered in Enugu and Lagos. / Progress in meeting milestones / Table 2: Assessment of achievements against 2013 milestones / Indicator and Progress by State Points % Score / 2.1 Extent to which the budget is credible and policy based / Fully Achieved : Eight states (Anambra, Enugu, Kaduna, Kano, Lagos, Niger, Yobe, Zamfara) / Partly Achieved: Two states (Jigawa, Katsina) 8 / 0.5 85 A++ / 2.2 Extent to which the budget is comprehensive and transparent / Fully Achieved: Three states (Anambra, Enugu, Kaduna) / Partly Achieved: Four states (Jigawa, Katsina, Lagos, Zamfara) / Not Achieved: Two states (Kano, Yobe) / Not Measured: One state (Niger) 3 / 1 44 B / 2.3 Level of predictability and control in budget execution / Fully Achieved: Five states (Anambra, Jigawa, Kaduna, Lagos, Niger) / Partly Achieved: Four states (Enugu, Kano, Yobe, Zamfara) / Not Achieved: One state (Katsina) 5 / 1 60 A+ / 2.4 Quality of accounting, recording and reporting / Fully Achieved: Four states (Anambra, Enugu, Lagos, Niger) / Partly Achieved: Four states (Jigawa, Kano, Katsina, Zamfara) / Not Achieved: One state (Yobe) / Not Measured: One state (Kaduna) 4 / 1 55 A / 2.5 Extent and quality of external scrutiny and audit / Fully Achieved: Five states (Enugu, Kano, Katsina, Lagos, Yobe) / Partly Achieved: One state (Zamfara) / Not Achieved: Two states (Jigawa, Niger) / Not Measured: Two states (Anambra, Kaduna) 5 / 0.25 66 A+ / Recommendations: / 1. The PFM database, when extended nationwide in partnership with the World Bank and national agencies, will become an essential tool to help inform a wide range of resourcing decisions. It is essential that SPARC’s ground breaking work in this area is migrated successfully to a sustainable ‘platform’ managed centrally before the end of the programme. / 2. Several SPARC states are starting to think about major investments in ‘second generation’ Integrated Financial and Management Information Systems (IFMISs). This is a very high risk venture. SPARC should prepare generic guidelines for circulation on the important features of, steps towards and risks in graduating to a second generation IFMIS (and the need to link with HRM systems). To the extent possible, these guidelines should provide sufficient detail to inform states on the ‘best practice’ standards for hardware and software specification, selection, installation and implementation / 3. Activities under this Output all relate to strengthening financial management systems and processes rather than improving state public financial management. The Output statement should be reworded along the lines of ‘State public financial management processes improved’. / Impact Weighting (%): 40% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No
Output 3: State civil service performance improved
Output 3 score and performance description: : Score: A+ (output moderately exceeded expectation) / Narrative summary of progress / Indicator Achievements / 3.1 Clarity and appropriateness of public service organisation and operational management. Mandates have been revised and updated for selected MDAs in Anambra, Enugu, Jigawa, Kano and Lagos whilst mandates have been mapped across government in Niger, Yobe and Zamfara. / A process for the regular review of mandates has been prepared and adopted in Kaduna and Lagos. / The majority of targeted MDAs have completed the first phase of corporate planning in Enugu, Jigawa, Kano, Katsina, and Lagos. Corporate planning is underway in targeted MDAs in Yobe and Zamfara. A system and guidelines for expanding corporate planning across government is being used in 5 additional MDAs in Kaduna. / 3.2 Extent to which HRM policies and organisation are in place. A HRM policy has been prepared and submitted to government in Anambra, Enugu, Jigawa, Lagos. / HRM related improvement plans have been prepared and submitted to government in Enugu, Kaduna, Niger and Yobe. / A revised individual annual performance management system (APER) has been adopted in Kaduna. / 3.3 Extent to which establishment planning and workforce planning, management and development is in place. A workforce planning approach paper has been prepared in Enugu and Lagos / A training policy has been developed in Lagos, alongside skills and capability gaps analysis, incorporating age, gender and diversity issues. / 3.4 Extent to which MDA performance management policies and procedures are in place. Service charters have been developed for targeted MDAs in Enugu, Jigawa, Kaduna, Kano and Lagos. / The capacity of a relevant unit to support MDAs in the preparation of service charters has been developed in Enugu, Jigawa, Kaduna, Kano, and Lagos. / Performance agreements between the Governor and selected Commissioners have been prepared in Lagos. / Progress in meeting milestones / Table 3: Assessment of achievements against 2013 milestones / Indicator and Progress by State Points % Score / 3.1 Clarity and appropriateness of public service organisation and operational management / Fully Achieved : Eight states (Anambra, Jigawa, Kaduna, Katsina, Lagos, Niger, Yobe, Zamfara) / Partly Achieved: Two states (Enugu, Kano) 8 / 0.5 85 A++ / 3.2 Extent to which HRM policies and organisation are in place / Fully Achieved: Seven states (Anambra, Enugu, Jigawa, Kaduna, Lagos, Niger, Yobe) / Partly Achieved: Three states (Kano, Katsina, Zamfara) 7 / 0.75 78 A++ / 3.3 Extent to which establishment planning and workforce planning, management and development is in place / Fully Achieved: One state (Lagos) / Partly Achieved: Three states (Enugu, Jigawa, Niger) / Not Achieved: Four states (Kaduna, Kano, Yobe, Zamfara) / Not Measured: Two states (Anambra, Katsina) 1 / 0.75 22 C / 3.4 Extent to which MDA performance management policies and procedures are in place / Fully Achieved: Four states (Enugu, Kaduna, Kano, Lagos) / Partly Achieved: One state (Jigawa) / Not Achieved: Two states (Niger, Yobe) / Not Measured: Three states (Anambra, Katsina, Zamfara) 4 / 0.25 61 A+ / Recommendations: / 1. In several states, SPARC is awaiting Executive Council (ExCO) approvals to move forward on several HRM fronts such as mandate mapping, corporate planning and workforce restructuring. As these HRM reforms move from analysis to implementation, progress is likely to slow as difficult political decisions need to be made that challenge vested interests. It is not surprising that progress in workforce planning scores a ‘C’ in Table 3 above. It is essential that SPARC assesses continually the extent to which state governments are willing and able to take forward the HRM reforms especially in the period leading up to the national elections. Lesson learning and dissemination of information of what is able to work and why, and vice versa, should feature in SPARC’s analytical/evaluation work. / 2. The current Output is worded as ‘civil service performance improved’. In reality, the activities and the indicators relate to systems and processes (as in Output 2 above). Therefore the Output statement to be reworded to reflect the emphasis on systems and processes such as ‘State civil service management systems improved’ / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 4: Federal support to state governance improved.
Output 4 score and performance description: Score: A+ (output moderately exceeds expectation)
Summary of progress / Table 4: Progress and assessment of achievements against 2013 milestones / Indicator 2013 Milestones Progress Score / 4.1 Effectiveness of National mechanisms for improving state governance. (a) The SPRM mechanism has been piloted and reviewed, (b) State level CGS is reviewed and adjusted, (c) LG-CGS is fully operational, and (d) the NGFS strategic plan has been updated and implementation started. Piloting of the SPRM is complete in two out of the four pilot states. The remaining two are in the third and fourth stages of the process. Based on the experience so far the SPRM mechanism has been reviewed and the base document improved. / The LG CGS is fully operational. The LGAs currently in the scheme stand at 511 with the addition of 250 LGAs to the already existing 261. / The NGF Strategic Plan has been approved by the NGFS and implementation has commenced. Met expectation = A / 4.2 State governments have a mechanism for accessing and sharing lessons through appropriate Federal organisations 10 state gov’ts have received SPARC lessons. SPARC continues to produced and disseminate relevant information to states through; SPARC Northern State Share Fair. NGF Share Fair events have held in the South East and South West promoting NGF SPARC supported material and other SPARC material. / HRM suites developed and made available to all SPARC states, plus Ebonyi State Five specially selected SPARC lessons collated, produced and disseminated. / Launch of a PFM Database and expansion of it by the World Bank and Central Bank of Nigeria to 26 more states. Launch of a Revenue Tool, which will be marketed for use by all 36 states. / Launch of a SPARC ‘help desk’ enabling access to information and support from technical experts and state government practitioners (primarily aimed at non-SPARC states). Substantially exceeded expectation = A++ / Recommendations: / 1. There is uncertainty around the future role SPARC could play in both the MDG-CGS Office as well as the NGF. Their role and importance for the implementation of SPARC has declined but may return post the 2015 elections. Therefore, SPARC’s cautious and ‘wait and see’ approach to supporting the NGF is pragmatic; focusing on opportunities to move the SPRM mechanism forward is appropriate and continued joint working with the Secretariat to disseminate/publicise lessons learned, guidance notes and the SPARC resource centre build on the work completed to date. Progress on both of these areas will be useful beyond mid 2015. / 2. In looking at other possible areas for SPARC support at the federal level (to help fill the ‘space’ created by the reduced support, especially to the NGF), such as the Fiscal Responsibility Commission (FRC) and the Bureau of Public Procurement (BPP), there needs to be caution in pursuing what might be seen as supply driven TA, particularly TA directed to the federal level regulatory bodies. Ideally, the nature and extent SPARC’s support in these two areas should emerge from the demands and needs articulated by the states where the operational challenges are present; in the current political climate, it is unlikely that states will be willing and able to specify their requirements. But in the absence of these requirements, it may be better to defer any SPARC support to the FRC and BPP and avoid the risk of doing work which is not taken up by the states post the national elections. / 3. Given the appropriate pragmatic and cautious approach to SPARC’s work at the Federal level, it is suggested that (a) the impact weighting is reduced from 20% to 10% and (b) the risk assessment is reduced from ‘High’ to ‘Medium’. If the weighting is changed for Output 4, then the weightings for Outputs 1 to 3 need to be adjusted. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

## Section B: Results and Value for Money
1. Progress and results
1.1 Have the programme and state logframes been updated since last review? Yes / As part of the annual work planning exercise conducted over May to June 2013, state and programme logframes were reviewed and adjusted. Key changes made to the logframes are summarised as follows: / Removal of output indicator 4.2 and renumbering of remaining output 4 indicators. Indicator 4.2 "Responsiveness and success of State Governments to National initiatives to improve state performance" was relocated as an outcome indicator in order to better integrate output 4 within the vertical logic of the logframe, given that the key outcome of the federal component is help nurture greater demand for governance reform at state level. / Adding an additional outcome indicator (5) to the programme logframe in order to better integrate Output 4 within the vertical logic (see (1) above). / Adding an additional output indicator (1.5) to all programme and State logframes. Indicator 1.5 "Extent to which political commitment to governance reform is evident" was included to capture SPARCs work on political engagement and to better capture this element of the Theory of Change within the intervention logic. / Adjustments to 2013 and 2015 state level milestones in order to: a) better align milestones with data availability (e.g. changing references from 2013 budget variance to 2012), b) improve the clarity of milestones, and c) reflect changing state government priorities (e.g. in terms of sectors or MDAs being supported). / Removing sub-milestones in response to either a lack of traction or commitment from state governments and adding sub-milestones in response to emerging priorities or areas where good state government commitment was evident. / In addition, in the revised programme logframe, the distinction between types/categories of states (namely A, B and C) has been removed and programme level logframe output 1-3 milestones now simply read "In at least 50% of states, the 2013 milestone has been achieved." / 1.2 Overall Output Score and Description - A+ (outputs moderately exceeded expectation) / 1.3 Direct feedback from beneficiaries / During the review the AR team met approximately 40 Government officials across 4 state governments, one Federal Government agency (the MDG-CGS Office) as well as the Secretariat of the Nigeria Governors’ Forum. Consistently, those met expressed support for SPARC’s work especially the quality, its ‘fit for purpose’ and the ways of interacting and engaging through adopting a facilitative approach. The ‘learning by doing’ approach to skills transfer, as well as the dissemination of lessons learned supported by detailed practice guidelines (such as the HRM guidelines)and practical tools (such as the revenue forecasting ‘model’), are viewed by the beneficiaries as important features of the technical support. There is evident demand for continued and greater ‘on-the-job’ training to be provided by SPARC especially to sustain the competency base as Government staff are routinely rotated into, and out of, posts. This practical and pragmatic approach to training by SPARC seems a more effective approach to skills development than alternative classroom based methods. / In terms of beneficiaries’ views on progress the responses varied between states and across outputs within the same states. Despite this mixed picture, it was possible to discern that in some of the ‘original’ 5 states the pace of reform had slowed. This was most evident in Kano and to a lesser extent in Jigawa. In contrast, in some of the ‘new’ states, the energy and drive for reform came through in discussions with senior officials; Zamfara and Yobe are the states emphasising their commitment to reform, at least from a technical perspective. However, irrespective of the pace of change, all those met in the states emphasised that reforms had only really started and that continued, external support will be needed beyond the end of SPARC in mid-2015.
1.4 Summary of overall progress / Nature and extent of the progress across the programme / Particular progress has been made in the preparation of State Development Plans, particularly in the original states but there is solid progress in Anambra and a good beginning has been made in both Katsina and Zamfara. 45 MTSSs have now been prepared and quality is steadily improving, both in terms of the content standards achieved and, importantly, the quality of links to budgets. With regard to measuring performance, comprehensive results frameworks are in place within SDPs and MTSSs in the majority of states, despite significant challenges surrounding the availability of data. / SPARC’s efforts on strengthening budget realism on the basis of improved revenue forecasting are yielding benefits, and the Revenue Forecasting Model has now been packaged and shared widely. Efforts have been made to improve political engagement, in particular to sensitise State Houses of Assembly (with SAVI) to demand improved budget realism, and improve scrutiny. A concerted effort to attain improved realism in the 2014 budgets, through a joint SPARC/SAVI/DFID Budget Engagement Plan, has been made, with actions undertaken from January 2013 to date. Technical support to budget execution include cash forecasting models, and revenue and expenditure profiling, as well as IGR improvement strategies and technical guidance to support debt management and procurement processes. Mandate mapping is virtually complete in almost all states. State governments’ interest in and capacity for corporate planning is strengthening. Momentum for HRM reforms is increasing. Seven states are working on the introduction of service charters and improvement plans or other forms of performance management. / To date, SPARC's federal work is helping to make a difference through its support for the mechanisms of the State Peer Review Mechanism (SPRM) and the Conditional Grant Scheme. The SPRM pilot phase is virtually complete and reviews suggest that the mechanism has strong future potential, both encouraging reform, and sharing experiences and lessons between states. The CGS is fully operational, and has been extended to local government. In addition to the dissemination of learning through each of these, SPARC has used a variety of mechanisms (Share Fairs, PFM database, Revenue Forecasting Model, HRM Resource Suite) to reach non-SPARC states. A new Access for Sharing Information (ASK) service is currently being launched.
Variations in progress between States / The progress summarised above is not homogenous across the programme. Performance varies in States; these variations are not necessarily related to the typology that SPARC adopted to guide its engagement with the 10 states given their differing positions on the ‘reform path’. Using the same scoring approach as for the programme outputs, the picture of states’ performance is evident in Table 5 below. / Table 5: AR’s scoring of SPARC performance in individual states / Typology and state Number of 2013 milestones fully achieved (Green or Green/Amber) Percentage of milestones achieved (ignoring milestones not specified) ARIES score / Type A / Jigawa 5 36 C / Lagos 12 86 A++ / Type B / Enugu 11 79 A++ / Kaduna 8 67 A+ / Kano 5 36 C / Yobe 5 36 C / Type C / Anambra 9 82 A++ / Katsina 6 55 A / Niger 9 69 A+ / Zamfara 4 33 C / From this table alone it is not possible to discern with certainty those factors which are militating against the achievement of satisfactory progress. However, the AR visits to a selection of the states reveals some possible ‘pointers’, such as the: / difficult political landscape in Kano with the reduced level of political engagement / security issues in Jigawa, Yobe and Zamfara / possible reform ‘plateauing’ or ‘reform consolidation’ in Jigawa as the momentum for change slows. / DFID, with SPARC’s inputs, have agreed a process with Kano to get the programme back on track by May 2014; the implementation by Kano of an agreed 17 Point Action Plan. The reasons for SPARC’s weak performance in Jigawa are less clear; perhaps it is ‘fatigue’ with trying to respond to many DFID initiatives in the state but also there may be other factors, including SPARC’s capacity to respond with the right technical assistance at the right time (given the security constraints). / 1.5 Key challenges / The key challenges to the delivery of the programme’s objectives include the following: / inherent complexity of governance reform in any environment but more so where ‘the way of doing business’ is so highly politicized; / initiating, and then maintaining, momentum for change when the existing and predominant forces and interests prevail to sustain the status quo; / absence of long term continuity in the political, managerial and administrative leadership of the reform processes; the low levels of experience of, and expertise in, delivering change necessitates a gradual approach with an emphasis on shared lesson learning; / lack of a compelling force that makes change unavoidable and inevitable; the weak, and only slowly emerging, external ‘voice’ to demand reform and hold the political class and governments accountable remains ineffective.
1.6 Annual Outcome Assessment – A+ (outcome moderately exceeds expectation) / Progress scoring / The programme’s intended Outcome is that “the efficiency and effectiveness of selected state level governments’ use of public resources is enhanced”. Performance against each of the Outcome indicators by state against the 2013 outcome milestones is shown in Table 6 below. / Table 6: Assessment of progress at Outcome level / Indicator and Progress by State Points % Score / 1. Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes. / Fully Achieved : Five states (Anambra, Enugu, Kano, Katsina, Niger) – / Partly Achieved: Two states (Kaduna, Yobe) / Not Achieved: One state (Zamfara) / Not Measured: Two states (Jigawa, Lagos) 5 / 0.5 69 A+ / 2. Realism and predictability of multi-year capital and recurrent budgets / Fully Achieved: Four states (Anambra, Enugu, Niger, Zamfara) / Partly Achieved: Two states (Kaduna, Lagos) / Not Achieved: One state (Katsina) / Not Measured: Three states (Jigawa, Kano, Yobe) 4 / 0.5 64 A+ / 3. Effectiveness of core MDA support for government planning, finance and human resources, performance management, and service delivery mechanisms / Fully Achieved: Six states (Anambra, Enugu, Jigawa, Kaduna, Katsina, Lagos) / Partly Achieved: Four states (Kano, Niger, Yobe, Zamfara) 6 / 1 70 A++ / 4. Percentage of SPARC supported PEFA/ SEAT dimensions improving by at least one rating. / Not Measured: All states (No milestone defined as SEAT/PEFAs are not scheduled to be repeated until 2014/15) / 5. Responsiveness and success of State Governments to national initiatives to improve state performance (Federal only) / Federal only A+ / Progress summary / For Outcome Indicator 1, the scores reflect a positive picture with respect to the number of states which have strategic development plans and MTSSs in place, or where they are under active development. / For Outcome Indicator 2, the assessment of achievement relies primarily on expenditure variances as a measure of budget realism. Overall the trends are for reducing variances in most states; however the non-availability of 2012 outcome data means that assessments on sub-milestones related to 2012 expenditure cannot yet be made for six states. Kano is particularly problematic, as government has not released accounts since 2010. / For Outcome Indicator 3, performance has not reached the same level of achievement for the two indicators above. In part this is explained by the definition of the milestones; the assessment of performance is complex because of the broad portfolio of PSM reforms which are covered by sub-indicators. As a result, strong state government performance in one area, for example corporate planning, may be undermined by less strong performance in another area. In some cases this reflects the political difficulty of implementing changes which directly affect civil servants’ jobs and conditions of service directly. In others, it simply reflects prioritisation of the workload, much of which falls on the same relatively small group of senior officers in the Office of the Head of Service. / Outcome Indicator 5 is fully achieved. Out of 774 LGAs, 511 have received grants. The Office of the Senior Special Adviser to the President intends to cover all 774 by 2015. The SPRM process whilst making a slow start, progress is evident but behind schedule. The Governments of Anambra and Ekiti (a non SPARC state) which have completed the process have begun implementing various recommendations from the State Programme of Action (SPoA), and reflecting these in state MTSSs.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / SPARC is a technical assistance programme; the largest cost driver is consultancy fees. As detailed in Part 5 of this section below, SPARC has actively sought to achieve greater value for money associated with these costs. This has contributed to a falling share of resources being spent on consultant fees. However, programme initiatives, in particular workshops, have increasingly become a significant cost driver. There are a number of reasons behind this trend: / The expansion of the programme into ten states means that more workshop events are being held, including State Evaluation and Assessment Tool (SEAT)/Public Expenditure and Financial Accountability (PEFA) exercises in the five original states and three new states during 2011/12. / The security challenges experienced from 2012 onwards meant that consultants were unable to travel to Northern states for significant periods of time, requiring the programme to hold more workshops for government officials out of state, including in Abuja. Whilst the increasing use of national consultants has to some extent ameliorated this, there remain instances where international consultant inputs for some Northern states require Abuja based workshops - in particular for Yobe where SPARC cannot provide in-state support. / 2.3 Is the project on-track against original timescale: Yes, in line with the scale-up approved in 2012.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Politics have been acknowledged as a determining critical success factor in SPARC’s implementation. Two examples of the role of politics have come into sharp focus during 2013. The first instance relates to SPARC’s federal work. The NGF underwent an election in March 2013 to elect a new Chairman. This led to the divide of the NGF as 19 Governors were in favour of the incumbent Chairman and 16 were opposed. The effect of this is that the NGF’s position has been greatly reduced leading up to the national elections in 2015. Whilst the fundamental design of the project does not need to be revised, SPARC has identified a number of mitigating strategies in response to identified risks, including as strategic options paper for responding to the NGF situation. Details of these risks and mitigating strategies are detailed in Part 4 of this section below. / The second example of where ‘politics matters’ is in Kano where the momentum for governance reform has slowed. DFID and the Kano Government have agreed an action plan of measures to help try and get the programme back on track and results are expected by end May 2014 at the latest. If sufficient progress in not achieved by the state government then the nature and scale of the SPARC support will need to be re-assessed by DFID. / There is increasing evidence that SPARC’s engagement with the 5 ‘new’ states is gaining traction. Anambra and Niger are performing well in terms of progress in meeting their milestones. Although programmes in Yobe and Zamfara are not demonstrating comparable levels of achievement, it is evident through discussion with senior officials in these states, that the interest in, and commitment to reform, remains solid. / Performance across the 10 states does vary and performance is not necessarily consistent with the typology groupings of A, B and C that SPARC is applying in relation to budget allocations and engagement approaches. There is a growing recognition within the SPARC Team that states need to be assessed on an individual basis rather than the ‘formula’ of the current typology. Adjustments are being made to SPARC state budget allocations where the judgement is made that the ‘better’ performers and/or more enthusiastic partners can progress further with additional funding. In designing a future governance reform programme post SPARC, there needs to be a consideration of how best to support the reform minded states whilst not losing track of the need to help ‘kick start’ those states at the beginning of their reform journey. In any approach, the question will remain of how best to respond to the inevitable ebb and flow of the political engagement with reform. The continuing experience of SPARC is that governance reform is a long term endeavour which is assumed in the programme’s Theory of Change (ToC). / There is a wealth of evidence demonstrating the programme’s successful approach in delivering the Outputs. Evidence confirming that improved business systems and processes result in better resource management is less convincing but the issue might be more related to presentation of the evidence rather than the availability of the information. The evidence that better resource management results in the improved delivery of basic services remains weak. / 3.2 Where an evaluation is planned what progress has been made? / Independent evaluations / No separate SPARC evaluation is planned. DFID’s Independent Monitoring and Evaluation Project (IMEP) is responsible for completing the annual reviews of SPARC. Also it is responsible for the independent evaluation of the suite of DFID’s State Level Programmes (SLPs), of which SPARC is part. A mid-term review of the SLP programmes was completed in January 2012. The content, approach and timing of the final evaluation are currently under discussion between DFID, IMEP and the SLPs. In addition, IMEP has produced a draft Comparator States Baseline Study in November 2013 as a starting point to help inform the SLP final evaluation. / Internal programme research / SPARC completed annual research studies in late 2011 and early 2013 and is planning to carry out a more impact oriented study during 2014. The primary objectives of this research are (a) to document the evidence base in support of the programme’s Theory of Change and (b) to review systematically performance and provide lessons to decision-makers at both state and programme levels, as part of internal reprioritisation and adjustment of strategies, implementation plans and budgets.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level and mitigation / Insecurity: The Boko Haram insurgency and State of Emergency has forced a continued suspension of international inputs in the northern states since mid-2012. Risk mitigation includes deploying a security advisor; undertaking weekly security risk assessments; enhanced journey management and vehicle tracking; and developing alternative means of programme delivery. / Lack of political will and predominance of vested interest: Political considerations continue to be the main driver for state planning and budgeting, undermining realism and causing poor linkages between plans and budgets. Political considerations impede the implementation of difficult reforms in the civil service and the legislative framework. Risk mitigation includes attempting to engage at higher political levels with more formal EXCO engagement. / Lack of continuity in political and administrative leadership: In states where there has been continuity in leadership over several years, or even two terms (such as in Jigawa and Enugu) it has been possible to begin to embed reforms. In states where continuity has been low, the reverse occurs. New administrations regularly jettison reforms associated with previous regimes. In 2015, there will be a leadership change in possibly eight of ten SPARC supported states. Risk mitigation includes establishing and/or reforming statutory bodies (such as the Bureau of Public Service Reform in Kaduna) and civil service structures, and supporting the passage of legislation to ‘enshrine’ reform in statute. / Politicisation and increasing preoccupation with elections: The 2015 elections grow closer and this has two main implications. First, a growing lack of interest in reform in favour of greater attention to politics. Second, a politicisation of institutions of governance such as the Nigeria Governors’ Forum. Consequently, the appetite for reform and interest in decision making reduces in the lead up to the elections. / Achieving sustainability of governance reforms remains a challenge: All of the above factors call into question the long term sustainability of these SPARC assisted governance reforms. Risk mitigation includes annual and incremental strengthening of processes which are gradually rolled across more and more of government. Sustainability is also encouraged by the creation of organisational structures and legal frameworks. Risks to sustainability are further mitigated with the enhanced capacity of the media, civil society and State Houses of Assembly which are being facilitated by SAVI with SPARC assistance. Hence, there are positive signs of SPARC’s probable sustainability when defined in terms of repeated processes, with evident signs of improved quality. These include for example the work Medium Term Sector Strategies where there is evidence that the MTSS process is ‘taking root’. Currently, however, sustainability does not feature in the articulation of the programme’s Theory of Change (ToC) and consequently is not referenced in the programme logframe. This objective should feature more prominently in the SPARC design and explicit actions taken by SPARC in the remaining life of the programme to deliver sustainable results based on a share understanding of how sustainability will be defined.
Risk of funds not being used as intended / Programme expenditure is in the control of DFID’s contracted service provider and no funds are provided directly to state governments. Programme expenditure consists of the delivery of TA, the provision of support to capacity-building activities, and the conduct of studies. There is regular reporting of activities against work plans and approved budgets. SPARC’s programme accounts are audited annually, and there are no reports of improper utilisation of funds. The SPARC programme received an unqualified audit report in March 2013 for the period January 2010 to March 2012. / 4.4 Climate and Environment Risk / There are no climate or environmental risks to the programme.

5. Value for Money
5.1 Commercial Improvement and Value for Money (SPARC Approach) / SPARC's approach to achieving Value for Money (VFM) in implementing programme activities is based on five specific principles, including commitment and leadership from senior team members; strong focus on achieving economy; obtaining commitment of state governments' own resources to working jointly with SPARC; and continuous assessment of VFM through performance and financial monitoring. / 5.2 Performance on VFM measures / Economy / SPARC has secured a range of cost savings since the start of the programme amounting to £3.7 million in total. Major expenditure savings amount to £599,500 (based on items with savings in excess of £10,000). These savings relate primarily to office accommodation (£212,000) and better use of human resources (£287,000). SPARC has also increased the role of full-time technical staff and compared to the provision of these inputs by short-term national consultants, this represents a cost saving of £2,445,936 for the period 2009-10 to 2012-13. In addition, SPARC has demonstrated a preference for using Nigerian consultants instead of bringing in expatriates. As a result, the average consultancy fee rate has fallen by 16% since 2009-10. An amount of £668,702 can be attributed as a direct cost saving. / Efficiency / Trends against efficiency indicators / SPARC has increasingly sought to improve the efficiency with which programme funds are utilised across states and work streams. The proportion of consultancy days provided by national consultants has risen from 45% in 2009-10 to 63% in 2013-14. This represents over a doubling of the ratio of national to international consultants from 0.8 to 1.7. The difference in fee rates between national and international consultants has enabled SPARC to provide an additional 3,029 days of consultancy inputs as a result, resulting in an efficiency cost saving of £498,196. / SPARC’s performance in implementing work plans has improved significantly over time, rising from an activity milestone delivery rate of 66% in 2010-11 to 86% in 2012-13. However, this has not been matched by an improvement in logframe output milestone delivery, where performance remains constant in the region of 63% to 69%. / SPARC has continued to implement its policy of increasing the role of full-time technical staff in supporting capacity development at state level. The share of Technical management and Support inputs has risen from 28% in 2009-10 to 33% in 2013-14. / SPARC has sought to keep increases in administrative spending to a minimum. Despite expanding into five additional states over 2011-12 and 2012-13, the share of Programme Management and Administration spending has remained below 2010-11 levels. Between 2010-11 and 2012-13 total expenditure increased by 39%, but spending on Programme Management and Administration increased by only 19%. / SPARC tracks the ‘cost of production’ for several key project outputs. The average cost of supporting a State Medium Term Sector Strategy (MTSS) has decreased from £153,839 in 2009/10 to £12,682 in 2012-13 and the average cost of supporting MDA corporate planning has fallen from £109,880 in 2010-11 to £33,732 in 2012-13. These efficiency savings have been driven by several factors: increased knowledge and expertise of state officials; economy of scale in providing support; a move from design and preparation to roll-out; lessons learned and applied by SPARC in providing support; knowledge management between states; and the increased use of local consultants and remote support (as a result of security restrictions). / Allocation of resources to states / Analysis of budget allocations to individual states for 2013-14 shows that the pre-defined funding envelopes for different types of states have broadly been respected, though there have been adjustments to reflect circumstances in individual states. Three states (Anambra, Enugu and Yobe) received significantly in excess of their defined budget, reflecting the level of political commitment and opportunity. By contrast, the Federal component received significantly less, reflecting the current operating difficulties. The SPARC management team advised that, going forward, more emphasis will be placed on levels of commitment, traction, and opportunity in determining annual budgets. This should ensure that expenditure is well aligned with prospects for successful outcomes. / Allocation of resources by work stream / The indicative logframe weightings for allocating resources to work stream, at state technical level, are P&S/M&E: 25%; PFM: 50%; and PSM: 25%. These weightings represent an overall balance of effort rather than a fixed resource allocation figure. SPARC management makes work stream resource allocation decisions based on: / priorities identified in conjunction with state governments, in line with state governance reform plans, and the SPARC theory of change; / understanding of political economy and opportunities or constraints for governance reform; / the balance of expertise, and associated cost required, to successfully deliver work plans. / Analysis of budget allocations to each work stream, for each state, showed that there has been a consistent tendency to allocate less than the amount indicated by the logframe weighting to the PFM work stream. This has been balanced by higher allocations to the P&S and PSM work streams. Beyond this, there is no consistent pattern – the balance of support between work streams differs each year for each state and, as such, appears to reflect the best opportunity to make progress. / Effectiveness / Progress against output and outcome indicators is reviewed and assessed in Section A of this Annual Review. SPARC has identified aspects of effectiveness in each of the three work streams: / Planning and Strategy (P&S) / In several states there is good evidence that MTSS content standards are being reached (Jigawa and Lagos) and of a marked and quantifiable improvement in these standards (Enugu especially, but also Jigawa and Lagos). However, in Kaduna and Kano the standards remain poor and there is little sign of improvement, partly due to continuing poor budget discipline and a failure by government to adhere to ceilings when developing budgets. At the outcome level, there is good evidence of an emerging reflection of MTSSs in budgets in Jigawa and Enugu and the prospects for this achievement in Lagos also seem good.[Source: SPARC Working Paper, Value for Money, Nov 2013] / Public Financial Management (PFM) / SPARC support has helped establish more realistic resource envelopes based on actual trends and more certain forecasts. Consequently annual budgets are more realistic and deliverable and the release of funds for budget execution is more in line with forecasts of available funds. For example, the average variance between actual and budgeted revenue has improved from 21% (2007-09) to 15% (2012) for the five original states. This suggests that a total of £651.4 million has been removed from budgets which would not have been funded, £216 for every pound spent by SPARC on this activity. There is also evidence of improvement in expenditure management in the form of more realistic budgets and better budget execution. [Source: SPARC Working Paper, Value for Money, November 2013] / Public Sector Management (PSM) / For corporate planning in particular, SPARC is now directly supporting fewer stages as responsibility for corporate planning support and roll-out across states is progressively being handed over to the responsible state government teams or units. [Source: SPARC Working Paper, Value for Money, November 2013] / SPARC has not carried out comprehensive research and analysis to assess overall programme effectiveness – whether activities are achieving the overall objectives as expressed in the logframe ‘goal’ level indicators. However, SPARC has established that progress is being made. / Working in support of related programmes in the education and health sectors, SPARC has contributed to increased spending through helping to improve the quality of sector strategies, predictability of sector budget releases, and the way in which public services are managed. This support, together with savings and increased revenues, has contributed to state governments spending an additional £170.4 million on health and education. This has helped enrol an additional 1.5 million children in primary and junior secondary schools. [Source: SPARC Working Paper, Value for Money, November 2013] / At a lower level, several of SPARC’s effectiveness indicators are focused on the number of outputs delivered and the average cost of delivering each output, which is more a measure of efficiency. SPARC have recognised the need to develop VFM measures in regard to the measurement and assessment of outcomes. These effectiveness indicators could be designed to assess the impact of programme outputs; for example, the extent to which MTSS priorities and resource allocations are reflected in state annual budgets. / Financial Impact / SPARC support has contributed to changes which have resulted in significant savings and increased revenues for state governments. It is estimated that through these initiatives (set out below), an additional £202 million has been made available for service delivery. Given total expenditure to date of £42 million, this represents a return of almost five to one. / Initiative / Supporting states to improve revenue administration and increase Internally Generated Revenue. Specific activities in Enugu and Kaduna States have raised an additional £94 million. / Assisting states to reduce wage bills by removing ‘ghost’ workers. With SPARC assistance, Katsina and Zamfara States reviewed payroll records and have saved £7.6 million. / Returning unused funds to the Treasury. Enugu, Jigawa and Kano States have streamlined and reduced the number of bank accounts in operation. As a result, £68.4 million has been transferred from closed accounts to the respective State Treasuries. / Reducing the debt burden. In Kaduna, SPARC has supported the establishment of a Debt Management Office and procedures for tracking and reporting internal and external debt. With better information, managers cut the debt burden by £32 million. / SPARC support for institutional reforms is giving other development partners the confidence to invest in state governments. For example, with SPARC's help, Lagos State Government successfully met the conditions required to access £240 million of World Bank loan financing. / 5.3 Role of project partners / An important trend, particularly where SPARC is engaging under a Type A arrangement, is that government itself finances technical assistance for reform processes. This is taking place at the Federal level and in Jigawa, Kaduna, Katsina and Lagos States. The total amount involved is £996,300 and represents financing that would normally have been provided by SPARC. One example, accounting for £400,000, is where four pilot states each contributed £100,000 to start up the State Peer Review Mechanism. The total amount identified excludes financing initiatives recently proposed by Yobe and Zamfara States. / 5.4 Does the project still represent Value for Money: Yes / The review team carried out an assessment of whether the programme, across the 10 States and at Federal level, provides value for money. This analysis was carried out by comparing the current position for each work stream with the baseline position at the start of the programme and the amount of financial support provided by SPARC. / The assessment of ‘value for money’ is based on the judgement of the annual review team, based on experience in implementing governance and financial management capacity building projects. The evidence base for each assessment is documented in detailed working papers. / Of the total expenditure of £42 million incurred by SPARC as at 31 October 2013, £28.3 million (67%) is attributed to individual states and a further £5.9 million (14%) has been spent supporting activities at the Federal level. Drawing on the analysis, the review team categorised SPARC financial support to individual states as providing ‘good value’, ‘fair value’ or ‘weak value’, as set out below, by reference to the following definitions: / ‘Good value’ – achievement is better than could be expected for the financial input; / ‘Fair value’ – achievement is in line with the financial input; / ‘Weak value’ – achievement is less than would be expected. / Assessment of Value for Money State Total support / Original States / Good Value Enugu £3,309,857 / Lagos £6,640,904 / Federal £5,948,667 / Fair Value Kaduna £3,531,688 / Jigawa £5,353,744 / Weak Value Kano £4,933,699 / New States / Good Value Anambra £451,695 / Niger £747,816 / Fair Value Katsina £835,806 / Zamfara £1,038,625 / Yobe £839,578 / Performance in Kano State has been adversely affected by an absence of political commitment, which has been discussed earlier in this report. Kano’s ‘weak value’ assessment might be resolved, for example by: / getting the programme back ‘on track’ which is unlikely given the imminent national elections; / focusing spending on specific activities which, if completed, might provide useful stepping stones for a more promising engagement post 2015. / SPARC Programme Wide Technical support has accounted for £7.3 million to date. Programme activities are implemented cross-state in support of each work stream and to ensure the overall success of the programme. In the absence of a baseline, the assessment of value for money is based on achievements, and associated costs, over the last 16 months. This shows that Programme Wide Technical activities make an important contribution to the overall progress of the project and can be regarded as providing good value. / To conclude, looking at the overall programme, it is fair to say that SPARC financial support represents value for money. / 5.5 Recommendations / 1. To demonstrate continued value for money, SPARC should continue to ensure that programme resources are allocated to states and work streams in a way that provides the best opportunity for achieving reform objectives. This should be a combination of a top-down strategic approach and a bottom-up work plan-based approach. SPARC has agreed to document their resource allocation approach for 2014-15. / 2. In terms of assessing programme effectiveness, SPARC should identify and adopt performance indicators that measure the impact of programme outputs, rather than the cost of achieving those outputs. SPARC should also liaise with other SLPs in an attempt to assess SPARC’s contribution to achieving overall programme objectives.

6. Conditionality
6.1 Update on specific conditions / There are no conditions applying to the SPARC programme

7. Conclusions and actions
Overall conclusion / The programme overall continues to perform well and moderately above expectation. SPARC’s financial support represents value for money. It has managed effectively the challenging transition set out in the approved Consolidation and Expansion Strategy with no serious concerns about the impact on quality and progress. The programme has an operating presence in all 10 states despite the security difficulties. Inevitably, in such a diverse and complex programme, performance varies between states and across components within states. Performance of the ‘original’ states is variable with concerns about results in Kano and, possibly, early warning signs about Jigawa’s. Solid foundations have been built in Enugu, and are beginning to emerge in Kaduna. Performance of several of the ‘new’ states is impressive as shown by the likes of Anambra and Niger; the motivation and commitment of most of these new states is persuasive, especially when looking to decide on future engagement beyond SPARC. / In terms of the performance by Output, it is not surprising to see Output 1 (Policy and Planning) outperforming the others and the difficulties being faced in delivering Outputs 2 (PFM) and 3 (civil service reform) which might be seen as a consequence of the perception that they pose a greater threat to undermining the status quo. Irrespective of current achievements and levels of commitment across all 10 states and between components, from a technical perspective, continued technical assistance will be needed beyond SPARC. It may not be needed to the same extent in all current 10 states. For example, the continued success of Lagos, and the wider reform achievements across that state, might call into question the need for continued SPARC type ‘across the board’ support beyond 2015. If DFID resources are constrained, and priorities need to be reset, then focusing on key areas of Lagos State might be an option given its demonstrable success in driving through its extensive reform agenda in recent years. / The federal component, in relation to the NGF and MDG-CGS, whilst having had its successes in the last year (and in earlier years), the sense is that these interventions may have reached their optimum contribution. The remaining period of SPARC’s engagement necessarily will remain opportunistic, endeavouring to protect gains already made and seeking to build on useful initiatives that are in the pipeline, such as the SPRM. / Actions / 1. Output recommendations: DFID to obtain feedback from SPARC on the recommendations made and agree necessary changes to work plans and/or budget allocations (where required). / 2. In respect of VFM: (a) to demonstrate continued value for money, SPARC should continue to ensure that programme resources are allocated to states and work streams in a way that provides the best opportunity for achieving reform objectives and (b) in terms of assessing programme effectiveness, SPARC should identify and adopt performance indicators that measure the achievement of overall programme objectives, rather than the cost of achieving specific outputs. / 3. Jigawa and Kano performance: SPARC to explore further the reasons for dip of performance in Jigawa and propose steps, with Jigawa’s participation and agreement, to revitalise the reform efforts; agree any necessary changes in work plans and/or budgets with DFID. DFID to monitor Kano’s completion of the agreed 17 Point Action Plan and by end May 2014 decide on the way forward. / 4. SPARC to make explicit its proposed approach to measuring those logframe indicators which, presently, are indicated as being measured at the end of the programme in mid 2015 but which, probably, need measuring at the end of 2014. / 5. Both SPARC and DFID should monitor closely the possible ‘slowing down’ effects resulting from the increasing political activity leading up to the national elections in 2015 and the expected resulting lack of focus on decision making regarding governance reforms. It is understood that SPARC will share with DFID its assessment of the likely challenges during the pre and post election period based on its experience of previous events. / 6. The sustainability objective needs to be become more visible in the implementation of the programme; the ToC needs to reflect this based on a shared understanding of how sustainability will be measured and specific targets set to deliver sustainable results by SPARC by mid 2015. / 7. The evidence base for demonstrating that improved processes for planning, monitoring, financial management and civil service management leads to more efficient and effective public resource management needs to be presented better. The evidence that more efficient and effective resource management results in improved service delivery needs to be collected and presented. / 8. If there is consensus that the A, B, C typology applied to the 10 states is becoming redundant, the implications of fully moving away from this framework needs to be considered by SPARC; alternative mechanisms (or rules of engagement) need to defined and adopted, but only if the proposed changes in SPARC’s way of working will result in achievable positive benefits for programme delivery within the remaining life of the programme. Two determining factors that influence the scale and nature of a governance programme in a state should be (a) the needs of the state and (b) the capability of the state to reform. In the current situation, it is probable that all states need assistance, so DFID will have to continue with selecting its priority states. The second factor, capability, will be demonstrated by a state’s track record of reform combined with an assessment of the political will to change.

8. Review Process
This review was completed by an external (to DFID) four person team with its membership comprising: one person from IMEP, an observer from the National Planning Commission and 2 freelance consultants contracted by IMEP. An initial Approach Paper was prepared prior to the start of the review and the national SPARC team supplied an extensive range of documentation prior to the work starting in Nigeria. The fieldwork in Nigeria was completed between the 25 November and 13 December 2013 and in that period, in addition to its work in Abuja, the team visited Jigawa, Kano and Zamfara. In these states, the team met with the SPARC state teams as well as a selection of key senior officials in the respective state governments. Whilst in Jigawa SPARC’s State Team Manager from Yobe briefed the team; this briefing was supplemented by the attendance of 3 senior government officials from Yobe who also travelled to Jigawa from Yobe. / In Abuja, the team met with representatives from the Nigeria Governors Forum, the MDG-CGS office, DFID state level programmes (SAVI, PATHS2 and ESSPIN) as well as DFID, the World Bank and SPARC’s national programme management team. Prior to departing Abuja, the team presented a summary of its initial findings and recommendations to SPARC and then to DFID.