ADDENDUM TO BUSINESS CASE FOR BRIDGE FUNDING AND SCALE-UP COST AND TIME EXTENSIONS

SUMMARY INFORMATION
Project Name	Africa Division funding to Africa Agricultural Development Company (AgDevCo)
Country or region targeted	Africa Regional, Ghana, Malawi, Mozambique, Sierra Leone, Rwanda, Tanzania, Uganda, Zambia, Zimbabwe
Type of cost extension	Cost extension
Original project budget	£99.5m
Original project start and end dates	1 April 2015 – 31 December 2020
Cost extension value	£55m
New project end date	31 December 2023
Business Case Quest Document No.	2015 business case – vault-questid4864496. / July 2015 addendum – vault-questid5365222 / July 2016 addendum – vault- questid5654405

INFORMATION
What is the project’s purpose?
The purpose of DFID funding to AgDevCo is to support poverty reduction and increased food security through catalysing additional private sector investment in agribusiness and agricultural infrastructure and increasing agricultural cross border trade in targeted countries, generating jobs and income for smallholders. / Over three quarters of those living in extreme poverty are in rural areas and two thirds of those, mainly women, earn a living from agriculture. / Investing in agribusiness (food production, processing and related services) and working with private companies to improve agriculture productivity is one of the most efficient ways to foster inclusive growth. It can also be effective in developing new manufacturing opportunities by processing of crops in rural areas, technology transfer and introducing new products, for example improved seeds, and financial services. / AgDevCo is a UK based investor and project developer with staff in nine African countries, investing exclusively in agribusiness in Sub Saharan Africa. AgDevCo is bound by its statutes not to distribute profits. Its investment objective is to build profitable businesses that contribute to food security, drive economic growth and create jobs. AgDevCo provides capital (debt and equity) and ongoing management and technical support to early stage agriculture companies, accepting high risks and moderate returns. / Over the next three decades Africa will experience unprecedented population growth. By 2050, 1 in 4 people on the planet will be African. By 2030, 90% of the world’s extreme poor will live in Africa, 80% in fragile countries – making Africa ever more central to DFID’s mission to support sustainable and inclusive development, peace and stability, and to end extreme poverty. Producing enough food for the growing population is a both a huge challenge and a very important opportunity for inclusive economic growth, investment and poverty reduction. / Investing to unlock agribusiness in Africa is in the longer term UK interest. It can generate economic opportunities, foster stability and counter the root causes of migration. It will also contribute to sustainably increasing food production which can benefit both African and UK businesses and consumers. The UK has world class research and business expertise in the agri-food sector and AgDevCo has a track record of structuring deals that allow other investors to come in, including British companies. / Most agriculture companies in Africa do not attract much needed investment because: (i) they are too early stage or too small (ii) the cost of investments is high due to lack of infrastructure (irrigation, electricity, land clearance) and (iii) the risks are high, for example climate variability and crop disease. / Most investors – including CDC and other Development Finance Institutions, look for bigger and less risky investments for example in large agro-processing companies or water bottling. The available deals however are few, without investments in smaller deals and in agriculture production. / AgDevCo invests in smaller deals and agriculture production. They build local businesses’ capacities, open up new income opportunities for local farmers and entrepreneurs, increase food production for the regional market, and create a pipeline for others, including CDC.
What is the objective of the cost extension?
The objectives of the BC Addendum are the following: / (i) Provide AgDevCo with the continuity of funding to allow the organisation to retain the current capability and continue to deliver development impact at scale, through early stage agribusiness investment with links to food production and smallholder farmers. / (ii) Enable AgDevCo to attract CDC and other DFI funding. Funding will allow AgDevCo to continue a transition towards financial sustainability that is a precondition to CDC investment. The cost extension will allow AgDevCo to continue investing while negotiations with CDC and other investors are ongoing. / (iii) Allow AgDevCo to actively scope expansion to Zimbabwe - as part of the HMG investment offer linked to the political transition in the Country – and other countries, including Kenya and part of the Sahel (Burkina Faso). / (iv) Update Ministers on ongoing negotiations and consultation on DFID participation in the new proposed Company structure, where AgDevCo’s shares are owned by a Company Limited by Guarantee, of which DFID would be a member. / (v) Rationalize the way in which we manage DFID relationship with AgDevCo, with more efficient finance and administration arrangements. / Within a year AgDevCo will have committed all the funds previously approved by DFID; AgDevCo is on track to achieve the expected results; and has developed a healthy pipeline of additional investments as part of its 2018-2023 strategy. / Since 2017, AgDevCo has developed a strategy to transition from grant to investment financing and ultimately from donors to commercial investors. At least four Development Finance Institutions have endorsed the new strategy in principle, and are in discussions about an investment in AgDevCo at portfolio level rather than deal by deal. DFI investment would guarantee substantial scale up of AgDevCo operations and development impact and further ensure future financial sustainability beyond grant funding. / CDC has indicated to AgDevCo that they are actively considering a $100m investment facility for AgDevCo. CDC aims to increase their investment footprint in the highly developmental agri-food sector in Africa. Their current investment strategy does not cover investments with direct links to production and early stage agribusiness that are the core of AgDevCo’s expertise. As such an investment in AgDevCo would be highly complementary to the rest of the CDC agribusiness portfolio. / CDC are likely to invest only in a portion of AgDevCo’s current portfolio and they have asked AgDevCo to move further towards financial sustainability as a precondition to their investment. / CDC and other DFIs acknowledge that there is high development impact and additionality in AgDevCo’s project development work and smaller early stage investments, although this part of AgDevCo’s portfolio requires grant funding or scaling down if investment income from AgDevCo’s portfolio cannot cover its costs. CDC is therefore supportive of the additional grant support covered in this BC addendum. / Over the next 12 months, we will continue to work with AgDevCo, CDC and other potential investors to restructure the business towards reduced reliance on grant funding, while ensuring continued development impact and additionality. As negotiations unfold, some flexibility in our approach is required, as described below in the implementation approach.
What is the additional and total support the UK will provide?
Through this cost extension the UK will provide the following additional funding: / Up to £55 million of re-deployable capital to catalyse private sector investment in agriculture and agribusiness infrastructure through AgDevCo, whose mission is to reduce poverty and improve food security through a not-for-profit investment approach. / Up to £50,000 from the original monitoring and evaluation budget will be re-allocated to cover legal advice costs linked to DFID participation in the new AgDevCo company structure. / The total amount covered by this business case will therefore be: / £152.8 million of re-deployable capital through the Africa Agricultural Development Company Limited (AgDevCo) / £1.7m for monitoring and evaluation / In line with previous arrangements, 60% of funding to AgDevCo will continue to be marked as contribution to the International Climate Fund allocation. / Initially Africa Division committed funding to AgDevCo through the Private Infrastructure Development Group (PIDG) in 2013-15 (£31 million) and through separate Business Cases (BCs) which cover wider national level agriculture transformation programs in Ghana, Mozambique, Rwanda, Uganda. The table below summarizes funding that Africa Division and Private Sector Department (PSD) committed to AgDevCo under the current business case and the current proposed cost extension. / Total before this Business Case Addendum / A Business Case Addendum / B Total Proposed New Business Case Value / (C=A+B) / Regional Fund – Africa Regional Department with contribution from Private Sector Department and DFID Zimbabwe routed through ARD £47,008,311* £55,000,000* £102,008,311 / DFID Ghana £7,627,294 £7,627,294 / DFID Malawi £12,904,029 £12,904,029 / DFID Sierra Leone £7,000,000 £7,000,000 / DFID Tanzania £10,186,572 £10,186,572 / DFID Zambia £13,037,445 £13,037,445 / TOTAL £97,763,651 £55,000,000 £152,763,651 / * Up to £27,000,000 resourced from Private Sector Department (routed through ARD) / ** Up to £15,000,000 resourced from Private Sector Department and up to £5,000,000 resourced from DFID Zimbabwe (routed through ARD) as per current arrangements
What are the expected results?
We expect AgDevCo to commit the additional investment funding by 2021. Given the nature of early stage agribusiness investment that AgDevCo focuses on, we expect most development benefits to take time to materialize (7-10 years, longer for some greenfield investments). / With UK support AgDevCo has so far already leveraged £117 million ($163 million) of third-party capital. Over 1.6 million people already benefit in rural areas from increased incomes as a result of the jobs and markets created by AgDevCo’s investments. AgDevCo consistently exceeded expected results in a difficult investment climate and the last Annual Review scored an A+. / The proposed £55 million additional funding will directly benefit an additional 1.5 million people by 2025. These include: / over 317,000 smallholder farmers’ households benefiting from sustainable income uplifts / over 8,300 additional Full Time Equivalent jobs / This is in addition to the 2.4 million people expected to benefit from previously approved funding (£99.8 million), bring the total to 3.9 million people directly benefiting by 2025 in Sierra Leone, Ghana, Rwanda, Malawi, Mozambique, Tanzania, Uganda, Zambia and Zimbabwe. The ratio of funding to people benefiting improves with the additional funding due to economies of scale.
What is the approach to implementation?
Implementation approach to Additional Funding / DFID objectives for the transition of AgDevCo from grant funding towards investment from CDC and other potential investors are to: / (i) Reduce AgDevCo’s reliance on grant funding from DFID, supporting AgDevCo to transition towards financial sustainability and a Permanent Capital Vehicle model, attracting a mix of capital providers. / (ii) Protect AgDevCo’s mission and its additionality, continuing to target early stage agribusiness and production agriculture, delivering development benefits while generating investment pipeline for other investors. We would not want AgDevCo to lose its risk appetite or transition into another private equity fund, struggling for agribusiness investments. / (iii) Protect our endowment in AgDevCo. We want to ensure that AgDevCo’s asset base is preserved and not channelled into other investors’ profits. We also want to protect AgDevCo’s highly regarded capability to deliver investment effectively in a highly developmental and risky space. Similarly we would like new investors and in particular CDC to take risks commensurate to their expected lower risk adjusted returns in their investments, rather than shifting all risks on to DFID. / (iv) Maintain flexibility, as negotiations progress with CDC and other investors. We are aware that there is a tension between development impact and AgDevCo’s additionality (objective i) and prospects for financial sustainability (objective ii). There might also be trade-offs between the amount of third party capital raised (objective ii) and the risk taken by prospective investors and implications for DFID endowment (objective iii). / Additional funding is required now to ensure that AgDevCo continues to deliver highly development investment in early stage agriculture and food production in Africa while negotiations with CDC and potential investors continue. Additional funding contributes to further progress towards financial sustainability that is a precondition for CDC investment. / The additional funding in this BC will cover: / a. An envelope to continue investment in 2019 -2021 estimated in up to £43.5 million / b. A tapering contribution to AgDevCo’s management costs, support to investees and impact monitoring up to 2023, estimated in up to £6.5 million. / c. up to £5 million allocated to actively scoping an expansion to Zimbabwe and possibly to other countries including Kenya and Burkina Faso. / In addition, £50,000 of the original monitoring and evaluation budget will be re-allocated legal advice on DFID’s role in AgDevCo’s governance. / We will ensure that our funding has the necessary flexibility to allow the best value for money and to attract rather than displacing CDC and DFI funding, as detailed below. / a. Flexibility of the Investment allocation / The immediate priority is to provide AgDevCo with the financial stability to continue investing and delivering results. Negotiations with CDC could be concluded positively before DFID funds for investments are drawn. In this case, once CDC confirms which portion of the portfolio they are willing to invest in and at which conditions, we will flexibly shift DFID resources from that part of the portfolio towards activities like project development and early stage investment that are highly developmental and that support the overall investment strategy. We will request that AgDevCo board includes securing CDC and DFI funding early as part of key performance indicators for AgDevCo Senior Management. At the same time, in the case that negotiations last longer than expected or do not conclude positively, AgDevCo will have assured continuity of operations and delivery. / If CDC or other investors’ funding displaces DFID investment allocation we will submit to Ministers about the use of displaced funding, which we would expect to be either used to deepen AgDevCo’s development impact by 2023 or spread to subsequent years. We expect to submit to Ministers in that respect by the end of 2019. / b. Flexibility of the tapering contribution to AgDevCo costs, project development and very early stage investment / AgDevCo has built a portfolio of assets that have started generating reflows that can cover part of their ongoing management costs. The overall costs that AgDevCo will be able to sustain will ultimately depend from the performance of their assets. CDC has requested AgDevCo to reduce costs and adopt more conservative risk/return assumptions as part of moving further towards financial sustainability. / While AgDevCo is already moving to reduce costs and revise assumptions to take into account CDC’s feedback, some level of project development and early stage investment funded through grants is desirable both because these are activities with high development impact and additionality and because they generate deal flow for the more remunerative part of the portfolio. / During negotiations, we will explore in more detail the nuances of the trade-offs between development impact and costs in order to define the best additionality and value for money for DFID grant use when blended with CDC and other DFI investment through AgDevCo. In order to do so, in the next 6 months we will review - in coordination with CDC - AgDevCo’s current assets and pipeline against performance, development impact and costs. / Once negotiations with AgDevCo and CDC are concluded, we will submit to Ministers about implications for use of DFID grant funding including any proposed re-allocation of funds or additional need for grant funding. / c. Flexibility of allocation to scoping investment in Zimbabwe and other countries / AgDevCo is currently scoping a small number of investments in countries where it does not operates an office but with which its staff is familiar, mainly investments across the border from countries of current operations, for example Kenya (from Tanzania) , Burkina Faso (from Ghana) and Zimbabwe (in which AgDevCo has a presence but not a full office). Part of the new funding will be allocated to pursue more organically investment opportunities in new countries with an initial focus on Zimbabwe. / The recent political transition in Zimbabwe and the current uncertainties around its short and medium term outcomes also require a flexible approach. Investment in agribusiness through AgDevCo could be an important plank of HMG investment offer in response to the political transition. Zimbabwe has high potential in the agriculture and food sector and the sector has high developmental potential. However the actual and perceived risks are high and the costs related to years of disinvestments are high. AgDevCo could fulfil an important role in scoping and developing highly developmental investment opportunities for other investors, de-risking and demonstrating the feasibility of investment. The organisation is well placed to do so. AgDevCo’s former commercial Agriculture Director is from Zimbabwe and has decades of commercial farming experience in the Country. He is still a Board Member. AgDevCo maintains a small presence in the country through the head of their Smallholder development Unit who is based in Harare. / Funding will be deployed following a series of go / no-go decisions that will take into account market and political conditions as follows. / Phase 1 - AgDevCo will conduct an initial scoping of potential investment opportunities in the country, other investors’ interest and prospective costs of operations. After that they will decide, in conjunction with DFID Zimbabwe team, whether there is scope to proceed with a period of grant funded investment project development. We expect this phase to conclude by the end of 2018, which will give DFID Zimbabwe team a chance to assess the investment potential taking into account the progress of the political transition. / Phase 2 – If a decision is taken to progress from Phase 1, a two year project development phase will start in which AgDevCo will deploy a regular presence in the Country to actively scope and develop specific investment opportunities. During this phase AgDevCo and the DFID team will take stock every six month of the development of the investment opportunities and the evolution of the political context. If during this phase no investments will be deployed, DFID and AgDevCo will consider terminating the expansion to Zimbabwe. / Phase 3 – If Phase 2 is successful AgDevCo in consultation with DFID will consider further expanding investment including deploying core balance sheet capital and DFI investment if appropriate. An assessment will be made of the grant needed to cover the costs and risks of operating in Zimbabwe at that stage, taking into account the evolved political context. / A similar approach will be used in other countries, including deciding whether to establish an office or operate investment from a neighbouring office during Phase 2. / DFID role in the new AgDevCo company structure / Current ownership and background to the transition / In July 2015, Ministers approved plans to transfer ownership to a Company Limited by Guarantee, of which DFID is a Member. In July 2016, Ministers agreed to delay implementing the arrangement, in order to allow CDC to consider wider company structure implications of an investment in AgDevCo; for example, they could not make an equity investment in a Company Limited by Guarantee. The structure of the proposed CDC investment is still not entirely clear but we are now clear that the CLG structure will work. / AgDevCo, currently a company limited by shares, is still owned by its founder and sole shareholder and we have been managing both operational risks and the risk of negative public perceptions arising from DFID funding and creating an endowment in a company owned by an individual. / Risks were mitigated by the following factors; (i) AgDevCo's statutes prescribe that no profit can be redistributed; (ii) DFID has the right to terminate funding at any time (iii) DFID must approve any company changes before they can take effect; (iv) AgDevCo’s founder and sole shareholder has repeatedly asked to gift his shares to a non-profit entity which we have delayed; (v) DFID has regular oversight of AgDevCo). Ministers agreed in July 2016 the residual risk is limited and commensurate to avoiding the risk to compromise an investment by CDC or another Development Finance Institution (DFI). / Potential investors expressed comfort with a structure in which the shares of AgDevCo Ltd are owned by a not-for-profit entity in which DFID has a formal role, as long as the company’s operational freedom is respected. We have therefore considered a number of Options. / Options explored and recommended, risks and approach / The current shareholder requested to gift 100% of AgDevCo’s shares to a Company limited by Guarantee (CLG) of which DFID is a member. The main viable alternative would be to establish much looser oversight through a third party entity, whether a new Trust or an existing third party organisation. / The proposed Option was previously approved by Ministers; we have developed details further with AgDevCo and CDC and potential investors reacted positively. Under the proposal, AgDevCo CLG will be the holding company to own AgDevCo’s shares in trust and protect its mission. DFID will have some positive and negative powers to protect the endowment we have created in AgDevCo and ensure that it continues to fulfil our intended development role in the foreseeable future. The CLG will not be involved in the operational running of AgDevCo or in investment decisions, which ensures comfort of incoming investors. The CLG will be diluted by new equity investors. / There is a risk that the recommended option could present problems for the accounting classification of AgDevCo and there are limits to the level of oversight that DFID can legitimately operate without being deemed to exercise shadow control of AgDevCo. / Over the next few months while negotiations unfold, we will carefully consider the balance of desirable DFID oversight vs the parameters of undesirable classifications of AgDevCo as public body, being under public control and/or requiring it to be consolidated into Government accounts. Such classification would be undesirable because it could (i) limit AgDevCo’s ability to achieve its development objective (e.g. restricting the quantity and riskiness of investment) and (ii) reduce the investment attractiveness, limiting AgDevCo’s ability to diversify financing (i.e. attract commercial financing), and become financially sustainable. This option is also undesirable to DFID for both accounting and operational reasons. / We are working closely with FCPD and they have an established link to HMT Head of Classification Unit. As we progress with further unpacking the details of the terms of our engagement with AgDevCo’s new governance structure, we will continue to consult with HMT on the parameters of undesirable classifications. / We are also re-allocating £50,000 from the previously approved monitoring and evaluation budget to cover external legal support on drafting, reviewing, and negotiating term sheets and legal docs to implement our agreed participation in AgDevCo CLG. / In consultation with HMT we may have to dilute the level of oversight that we exercise through participation in the CLG in order to avoid undesirable accounting classifications. If during the process of negotiation we come up against unsurmountable obstacles in terms of the trade-offs between our desired level of oversight and accounting classifications, we might have to pursue alternative routes which give DFID even less direct oversight. / The alternative routes include: (i) setting up a Trust to manage our endowment in AgDevCo within loose parameters (ii) endorse an existing third party organisation with participation in AgDevCo , giving up all direct oversight rights and setting up our requirements in our funding agreements. / We will work within the Ministers’ initial steer on the proposed option. Should we face insurmountable obstacles in implementing Ministers’ steer we will inform Ministers and request a new steer. / In the current proposal under consideration as part of the recommended option, as AgDevCo shareholders, the CLG will have powers to: / Scrutinise Company reports at annual general meetings; / Appoint / terminate appointment of AgDevCo board Directors; / Approve / reject remuneration of AgDevCo non-executive Directors; / Accept / reject AgDevCo Ltd audited accounts / Approve / reject major changes in the capital structure of AgDevCo / Approve / reject major changes in the proposed strategy of AgDevCo Ltd insofar as it will or may impact adversely on its ability to comply with its purpose as set out in the Memorandum and Articles of Association / AgDevCo CLG will have three classes of Membership: / (i) Class A (DFID) with special rights - in addition to standard members’ rights - to: / reject any changes to the Memorandum and Articles of the CLG; / reject the recommendation of the Board on the appointment of the Chair of AgDevCo Ltd. / require a non-executive Director of AgDevCo Ltd to resign if there is evidence that he/she has acted and is judges likely in future to act in a manner inconsistent with AgDevCo’s objects as set out in its Memorandum and Articles and principles of good governance. / reject proposals for changes to remuneration of AgDevCo Ltd’s non-executive Directors if there is evidence that remuneration would exceed benchmarks. / reject proposals for changes in the capital structure of AgDevCo Ltd (possibly time bound) / reject proposals that would result in any distribution of value from AgDevCo Ltd relating to investments funded by DFID other than as provided for in agreements already approved by DFID / reject any proposal in relation to the distribution of any value from AgDevCo Ltd in the event of winding up of the company veto any special resolution / approve ordinary class members / (ii) Class B (Keith Palmer, AgDevCo founder and current shareholder) with special rights - in addition to standard members’ rights - to: / consent to any changes to the Objects clause; / approve ordinary class members / (iii) Class C (at least two) ordinary class members with standard rights to be nominated as highly reputable individuals with an understanding of AgDevCo mission and agreed between DFID and the current shareholder. / Revising the way in which we manage DFID relationship with AgDevCo / We currently co-manage our relationship with AgDevCo with ARD managing the corporate relation at HQ level and Country Offices providing Country liaison and oversight. A DFID-wide Steering Committee ensures coordination and corporate coherence. / While the overall approach will remain, we will rationalize financial management by centralizing funding within ARD for the central business case, while maintaining strategic relationship in Country. Country relationships are well established in Zambia, Tanzania, Malawi, Uganda, Rwanda, Mozambique, Ghana and Sierra Leone. We propose that the country relationship becomes more strategic focusing on results, synergies with other HMT activities and feedback from AgDevCo on business led advocacy issues that the office could usefully pick up. We have consulted Country Offices who broadly agree. We will have to manage the risk that Country Offices might disengage if they do not hold a budget line and conversely cope with the increased ARD burden on programme management. / The additional funding from DFID Zimbabwe will be transferred to ARD to be incorporated in the new central financial management arrangement / Funding to AgDevCo from DFID Uganda under the separate business case Northern Uganda – NU-TEC and from DFID Rwanda under the separate IMSAR Business case will continue to be managed locally by the relevant Country Office. However funding from these two separate Business Cases continues to be covered under the single funding agreement between DFID and AgDevCo and relevant administration procedures.
Describe any key changes to the original business case?
The following changes to the original business case and subsequent business case addenda are made through this addendum: / Amount of Funding and Timing / £55 million additional funding will be provided to: / (i) enable investments in AgDevCo’s immediate pipeline over 2019 -2021; / (ii) cover a tapering proportion until 2023 of the fund management and operational costs to manage those investments, including providing business development services to early stage companies and project development / (iii) allow AgDevCo to actively scope expansion of investments in Zimbabwe and other countries / As with the original Business Case, funding will be provided for a central regional fund not restricted to individual countries funded by Africa Regional Department and Private Sector Department (£55 million) which includes up to £5million to scope and potentially initiate AgDevCo’s expansion to Zimbabwe. / Geographic coverage will expand to Zimbabwe and possibly Kenya, Burkina Faso and other countries in Sub Saharan Africa, subject to further scoping and consultation with DFID. / £50,000 will be re-allocated from the original monitoring and evaluation budget towards the costs of external legal advice on DFID’s role in AgDevCo’s new company structure. / The timeframe of DFID funding to AgDevCo will be extended up to December 2023. / Economic appraisal and cost benefit analysis / The economic appraisal and cost benefit analysis (CBA) was updated in 2016. This year we have conducted a cost benefit analysis of the additional proposed funding based on the same model used in 2016. The paper is attached as Annex 1. / The economic costs considered in the quantitative CBA are: / - the cost of DFID funding, / - the cost incurred by AgDevCo to develop and manage investments, including the costs of supporting early stage investees, to deepen development impact by stimulating wider benefits to local farmers and the costs of monitoring impact and implement their gender action plan. / - the cost of capital leveraged by AgDevCo and co-invested in their portfolio. / The analysis distinguishes between three types of economic benefits accruing from AgDevCo’s investments: (i) income uplift for smallholder farmers directly benefiting from the investments; (ii) income uplift for employees in jobs created or maintained by AgDevCo’s investments; and (iii) future returns to investments measured using the proxy of Earnings before interest, tax, depreciation and amortisation (EBITDA). / The time horizon for the analysis is 15 years which is considered the minimum appropriate timeframe for agribusiness investments and is in line with the timeframe of DFI investment currently being considered. We continue to use the same value for money measures to monitor the most crucial and sensitive assumptions made. / Treatment of Benefits and Costs in the Cost-Benefit Analysis is shown below: / The CBA assumes that an investment from DFID of £55 million will trigger at least an additional £20 million within the next 5 years. This is realistic given existing advance negotiations for additional grant funding and negotiations with DFIs. / The assumptions about the level of investments that AgDevCo will be able to sustain with the additional funding are conservatives to take into account CDC input. Benefit stream accounted for are therefore equally conservative. / The CBA shows that within the period considered the discounted economic benefits of AgDevCo’s investments exceed the discounted costs associated to the investments by a ratio of 1.21. The sensitivity analysis does not raise significant concerns. / Over three quarters of economic benefits accrue as income uplift to smallholders reached by the investments and employees taking jobs created or maintained by the investments, rather than businesses themselves. / This confirms the pro-poor nature of the approach and the additionality of the interventions as investors prioritise investments with higher financial returns over investments with positive externalities and development benefits. These aspects are crucial to DFID investment rationale and will be continuously monitored as part of our Value for Money assessment. / As with the original business case, the CBA does not account for investments made by AgDevCo from reflows from the initial investments. In addition wider benefits accruing in the economy beyond income uplift of direct beneficiaries are not quantified, making the assessment inherently conservative. / Similarly, the analysis does not take into account the economic benefits deriving from the demonstration effect of AgDevCo’s investments, which is likely to attract more investments in a critically underfunded and pro-poor sector in rural areas. / Treatment of Assets / The treatment of assets created with the additional funding does not change from the original Business Case. Through the provision of debt and equity AgDevCo will recoup a substantial proportion of the funds it invests. As a non-profit-sharing investment company, AgDevCo statutes prescribe that they will redeploy funds into future projects generating even greater employment, income and development outcomes. DFID will monitor AgDevCo’s balance sheet and request valuation annually. DFID will have the right to scrutinize any change in AgDevCo’s main policies including how reflows are managed and this will be included in the revised accountable grant agreement. / We have previously requested and received relevant clearance by Private Sector Department (PSD) and Financial Accounting and Control (FCPD) related to the creation of financial assets and treatment of those assets as per Smart Rule 11. We will continue to work closely with PSD and FCPD to take into account relevant guidance. / Funding mechanism / The Business Case addendum approved in July 2015 indicates an accountable grant as the vehicle to disburse funds to AgDevCo. / We will amend the current accountable grant to cover the additional funding, the new end date and any additional safeguarding clauses as advised by DFID Safeguarding Unit. / We will follow the latest guidance from the Safeguarding Unit to ensure compliance with the additional requirements on safeguarding for accountable grants. / Updated risk matrix including safeguarding / The DFID risk register has been amended in the last Annual Review (June 2017) and it is regularly discussed at DFID wide quarterly Steering Committee meetings. We have further reviewed and strengthened DFID risk register based on the Due Diligence Refresh that we conducted in late 2017 and the comments provided by Internal Audit Department in ARD internal audit. / The most significant risks to DFID currently are: / AgDevCo being owned by a sole shareholder. This risk is addressed by the process highlighted to transfer shares to a Company limited by Guarantee of which DFID is a member. / AgDevCo not receiving funding from CDC. Although this could impact the scale that AgDevCo could operate at in future, grant funding on its own delivers development benefits. The proposed bridge funding is expected to bring AgDevCo close to financial sustainability. AgDevCo Boards keeps financial performance and costs under constant review. Should investment performance fall below expectations, a temporary reduction of further investments would follow. While AgDevCo starts detailed negotiations with CDC on the proposed investment facility, they will continue to have an open conversation with at least 3 other potential investors who have shown interest. / Trade-offs between development impact and financial sustainability. The process described in paragraph 35 above will analyse in depth the nuances of the trade-offs between development impact costs and risks of AgDevCo’s current assets and pipeline investments in order to achieve the most desirable balance of additionality, development impact and value for money. / Weak regulatory systems are a key concern in all countries in which AgDevCo operates. AgDevCo has made consistent efforts to improve ESG risk management and to work with investees to build capacity and improve ESG standards. At country level and in the UK reputational risks are followed up and discussed with DFID and actions/mitigation measures agreed on for serious risk areas. AgDevCo country teams are key interlocutors with investees on risk management plans and implementation of these. However, oversight of investees’ ESG standards and practice, and even more so, those of further downstream investee partners, will remain challenging and in need of consistent monitoring. / AgDevCo has been requested to review their safeguarding practices as part of a DFID wide exercise. AgDevCo has recently revised and strengthened their Staff Code of Conduct as a result of interaction with DFID in the process. / The overall risk rating remains ‘Major’. AgDevCo’s business model, investing in early stage companies who cannot access finance from other institutions, by nature, assumes major risk. / AgDevCo maintain their own comprehensive risk register which at present includes 23 key risks. The risk register is updated and presented to AgDevCo’s Audit and Risk committee quarterly. Changes are highlighted quarterly to DFID and discussed at DFID Steering Committee. / Monitoring and Evaluation / Evaluation / In 2016 Ministers approved reallocating funds for AgDevCo’s evaluation with a flexible and pragmatic approach to: (i) contribute to the implementation of some of the recommendations of the review of AgDevCo’s M&E and data collection systems; (ii) contribute to the implementation of AgDevCo’s gender plan; (iii) commission additional data collection and independent analysis as necessary to answer our evaluation questions; and (iv) commission external reviews and analysis as part of DFID own project review processes. / Monitoring / A revised development impact framework and logframe were approved in 2017. / The four categories of development impact that the framework assesses are: / Additionality: whether AgDevCo’s funds are potentially acting in competition to other lenders and investors to deliver the same service, or whether they are serving a distinct part of the market that is underserved. The stage that the business is in its financial maturity could be used as a proxy for assessing additionality, as AgDevCo is targeting early stage investments that are overlooked by Development Finance Institutions and other investors. / Number of individuals reached: it will assess the breath of impact measured by the number of expected beneficiaries. It is the most common development impact measure and often the only measure for impact investors. / Income uplift: it will assess the depth of impact, based on expected income uplift of direct beneficiaries as a result of the investment. / The extent of transformational impact of change: a qualitative measure designed to assess the depth of change that is expected as a result of the investment beyond direct beneficiaries. This relates to both the nature of the investee’s activities and / or the impact that the investment has on changing the rural economy. / For every proposed investment, AgDevCo assesses each category on a range from 4 (maximum development impact) to 1 (minimum development impact). The average of these score would give the ex-ante Development Impact score of the investment. / We will continue to keep the framework and the specific parameters under each category under review. / We are also foreseeing revising AgDevCo development impact future estimate based on their actual performance in 2013-2017. / International Climate Fund / In line with previous arrangements, 60% of funding to AgDevCo will continue to be marked as contribution to the International Climate Fund allocation. / AgDevCo addresses two International Climate Fund’s thematic areas: / Adaptation to climate change, through investment in smallholder agriculture, water resource management and investees’ corporate social responsibility / Low carbon development, by helping agricultural enterprises develop clean energy solutions and reduce emissions / We will continue monitoring progress and report to the International Climate Fund (ICF) through the three Key Performance Indicators (KPI) listed below: / KPI 1: Number of People supported by ICF Programmes to cope with the effects of climate change. / KPI 5: Number of direct jobs created as a result of ICF / KPI 7: Level of installed capacity of clean energy as a result of ICF support. / Gender Equality / As noted in the original BC, AgDevCo’s work has the potential to make a significant difference to women’s economic empowerment opportunities in project countries and to provide evidence of success and learning in this area. Through monitoring and evaluation arrangements AgDevCo is demonstrating impact on poorer members of society, including women and girls. AgDevCo already disaggregates all beneficiaries’ results by sex and has agreed an aspirational target of 50% of development benefits accruing to women. Since 2016, AgDevCo has devised and implemented a Gender Policy and action plan. / AgDevCo have highlighted five potential areas for action to improve investing for women in its Gender Policy: / Businesses delivery particular benefits for women employees / Investing in crops or business types in which women tend to play a particularly important role as growers, processors, distributors or other / Investing in businesses run by a women entrepreneur / Investing in business with a particular benefit for women consumers, whether because of product or service itself, the way it is packaged or the way it is delivered. / Investing in businesses with a particular effect on women’s nutrition. / In the past two years AgDevCo conducted a systematic analysis of their portfolio to identify practical ways to improve impact on women. Two recently published reports draw on two years of field work exploring how AgDevCo and 15 of its investees across Africa are promoting gender equality, and removing barriers to women participating in the agricultural sector. They provide practical tips and best practices for other investors as well. / AgDevCo takes a pro-active approach to securing women empowerment opportunities at each stage of the investment process: from deal origination and due diligence processes, to execution, monitoring and evaluation. In addition, AgDevCo works closely with investment businesses to reduce barriers to women participating in four key dimensions of the agricultural value chain: / Example of practical measures put in place by AgDevCo’s investees in the past two years include: / empowering female employees to compete for leadership positions, including support groups and senior mentorship programmes (Malawi) / introducing on-site childcare facilities, providing advance payments for food and healthcare expenses, and an onsite grocery store to save time women spent travelling to buy basic household goods (Mozambique) / updating land registration procedures so all household members are registered as individuals, rather than records only including the male head of household (Malawi) / using female lead farms and extension staff to promote female participation in out grower schemes (Tanzania).