Annual Review - Summary Sheet

Title: Dar es Salaam Urban Jobs Programme
Programme Value: £10.5 million		Review Date: January 2019
Programme Code: 205092	Start Date: January 2018	End Date: May 2022

Year	2019
Programme Score	A
Risk Rating	Moderate

A. Summary and Overview (1-2 pages)

Description of programme

Dar Jobs is a 5 and half year £10,500,000, urban market systems programme, the purpose of which is to support sustainable change in sectors that have the potential to generate jobs and incomes for thousands of poor people, particularly women and youth. Dar Jobs is specifically designed as an adaptive programme suited to working flexibly in a rapidly changing urban market context. A market systems approach was selected because it is best suited to tackling challenges that require intervention at multiple levels with different actors. The programme will test different approaches and will generate rapid feedback to inform course corrections and support continual learning and improvement. A key strength of market systems programmes is their ability to use a wide range of different tools, including financial tools – such as grants, loans, cost shares and risk guarantees – and non-financial tools – such as technical assistance, research, disseminating ideas, and facilitating coordination.

The programme will commence with activities in the manufacturing, solid waste management and childcare sectors, though it will retain the flexibility to scale up or down, drop or add sectors depending on performance. Funds will be disbursed to selected businesses to share the risks of investment and test business models that can create economic opportunities for the poor. Funds will also be used to directly fund activities enabling business, local government or civil society organisations to address constraints to development in the target sectors.

DFID has significant experience implementing market systems work, including in Tanzania. Our experience has helped to underline critical success factors which have been incorporated into the design of the programme, and should continue to be monitored through implementation. A successful market systems programme should:

- Tackle problems with the market system as a whole: working at different levels with different actors.
- Ensure impacts are inclusive: in this case delivering benefits for the poor as workers or consumers, in particular for women and youth.
- Ensure sustainability: by addressing underlying causes and not replacing market actors.
- Deliver impact at scale: delivering interventions that can be tested and then replicated at scale.
- Learning and adapting: responding to the complexity of urban markets through active testing, learning, and adjusting in response to feedback.
- Think and work politically: by investing in on-going political economy analysis and stakeholder engagement to navigate the complexities of Dar’s evolving local governance and administration, involving multiple levels of government.

The procurement process was completed in October 2018, with a consortium of IPE International, Springfield and Diligent Consulting [the consortium] winning the contract. Dar Jobs commences with a five and half month inception period, which will be used to test approaches, undertake analysis, and form important partnerships within the sectors. The inception phase will comprise of five main milestones and a design of the full programme. At this point, DFID retains the option to continue to the implementation phase, close the programme, or shift direction and scale.

#### Context

Given the novelty and complexity of Dar Jobs, which at the time was DFID’s first market systems programme in an urban context, the decision was taken to change the procurement strategy and to contract separately the work for design and implementation. This led to a longer than anticipated procurement process. Despite the time elapsed since the original business case was approved, the programme remains highly relevant to the context of Dar es Salaam. The city remains the third fastest-growing city in Africa, and is on track to become a megacity of 10 million people by 2027. However, much of the city’s rapid growth has been jobless growth. Dar’s unemployment rate is 21.5%, compared to 10.3% nationally, and underemployment rates are much higher. With around 800 thousand young people entering Tanzania’s job market annually, harnessing labour-intensive sectors that can generate jobs for the urban poor is a critical, and growing, challenge. The challenging business environment in Dar es Salaam is an important risk that the programme will need to manage (see risk section), but also Dar Jobs stands to have a positive impact by working with government and other actors to identify improvements to the rules and regulations governing the sectors. The consortium will need to keep under review the changing policy and regulatory environment, as it impacts the selected sectors.

Summary supporting narrative for the overall score in this review

Overall a score of A (meeting expectations) has been given. The fact that the programme was only contracted in October means there is limited progress to report, however the programme has launched successfully and the inception phase is underway.

Summary of progress and lessons for the year ahead

This is a light-touch annual review. The contract for the Dar Urban Jobs programme was signed 18 October, with IPE Global, working with the unincorporated joint venture members, Springfield Centre for Business in Development Limited and Diligent Consulting Limited. The five and half-month inception phase commenced end October, therefore this annual review is mostly a forward-looking review that seeks to capture any issues identified early-on and establishes the main actions for the 2019 reporting period. This brief review covers two relevant outputs;

Output 1- Launch Dar Urban Jobs programme

Output 2- Inception phase completed, leading to full programme design and implementation underway

The first full annual review will take place in January 2020.

Key Points and Recommendations

Communication

ACTION: DFID SRO and consortium to agree jointly how to inform Government and other stakeholders and seek their input. This should happen as soon as possible. The consortium plan to complete a communications strategy, together with informative materials, by February 2019, but it may be necessary to introduce the programme to some stakeholders ahead of that.

Strategic focus

ACTION: The consortium should re-assess the relevance of the selected sectors, given the time elapsed since the business case was completed, taking into consideration Government priorities and wider changes in the business environment. It should also update the early mapping of other relevant initiatives in the city and ensure that they are complementary.

Staffing

ACTION: DFID SRO and programme manager, together with the consortium leadership team, to keep team capabilities under review over the inception period and ensure adequate mentoring and other support is provided from the international offices of IPE and Springfield.

Inclusion, safeguarding and political economy

ACTION: DFID SRO to ensure a multi-disciplinary team of advisers is involved from the inception phase, and to ensure that design decisions are informed by robust social, gender and political economy analysis. The consortium should establish clear responsibilities for women and youth results.

ACTION: Consortium to think early about the programme’s safeguards approach, including initial thoughts in the standard operating procedures, and ensure a comprehensive strategy is in place by May 2019. SRO to ensure support is on-hand as necessary.

Decision-making, monitoring and evaluation

ACTION: Consortium to ensure that the proposed governance structure and processes incentivises pilots and sets out a clear procedure for moving from pilot to scale. Market systems programmes are more effective when timely decisions are taken to scale or drop interventions, based on performance.

ACTION: The consortium to design a dashboard approach, to allow full oversight of the different interventions, understand how they are contributing to impacts and outcomes, and support fast decision-making about scaling activities up or down.

Value for Money

ACTION: SRO to seek support of DFID Tanzania economists in assessing the VfM plan and metrics.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output 1	Contract signed and programme launched
Output number per LF			Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Contract signed by November 2018	October 18th 2018	Complete
Office established and programme launched	Team working by November	Complete

Provide supporting narrative for the score

This output is scored A, targets achieved, because Dar Jobs launched on 29 October following the contract signature on 18th October. The mobilisation of the core team was complete by 3rd December, when the solid waste management sector lead joined. The senior leadership team, comprising of the programme director, team leader and deputy team leader were in-place immediately and so work began within two weeks of the contract being signed. In addition, the consortium undertook to use the existing office facilities of the local partner, Diligent Consulting, so office space was available immediately. Between the procurement process and launch, a limited number of staff changes have been made because some of those originally proposed staff were no longer available. The contract specified a list of core staff who could not be changed without DFID’s prior written agreement.

Key points and actions

Thought will need to be given to how the programme launch is communicated with stakeholders, including Government, to ensure good coordination and acceptance by decision-makers in the relevant sectors.

ACTION: DFID SRO and consortium to agree jointly how to inform Government and other stakeholders and seek their input. The consortium plan to complete a communications strategy, together with informative materials, by February 2019, but it may be necessary to introduce the programme to some stakeholders ahead of that.

Output 2	Complete inception, with full programme design, within six months of contract being signed.
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	70%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Develop SOP, Business Process, and Governance Framework	14/12/2018	Delayed
Market system analyses for each of the three target sectors completed	12/04/2019	On-track
Intervention plans and results chains completed	12/04/2019	On-track
Communications Strategy completed	22/02/2019	On-track
Draft report summarising Stage 1 key activities and achievements submitted	19/04/2019	On-track
Complete log-frame with targets and timed milestones submitted	12/04/2019	On-track
Final report summarising Stage 1 key activities and achievements submitted and approved by DFID	19/04/2019	On-track
DFID written approval to progress to Implementation phase (subject to satisfactory completion of inception phase)	20/05/2019	On-track
Implementation starts (pending DFID decision)	09/06/2019	On-track

Provide supporting narrative for the score

The output is scored A- targets achieved, because at this very early stage the programme is on-track to deliver the inception phase milestones on time. The indicators all relate to the five and a half-month inception phase, which will define a logframe and results framework for the implementation phase. The slight delay to delivery of the first milestone, completion of the standard operating procedures, business processes and governance framework, is not impacting other milestones. These milestones will be assessed during the complete annual review in January 2020, together with the action points below.

Key points and actions

Given the time elapsed between the approval of the business case and the programme launch, it will be important to update the early analysis and ensure that the programme focus remains relevant. The consortium has agreed with DFID to keep under review whether the initial selection of the child care services, light manufacturing and solid waste management sectors remains optimal, or should be substituted based on more up-to-date evidence. Developments could include market changes or new policies and regulations. In addition, other development partners, such as the World Bank, have launched or are planning to launch related initiatives in Dar es Salaam which did not exist when the original business case was submitted. Furthermore, a market systems approach can be undermined, if other actors working in the same sectors adopt conflicting approaches, such as providing services for free instead of stimulating a sustainable market response.

ACTION: The consortium should assess the continued relevance of the selected sectors, taking into consideration Government priorities and wider changes in the business environment. It should also update the early mapping of other relevant initiatives in the city and ensure that they are complementary.

Lessons from other market systems programmes show that it is vital to have in-place a team which is highly skilled in working with markets and facilitating change rather than substituting for market actors. The team will receive training and mentoring arrangements should be kept under review. In addition, the consortium should provide strong input from international staff and consider options like increasing staff days allocated to inception. The core local team should be freed-up to focus on building relationships and identifying and managing interventions, not on process.

ACTION: DFID SRO and programme manager, together with the consortium leadership team, to keep team capabilities under review over the inception period.

The programme will need to draw on a multi-disciplinary team to ensure it covers adequately issues of inclusion and political economy in particular. The partner has indicated that it might be challenging to meet ambitious inclusion targets (women and youth) whilst ensuring commercial sustainability. This and other emerging challenges will need to be kept under review by a multi-disciplinary team of DFID advisors, to ensure that design decisions are informed by robust social, gender and political economy analysis. Fortnightly meetings between DFID and the implementing partner will allow for timely discussion about challenges and early course corrections.

ACTION: DFID SRO to ensure a strong multi-disciplinary team of advisers is involved to ensure that design decisions are informed by robust social, gender and political economy analysis. The consortium should establish clear responsibilities for women and youth results.

Related, DFID and the consortium have discussed the importance of early work to design a strong approach to safeguarding, and social development expertise from DFID is already supporting the discussions. This will be especially relevant to the child care sector, which presents particular safeguarding risks, so a strategy and clear responsibilities should be defined. Positively the consortium is already seeking advice on these issues, including from other relevant programmes.

ACTION: Include initial thoughts on the programme’s safeguards approach in the standard operating procedures, and ensure a comprehensive strategy is in place by May 2019. SRO to ensure support is on-hand as necessary.

Market systems programmes require a strong governance and decision-making process. Given the emphasis on experimentation, piloting and adaptive programming, interventions will need to have a clear concept note and justification prior to approval. Decisions to either scale-up or drop activities should be taken early and sector leads need to be incentivised to pilot new activities, and to drop or scale-down interventions which do not show promise. In addition, the consortium has proposed that there be a separate advisory board for each of the three sectors, given their differences and the importance of finding the most relevant expertise (the terms of reference for the programme proposed only one). Management will consider the cost-benefit analysis of such an approach, and will also give thought to how any internal economies, such as lessons and impacts across the different sectors, might best be captured.

ACTION: Consortium to ensure that the proposed governance structure and processes incentivises pilots and sets out a clear procedure for moving from pilot to scale.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

The theory of change set out in the business case remains relevant. The consortium has further defined a theory of change which sets out their early understanding of the pathways to reform in the selected sectors leading to job creation, though at this stage the theory of change does not elaborate sufficiently how interventions might lead to jobs for women and youth. DFID and the consortium agree that it is not useful to expend time further elaborating a high-level theory of change, but rather the programme should focus on developing sector-level theories of change, including results for women and youth, which will guide decision-making and should be seen as live documents.

It is too soon to assess progress towards outcomes but this will be assessed in the January 2020 annual review.

## D: VALUE FOR MONEY (1-2 pages)

Key cost drivers and performance

The overall approach to delivering Value for Money will be through performance related payments linked to five specific and agreed SMART (Specific, Measurable, Achievable, Realistic, Timed) key performance indicators for the duration of the implementation of the programme. An important innovation of Dar Jobs is that it retains the flexibility to define and agree the fifth performance criteria on a six-monthly basis, to provide DFID the added flexibility to hold the supplier to account for addressing specific weaknesses in performance as they arise.

VfM performance compared to the original VfM proposition in the business case

It is still too soon to assess VfM against the original business case. However, the consortium’s proposed approach includes several important VfM measures which will be assessed through the inception period.

Assessment of whether the programme continues to represent value for money

It is too soon to assess whether the programme continues to represent value for money but this will be assessed in May 2019, when a decision is taken as to whether to move to implementation, and again during the January 2020 annual review. The SRO should ensure that DFID economists are involved in the assessment of the value for money matrices, given the complex nature of adaptive and responsive programmes. ACTION: SRO to seek support of DFID Tanzania economists in assessing VfM metrics.

Quality of financial management

Discussions are underway to ensure timely and accurate financial forecasts and reporting. The first payment will not be made until April, following completion of the first set of milestones.

Date of last narrative financial report	NA
Date of last audited annual statement	NA

E: RISK (½ to 1 page)

Overall risk rating

The overall programme risk is assessed to be moderate. Specific risks include the challenging business environment in Tanzania, which makes it vital that the programme develop an effective communications strategy. Investing in small businesses, especially but not only in the child care sector, will present safeguarding risks and a thorough safeguarding strategy will need to be designed before implementation begins. This should include screening and due diligence processes for potential implementing partners. A complete risk assessment and mitigation strategy will be designed by the end of the inception phase in May 2019 and should be assessed against the risks identified in the original business case, in addition to any developments.

Outstanding actions from risk assessment

Not applicable

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery against planned timeframe:

Although longer than anticipated, the procurement process was designed thoroughly to ensure DFID got VfM from a complex programme, and the response of the market was very strong. Delivery of the inception phase is so far on-track though it is still early in the process. Bi-weekly meetings between the teams is helping to ensure timely delivery against the timelines agreed in the contract.

Performance of partnership:

The fortnightly meetings have provided opportunity for frank discussion and an open partnership. DFID is inviting challenge on its assumptions, including the selection of the focus sectors, whilst ensuring that the programme’s ambition remains the same. Fortnightly written reports allow regular updates of a shared delivery plan.

Asset monitoring and control:

It is not expected that significant assets will be purchased during the inception period but asset monitoring will be scheduled for the implementation phase, assuming a decision is made to proceed.

Outstanding actions from risk assessment: None

G: CONDITIONALITY (1-2 pages)

Update on partnership principles (if relevant)
There is no specific conditionality attached to the business case.

F: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Evidence and evaluation

Market systems programmes need to be informed by a very strong approach to monitoring, evaluation and learning. The Dar Jobs team should think creatively about the tools needed to inform ongoing decision-making. These include a sector vision document that sets out the pathway or pathways for transformation in the sector, and explains why the team is choosing the interventions they are. The sector vision itself can be a live document. DFID and the implementation team should consider a menu of deliverables to ensure accountability whilst retaining the flexibility to innovate and adapt. In addition to agreeing deliverables, the team could establish a set of stretch targets.

Good practice from similar programmes suggests that sector leads need to be incentivised to innovate and pilot different activities, but also to call an activity a failure and drop it. ACTION: The consortium to design a dashboard approach, to allow full oversight of the different interventions, understand how they are contributing to impacts and outcomes, and support fast decision-making about scaling activities up or down.

Monitoring progress throughout the review period
The programme has started with bi-weekly meetings between the DFID SRO and Programme Manager and at least the programme team leader. These meetings are supported by short fortnightly written updates, and are used to assess progress towards the milestones and agree any changes. Assuming the programme moves to implementation phase in 2019, there will be an agreed governance and oversight structure, and the frequency of these meetings can be reviewed. One key area for agreement is the correct way to involve a multi-disciplinary team of DFID and wider HMG expertise.