Project Completion Review – post April 2018

Title: Support to the Public Procurement System in Mozambique
Final Programme Value (full life): £2,9 mln	Review Date:	June 2018
Programme Code: 202463	Start Date 26/11/2012	Final End Date: 31/03/2018

Summary of Programme Performance

Year	2013	2014	2015	2016	2018
Programme Score	B	A	A	A	A
Risk Rating	Severe	Severe	Major	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202463/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202463/documents

A. Summary and Overview (1-2 pages)

Description of programme and what it has achieved

 “Support to the Public Procurement System in Mozambique” was a DFID-funded Programme implemented from February 2014 to March 2018. It was designed to fill an important gap of the procurement function in Mozambique’s public sector which was considered as one of the biggest challenges in service delivery and Public Finance Management (PFM).
The programme supported the Procurement Department “UFSA” (Unidade Funcional de Supervisão de Aquisições - UFSA) which is part of the Ministry of Economy and Finance under the National Directory of State Assets (it is not an independent Agency). It is mandated to act as an oversight function responsible for spending around 15% of Mozambique’s GDP.
The programme was implemented initially through a combination of direct financial aid through UFSA from 2014 to 2015 and technical assistance (TA) through Crown Agents (CA). From 2016 to the closure of the Programme, the Programme was delivered fully through TA. TA was provided in the form of one long-term Resident Adviser and short term TA missions which was coordinated by Crown Agents in collaboration with UFSA and DFID.
The programme provided targeted support in the following five output areas:

1.	Strengthening UFSA's performance through the provision of high quality strategic support
2.	UFSA's strategies, plans and operations are informed by evidence on procurement
3.	An effective monitoring and compliance framework supports UFSA's oversight function
4.	Enhanced capability of Procurement Departments (UGEAs) to
 undertake more effective, efficient and transparent procurement
5.	Improved public access to public procurement information

In respect to area 5, the project complemented another DFID Programme on Support to Anti-Corruption Initiatives (SACI) that encouraged advocacy and awareness of transparency and corruption issues among civil society and citizens.

The project design included a pilot component focused on facilitating dialogue and interactions with the education sector which was later replaced by the Water and Sanitation sector in 2016. This approach ensured that reforms are not tackled and supported only by central institutions (e.g. Ministry of Finance) and from the top downwards (by national level ministries), but also at sectoral level and deconcentrated operational levels. This multi-pronged approach for supporting coordinated reforms at a national and sector level was expected to increase the pace of reform by generating ownership outside the Ministry of Economy and Finance (MEF). It also had the objective of improving service delivery and policy implementation.

Despite an uncertain operating environment for much of the period 2015 to 2017 (elections and new public administration put in place; restructuring of the Ministry of Economy and Finance; decentralisation of procurement to Ministries, provinces and districts in 2015; debt crisis and operational cuts in 2016), the project made progress and delivered the following results:

- New Procurement Decree and regulation which led to a reduction in direct awards and more competitive processes – from 66% in 2015 date to 47% in 2018 (source: e-SISTAFE – data on procurement spend).
- Public Expenditure and Financial Accountability (PEFA) rating of PI-24 improved from a D to C+. This is mainly as a result of more competitive procedures due to the review of the Procurement Regulation and roll out of training.
- More transparent processes underpinned by the design of the new Government Procurement Portal leading to the publication of most tenders at central level. 31% now published as compared to 0% in 2015 which will improve the information flow with the private sector and society.
- New Procurement Manual since January 2018 and full roll out of training in Maputo and 11 provinces. 470 UGEAs in all 11 provinces (including additional training to 20 UGEAs in the WASH sector in Nampula and Zambézia) totaling 899 UGEA staff trained using training courses and materials funded by DFID.
- A new e-Procurement Strategy, which if rolled out, would enable enhanced compliance and data collection.
- 9 education and information workshops were held with the private sector to discuss the changes in the procurement regulation in all provinces except for Gaza.
- An updated UFSA’s 2018-2019 Strategic Plan that is aligned to MEF’s 2016-2019 Public Finances Strategic Plan to promote a more unified approach to the national policy on procurement reform.
- A final event was organised on 23 February 2018 to disseminate project achievements and discuss procurement challenges with Government and the private sector and to launch the new Manual.

There are two main challenges that undermine procurement reform in Mozambique and relate to UFSA’s position within Government. The Project supported a Concept Note ‘Future of the Public Procurement System in Mozambique’ dated July 2015 to assess the question of whether UFSA’s position in the Government structure was sufficient to enable it to carry out its mandate. The conclusion was that its role is limited by its lack of independence and authority as a subordinated department within MEF. The World Bank recommended in 2005 the establishment of a totally autonomous regulatory agency that would also take up the prior review functions of the Administrative Tribunal in matter of procurement. Unfortunately, as this project reaches it completion, the issue of UFSA’s status within Government remains unchanged from the 2015 findings. We continue to advocate that this should be reviewed and that UFSA should be elevated to the status of an autonomous regulatory body.

Weaknesses also continue at the operational level i.e. capacity and practices of decentralised procurement units (UGEAs) especially at the provincial and district layers of administration, and at the supervisory level.

Top lessons

- Having a Resident Advisor embedded in Government was key to the project’s success. This helped deliver the programme, build trust and provided DFID with strategic and political economy insights of procurement issues in Mozambique.
- While UFSA is committed to improving procurement, it faces a weak organisational structure and weak management within its Department. While this was highlighted in the original Business Case, the project did not manage to tackle the management and organisational structure of UFSA.
- Another major obstacle is continuous weak procurement enforcement which stems from the lack of independence of the Procurement Department. Risks are that UFSA remains understaffed, poorly organised and that the monitoring and compliance tools are diluted toward data collection only.
- Introducing transparency and accountability within government in particular around Procurement cannot be tackled by technical support solely. While Procurement reform was previously raised through the General Budget Support Group (GBS) platform at senior level – policy dialogue around procurement reform has been lacking since the suspension of GBS in 2016. Future PFM programmes need to be developed and coordinated at senior level and be central to donor-government discussions.

Follow up actions required following closure

1. Head of Office follows up with the Minister of Economy and Finance on the reimbursement of the 2015 unspent FA funds by September 2018.
2. Programme Manager ensures publication, in the development tracker, of the Project Completion Review by August 2018.
3. Programme Manager archives final key documents, and SRO shares with donors active in the sector by August 2018.
4. SRO and Programme Manager ensure that key recommendations are considered in subsequent DFID programming and share lessons across DFID office within three months of programme closure.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Strengthened UFSA's performance through the provision of high quality strategic support
Output number per LF		1	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Planning and management of UFSA's operations reflect strategic priorities	a. Short-term technical assistance (STTA) mobilised to undertake a review of UFSA’s strategic plan and MEF Public Finance strategic plan 2016-2019 to ensure alignment	Met / The Project helped review UFSA’s strategic plan and align it to the national Public Finance Strategic Plan
	b. Review of implementation of current UFSA strategic plan (2014-19) to feed into new Strategic Plan	Met / 2018 UFSA’s annual operational plan follows priorities as outlined in the revised Strategic Plan
1.2 Targeted technical assistance outputs delivered to strengthen UFSA operational and organisational performance	a. A STTA plan for 2017 has been agreed, included in the 2017 work plan and budgeted	Met / STTA plan was budgeted, agreed and completed
	b.UFSA has its own operational budget from DNPE	Met / Source: Annual Operational Budget

Provide supporting narrative for the score

The overall progress against the milestones met expectations. UFSA has improved its strategic priorities for procurement reform and is fully aligned with the new PFM Strategy as well as its operational annual plan.

The Project mobilised technical support to help UFSA review its Strategic Plan in October 2017. UFSA’s Strategic Plan was updated and is now in line with the new PFM Strategy. Key changes to UFSA’s Strategic Plan were the inclusion of targets to: 1) increase compliance to the procurement regulation and more competitive bidding 2) raise transparency through the publication of tender information (tender and award notices) on the Procurement Portal. Main findings included the need to implement a national e-Procurement system and increase UFSA’s mandate to act as independent administrative complaints and grievances review body to be able to enforce compliance. The latter received little traction to date.

Some of the main priorities going forward will be to:

- Provide more detailed, comprehensive and easily accessible publication of tender information;
- Strengthen the Portal and ensure its effective use by state institutions and the private sector;
- Enforce compliance in procurement and tendering procedures;
- Continue to explore readiness to move towards an e-procurement environment;
- The majority of objectives in 2017 focused on capacity building of internal and external stakeholders and making information accessible through UFSA’s portal.

In 2017 until project closure UFSA implemented:
- A training programme for all UGEAs across Ministries down to provinces and districts;
- A new procurement manual and guidelines offering a practical step by step guidance on how to do procurement, supervision, training, as well as how to raise complaints and grievances;
- Supervision of around 90 UGEA’s and a pilot project of 30 UGEAs to implement monitoring which was underpinned by a new Monitoring and Compliance Framework;
- 9 information workshops in all but one province;
- A communications strategy to improve information sharing of procurement regulations and UFSA’s portal with more information being made available to the public, including procurement regulations, statistics, standard technical specifications (Goods and Services Catalogue – CBS), publication of tender notices, access to the Unified Suppliers Registry (CEF) etc.

Lessons identified this year linked to this output and recommendations for future programmes

A key constraint is the economic crisis of Mozambique that began from 2016. Although the economy is picking up, all operational costs have been frozen across the Government and budgets have been cut for all Departments including UFSA. It is therefore extremely difficult for UFSA to fully implement its Strategy in the current conditions. DFID provided support to the delivery of training and supervision but over the long term, and with DFID’s exit, this remains a concern.

DFID managed to link this Project to the DFID WASH programme and deliver targeted training to the WASH sector at local level. UFSA, Crown Agents and SNV provided positive feedback on the training provider which prompted this Project to expand the training and supervision to the rest of the provinces in 2018. It is now being delivered through UNICEF. All training has been delivered except for two provinces. Given the needs observed, DFID sector programmes should include procurement capacity training in their programming in future.

Output Title	UFSA's strategies plans and operations are informed by evidence on procurement
Output number per LF		2	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 A reliable and user-friendly MIS is introduced to generate relevant, accurate and timely information on procurement operations	1.UFSA issues quarterly report to MEF on procurement statistics and trends and publishes the report on the website	Met / Data collection is published on UFSA website on a quarterly basis and includes central and provincial data per sector. UFSA management is focusing on improving current practices by increasing monitoring of weakest procurement entities.
	2. UFSA and MEF have quarterly meetings to study the UFSA report	Met / UFSA reports to MEF on a monthly basis the procurement statistics from E-SISTAFE procurement information and the monitoring and compliance database used in defining 2017 pilot supervision
	3. Evidence that information being obtained through the MIS and supervision visits is feeding into better policies and a more focussed Training and Supervision Plan.	Partially Met / The 2018 Training and Supervision Plans have been developed based on data from the supervision database. Not all sectors have focused on training plans yet . The WASH sector did because of the twinning of this Programme and the DFID WASH Programme: 20 UGEAs from Nampula and Zambezia benefitted from more focused procurement/tender training specific to the WASH sector. UFSA will need to step up its analysis of data so that it can target best practices nation wide.

Provide supporting narrative for the score

The overall progress against the milestones met expectations.

2.1 a) UFSA prepares monthly statistics, detailed by procurement method, level of government, administrative procedures and financial volumes, by category of spend (goods, works, services and consulting services). Statistics are published on the Procurement Portal on a quarterly basis. UFSA’s management is focusing on improving current practices by increasing monitoring of weakest procurement entities.

2.1. b) Through the project, data analysis is taking place and provides information on key weaknesses in tendering/contracting at various levels. However UFSA does not currently have the necessary level of staff to do the analysis and is unlikely to take this forward after the closure of the Project. DFID sees this as a missed opportunity.

 2.1. c) MIS provides information however UFSA has not been able to provide quality reports of its supervision visits that would have fed into better management and policy decisions.

Lessons identified this year linked to this output and recommendations for future programmes

The lack of an e‐Procurement system is a major barrier to improving the efficiency, effectiveness and transparency of public procurement in Mozambique. Currently, key procurement data cannot be retrieved from e-SISTAFE as it only holds basic payment data related to contracts (disaggregated public expenditure on goods, services and investments). The lack of procurement data makes it almost impossible to quantify the true extent of the issues and challenges.

The current e-SISTAFE functionality (developed in 2013) is an improvement over the previous complete lack of procurement information. Through this Project, the year 2015 was the first for which data was collected for the full year. It established a baseline of the use of different procurement practices– and particularly on the use of Direct Award – which can now be tracked.

Going forward UFSA will need to rethink how it staffs its supervision team and ensures compliance in data collection and analysis.

Output Title	An effective monitoring and compliance framework supports UFSA's oversight function
Output number per LF		3	Output Score	B
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Effective tools and methodologies for monitoring UGEAs compliance in a systematic way are developed, tested and mainstreamed	1. UFSA has a targeted, and fully budgeted, supervision plan for 2017	Met / 2017 supervision plan agreed between UFSA and CA targeted 120 UGEAs
	2. 32 pilot UGEAs of the Central level and Maputo and Gaza provinces have been supervised twice (February and May)	Partially Met / 30 pilot UGEAs supervised in February/March 2018 and 15 pilot UGEAs supervised in November/December 2017
	3. For the pilot UGEAs there has been a 25% improvement in procurement compliance recorded in May 2107 against the February results	Not Met / 5 % was achieved against the 25% target.
3.2 Evidence of improved coordination, data sharing and strategic collaboration with the internal and external audit institutions (Inspector General of Finance and Administrative Tribunal)	1. An operational MoU is established between UFSA, TA and IGF detailing collaborative work between them in respect of monitoring and supervision	Met / Collaboration among UFSA, IGF and TA has been evidenced by 3 meetings with TA in 2017 and 8 joint audits with IGF in October, according to plans set out between the 2 institutions. Both believed that an MoU was not necessary given the existence of joint annual work plans which serve the same purpose.
	2. UFSAs M&C database made available to IGF and TA online	Met / UFSA made database available to IGF Source: IGF auditors provided with access to the database. UFSA exchanges information with TA during joint planning meetings)
	3. UFSA supervision work plan for 2017 (see indicator 1 of this output) contains evidence of alignment with IGF audit plan	Met / UFSA's 2017 work plan contemplated 8 joint audits with IGF / Source: Audit reports were co-signed by UFSA, checked by Crown Agents.
	4. Audit recommendations on procurement and degree of compliance systematically monitored by USFA and IGF	Met / UFSA met 4 times in 2017 to review audit recommendations of joint audits
	5. Execution of at least 80% of joint audit plans and information-sharing adhered to	Not Met / 6 Joint Audits against 15 expected

Provide supporting narrative for the score

The overall progress against the milestones partially met expectations. This component was the most challenging and did not deliver as expected. Even though not all milestones were achieved, improvements were made over the course of the Programme with the institutionalisation of the monitoring and compliance (M&C) framework, a new supervision tool and a database which did not exist before the project.

The programme aimed to improve compliance and efficiency in procurement. Better monitoring and supervision was intended to help management identify and address key weaknesses in the system. Training was then targeted to address these weaknesses.

The programme’s other main objective was to introduce a new approach to supervision visits with an aim to increase efficiency. UFSA’s supervision missions would have a follow up monitoring visit in order to check whether previous recommendations were implemented.
The programme prioritised UGEAs most at risk, complemented by data collection collected through the monitoring database. The project provided training to 20 members of the national supervision team in November 2016 and a refresher course in February 2017. It intended to collaborate with the internal and external audit authorities and the Administrative Court, given that all have a remit in procurement. The latter proved to be challenging with no systematic coordination happening among these institutions. There were very few joint audits happening. 78% of the planned supervisions took place. Of the planned total 90, 70 supervisions were undertaken, of which 6 six were joint audits with IGF. Another 6 were implemented through the DFID WASH Programme in Zambézia and Nampula.

The key challenge was weak capacities within UFSA’s central supervision team to do the monitoring work and failure to comply to agreed deadlines. For example the work plan foresaw 2 supervision missions for each UGEA in 2017 – only one took place. Missions kept on being postponed. This underlines a weak management structure and weak leadership to enforce agreed workplans.

In terms of findings through the monitoring work, most pointed out to weak or no procurement plans. MEF established from 2015 onwards the need to prepare procurement plans. Even though there is no eProcurement system - anecdotal information combined with empirical evidence of the M&C pilot indicates that half of the UGEAs prepare procurement plans. Of those that do prepare most do not conform to best procurement practices.

Lessons identified this year linked to this output and recommendations for future programmes

Supervision capacity is an important function, especially in a decentralised procurement system as is the Mozambican one. Procurement rests on sector procurement departments. Authorities have to be well trained and guided on best practices, empowered to launch tenders and held to account for their actions. This can only be achieved through an efficient and effective monitoring and compliance system. It is therefore essential that UFSA either strengthens its own internal resources to be able to undertake its mandated supervision role, or it makes provision to outsource the supervision activity to suitable qualified providers who undertake this function under UFSAs management.

Output Title	Enhanced capability of UGEAs to undertake more effective, efficient and transparent procurement
Output number per LF		4	Output Score	B
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Evidence of strengthened UGEA capacity	1. 25% improvement in procurement compliance for the 32 pilot UGEAs recorded in May 2107 against the February results due to an aligned supervision and capacity building approach	Not Met / 5% was achieved against the 25% target.
	2. UFSA has prepared a budgeted Training Plan for 2017	Met / Training Budget prepared and executed in 2017
	3. The operational procurement manual is available on the UFSA website for use by all UGEAs	Partially Met / Procurement Manual prepared but not yet published on Procurement Portal

Provide supporting narrative for the score

Milestones have been partially achieved. The focus of this output is on capacity building and training for UGEAs – at all levels and across the Ministries. 2017 milestones measured the impact of training.

- The Project overestimated the rate at which the use of direct awards would decrease following the implementation of the new regulation and training received. Even with the training received in 2016 and 2017, procurement departments both at national and local levels still use uncompetitive procedures.
- UFSA budgeted its training plan which was co-funded by DFID. The 2017 detailed training programme was designed following the 2016 training needs assessment.
- The Procurement Manual although launched at the Final Event in February 2018 has not been uploaded on UFSA’s Portal. This means that neither Government staff nor the private sector have access to it.

The amount of proportional spend through direct awards in the provinces is greater than at central level, even though more than 60% of the spend takes place at central level. MEF is in line with good practices while some sector Ministries do not use competitive practices. Some factors were identified as undermining the development of training activities. The main ones identified were deficiencies in the coordination and communication between UFSA and provincial Procurement Departments. Limited financial resources was and will continue to be the main constraint in the development and sustainability of a professional training system in procurement.

Statistics reveal that the main challenges with the procurement system relate to management and leadership shortfalls. The amount of non-competitive procurement practices in the form of direct awards will not be totally addressed by the new regulation. The Project’s approach was to tackle procurement transparency and efficiency by educating and training procurement staff on the new regulations, increasing supervision and capabilities and introducing better data collection/analysis. Procurement is decentralised and improving capacity of UGEA staff to do procurement will be a slow process but the motions to address this have started through this capacity building programme.

Lessons identified this year linked to this output and recommendations for future programmes

At the beginning of the Project – approval of job profiles was part of donor reform dialogue. The idea was to ‘professionalise a procurement career within Government’, as part of the decentralisation of procurement. However still to date, there is resistance by certain sectors of the administration to the proposal, and MEF has not committed to a general procurement function (PF) career or job profiles.

Change management is a slow process but the motions to address this have started through this capacity building programme. We recommend that support to capacity building is ramped up through our sector work.

Output Title	Enhanced capability of UGEAs to undertake more effective, efficient and transparent procurement
Output number per LF		5	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
5.1 Evidence of gradually improving UFSA internet portal (in terms of publishing relevant and timely procurement information to bidders and the public)	1. Evidence of highlighting of UFSA's role in procurement oversight through the implementation of UFSA's Communications strategy (at least 30% of Central level UGEAs publish tenders on the Procurement Portal plus indicate baseline as measured in 2016 mapping of UGEAs)	Met / 31% (Jan-Dec 2017) / Source: quarterly statistical tables published in 2017 on UFSA Portal
	2. Evidence of engagement with civil society - through publication of UFSA quarterly report and promotional activities	Met / 9 Workshops held, in the three regions of the Country. 96 participants from private sector and associations

The overall progress against the milestones met expectations.

The objective of this output was to ensure improved private sector access to critical procurement information and bidding opportunities. The Project improved the quality of UFSA’s web Portal in line with OECD standard criteria (http://www.ufsa.gov.mz/). It should also help establish a harmonised supplier database within e-Sistafe in line with the national procurement legislation. The project also helped increase transparency of the public procurement system and facilitated communication and meetings between UFSA and the private sector.

The Portal came online in 2016 and good progress has been made by UFSA to improve it. It is increasingly used by UGEAs and suppliers in their day to day procurement operations. One of the highlights of the Portal is that since March 2016, UFSA publishes quarterly procurement statistics for the general public.
One of the main measurements of the Portal’s success is the number of notices published since the Portal was launched in April 2016 which has steadily increased.

 Notices Published on the Portal since Launch (April 2016)

Source: www.ufsa.gov.mz

Lessons identified this year linked to this output and recommendations for future programmes

Key to achieving sustainability in access to procurement information is the need to invest in innovative ways to engage with the Mozambican public.

Some of the actions planned, for example to grant access to UGEAs to the Portal was not prioritised by UFSA. This means that the number of tenders on the Portal is incomplete (only 31% of the total procurement notices are on the Portal).

The target for the Project was met given that it started from a low baseline. Given current talks of further decentralisation, UFSA would have to grant access to the Portal to Ministries as well as provinces.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The outcome is that public institutions at the national and provincial levels run transparent and open procurement competitions. The ultimate goal is that the public procurement system ensures more efficient public spending. The direct results will:

1.	Strengthen UFSA's performance through the provision of high quality strategic support
2.	UFSA's strategies plans and operations are informed by evidence on procurement
3.	An effective monitoring and compliance framework supports UFSA's oversight function
4.	Enhance capability of UGEAs to undertake more effective, efficient and transparent procurement
5.	Improve public access to public procurement information

 The key assumptions were:
- TA support can enhance technical capacities in UFSA and will strengthen the institutional framework of the public procurement system
- Sufficient resources to UFSA and Procurement Departments to fulfil its mandates
- Data is monitored and used to enforce compliance

The theory of change remains valid but some of the assumptions are not holding. The Project underestimated UFSA’s management and organisational capacity which to date remains extremely weak and is a key constraint to procurement efficiency and monitoring. UFSA resources are constrained by lack of donor support and lack of government funding to procurement reform in particular around training and supervision (compliance spot checks).

Many unknowns affected the Project. The Project did not expect for elections to stall the development of legal reforms and a restructuring of the Ministry which led to delays in some of the capacity building efforts. The economic crisis in 2016 affected the availability of public funds for investments and operational costs (monitoring missions were scrapped in 2017) and stalled new reforms such as the roll out of an eProcurement system.

The Project’s success lied in a stronger private sector that fed into communication events and was able to influence change and decision-making. The TA provided was extremely important and without it some of the frameworks, training tools, data transparency would not have been implemented.

Summarise the programme’s theory of change and major changes to it in the past year (1/2 page)

No major changes or shifts were made to the Project - The WASH sector pilot was added in 2016.

Explain major changes to the logframe in the past year (1/2 page)

The logframe was updated following the last Annual Review in December 2016 to include follow up monitoring missions to measure the impact of training provided. The support to update UFSA’s Strategic Plan was added.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

The Business Case proposed a series of qualitative VfM measures (aside from analysis of cost drivers) as the basis for assessing VfM of the programme against indicators of economy, efficiency and effectiveness. At the end of the programme, a robust assessment of VFM was conducted using quantitative and where possible monetary analysis. It concluded that the programme represented a high level of VFM. Examples and evidence are provided below.

Key cost drivers and performance

The key costs drivers for the project were the quantity and length of Technical Assistance (TA) and the number of trainings held. Costs of travel (e.g. air fares) and training (e.g. venues) were monitored and managed to ensure good value for money. The programme put in place processes to manage these cost drivers including:

Financial management processes - budgets were developed based on the Annual Operating Plan (agreed with DFID and UFSA) and the logframe. Expenditure was reviewed on a quarterly basis. Financial forecasts were monitored closely, with disbursements followed up on a monthly basis in order to avoid slippages on disbursements.

Procurement processes - when selecting suppliers e.g. for training centres and training facilitators, multiple quotes were obtained. Standard practice included a due diligence on suppliers. Savings were made through negotiating price reductions and discounts as well as purchasing tickets ahead of travel to keep fares low. These savings were reinvested into the project.

.

Economy

Two indicators were used to measure the cost (and value) of inputs on 1. Budget vs. actual expenditure on main cost categories and 2. Average unit costs:

Overall, the forecast of expenses was is in line with the total approved budget. The main area of overspend was on trainings including logistics. This overspend was covered by an underspend in most other budget lines, particularly for Short Term Technical Assistance (STTA) and other activity expenses such as printing of materials and advertising.

Average unit costs for International STTA were slightly lower than planned. This was due to using more TA days at the lower fee rate. Unit costs for International Long Term Technical Assistance (LTTA), National STTA and LTTA remained the same as planned.

Savings allowed for a one-month no-cost extension to plan the end of project seminar for the private sector and Government.

Efficiency

The indicator used to measure efficiency was the costs of training per participant completing the course which in 2017 was calculated to be £151, based on the training course lasting 4 days and completion rate of 90% among participants. Examples of efficiency include:
- The project coordinated with other DFID funded projects. For example, following a training of UFSA, UFSA provided procurement training for a WASH programme in two provinces, which was funded by SNV (Netherlands Development Organisation).
- Procurement training has also been coordinated between the project and GIZ, who are using similar methodology and materials.
- The project planned to train 200 UGEAs (Management Unit for Implementation of Procurement) and trained 850. This was achieved by implementing the public sector training pool with 66 public servants as trainers, which greatly reduced the cost by avoiding the need to outsource the training.

Effectiveness

The indicator proposed in the Business Case was the share of supervised tender processes with complete documentation at central and provincial level. The analysis done covered 30 out of 1000 UGEAS based on the data available. At central level the results indicate overall 65% of conformity with the Procurement Regulation and at provincial level - overall 67% of conformity with the Procurement Regulation. It does not include education sector given this component was dropped.

Examples of processes in place to promote effectiveness include:
- Quarterly and Annual reporting to DFID and UFSA with a report available in both English and Portuguese
- Evaluation of training – including trainers’ performance evaluation, participants learning evaluation and participants’ satisfaction evaluation. These were used to adapt training activities according to the evaluation results and lessons learned
- Mid-term evaluation was undertaken which informed programme orientation.

Evidence of effectiveness includes:
- Components that were not effective were closed or modified. For example, early on in the programme the decision was taken to close the Education pilot due to lack of government buy in to the proposal. Resources were reallocated to components that were showing more results.
- Training held in districts was redesigned in response to an issue in the level of knowledge among participant. Extra training was provided to get them up to the level required to complete the course.
- There has been continual redesign of the project, for example the database that advertises procurements has more users than originally envisaged and more advertising.

Evidence of Cost -Effectiveness to date

In 2017, the Government saved $97,750.00 by switching from newspaper advertised tender notices and contract awards to using the Portal.

 There is also evidence that the benefits used to assess the cost-effectiveness of the programme at design stage are being realised. These are in line with benefits identified in the original economic appraisal in the business case but a financial value has not been estimated. They include:

Improved transparency through improved data collection methods and information management system and more interaction with private sector. The portal has greatly improved transparency, now has a wealth of information that is available to the private sector

Better compliance through capacity building and supervision of staff from UFSA, UGEAs and DPPFs. Steps in the bidding process correctly followed. Capacity has been built in DPPs - there is a training plan and people are following processes including supervision. Effective tools and methodologies for monitoring UGEAs compliance in a systematic way have been developed, tested and mainstreamed.

Evidence of Equity to date

The approach to measuring equity was to look at distribution by location. During the course of implementation, the project reoriented away from solely providing support to the central government procurement service and provided capacity strengthening to all districts.

UFSA’s training data on number of participants per course show that the percentage of women and men were evenly divided. This demonstrated an increased participation of women in the UGEAs, which lines up to the equivalent of other departments involved with public finance.

To note that at the end of the programme 13 of the 20 strong staff of the Supervision Department are female, up from the evenly divided number of 2015. The project contributed to the increased number of female supervisors, through the training courses provided in 2016 and 2017.

On the other hand, the composition of the training staff, who were predominantly female in 2014 has changed to more male than female (4 men and 3 women staff).

Through the increase of the quality and reach of government procurement, especially by fostering more competitive procurement (versus the practice of direct awards) in contracts aimed at SMEs (small and medium enterprises, including individual entrepreneurs), indirectly, the programme, supported Mozambique’s small business community. In general at least half the SME’s are commanded by females and employ a large contingency of female labor in most African economies (including Mozambique). Therefore, it can be inferred that the programme helped promote gender equality through procurement.

Evidence of Sustainability to date

Evidence sought to assess the sustainability of the project activities and extent of level of engagement of key stakeholders and partners. The project promoted sustainability from the outset:

- TA project and government counterparts built capacities and institutionalised the M&C framework for example.
- Government stakeholders were involved in the design of activities and led the prioritisation of yearly work plans.
- UFSA capacity to analyse data was promoted. The 2018 supervision plan was finalised using data retrieved from the supervision missions (ie UGEAs at most risk).

Government now systematically collects information from the financial system and publishes it on a quarterly basis. Different parts of government are more joined up than at the start of the programme.

E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

Throughout the lifetime of the programme risks were updated regularly in line with DFID’s guidelines and discussed at quarterly meetings. The original risk matrix prepared in the context of the Business Case rated the programme as high risk mainly because the Project started from a low base with huge weaknesses identified in the procurement system.
Fiduciary and corruption risks were also assessed as substantial. In 2014, there was a significant review of the original risk matrix to better reflect the programme and country circumstances. Risks around UFSA’s commitment have been reassessed on the upside, and the successful integration of the TA component has helped mitigate fiduciary risks and speed up delivery.
Following the 2015 Annual review, the risk rating was downgraded from high to moderate. The overall size and impact of this programme relative to others in the portfolio suggested that a Moderate rating was warranted. Other factors that down played the risk was the closure of the Financial Assistance (FA) component and the commitment demonstrated by UFSA to improve procurement capacity under the constraints the Government suffered during the economic crisis.
The following main risks were observed in the final year of the programme, as well as actions taken to try to avoid their occurrence:
- Inadequate funding provided by the Government to execute UFSA’s activities and mandate compounded by the economic crisis. This risk was in most part mitigated by DFID agreeing to fund some of the supervision and training activities held in the provinces.
- Weak capacities at central level. This was partially dealt with by increasing staff training.
.
The risk rating remained moderate until project closure.

Update on partnership principles
N/A

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The ‘Support to Public Procurement System’ programme in Mozambique was designed to contribute £3.9m over 5 years (2013–2016) which consisted of £2,360,108.00 in Financial Aid (FA) to the Government of Mozambique(UFSA) and £1,575,681.00 in Technical Assistance (TA) delivered by Crown Agents.

Given weak absorption capacity and low spending rates of the FA component, the 2015 Annual Review recommended to reduce the FA component and reallocate funds to Crown Agents. The Crown Agents contract was increased by £750,000.00 to £2,238,659.00. The project was extended from 30 June 2016 to 28 February 2018. In October 2017, DFID and Crown Agents agreed to a no-cost extension to the programme given that funds were remaining to carry out a final seminar. The new end date of the CA contract was adjusted from 16th February to 16th March 2018 and end date of the project was extended to 31 March 2018. The total spend for the Project was £2,851,398.74. The programme has no assets.

The project management relationship between DFID and Crown Agents was good. Payments were 100% milestone based and paid against quarterly reports upon delivery of milestones. The programme received Crown Agents’ financial audited statements covering the period up to December 2016. Close coordination between DFID, Crown Agents TA team and main government stakeholders was key to ensuring a good commercial relationship. At the outset of the project DFID held coordination meetings with UFSA as often as needed (on average every 1 to 2 months) and engaged on a regular basis with the Crown Agents Resident Adviser.

Audited statements for Financial Aid were submitted to DFID every year which were unqualified. An audit carried out by Ernst &Young in 2016 revealed £173,000.00 of non-spent FA funds. Government has agreed to reimburse to DFID. DFID has started the process of refund and UFSA sent an official request to the Treasury to reimburse the funds to DFID. We are awaiting reimbursement.

The Crown Agent Project Management team, based in London, visited Maputo on a regular basis (around 3 times a year) and engaged with UFSA and DFID to monitor project performance. These visits generally included:

- An overall project update meeting with the DFID Programme Officer on finances and milestone payments;
- An operational progress update and forward planning meeting with the Director of UFSA;
- A joint UFSA and DFID project meeting to discuss progress, risks and results;
- Team meetings with the Resident Advisor; and
- From April 2016 mission debriefs with the PFM Donor Group took place to ensure information sharing and closer coordination with the donor community.

Date of last narrative financial report	25 February 2018
Date of last audited annual statement	31 December 2015

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

DFID held Management Meetings with UFSA on average every 1 to 2 months and engaged on a regular basis with the Resident Adviser. Crown Agents provided quarterly performance reports to DFID and UFSA. These were used to discuss progress, performance and any emerging bottlenecks.

DFID also liaised on a regular basis with the Crown Agents Programme Management team, based in London, who regularly visited Maputo (at least 3 times a year) to monitor project performance against the work plan and logframe. Crown Agent’s final mission took place during the week of 15th February 2018 to finalise the PCR, discuss project closure with DFID and UFSA and present the final results of the project at the Final Event.

Evidence

The Project carried out an assessment of the PEFA 24 indicator to measure the impact of the Project. The PEFA 24 went from a D in 2015 to a C+. DFID is currently co-funding an OECD MAPS Assessment which will provide an updated assessment of Mozambique’s procurement system by December 2018.

Throughout the Project, data collection and analysis was promoted through the establishment of a Monitoring Information System (MIS). The data is now made available on UFSA’s Portal.

Learning

The following lessons learnt include:
- Having a Resident Advisor embedded in Government was key to the project’s success. This helped deliver the Programme, build trust and provided DFID with strategic and political economy insights of procurement issues in Mozambique.
- The length of the programme (4 years) enabled to make some real systemic changes that otherwise would not have been possible. Reforms take time to embed and short-term projects have limited ability to make real meaningful changes due to the time things take to evolve. An example of this was the procurement portal which started in 2014 but was not implemented until the end of 2016 due in part to the need for extensive consultation, design, testing and continuous improvements that were necessary prior to its launch. Having the flexibility of a four-year duration also meant the project was able to withstand the instability caused by the 2014 election and the resulting change in Government, including a major change in the Government structure within which UFSA was subordinated.
- A lesson for all parties in this project has been to ensure that log frame indicators, whilst needing to be ambitious and stretching, remain achievable and realistic. Our target for a 25% improvement in procurement compliance for the pilot UGEAS was over ambitious, despite early indications that this may be possible.
- While UFSA is committed to improving procurement it faces a weak organisational structure and weak management within its Department. While this was highlighted in the original Business Case; the project did not manage to tackle the management and organisational structure of UFSA with the Ministry of Economy and Finance.
- Another major obstacle is continuous weak procurement enforcement which stems from the lack of independence of the Procurement Department. Risks are that UFSA remains understaffed, poorly organised and that the monitoring and compliance tools are diluted toward data collection only.
- Introducing transparency and accountability within government in particular around Procurement cannot be tackled by technical support solely. While Procurement reform was previously raised through the General Budget Support Group (GBS) platform at senior level – policy dialogue around procurement reform has been lacking since the suspension of GBS in 2016. Future PFM programmes need to be raised and coordinated at senior level and form part of donor-government discussions.
- A key challenge is the lack of an eProcurement system that tracks and measures procurement at all levels. Although not part of the Project’s mandate, it did not support improved contract management (eg, purchase and delivery of medicines). A key recommendation is that this type of support is provided through DFID sector support with a strong link to M&E that allows assessing trends in progress.

Progress on recommendations from annual reviews for this programme

Most recommendations have been taken place and been implemented such as:

- The need to have a prioritised yearly work plan with Government. The objective was to prioritise efforts and work strands in the final year to focus on sustainability and institutionalisation of good practices.
- Support the update of UFSA’s new Strategy in 2017 as the previous one came to an end in 2016.
- Institutionalise training across the country. Yearly training plans are now budgeted and part of UFSA’s mandate.
## Smart Guide
## The Project Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.
The Project Completion Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it aimed to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. You should assume that readers may not go beyond this summary. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. There needs to be a record of any follow up actions that may be required after completion of this review (eg related to final payments, audited statements etc – see the extension and closure section in the Smart Rules). These may sit best in the Delivery Plan – but you should agree them with the person signing off the PCR and include them in this (publicly available) report or the Delivery Plan.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the PCR for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review (Business Case approval if the programme is under 15 months and hasn’t had an AR) and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in Section A. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress against outcomes
Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved? Review this in view of the overall programme score; but it is possible that outputs were delivered but the envisaged outcomes or impact were not – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact. You should refer to the indicators in the logframe. Did any unexpected outcomes emerge? Were there any significant changes in the planned timetable for delivery of the programme? Were there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact were valid e.g. did the ToC logic, supporting evidence and assumptions hold up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications were for the programme. Ideally changes should not have be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started.
D: Value for Money
Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme You should refer to VfM measures and metrics from the Business Case and/or ARs. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind. You should note any formal extensions or amendments to the programme giving brief details about cost, duration and the reasons why. Signifcant changes to logframe indicators or targets may also be relevant.

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) during the past year and over the life of the programme / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context in the past year and how they impacted on the programme and were mitigated. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review (remember that projects remain open until they are archived, even after the PCR is complete). / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences?
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could have been a more effective partner to help deliver the programme (key points could be included in Section G too). / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how they engaged with the programme implementer(s) and DFID. Briefly describe the PCR process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Include any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned or has taken place set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications or follow-up actions of that learning for this programme may be best captured in Section A / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from ARs (especially the last one) should be provided.