Annual Review
Project Title	: English in Action
Date project started	: May 2008
Review date	: May 2014
Introduction and Context
What support is the UK providing?
English in Action is a £50 million programme being implemented over nine years (2008-2017). EiA is designed to improve the teaching and learning of English in Bangladesh; the project works with Government Primary and Secondary Schools, with out of school children via NGO partnerships, and with adult learners via a mass media component.

What are the expected results?
EIA expects to increase social and economic inclusion for more than 25 million Bangladeshis by developing English language skills for school pupils and adult learners. The project also expects to contribute to the economic growth of Bangladesh by providing English language as a tool for better access to the world economy. EIA will take this forward through the development and delivery of inclusive national programmes. The beneficiaries will be male and female adults in urban and rural communities, teachers of English, and school-aged children. Progressive and innovative approaches to teaching and learning will ensure that all beneficiaries have the opportunity to develop English as a practical skill. / By the end of the final year of the programme (2016/17), the following outputs are expected to be delivered: / The proficiency in communicative English among the population of Bangladesh to increase measured objectively using Trinity levels. / Employer satisfaction (with employees’ communicative English) to increase from 68% of employers in the baseline to 80%. / Motivation for learning and using English among the population of Bangladesh (students 51% to 65%, teachers from 64% of to 80%). / Increase the numbers of teachers and pupils participating in English in Action school interventions to 64,500 teachers and 6.75 million pupils (3.29 male and 3.46 million female). / A cumulative total of 9 million people will have used BBC produced EIA media products regularly by the end 2017. / National systems and structures take on key elements of EiA initiatives as part of ongoing large scale reform initiatives, with the aim of these becoming ‘business as usual’ over time

What is the context in which UK support is provided?
EIA was designed in response to a request from the Government of Bangladesh. English language skills are in short supply. This is a result of two main factors: poor quality English teaching in schools; and limited access to English learning materials for school leavers and adults. / Few people under fifty are confident, fluent English speakers, and English is the most commonly failed examination subject at the secondary certificate level. Lack of English language skills is regarded as a constraint to economic development. For example, employers state that job applicants and employees lack English language skills necessary to work effectively. A pre-appraisal mission recommended that the problem be addressed at scale, through a project that would have substantial reach and impact. Previous shorter term, smaller scale interventions were not fully successful and results were not sustained. Reasons for this included the lack of scale, the lack of extended timeframes, and an absence of focus on adult learners.

Section A: Detailed Output Scoring
Output 1: Primary teachers’ classroom practice and the English language skills of both teachers and pupils improved
The overarching aim for the primary schools component is to improve the English language skills of Bangladeshi school pupils. To achieve this, EiA will strive to improve both primary teachers’ classroom practices and their English language skills. / The immediate beneficiaries of Output 1 are the teachers and pupils in the primary education programmes of Bangladesh. / Outputs 1 score and performance description / Output Score for Output 1: A + (moderately exceeded expectations) / Progress against expected results / Performance Indicator Milestone Achievement / Reach: / The cumulative numbers of teachers, and pupils participating in English in Action primary interventions Primary Teachers: / 7,500 (50%M, 50%F); / Primary Pupils: / 540,000(49%M, 51%F) Exceeded target / 7, 523 (45%M, 55%F) / 542,000 (50%M, 50%F) / Practice: / The number of teachers incorporating EiA teaching approaches in their classroom practice 20% student talk in a lesson; / 60% of that talk is in English Exceeded target / 27% student talk in a lesson; / 91% of that talk is in English / English Language skills / The proportion of EIA supported teachers and students reaching a particular English Language competence grade on Trinity Scale. Teachers: / 7.5% increase over baseline at level 2 or above / 7.5% increase over baseline at level 3 or above / Students: / 5% increase over baseline at level 1 or above / 5% increase over baseline at level 2 or above Teachers: Not achieved / 6.5% increase over baseline / 3% increase over baseline / Students: Exceeded / 34% / 20% / Summary of Progress and Performance / During the scale up period, EiA reached 7,523 primary teachers (compared to 508 in the pilot phase). Milestones for reach have been achieved. Achievements for classroom practice have exceeded target, most notably in the area of the percentage of student talk that is in English. / Scale-up has been achieved through highly innovative approaches. Direct intervention from core trainers and English Language experts has been reduced, and the ‘trainer in your pocket’ – mobile phone and memory card – has taken a central role in modelling both teaching methodology and English skills for the classroom. Decentralised peer support via teacher facilitators, and local cluster meetings have also been important to successful scale-up. Decentralisation has also been a key factor in allowing the activities of the primary school component to proceed in spite of the problems posed throughout the year by frequent political unrest. Providing training and support for Head Teachers and quality assurance via local government staff has helped to ensure that lessons learned in training are transferred to classroom practice. / All materials produced by the primary schools component are of a high quality and the video materials show Bangladeshi teachers in typical Bangladeshi classrooms. This authenticity helps promote uptake of EiA methodological approaches, by demonstrating that a communicative approach is ‘do-able’ in local circumstances. / Importantly, EiA’s model of teacher development is not subject-specific. It is an overall ‘recipe’ for improving classroom practice, and conforms to best practice in teacher development as set out in the Education for Development (E4D) evidence base, and in DFID’s 2013 systematic review of impacts and cost-effectiveness of strategies to improve performance of under-trained teachers in the classroom in developing countries. / All Output 1 testing is linked to the internationally recognised Trinity Grade Scale, which is developed based on the common European framework of language testing, developed to assess students’ English Language ability objectively. It is a 12-grade scale. A summary of attainment levels for the first four grades on the scale is as follows: / Trinity Grade 1 – requires knowledge of greetings and some basic personal information / Trinity Grade 2 – speakers can offer and respond to short, simple questions, requests and statements relating to personal details and situations / Trinity Grade 3 – speakers can exchange basic everyday information, asking and answering questions using simple sentence patterns / Trinity Grade 4 – speakers can talk about a prepared topic, asking and answering questions about it / The review team is content with the quality of the Trinity examination board testing and with the internal quality assurance methods used by Trinity. Statistical analysis is undertaken by an independent statistician, and overall the processes provide evidence that assessment of general English Language competence is reliable. / For Performance indicator 3 – the improvement of English language skills, student achievement is substantially above target. On the other hand, for teachers, there is only a small gain in skills, and this is below target. / Two reasons why the teachers’ English skills gains have fallen short of the targets may be: / Teachers have received training in ‘English for the Classroom’ - English for a specific purpose. The Trinity tests which are used to measure improvement capture progress in general English. There is thus a mis-match between what has been taught to teachers and what has been tested. / In support of EiA’s Social Inclusion Strategy, Phase III has targeted teachers in the poorest Upazillas, as a result the English language skills of teachers in this Phase may have been lower than teachers included in the Baseline assessment. / Establishing causation in education interventions is often challenging, and it was not possible to be fully certain of the reasons for teachers’ underperformance against this indicator. It is interesting that targets set for the improvement of pupils’ English language skills have been exceeded. This implies an absence of correlation between improvement in teachers’ English language skills and English language learning gains made by pupils. / In general, a limitation of EiA is the lack of a counterfactual or a quasi-experimental design. This could be described as a ‘legacy’ issue – when EiA was being developed, there was less focus on the need for a counterfactual. Strength of evidence within education interventions has been a rapidly growing field over the last ten years, for example, through the work of the 3ie initiative. However, the lack of a counterfactual makes it difficult to fully attribute pupils’ English language learning gains to the EiA intervention. / Overall, this component can be particularly commended for reaching a large number of students who have shown improved English language skills. / Recommendations: / 1) In relation to the English Language Skills Performance Indicator, EiA should explore reasons for underperformance in the improvements in teachers’ English language skills, using external expertise if possible. This could include scrutiny of the research evidence examining the relationship between students’ English language learning outcomes and the English language skills levels of their teachers. / 2) The increased amount of student talk in a lesson is a significant achievement. However, sustainability of learning gains will depend on the type of talk. Research in the E4D field suggests that often student input in English is confined to ‘safe talk’ – repetition of already known words and phrases, choral repetition, singing songs in English, etc. Small scale, well-designed independent research using discourse analysis techniques could provide valuable information about the nature of student talk in EiA classrooms, and could provide useful knowledge about both the likely impact and sustainability of EiA’s teacher training approaches. This should be undertaken. / 3) The use of m-learning and peer support to bring about improved teaching practices and ultimately improved learning outcomes for students is highly innovative. DFID should consider commissioning independent research into the role of m-learning and peer support within EiA; if strong evidence can be found for the success of this approach, it will be of great interest to the E4D field. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Change people’s perceptions of English language learning, reduce barriers to English, and support the development of an English language media sector through the innovative use of television, mobile phones, and other media platforms
Output 2 score and performance description: / Output Score for Output 2: A++ (Substantially exceeded expectations) / Progress against expected results: / Performance indicators Milestones for 2014 Progress / Reach / Cumulative numbers of Bangladeshis accessing BBC produced EIA media products. A cumulative total of 8.5 million people using BBC produced EIA media products regularly by the end of March 2014 (65%male, 35% female) Exceeded expectation / 10.25 million / (46%M, 54%F) / Perception / Perception of reduced barriers and increased positivity towards learning communicative English among school leavers and adults 43% of people who have used BBC EIA products will report increased motivation to learn and /or increased confidence to use English in their everyday lives (47% of males, 35% of females) Exceeded expectation / 60% (62% of males, 59% of females) people who used EIA products have reported increased motivation and confidence to use English / English language skills / The percentage of people exposed to BBC produced media products showing an increase in average competence as evidenced by speaking and listening test. 49% of people who have used BBC media products showing increased English Language ability Exceeded expectation / 56% people showed increased English language ability / Summary of Progress and Performance / For all three performance indicators in Media and Adult learning, progress has substantially exceeded expectations. / In relation to Reach – as evidenced by a series of nationally representative surveys: / Forty four million Bangladeshis are aware of at least one EiA media (BBC Janala[1]) product / Twenty eight million people used or watched at least one media product / 10.25 million people are highly exposed to EiA (i.e. have accessed at least one product five times). This is an increase of 50% from 2011 / ‘Dwell time’ – the time spent engaging with learning via the website is an impressive 16.5 minutes[2] / The mobile learning platform has now received over 24 million calls from 7 million users / 4.1 million people follow lessons in Prothom Alo, one of Bangladesh’s leading newspaper / In relation to Perceptions – as evidenced by a baseline survey in 2009, a midline survey in 2011, and a second midline survey in December 2013: / People who use BBC Janala have very positive attitudes towards the products. They (98%) think that BBC Janala has made English easy to learn and they think (93%) it makes English accessible to everyone / Those highly exposed to BBC Janala are more likely to report increased levels of motivation and confidence to learn English / In relation to improved language skills - as evidenced by self-report data: / Nearly one-third (31%) of BBC Janala users felt they learned a fair amount or a lot of English from BBC Janala products. This varied amongst the various platforms e.g. 88% of respondents who used the website reported learning how to speak some English words from the website compared to 50% of those who used Prothom Alo and BBC Janala mobile. / As evidenced by objective testing: / Test data indicates that 56% of those using EIA media products have achieved measurable increases in their English competency. Testing procedures were developed by an independent expert in the field, in response to a 2012 Annual Review recommendation, and test approaches are valid and reliable. / The Media and Adult learning component has made a significant contribution to DFID’s cross-cutting theme of social inclusion. Quantitative data are impressive; 54% of users are female; 83% of users are rural; and 79% of the repeat users (‘highly exposed’) are from the two lowest socio-economic classes. / In addition to this quantitative data, materials produced for the ‘four’ platforms in the media and adult learning component are of an excellent quality. As evidence of this, BBC Janala has won five international awards – including awards for technical excellence and for serving the poorest sections of society with high quality media products. At least two elements of BBC Janala’s approach to materials/ content design are in line with best international practice in both English language skill development and adult learning. / Firstly, the mobile, newspaper and web platforms share a well-structured common core syllabus: the BBC Janala - Amar Engreji (“My English”) course. The course, in three stages, offers personalised learning on mobile and web. Rather than listening to particular lessons in any given week, users can access all the course content in sequence, at their own pace. The system recognises individual callers or web users and offers them the next lesson in the series, whether 3 hours or 3 weeks between access points. This is the first personalised English Language mLearning platform of its type anywhere in the world. Learning is self-paced; learners can track and evaluate their progress, and on successful completion, receive a course report and certificate in acknowledgement of their achievement. / Secondly, BBC Janala also uses a CLIL (content and language integrated learning) approach. This means that English skill development is combined with content and information which is highly relevant to the lives of many Bangladeshis. For example, Nijey Nijey Shekha (Learning by Yourself) provides motivating and engaging examples of ordinary Bangladeshis undertaking a learning challenge. Specific scenarios include a rural health worker who needs English to support her work communication – reading medicine instructions, talking to NGO staff - or providing Bangladeshis who wish to become migrant workers with information about how to take this forward using the appropriate channels. / The Media and Adult learning component has also worked collaboratively with the schools components and other NGOs. A key achievement here has been the creation of self-help, peer-led English Clubs in 31 districts, often working with the poorest and in remote communities. Recent data show that over half (56%) of club members showed an improvement in their English language competency score, measured through the objective test used to capture progress for users of other BBC Janala platforms. / Data from 123 clubs also show that: / Over half (55%) of the people who participated in the clubs were more motivated to learn English at the end of the club compared to the start. / Learning English helped people in their jobs. 40% of those who reported that English had helped them in their current job also reported an increase in their income level across the study period. / English Learning Clubs helped the members feel confident in using English and also they felt they were respected in their communities and were able to help others with tasks involving English. They felt more confident to be interviewed for a job in English, to fill in forms and to introduce themselves to a native English speaker. / Nearly all club members felt they had learned from the clubs. They felt the English they learned helped them to do better in their current jobs, helped with their studies, in their hobbies and to communicate with others more easily. / The media component has engaged in a significant amount of capacity building, including the development of a Media Alliance. The work with Bangladesh TV (BTV), the main public sector broadcaster, should be specifically noted. BTV staff state that they have benefitted greatly from capacity building work from BBC Janala, and are very keen to see this continue.
The EiA media component has provided access to English skills, linked to highly relevant content, to the poorest in Bangladesh. It has also provided for a predominantly rural, and female group. For the many millions of Bangladeshis who have left school but want to learn English to improve their earning potential, face-to-face tuition is prohibitively expensive. Through EiA’s media component, quality English language learning on television is provided free of charge through popular formats such as drama, comedy, factual and animation in slots that command large audiences. Lessons are available at low-cost using the mobile phones that people already possess (half the price of a regular call) and through the first bilingual English Language Training website. This has been designed for the slow connection speeds of Bangladesh, as downloadable files through a mobile internet (WAP) site and as print copy in one of the country’s popular Bangla-language national newspapers. / The EIA media component (BBC Janala) will close by the end of June 2014. To ensure sustainability, two options were presented to DFID and the EiA team. The strongly preferred option is for BBC Janala to work with a private sector partner; this partner will provide additional, paid-for services to BB Janala users. The aim is to make low-cost provisions available. There is currently no low-cost, high quality language testing available in country. The expectation is that profit generated from testing will be returned to BBC Janala to support the relevant platforms developed via EiA funding. The preferred option is described by DFID commercial adviser as a ‘win-win’. As part of institutionalisation it makes sense for BBC to continue its future work with a Private Partner to allow the services being provided by BBC Janala to continue without DFID funding; especially since are developmental benefits in these services continuing. / The second option is to hand over BBC Janala platforms to local service providers. Reasons why this is not an optimal solution include: / Partners are not yet ready to receive products / Leadership skills are not fully developed / There is a potential price increase / There would be branding considerations / Access would be likely to reduce in the medium term / Recommendations for Output 2 / DFID to support BBC Janala as fully as possible and within necessary timescales to facilitate the transition to private sector delivery / Wherever possible, continued informal contact between EiA and BBC Janala, including joint dissemination activities, should continue. / BBC Media Action should continue capacity building work with BTV (including through other platforms funded by DFID HQ), if resources are available for this important work. / DFID and BBC Janala should consider the assessment and evaluation of capacity building work – this has been a major achievement of the project and it would be useful to develop qualitative and quantitative indicators which can measure achievement. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Low (check in logframe) / Revised since last Annual Review? N
[1] BBAC Janala is the public-facing brand of all EIA adult learning products
[2] Some international and Bangladesh comparisons (although, it should be noted that BBC Janala site is unique in terms of the service it provides): Guardian: 3:46; Wikipedia: 4:30; Daily Star: 8:42; Prothom Alo: 9:42; Bikroy: 11:50; YouTube: 18:18. Source: alexa.com

Output 3: Secondary teachers’ classroom practice and the English language skills of both teachers and pupils improved
The overarching aim for the secondary schools component is to improve the English language skills of Bangladeshi school pupils. To achieve this, EiA will strive to improve both secondary teachers’ classroom practices and their English language skills. / The immediate beneficiaries of Output 1 are the teachers and pupils in the secondary education programmes of Bangladesh. / Output Score for Output 3: A (met expectations) / Progress against expected results / Performance Indicator Milestone Achievement / Reach: / The cumulative numbers of teachers, and pupils participating in English in Action primary interventions Teachers: / 5,000 (70%M; 30%F); / Students / 2.08 million (48%M; 52%F Achieved target / 5, 028 (81%M; 19%F); / 2.09 million (47%M; 53%F) / Practice: / The number of teachers incorporating EiA teaching approaches in their classroom practice 20% student talk in a lesson / 60% of that in English Exceeded target / 24% student talk in a lesson / 88% of that in English / English Language skills / The proportion of EIA supported teachers and students reaching a particular English Language competence grade on Trinity Scale. Teachers: / 7.5% increase over baseline at level 3 or above / 5% increase over baseline at level 4 or above / Students: / 10% increase over baseline at level 2 or above / 5% increase over baseline at level 3 or above Teachers: Not achieved / 2% increase over baseline / -3% decrease over baseline / Students: Exceeded / 14% increase over baseline / 11% increase over baseline / Summary of Progress and Performance / During the scale up period, EiA reached 5,028 secondary teachers (compared to 243 in the pilot phase). Milestones for reach have been achieved. Achievements for classroom practice have exceeded targets set, most notably in the area of the percentage of student talk that is in English. / Progress has been achieved for Output 3 in the same manner as Output 1 - through highly innovative approaches. Input from master trainers has been reduced, and the ‘trainer in your pocket’ – mobile phone and memory card – has taken a central role in modelling both teaching methodology and English skills for the classroom. Decentralised peer support via teacher facilitators, and local cluster meetings have also been important to successful scale-up. Decentralisation has also been a key factor in allowing the activities of the secondary school component to proceed in spite of the problems posed throughout the year by frequent political unrest. Providing training and support for Head Teachers and quality assurance via local government staff has helped to ensure that lessons learned in training are transferred to classroom practice. / As with Output 1, all materials produced by the secondary schools component are of high quality and similarly the video materials show Bangladeshi teachers in typical Bangladeshi classrooms. This authenticity will promote uptake of EiA methodological approaches, by demonstrating that a communicative approach is ‘do-able’ in local circumstances. / From the beginning of 2014, the secondary schools component is working with the technical and vocational education sector. Currently this is a pilot, but there is clearly willingness to roll EiA approaches out across the sector if evidence of success is provided. / In the area of English language skills, students have moderately exceeded targets. However, there is little or no evidence for a change in the English language competence of secondary school teachers. / Reasons for this may be: / Testing was of general English ability – training was specifically in English for the Classroom. Anecdotal reports suggest that teachers may not be able to transfer the specific English needed for teaching into general communicative contexts, and that English for Specific purposes – in this case classroom communication – may exceed skill levels in General English. / In Phase III, teachers were drawn from the poorest Upazillas, and there was no re-assessment of English language baseline competence – the attainment levels of teachers on entry to EiA may have been significantly lower than the small baseline cohort. / There may be other factors influencing why teachers failed to attain expected targets – attribution is always difficult in language education, and ongoing research would be needed to unpack the underpinning reasons for this underachievement. / Overall, this component has reached a very large number of students, and has increased students’ use of English in the Classroom. Furthermore, there has been a useful improvement in students’ language skills. / Recommendations / Recommendations for Outputs 1 and 3 are identical, and relate to deepening EiA’a research evidence for both Primary and Secondary schools. The Recommendations for Output 1 are repeated here in the interests of clarity. / 1) In relation to Performance Indicator 3, EiA should explore reasons for underperformance in the improvements in teachers’ English language skills, using external expertise if possible. This could include a thorough scrutiny of the research evidence which examines the relationship between students’ English language learning outcomes and the English language skills levels of their teachers. / 2) The increased amount of student talk in a lesson is a significant achievement. However, sustainability of learning gains will depend on the type of talk. Research in the E4D field suggests that often student input in English is confined to ‘safe talk’ – repetition of already known words and phrases, choral repetition, singing songs in English, etc. Small scale, well-designed independent research using discourse analysis techniques could provide valuable information about the nature of student talk in EiA classrooms, and could provide useful knowledge about both the likely impact and sustainability of EiA’s teacher training approaches. / 3) The use of m-learning and peer support to bring about improved teaching practices and ultimately improved learning outcomes for students is highly innovative. DFID should consider commissioning independent research into the role of m-learning and peer support within EiA; if strong evidence can be found for the success of this approach, it will be of great interest to the E4D field. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 4: A rigorous monitoring and evaluation framework and research framework built upon baseline studies to monitor and assess project impact and generate knowledge products and support capacity building.
Output 4 score and performance description / Output Score: A+ (Moderately exceeded expectations) / Progress against expected results: / Performance indicators Milestones for 2014 Progress / 4a) Number of knowledge products developed 15 research reports / 9 research briefs Met target / 15 research reports / 9 research briefs / 4b) Amount of research disseminated via conferences/ papers / presentations peer reviewed journals/ chapters in academic books/ distribution of reports to key stakeholders within B’desh and to research data bases (R4D and Open Resource Online within OU) 29 conferences / 4 papers / 2 chapters Moderately exceeded target / 37 conferences / 7 papers / 7 chapters / Summary progress and performance / Output 4 has moderately exceeded expectations. / Key achievements for research work under media and adult learning during 2013 – 2014 have been: / A major midline survey with a nationally representative sample of 6,000 TV viewing adults / Audience pre-testing and feedback for media outputs / Research into the economic impact of English language skills in Bangladesh / High quality research and testing undertaken to capture progress in adult learners’ English language skills / For the Schools components, key achievements have been: / Continued implementation of quality assurance processes with 12,500 teachers – monitoring of workshops, cluster meetings, teacher facilitator meetings, and classroom observations. / Capacity of Teacher Facilitator and Upazila Education Officers developed and used in an increasingly decentralised Quality Assurance model / Further development of the research collaboration with IER at Dhaka University / Research studies undertaken on teacher and student attitudes and perceptions, English language competence, classroom practice, and new elements of the Phase III teacher support model. / Joint research outputs / EiA’s theory of change rests on the assumption that the improvement of English language skills in Bangladesh will lead to economic development, for individuals and society. EiA studies are now available in support of this. An employer satisfaction survey - a study undertaken by Euromonitor examines the relationship between English language competence and economic status, using data from two national surveys and a second one, economic analysis conducted by BBC Janala based secondary data available from project. During 2013 – 2014 a synthesis report has been produced which combines evidence from previous work. This synthesis paper is an important contribution to an emerging field. / Employer satisfactions survey: Key findings of the research were - / Employers find that: / 51% of applicants do not have the English language skills which employers need / 45% of current employees do not have the English language skills which employers need / 64% of employers would prefer employees with English skills over those without English skills / 77% of employers believe that the need for English language skills is increasing. / The review team note that these results may be partly influenced by perceptions of English skills in Bangladesh – i.e., English language competence remains associated with high status and high overall levels of education, and is viewed as a core skill attainable in the main by the more affluent sections of society. There has been no analysis of the specific English language skills which employers need and so data is based on employers’ perceptions. Research into the specific English language skills which are needed for particular work roles in different employment sectors would yield useful information and could inform the ongoing work on the development of English language skills provision within the vocational education sector. / The Euromonitor survey. This study sought to identify the economic benefit of English skills for Bangladeshi people seeking formal employment. Data were collected from the largest recruitment agencies, and forty percent of the total formal employment market and (online and print) job advertisements was analysed to uncover stated requirements for English language skills. / Key findings were: / 20% of print and 40% of online jobs required English (see review team comments relating to the Employer Satisfaction Survey above). / Wages were 25% to 30% greater in jobs where English skills are needed. / There was a 30% to 50% higher chance of being employed in the formal sector with good English skills. / However, there is an absence of data relating to the large informal sector in Bangladesh, where many of the poorest are employed or self-employed. / BBC Media Action Research study / This study focused on the relationship between tested and perceived English proficiency and economic status. It drew on two existing datasets: the BBC Janala Midline Survey 2011 and the BBC Janala Pre-/Post-Competency Study 2012. The relationship of level of English skills (tested and self-reported) with monthly disposable household income was examined using linear regression analysis. / Key findings were: / All individuals: 1 point increase in English language competence (ELC) associated with 250-260 Taka increase in monthly household income/expenditure / Employed: 1 point increase in English competence associated with 330-390 Taka increase in monthly income/expenditure / Skilled employees: 1 point increase in ELC associated with 464–600 Taka increase in monthly income/expenditure. / For employees with intermediate English the BBC data shows an income premium of 22% and Euromonitor shows an increase of 27%. / It would be interesting to review economic gains for Bangladeshis who have English attainment levels below ‘intermediate’ – minimally Trinity Grade 4. As stated in EiA’s synthesis report, this work shows, overall, a significant correlation between the development of English skills and economic gain for Bangladesh – thus broadly confirming EIA’s theory of change. / Recommendations / 1) Strength of evidence is needed for effective advocacy. For Components 1 and 3, a great deal of the research evidence is internally generated via EiA’s quality assurance systems. Whilst commissioning of external, independent research evidence has been a recommendation of Annual Reviews in 2011 and 2012, this has not been fully taken forward. OU is now using DFID’s ‘How to’ Note to evaluate strength of internal evidence generated by O1 and O3. At present this work is formative. It would have greater status if this were the result of peer review. OU should therefore seek independent peer review of their main research products so that strength of evidence can inform and shape advocacy in Phase IV of EiA. / 2) For Phase IV, a revised and succinct research and evidence plan should be developed, in the light of timescales/ resources. / Impact Weighting 15% / Revised since last Annual Review? /N / Risk/Medium / Revised since last Annual Review? /N

Output 5: Influence institutionalisation and sustainability of EIA approach through critical engagement with crucial stakeholders and advise on revised English Language Education Policy for GoB.
Output 5 score and performance description / Output Score: A+ (Moderately exceeded expectations) / Progress against expected results: / Performance indicators Milestones for 2014 Progress / Number and extent of Strategic partnerships with key organisations in education and English language media sectors; no. of sector professionals (broadcast and ELT) taking part in ELT media capacity initiatives. Education partnerships: / 3 or more / ELT media partnerships: / 100 Exceeded target / Education partnerships: / 5 achieved / ELT media partnerships: / 161 / Number of policy seminars with / Key decision makers, on English language education policy reform to support communicative teaching and learning 3 policy seminars Target not met / 2 held, 1 planned / Summary progress and performance / During 2013 – 2014 the quantitative targets set for strategic partnerships have been moderately exceeded. The target set for policy seminars has not been met. Political unrest and GoB staffing changes have created challenges for EiA during the last year to meet the target for policy seminar as it needed wider participation of various stakeholders. Many of these challenges have been outside the direct control of the project. / During 2013 – 2014, key achievements for Output 5 include : / A joint Directorate of Primary Education (DPE)/EiA proposal for the integration of EiA elements into subject based training / EiA participation in evaluation of revised National Curriculum and Textbook Board (NCTB) primary textbooks / EiA participation in initial training of Education Managers through collaboration with DPE and Directorate of Secondary and Higher Education (DSHE) Monitoring and Evaluation wings / A redesign of the BBC Janala website to enable wider and improved access to all content created by the project, including downloadable copies of English Club materials and on-line versions of TV programmes / Piloting EiA approaches in Kishoreganj Upazila autonomously, using School Level Improvement (SLIP) funds / Skills development – EiA has facilitated professional development for the instructors training teachers in the technical schools and colleges as part of the Skills Development Project (SDP) funded by ADB. / The schools components of EiA have worked hard to build and sustain partnerships with strategic stakeholders. For teacher development, these include: / A joint proposal for primary Teacher Professional Development programme with DPE / An agreement for collaboration on secondary Teacher Professional Development with DSHE / EiA taking the academic lead for English on new the Diploma in Education (pre-service teacher training), with National Academy for Primary Education (NAPE) / For materials development, these include an agreement with the National Curriculum and Textbook Board (NCTB) for contribution to primary English: / textbooks / teacher editions / student workbooks / For Monitoring & Evaluation: / agreement with DPE Monitoring & Evaluation Division / MoU with DSHE Monitoring & Evaluation Division / Joint M.Phil programme with Institute of Educational Research, DU / Additional activities include working with / Teaching Quality Improvement Project II (TQI II), funded by ADB / Skills Development Project (SDP), funded by ADB / EIA is also collaborating with the World Bank in its Secondary Education Quality and Access Enhancement Project (SEQAEP) / Policy seminars on monitoring and evaluation and on assessment have been held with stakeholders and GoB; the seminar on assessment is particularly valued since changes in assessment make EiA approaches much more likely to be sustained. For example, as a result of the seminar, clear interest in classroom based testing of speaking and listening has been expressed by the senior management of the Directorate of Primary Education. As a result teachers will continue to give class time to the teaching of this valuable skill – in the long term, what is not tested is not taught. Two of three seminars have been delivered and one further seminar is planned (on Women, English, and Technology) for June 2014. / EiA media and adult learning has successfully engaged a very wide range of partners, including all six national mobile operators, state and private TV companies, and a national newspaper. / A Media Alliance has been built, and the qualitative evidence gathered during the review process indicates that partnership work and capacity building by EiA media and adult learning has strengthened the English language industry. Partnerships have grown – especially with local NGOs around clubs; and direct evidence from the field visits indicate that there is a strong will for this work to continue. Direct capacity building with Bangladeshis has been significant with 136 participants and 25 experts engaged, against a target of 100. / The review team is aware, however, that in spite of excellent efforts, EiA’s approaches are not yet regarded as ‘business as usual’ by DPE or MoPME. EiA needs to continue to work hard to promote areas of best practice within the project. The final phase of the project deals with Institutionalisation and Sustainability. This is reflected in the number of recommendations relating to Output 5. / Recommendations for Output 5 / 1) The review team recommend that four key areas of EiA should be prioritised for sustainability: / The teacher training model –this is transferable across the curriculum. Evidence shows that this is in line with best practice, and that it is a ‘recipe’, not a menu – the various strands of the model work synergistically to ensure that lessons learned in training are transferred to classroom practice. / English language skills development for economic growth and individual prosperity / Continued uptake of BBC Janala products and BBC Janala’s capacity building work with the media sector, with a focus on capacity building with BTV. / The dissemination of knowledge products developed via EiA. / Future year indicators and milestones against output 5 needs to be reviewed to have more specific focus on sustainability and institutionalisation. / As part of the logframe revision the impact weighting for output 5 should be reviewed given the importance of institutionalisation in the final phase. / To bring about sustainability, the review recommends: / 2) The development of a clear and strong advocacy plan within next six months, which presents evidence from within EiA and from the literature base; this should be accompanied by transparent costs. The advocacy plan should include a stakeholder analysis, including identifying key allies and possible obstacles and a strategy around how to influence them. This advocacy plan should be developed in close collaboration with DFID, so that EiA can influence GoB as effectively as possible until the end of the project. / 3) For Output 1 (Primary Schools) PEDP III is the main route to sustainability. DFID to facilitate and advocate inclusion of TA from within EiA in the sector programme wherever possible. This should focus on teacher development models which have been proven to be best practice by evidence from systematic review and from within EiA. / 4) NCTB expressed willingness to include TA from EiA in the ongoing work of textbook / teachers’ guide refinement by June – EiA should follow this up as soon as possible since activities are ongoing. EiA’s contribution to the Teacher’s Guides (cross curricular) would be highly valued. / 5) School Level Improvement Plan (SLIP) funds, under PEDP3 have been used to implement EiA approaches; EiA should consider how ‘bottom-up’ methods might be used to increase the likelihood of sustainability. For example, School Management Committees have influence at local level and might help disseminate the usefulness of EiA’s work. / 6) For Secondary Schools, a MoU has been signed with the Teaching Quality Improvement project (phase 2). Bearing in mind the ‘recipe’ concept, activities should be revisited in the light of time/ resource constraints. Cost options might be based on phasing/numbers of teachers trained, since this is a key cost driver. / 7) For Secondary Schools – the Secondary Schools Improvement Project led by the Ministry of Education and funded by ADB is a key initiative and EiA should seek to influence as much as possible within time/ resource constraints. / 8) The GoB led, ADB funded Skills Development Project is keen to implement EiA approaches once there is clear evidence of the success of the intervention – there is thus a need to gather high quality evidence to embed the work of the project in this sector. / 9) The schools components, at this stage of the project, need to develop phase-out plans as part of the institutionalisation strategy within next six months. / 10) All activities undertaken to bring about sustainability should be accompanied by clear research evidence and clearly set out costs. During 2013 – 2014 the quantitative targets set for Output 5 have been moderately exceeded / Impact Weighting 15% / Revised since last Annual Review? /N / Risk/High / Revised since last Annual Review? /N

Section B: Results and Value for Money.
1. Progress and results
1. 1 Has the Logframe been updated since last review? / Yes. Note- the programme had prepared a much tighter Logframe for the planning of additional funding – this should now be used to augment the existing Logframe. / 1.2 Overall Output Score and Description: A+ (Moderately exceeded expectations) / The review team finds a high performing and well-managed project. Whilst EiA has focused on building English language skills to support economic development, the review note that the teacher training model used by the schools component exemplifies good practice, as evidenced, for example, by DFID and AusAID’s recent systematic review[3] and is a model which will enable lessons learned in training to be transferred to the classroom. In the final phase of the project, this training model can be incorporated within ongoing education reform initiatives. / The review notes the highly innovative use of m-learning. The use of mobile phones, either for teacher training or for English language skills development, has not been fully disaggregated from the overall training approach. As noted elsewhere in this review, additional research is needed and the results will be of great interest to E4D work. / The theory of change sets out a good rationale for the impact of English language skills on economic development. EiA has made a significant contribution to this emerging field of research. / 1.3 Direct feedback from beneficiaries / Classroom observation / The review team visited four classrooms in Kishoregangj. This was a small convenience sample. Overall we found good evidence of the uptake of EiA approaches, though we believe that unless EiA is embedded within mainstream practice, improvement in classroom practice may be fragile. The review team examined a selection of student notebooks and found mixed evidence of systematic learning and teaching approaches – some notebooks contained little written work in English, errors were not always corrected or not accurately corrected, and there is some evidence of rote learning as teachers prepare students for examinations – for example, repeated copying of a business letter. EiA has wisely chosen to work with GoB prescribed textbooks – English for Today – but this is outdated and constrains best practice in learning and teaching. (Textbook revision is underway, however). Teachers would benefit from further training, with a focus on lesson planning and the use of more varied classroom interaction patterns – interaction remains predominantly from the teacher to the whole class. We are pleased to note that English was used as the language of instruction throughout the observed lessons. / Students were engaged and participated well in all four observed lessons, and were willing to engage in conversational discussion with the review team, albeit with some shyness. In one class in particular several students had strong English skills – perhaps stronger than the skills demonstrated by the class teacher. This was of course a very ‘light touch’ observation, but is in keeping with the data around improvement levels in English – learning gains are considerably greater for students than for teachers, in particular within Secondary schools. / Focus group discussions / The teachers themselves are enthusiastic about EiA and the ‘rapid change’ which the project has brought to their work. There is a willingness to share the EiA experience with teachers of other subjects, and a keen interest in sustaining and extending the work of English Clubs. / The first focus group commented on the usefulness of the SLIP model in supporting the work of EiA. This is viewed as a ‘bottom up’ initiative and discussants felt that it could be used more widely across Bangladesh to support EiA’s work. Other suggestions for embedding the work of EiA were via the sub-cluster training currently available to teachers. Discussants also suggested that sub-cluster meetings could be a way of encouraging other schools to use SLIP funds to take EiA forward at school level. For both groups, specific benefits of participation in EiA and in English Clubs were: / Availability of high quality materials / Availability of technology / Peer support / Development of their own English language skills (and confidence in using these skills) / All participants agreed, however, that more face to face training was highly desirable (discussants had only received one day of face to face training).
[3] Orr, D. et al (2013). What are the impacts and cost-effectiveness of strategies to improve performance of untrained and under-trained teachers in the classroom in developing countries? Systematic Review. London, EPPI-Centre Social Science Research Centre, Institute of Education, University of London.

1.4 Summary of overall progress / The overall programme outputs moderately exceeded expectation. The media/ adult learning component is innovative and of a very high standard indeed. BBC Janala should be commended for finding a way forward which will hopefully secure sustainability across all ‘four’ media platforms. The review team finds the work of the schools component to be broadly successful at this stage, though flags caution in disseminating the innovative use of technology until the research evidence is strengthened. The external reviewer also urged to peer review the evidence generated by the schools component, in the light of heavy reliance on internal M&E processes as a basis for claims of effectiveness. / The review team noted the achievements of the schools component during the reporting period. Innovations which have been introduced to support scale-up include: / New Teacher Development and Classroom Materials / A greatly increased use of video, to show teachers’ examples of communicative language practices, filmed in authentic classroom contexts, with teachers and students from the pilot phase. / New Technologies / Use of low-cost mobile ‘feature’ phones (Nokia C1-01), used to play audio-visual materials stored on a memory card, played over low-cost speakers. / More ‘School Based’ teacher development / A stronger focus on school-level improvement, including: / An explicit role for Head Teachers, with professional development materials to help them in pro-actively supporting teacher development within their schools. / Inclusion of primary Head Teachers, as participating ’Teachers of English’ within the teacher development programme / Promotion of peer-observation of classroom practice within schools. / Strengthened Teacher Facilitator role / In Phase III, Teacher Facilitators (TFs) run cluster meetings almost entirely independently, using revised TF support materials and guidance. They depend upon the revised teacher materials (in particular, the video materials), to provide ELT expertise and demonstrate communicative approaches in practice. This is innovative and has been a major factor in successful scale up. / More explicit focus on Social Inclusion / In both teacher development materials, and guidance on cluster meetings, for Teacher Facilitators. / Introduction of GoB Upazila Education Managers in Quality Assurance / GoB Education managers are being deployed to provide Quality Assurance through classroom observations of participating teachers. This decentralization, along with the increased importance given to teacher facilitators, has enabled work to continue despite political unrest during 2013 – 2014. / Evidence from previous English language programmes in Bangladeshi schools show that gains are fragile unless fully embedded in mainstream practice. Whilst the review was impressed by the range of work undertaken to support institutionalisation, it notes that sustainability has been adversely affected by political change and instability that are beyond EiA’s control.
1.5 Key challenges / The key challenge of the reporting period has undoubtedly been scale-up and maintaining quality. / 12,551 teachers are now participating in EIA school interventions (up from 751 in 2011) and with little evidence of decrease in quality. / Over 44 million people are aware of at least one EIA media product, and 28 million people have watched or used one media product (up from 24 million in 2011). / 10.25 million people are using EIA media products more than five times i.e highly exposed (up from 7.5 million in 2011; and 1.75 million above Logframe targets). / As scale-up continues and EiA rely more and more on the training teachers via mobile phone videos and less on teacher trainers, ensuring that the less intensive method of teacher training does not have a detrimental impact on English language skill will be a key challenge. / Political instability throughout the year has been a challenge – this has needed flexible planning and EiA should be commended on overcoming this problem, through creative and flexible solutions, and very high levels of effort from all service providers. / In relation to this, there has also been a turnover of GoB officials. This has an impact on Output 5, Institutionalisation and sustainability (I&S) gains remain fragile. Phase IV will be demanding, particularly in the light of time and resource constraints. A high quality advocacy plan, jointly developed by EiA and DFID, is central to overcoming the challenges of I & S. / EiA have done some work on how English Language can lead to better economic outcomes. However, in order to convincingly demonstrate impact at the outcome level more work must be done with larger samples and more done on controlling for other English Language instruction.
1.6 Annual Outcome Assessment / Outcome indicator: To increase significantly the number of people able to communicate in English to levels that enables them to participate fully in economic and social activities and opportunities. / Outcome Indicator 1: Increases in proficiency in communicative English among the population of Bangladesh. 2014 Milestone: Numbers of teachers and students classified at higher (improved) levels of proficiency compared to baseline. / Progress: Partially achieved. Achievement of students exceeded the target by 210%. However, target for teachers not achieved. Only 49% of the targeted teachers reached the expected level of competency. The scale up phase (period under review) has less contact hours with teachers and also reached teachers in more hard to reach and marginalised areas. Assumption is that a combination of both may have contributed to not meeting expected level competencies. It should be noted that despite the under-achievement in teachers’ competence, results for students’ competence – which is the primary objective of the schools component of the project – are still strong. / Outcome Indicator 2: Employers’ satisfaction (with employees’/applicants’ communicative English). 2014 Milestone: (Decreasing) 42% of applicants without EL skills and (increasing) 75% of employees with necessary EL skills. / Progress: Not achieved. According to the Euromonitor and employer study 51% applicants did not have necessary English language skills and 55% employees had necessary English language skills. / Outcome Indicator 3: Motivation for learning and using English among school population of Bangladesh. 2014 Milestone: 60% of students and 75% teachers report that English is very important and 55% students and 40% teachers report that English is difficult to learn. / Progress: Exceeded target. More (95%) students and (94%) teachers have reported that English is important to learn and less (33%) students and (7%) teachers reported that English is difficult to learn. / Outcome Indicator 4: Use of English language news and media: online, broadcast or print-based. 2014 Milestone: 30% improvement from baseline. / Progress: The 2013 midline shows that 9.8% of people in Bangladesh use English language news media (online, broadcast or print). This is equivalent to 7.62 million. The baseline figure was 5%. So there has been an increase. However, the target groups surveyed were slightly different over the three studies (in keeping with the different target audiences) and it cannot be said for certain that the methodology used to get to the 9.8% figure is exactly the same as in baseline. There are also the census-based population changes to take into account. The project prefers to report that 9.8% of people in Bangladesh use English language news and media figure, rather than as a percentage increase on the baseline figure. / Are the outputs going to achieve purpose? / Overall, the Logframe measures success at this key level. The theory of change, developed in response to a 2012 recommendation, is very useful. However, the TOC would be more useful if assumptions are as fully unpacked as possible. Quantitative research and longer term tracking is needed for this to happen. / It remains important that EIA addresses to what extent, in the context of Bangladesh, enhanced English language skills can make a significant contribution to economic growth, and whether, and to what extent, enhanced English skills enable fuller participation in economic and social activities and opportunities. There is thus a need for a fuller examination of links between outputs and purpose – the case for an overall causal link between English language skills and economic development has not yet been made. In Phase III, evidence has been provided of a significant correlation between English skills and economic gain, but this focused on the formal sector and on those with intermediate English language skills. / This is a growing research field, and research evidence is of necessity nuanced and confined to a specific geographical context. EIA has the potential to contribute to this research field; to take this work forward, the project needs to strengthen and deepen links with technical and vocational initiatives, with industry, and with the informal sector. / In Phase IV, monitoring, evaluation, and research which could provide evidence of the impact of EIA on economic and social participation, and employability, could be strengthened. This would provide evidence of how, and in what ways, the project outputs contribute towards the overall purpose. DFID B will need to internally discuss and decide about the scope of this.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / Key costs for the project include: equipment, education supplies including teacher training materials, production and printing of learning materials, salaries for the management staff and travel and other transportation. / Value for money is achieved in the procurement process through vigilant monitoring and controls. Most procurement, particularly of large assets is carried out by Crown Agents. A competitive bidding process ensures the best value is acquired for the products needed. / The project value for money framework outlines a process of continual review, and project staff were able to provide numerous examples of where this had led to cost reductions. For example, teachers now use their own mobile phones rather than EiA supplying them, and EiA no longer subsidises BBC Janala/Prothom Alo lesson books, which are now sold at cost price. / Management costs are included in the BMB fee rates which were negotiated at the outset of the project. This has the potential to offer good value for money as the rates have not increased over time. However, the rates do not seem to be attached to a specific person meaning there is scope for a less experienced agent to be put in place but still charged at the same rate. It would be useful to get clarity over management rates, regardless of how they are charged – without the information the DFID team cannot challenge a decision. / Regular financial audits are not conducted at the field level, and would be beneficial. In 2014, DFID undertook a comprehensive financial and procurement audit of the project which included complete field level assessment. In the remaining 3 years of the project, annual financial audits will also include a sample assessment at field level. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / a) For teachers, there is no strong evidence of improvement of English language skills. There may be several reasons for this, including: / Trinity examinations assess general English language competence. EiA trains teachers in English for the Classroom – skills will not transfer into general English competence. However, the review notes that this is something that cannot be addressed easily. The project was designed to assess English language competence of teachers from the beginning. Going forward, it can be explored if future assessment of teachers can include some aspects of assessing English for classroom – but it should be noted that it will then differ from the baseline. / At secondary level, the notional number of hours needed to improve by one Trinity (or CEFR) level increases substantially and this will impact negatively on attainment levels / At scale-up, the schools targeted were from areas of greater deprivation – thus the baseline information will be unrepresentative of these cohorts of teachers. / EiA should consider the implications of this for the project as a whole. However, it is noted that this has had no apparent impact on the improvement of pupils’ English language skills, which exceed targets. While this needs to be further analysed, the project noted that changes in teachers’ professional development materials, which was improved to focus more on classroom teaching learning process based on lessons learned from pilot phase, may have played a crucial role. / b) The synthesis study, described in Output 4 above, finds a significant relationship between the development of English language skills and economic progress for Bangladeshis. This broadly supports EiA’s theory of change. These findings are of necessity specific to Bangladesh but nevertheless deserve to be fully disseminated within the E4D field. / 3.2 Where an evaluation is planned what progress has been made? / No overall evaluation is planned, but the review team recommend independent peer review of research outputs, and independent evaluation of the use of m-learning to bring about improved classroom practice.
4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The main risk for EiA is sustainability for the schools component. For the project to be sustainable, key elements need to become ‘business as usual’ within Government structures. The main challenges to achieving institutionalisation, and hence sustainability within the education system, are, at this stage of the project: / Time / Resources – both human resources and finance / Partnership working with GoB and key stakeholders / GoB capacity, in the light of many recent changes in staffing and lack of flexibility. / To address the above challenges, developing the recommended advocacy and institutionalisation strategy should help to rationalise and identify best ways to effectively and efficiently utilise the resources (time, money and human resources) to take a more focussed approach to work with the government. / However, aspects of challenges will continue to be there despite the concentrated efforts, simply because both primary and secondary education sector operates a large multi-layer, multi-stakeholder system with more than 27 million students. Changing any system/processes within that would require long term on-going intensive engagement, for which the project has limited ability given the resource constraints.
4.3 Risk of funds not being used as intended / Risk of funds not being used as intended is low. Overall EIA is considered as a well-managed project with costs being carefully controlled. There has been a recent financial audit but this is outside the scope of the Annual Review and is being managed separately. / 4.4 Climate and Environment Risk / The project promotes key messages on climate change and environmental issues and there may be net benefits from a raised awareness of environmental issues. Environmentally friendly approaches to materials production are used and advocated wherever possible (stakeholders, private sector and GoB)

5. Value for Money
5.1 Performance on VfM measures / Overall EiA has a strong VfM strategy that shows there is a good level of understanding of VfM issues. VfM monitoring consists of use of a range of indicators at multiple levels in the project, and input unit costs show a strong downward trend. The programme has met or exceeded all milestone targets set in the log frame. / 5.2 Commercial Improvement and Value for Money / Cost-effectiveness measures across the project are available for the first time this year, in response to previous recommendations, and will be tracked going forward. / Primary students: £9.80 / Secondary students: £2.77 / Adult learners: £3.52 / EiA recognize the desirability of benchmarking these costs if and when comparable data becomes available internationally / Phase II Phase III Phase IV / Key Economy Indicators / Unit cost of teacher training primary in service £633 £302 £90 (projected GoB contribution of £67) / Unit cost of teacher training secondary in service £610 £282 £77 (projected GoB contribution of £67) / Unit cost of adult learning activities Year 4 Year 5 Year 6 / Television (cost per minute) £4,195 £3,949 £2,446 / English club (cost per page) £6,966 £2,280 N/A / Mobile (cost per minute) £926 £644 £515 / Web (cost per minute) £4,023 £2,040 £602 / Book (cost per page) £605 £104 £111 / Industry training (participant) £2,048 £1,508 £238 / Recommendations for VfM / 1) Given the changes in the programme make-up VfM indicators should move from unit cost measures to key cost drivers by output. / 2) Unit costs figures are being pulled by scale-up; while scale up is vital and impressive, it would be more useful to track the key cost drivers for each output (work on this is already happening). / 3) Phase IV metrics include a significant contribution from GoB to teacher training. Some modelling should be done to calculate the impact of this not happening. / 4) Effectiveness indicators for Phase IV are predicted to fall as the intervention is incorporated by GoB and so becomes less intensive. / 5) With the change in modality from direct intervention to GoB implementation, the proportion of primary and secondary students increasing a competency grade is forecast to fall from Phase III to Phase IV. These assumptions should be viewed in the light of the Phase III achievements. The project needs to make conscious efforts to mitigate this by working closely with the training and monitoring division of both primary and secondary sector. / 6) These should be closely monitored throughout Phase IV, and a clear plan should be drawn up for how to mitigate larger than expected decreases in effectiveness. / Key Challenges for VfM / The main issue for VfM is the current challenges of Output 5, in spite of strong progress in Phase III. Challenges for O5: / Time / Finances / Reduced human resources / Access to the right people at the right time / Capacity of Government, given many recent changes in staffing and lack of flexibility in the system. / Partnership working – with GoB and key stakeholders / Addressing VfM challenges / Develop a focused advocacy strategy and plan within the next six months– EiA and DFID in partnership: and a clear communication strategy to support this / Support communication with simply presented costs and options around phasing/ teachers targeted / Revisit MoUs and trim/ prioritise (within the limits of a package of good practice) / GoB very interested but want research evidence and costs – need to communicate ‘what works’ in E4D / ‘Fit in’ with GoB initiatives and seek refinement/ adaptation / ADB and JICA value EiA’s training model highly and want to advocate and support where needed/ possible. In addition, as part of the quality working group (one of the joint working group of PEDP III development partners (DP) and DPE) discussion dialogues are held, when appropriate, with counterpart DPs regarding embedding EIA approaches and EIA also joins selected issue specific discussions. / 5.3 Role of project partners / The project is managed by BMB and this remains an area of great strength. There are strong quality assurance procedures in place, excellent human resources, transparent processes, and detailed monitoring. BMB is also part of the implementing team, along with the Open University and (until June 2014) BBC Media action. The implementing partners work well together. Cross-project strategic collaboration and peer support/ feedback have enhanced the quality of the schools component and the media/ adult learning component. Examples of synergy include the BBC Janala English clubs operating in schools, and joint capacity building in the creative workshops organised by BBC Janala. / Two NGOs are also involved with EiA – Friends of Villages in Bangladesh (FIVBD) and UCEP (Underprivileged Children’s Education Project). Both NGOs state that they have good relationships with EiA; UCEP is keen to deepen engagement with the project to include teacher training. Key activities have been: / UCEP – Secondary Curriculum Integration / EIA provided technical support to UCEP to revise and pilot their Teachers’ Guides (TGs) for class six, seven and eight during 2012. Alongside a capacity building opportunity, this exercise created a scope to embed EIA methods in UCEP’s secondary materials. As the national curriculum has been revised recently, UCEP will need to revisit these TGs again and building on the work done so far, if required, EIA would be happy to provide technical assistance. The contents of these teachers’ guides complement EIA’s teacher professional development materials used in the cluster meetings. / FIVDB - English Reading Scheme (ERS) for Primary / In partnership with FIVDB, EIA took up a small-scale pilot initiative aiming to develop an English Reading Scheme (ERS) through a series of capacity development workshops. It was decided that the ERS would consist of a set of graded reading materials and associated activities, closely linked with the English for Today textbook and complement other EIA Primary Teaching and Learning Programme (PTLP) materials. This partnership involved in-kind contributions (workshop venue, food cost etc.) from FIVDB and EIA provided technical expertise, print cost as well as partial cost for the workshops. / Eighteen graded readers/story books for class one, two and three have been developed and piloted in 18 Govt., FIVDB and UCEP schools in Sylhet last year. Additional activities with instructions for ‘shared reading approach’ were also developed and used by the pilot teachers. The aim of the pilot was to find out the effectiveness and appropriateness of the ERS materials with regard to the targeted learning outcomes, as well as gather information on the pilot experience. Based on the findings, further revisions will be conducted this year. In June’13, FIVDB organized an internal workshop in Sylhet to orient their staff (36) about this new component (English Reading Scheme) in their programme. It was anticipated that the pilot will be extended for another year with increased number of schools, after which FIVDB will absorb the ERS materials into their own curriculum and a pre-planned study involving reading tests will be conducted with the new cohort of children. However, because FIVDB lost their funding for the programme, EIA is currently seeking other appropriate organisations who would be willing to use the readers for their learners. Initial discussions have taken place with Bangladesh ECD Network (BEN) and Asia Foundation. Most recently, Save the Children expressed keen interest to use the ERS materials for their non-formal education programme in 6,000 schools as well as the new pilot initiative – Reading Enhancement for Advancing Development Activity (READ) project with the Government schools. / 5.4 Does the project still represent Value for Money: Y / This is enhanced by the quality of products, the extent of reach, and the innovative delivery methodology; although, as mentioned elsewhere in this review VfM is threatened through any potential failure of sustainability. / 5.5 If not, what action will you take? / Every effort should be made to address the challenges posed by key elements of EiA becoming embedded in mainstream practice – this is the key to success in Phase IV and sustainability beyond the life of the project.

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
The review found EIA as a high-performing, well-managed project, with a need in some areas for a strengthened evidence base so that findings can be disseminated to the E4D field with confidence. / Phase IV will be challenging but through clear and targeted advocacy, EiA’s good practice can be incorporated within GoB initiatives. It is noted that advocacy for EiA’s teacher training model should not be confined to English language skills, but should be cross-curricular. / The review commends all involved for their achievements, especially over the last year, when circumstances have been very challenging.

8. Review Process
The external review team consisted of one international, one national consultant, and a DFID economic advisor who is a VfM expert. The international and national consultant worked remotely for six days, and in country with EiA and DFID in Bangladesh for eleven days between 23rd April and 4th of May. DFID economic advisor worked in-country for six days. The international consultant, the local consultant made a field visit to Kishoregangj and Mymensing. Team leader of human development team partially joined the field visit. The team observed four classes and conducted two focus group discussions. Extensive project documentation was made available to the team, and presentations on annual progress (looking back) and future plans (looking forward) were made by the implementing partners. Meetings were held with EiA project partners i.e. BMB management, Open University (OU), and BBC Media Action and DFID cross cutting advisers e.g. commercial adviser, results adviser and education adviser for sector programme. The team also met with representatives from donors e.g. JICA and ADB, and with EiA’s two local NGO partners, FIVDB and UCEP. From within the Government of Bangladesh, the team met representatives from DPE, SDP, NAPE, NCTB, DSHE, and TQI. DFID Education adviser also joined some of the above meetings with stakeholders. / Team members of HD team, DFID B supported the work of the review, and provided both input and feedback on the drafting of the Annual Review. The review report and scoring was finalised by DFID Education adviser and Team leader of Human Development team.