## Logframe 2018
Project 204114 - Tax Administration Diagnostic Assessment Tool (TADAT)
IMPACT |  |  |  | Baseline | 2015 | 2016 | 2017 | 2018 | Source
TADAT contributes to strengthened tax administration systems and domestic revenue mobilisation efforts globally. | Impact Indicator | Extent to which TADAT-influenced reform programmes lead to improved tax administration performance in developing countries. | Planned | No TADAT assessments | N/A | N/A | N/A | Repeat LIC/LMIC assessments showing improved scores | Mid-Term Review TADAT Secretariat reports Stakeholder feedback
Achieved
OUTCOME |  |  |  | Baseline | 2015 | 2016 | 2017 | 2018 | Source
TADAT assessments improve tax administration knowledge, and inform tax reform discussion and decision-making. | Outcome Indicator | Extent to which TADAT assessments facilitate dialogue about tax administration reform and directly influence donor programmes and tax administration reform plans. | Planned | No dialogues or reform plans based on TADAT assessments |  | TADAT assessments facilitate dialogue and influence reforms plans in all cases |  | TADAT assessments facilitate dialogue and influence reforms plans in all cases | Mid-Term Review TADAT Secretariat reports Stakeholder feedback
Achieved
OUTPUT 1 |  |  |  | Baseline | 2015 | 2016 | 2017 | 2018 | Source | Weighting
Preferred Assessment Tool: TADAT is the preferred tax administration diagnostic and performance assessment tool globally. | Output Indicator 1.1 | Cumulative total number of TADAT assessments that are carried out globally (national and subnational). | Planned | No assessments | 15 | 30 | 50 | 70 | Mid-Term Review TADAT Secretariat reports | 60%
|  |  | Achieved | 4 | 17 | 37 | 51 | 71
| Output Indicator 1.2 | Cumulative total number of TADAT assessments undertaken in low-income (LICs) and lower-middle income countries (LMICs). | Planned | No assessments | 7 | 15 | 25 | 35 | Mid-Term Review TADAT Secretariat reports
|  |  | Achieved | 1 | 9 | 22 | 30 | 41
| Output Indicator 1.3 | Number of institutional groups, and technical providers using TADAT. | Planned | None | Added post-2017 AR (recommendation) |  |  | All | Mid-Term Review TADAT Secretariat reports
|  |  | Achieved |  | N/A | N/A | N/A | All
OUTPUT 2 |  |  |  | Baseline | 2015 | 2016 | 2017 | 2018 | Source | Weighting
Systemic Quality Assurance: TADAT assessments are of a high quality and effective in identifying the relative strengths and weaknesses of tax administrations. | Output Indicator 2.1 | TADAT is regularly maintained to include good practices that are tested, proven and applied by the majority of leading tax administrations. | Planned | N/A | Technical Advisory Group is established to maintain technical quality | N/A | Independent mid-term evaluation is completed | Framework and Field Guide adapted to reflect evaluation recommend-ations | Mid-Term Review TADAT Secretariat reports Stakeholder feedback | 20%
|  |  | Achieved |  | Delivered | N/A | Delivered | Delivered
| Output Indicator 2.2 | Proportion of TADAT PARs selected for quality assurance that comply with the standards set out in the Field Guide. | Planned | N/A | All | All | All | All | Mid-Term Review TADAT Secretariat reports TAG Performance Assessment Report quality assurance reviews
|  |  | Achieved | 5 | All | All | All | All
OUTPUT 3 |  |  |  | Baseline | 2015 | 2016 | 2017 | 2018 | Source | Weighting
Effective Dissemination: TADAT facilitates enhanced understanding by key stakeholders of international good practices in tax administration through training and impactful outreach activities | Output Indicator 3.1 | Cumulative total of trained TADAT assessors and team leaders | Planned | Zero | N/A | 250 | 300 | 350 | Mid-Term Review TADAT Secretariat reports Stakeholder feedback | 20%
|  |  | Achieved |  | 69 | 302 | 390 | 439
| Output Indicator 3.2 | Extent to which TADAT outreach is significant and impactful at international, regional and country levels | Planned | No TADAT outreach | Outreach activities* established | Outreach activities continuously undertaken | Outreach activities continuously undertaken and evaluated | Outreach activities continuously undertaken, evaluated and improved | Mid-Term Review TADAT Secretariat reports * i.e. TADAT assessor and non-assessor training, newsletters, website and presentations at conferences (and show geographical spread of this outreach)
|  |  | Achieved |  | Delivered | Delivered | Delivered | Delivered