Business Case

Summary Sheet

Title: Lebanon Economic Reform and Infrastructure Investment (LERII)
Programme Summary: A flexible and adaptive programme to support the Government of Lebanon deliver key economic reforms and infrastructure investments important for sustainable growth and stability.
Programme Value: up to £32.5m		Country/ Region: Lebanon
Programme Code: / 300426	Start Date: / January 2019	End Date: / January 2024
Overall programme risk rating:	Moderate
Vault Number:

## Intervention Summary

Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver

Lebanon is facing macroeconomic challenges. The country has the third largest debt to GDP ratio globally, persistent fiscal and current account deficits and chronic lack of investment in public services and infrastructure. These structural issues pre-date the Syria crisis. However, the Syrian conflict has disrupted trade flows and reduced investor confidence, costing Lebanon an estimated 30% of cumulative GDP. Lebanon hosts the highest per capita level of refugees in the world, exacerbating pressure on services and jobs.

Most observers agree that action is needed to put the economy on a more sustainable footing. The £11bn of investment pledged at the April 2018 CEDRE conference could help tackle the infrastructure deficit and build investor confidence, provided it can be spent well, and crucially, linked to implementation of commitments to make changes both at the macro and sector level. This Business Case sets out our approach to delivering on the UK’s CEDRE pledge and comprises two main components:
1. up to £20m to support preparation and investment in large infrastructure projects in line with government priorities. The funding will be delivered through the European Bank for Reconstruction and Development (EBRD) over a five-year period. Delivery of this component is linked to progress in government reform;
2. a technical assistance (TA) facility (up to £10m) to support the delivery of economic reforms. The facility will be flexible and able to adapt to Lebanon’s complex political economy, and delivered through a competitively procured implementing partner over a four-year period.
An additional £2.5m over five years will be set aside for monitoring, complementary analytical work and a programme-funded post to provide additional capacity and maximize learning.
UK support will increase the chances that the Lebanese government delivers key economic reforms and secures investment for infrastructure that is well-built and operated. The potential return is very high. A more sustainable and higher growth economy, accompanied by infrastructure investments, has the potential to significantly improve poor people’s lives, including girls and women and the large number of refugees currently in Lebanon. If Lebanon were to face economic crisis, it would be the poorest who would be hit hardest and intercommunity tensions could quickly transform into violent conflict.
Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
Yes. A stable and prosperous Lebanon contributes to the security of the region and of the UK.
What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
This programme is contributing to DFID’s SDP objectives to unlock opportunities for economic development; provide support for ongoing crises, including Syria; and to spend at least 50% of DFID’s budget on fragile states and regions. If progress were made on economic reforms, there would be scope for significantly scaling up the infrastructure component of the programme in the longer term.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
Yes. The programme directly supports the Lebanese government’s economic vision and capital investment plan. We are working closely with other major donors and financial institutions to ensure our efforts are coordinated. On an exit strategy: DFID activities will be time-limited and do not bind us to a long-term commitment, although we will seek assurances on maintenance of any investments.
Has the programme considered working with HMG Departments and accessing cross-HMG funds?
We are working closely with FCO and CSSF colleagues in design and implementation of the programme. FCO Ministers and senior officials will play an important role in engaging with GoL politicians and senior officials to build support. The programme is not suitable for funding under existing cross-HMG funds although we plan to work closely with CSSF-funded initiatives on fostering political reform and dialogue, including on economic issues.

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
This project is a key component of the UK’s wider portfolio supporting economic development and job creation in Lebanon. Other programmes are creating jobs through direct support to SMEs and local infrastructure investments; this programme addresses overarching constraints to growth and job creation by focusing on economic reforms that reduce costs and improve the wider investment climate for business, thereby reinforcing our other programmes.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
Flexibility and adaptation is at the heart of our approach. Programme design has drawn from DFID best practice to ensure we are able to adjust our approach in response to the evolving context and our improved understanding of Lebanon’s complex political economy. Break points will be built into agreements with implementing partners at key decision points.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
The net risk for the programme is assessed as moderate and consistent with DFID’s net risk appetite in Lebanon which is also moderate. The programme is designed with the challenging political context in mind and we are building flexibility into our Lebanon portfolio in case we need to re-allocate resources due to slow progress.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not? Yes. The programme will be incorporated into the British Embassy Beirut Communications plan. Infrastructure projects supported through the programme will be branded with the UK aid logo.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
Yes. The programme has been designed with substantial input from FCO colleagues, including Her Majesty’s Ambassador to Lebanon; DFID’s Better Delivery Team; Procurement and Commercial Department; a peer review group of economists with experience of the Lebanon context; and other DFID advisory staff including those with experience on conflict sensitivity, M&E, climate and environment, gender and flexible and adaptive programme approaches.

Does the SRO and team have the capability and resources to deliver this programme?
Yes. The SRO role will be held by the Economic Opportunities Team Leader. S/he will be supported by an A2L economic adviser and a programme manager. Due to the resource-intensive nature of this type of programme, an additional member of DFID staff will be embedded with the TA provider, to ensure close oversight, and to maximise learning.
Strategic Case
#### The context and need for intervention
Since the end of Lebanon’s civil war in 1990, the Lebanese economic model has proved highly resilient to political and economic shocks, weathering partial occupation by Syrian and Israeli militaries, the assassination of Prime Minister Rafik Hariri in 2005, war between Hizballah and Israel in 2006, internal conflicts in 2007 and 2008, and external shocks including the global financial crisis.
More recently, Lebanon has been hit hard by the eight-year conflict in neighbouring Syria, which has seen export routes closed, investment risk increased, and over one million refugees seek shelter in Lebanon, putting pressure on public services. Economic growth has slowed from 10% in 2009 to 1-2% in recent years, also due to the fall in the value of oil. This reduced the incomes of Lebanese diaspora based in the Gulf, reducing inward investment and finance from the diaspora.
The Lebanese political settlement has hampered a coordinated response to these economic challenges. Disagreement between different Lebanese political blocs meant two and a half years without a President and, until 2017, no budget passed for 12 years. Many economic reform and infrastructure investment opportunities which could have supported economic growth during this period have been delayed for years or decades or blocked by different factions within Parliament. It is estimated that the cost of the confessional government system, and associated blockages, at nine percent of GDP annually.[1] Slower economic growth has exposed two fundamental weaknesses in the current Lebanese model:
[1] Chaaban (2014) cited in Le Borgne, Eric and Jacob, Thomas (2016), Promoting Poverty Reduction and Shared Prosperity: A systematic Country Diagnostic, World Bank Group, Report No. 103201, January 2016, page 4
An entrenched government deficit, which has averaged at around 8% of GDP for the past seven years, has seen the growth in public sector debt outpace the growth in the economy. Servicing the interest on the Government’s outstanding debt now accounts for around 10% of GDP or a third of total government expenditure, one of the highest rates in the world. Debt has exceeded 150% of Lebanese GDP, the third highest in the world, and the IMF expect this to reach 180% within three years without rapid policy action.[2]
[2] IMF Article IV report, 2018

A current account deficit averaging around 20% of GDP over the past 5 years. As the Lebanese Lira has been fixed in value to the US Dollar at the same rate since 1997, this deficit must be financed by inflows from abroad, or through the Central Bank’s foreign currency reserves. Lebanese diaspora investments in real estate and cash deposits at Lebanese commercial banks have historically financed this deficit. In recent years, however, a weaker real estate market and increasing need to subsidise the Government’s growing debt, has seen the Central Bank increasingly spend its own resources to attract foreign currency.
An economic crisis, if it were to occur, would seriously undermine the ability of the Lebanese state to maintain peace and security. An economic crisis would play into the politicisation of the refugee issue and aggravate inter-communal socio-economic tensions including over real and perceived unequal access to resources and jobs. An economic shock and financial hardship would increase the risk of a return to sectarian/inter-confessional violence. Renewed conflict within Lebanon would reduce the security services’ capacity to effectively counter Daesh or other terrorist organisations’ infiltration and operation within Lebanon. All of these dynamics would significantly increase absolute poverty and humanitarian need, potentially for decades.
Given this very difficult context, the Government of Lebanon (GoL) has proposed a significant programme of infrastructure investment, paired with economic reforms. The GoL has identified that the most promising route to avoid further economic decline is a significant capital investment injection to boost economic growth, combined with reforms that could further accelerate growth, though increased private investment, whilst reducing the Government’s need for more borrowing.
A focus on infrastructure is sensible given Lebanon’s significant infrastructure gap. Lebanon’s high interest bills have discouraged productive investment. At less than 2% of GDP in recent years and just 1.1% of GDP in 2015, Lebanon’s capital expenditure is among the lowest in the world. Public expenditure on infrastructure in upper middle-income countries averages 7% of GDP.[3] The gap between 1-2% and 7% every year, extending over a long period, largely explains the poor state of Lebanon’s public infrastructure, particularly in electricity, water supply, waste management, transport and ICT sectors. Very low levels of public investment have been compounded by insufficient maintenance of existing infrastructure as well as poor policy (e.g. high electricity subsidies) and increased pressure on infrastructure from very high numbers of refugees.
[3] Abdul Abiad et al (2017) The Role and Impact of Infrastructure in Middle-Income Countries: Anything Special? Asian Development Bank Economic Working Paper https://www.adb.org/sites/default/files/publication/359136/ewp-518.pdf
Inadequate infrastructure increases costs to firms and undermines the economy’s competitiveness. Out of 137 countries in the World Economic Forum’s competitiveness index, Lebanon ranks 130 in quality of overall infrastructure, with quality of electricity supply at 134 and quality of roads at 120.[4] However, for new infrastructure to succeed and to have the desired impact on economic growth, sectoral and horizontal reforms and preparatory work must also be delivered by the Government. Private sector investment will not increase without the reforms that are needed to improve the rate of return on their investment. Growth without reform, i.e. growth based only on concessional loans and grants, will not deliver sustained growth. Such reforms need to be undertaken in a manner which avoids worsening the lives of the most vulnerable and generating grievances that could fuel instability and conflict.
[4] World Economic Forum, Global Competitiveness Index 2017-2018.
The GoL set out their plans at the Conference for Lebanese Economic Development and Reforms (CEDRE), hosted in Paris on 6th April 2018. This included a Capital Investment Programme (CIP) of around 280 projects with an estimated total cost of around $23 billion over a period of 8-12 years; as well as a Vision for Stabilisation, Growth and Employment[5] which contained commitments to deliver key reform measures such as electricity sector reforms and reductions in the budget deficit that would support sustainable and inclusive economic growth. The GoL called on the international community’s support to deliver this package, given the country’s challenging fiscal position and the additional pressures brought by the Syria crisis. And in response, the international community pledged $11 billion in concessional loans and grants to finance the government’s plans.
[5] http://www.pcm.gov.lb/arabic/ListingAndPDFWithDropdown.aspx?pageid=11224
The CEDRE conference emphasised the critical link between delivery of reforms, and a successful programme of infrastructure investment. In the run up to the CEDRE Conference, the World Bank worked with the GoL to assess the CIP projects against different criteria, including strategic importance, feasibility, financial viability and social benefit. This assessment also sets out which reforms must be implemented, and what other enabling actions must be undertaken, before individual projects are able to deliver their potential economic and social impact.[6] The CEDRE Joint Statement between international donors and the GoL[7] reiterated this point, as did the IMF statement which noted the growth and investment opportunity presented by the conference, whilst emphasising that the immediate focus should be on delivering substantial economic reform and strengthening public investment management to ensure successful implementation of the CIP.
[6] http://documents.worldbank.org/curated/en/935141522688031167/pdf/124819-WP-PUBLIC-APR-6-1030-AM-DC-Full-Version.pdf
[7] https://www.diplomatie.gouv.fr/IMG/pdf/cedre_statement-en-_final_ang_cle8179fb.pdf
The investments and reforms promised at CEDRE would, if implemented, have an important signaling effect. In recent decades, a number of projects and important policy reforms have been ‘stuck’ in Parliament or approved, but then poorly implemented. Beyond the positive impact of the investments and reforms themselves, successful implementation would signal to international credit markets and private investors that Lebanon is increasingly open for business, helping to restore investors’ confidence, potentially stimulating investment and growth and reducing the Government’s borrowing.
#### The need for DFID intervention
At the CEDRE conference, Minister Burt pledged an additional £20m of grant financing on behalf of the UK, which would be forthcoming as the Government of Lebanon makes progress delivering economic reforms. This business case sets out how DFID plans to support the Government’s reform and economic recovery plan and fulfil Minister Burt’s pledge.[8] Whilst the UK contribution is modest relative to the infrastructure financing need, our potential to help the Government deliver meaningful economic reforms is more significant. A more sustainable economic trajectory accompanied by infrastructure investments has the potential to significantly improve poor people’s lives, including girls, women and refugees.
[8] Whilst the UK pledge represents a small amount of the c.$11bn total, much of the rest was offered as loans which would require additional grant funding (for project preparation, and to subsidise the rate of interest to make the loans more concessional); or was simply ‘re-packaged’ existing commitments.
DFID is a relative newcomer in Lebanon but has quickly established itself as a leading donor supporting Lebanon’s economic development and broader stability.[9] This has included building on the success of the 2016 London Conference to work with the GoL to deliver progress on economic opportunities and jobs. UK has built up considerable macro- and micro-economic expertise on Lebanon and has played a leading role in donor coordination on this topic.  We have good relationship with the key economic institutions in Lebanon, from the Prime Minister’s Office, Ministry of Finance to the Central Bank (BdL). The UK’s position as the largest shareholder in the World Bank (WB), also means we play an active part in WB decision-making, which is significant as the WB’s offer of $4bn in concessional loans was the largest single pledge at CEDRE.
[9] In 2017 the UK were the fourth largest donor to Lebanon behind the US, EU and Germany. We are also the leading donor providing multi-year funding commitments.
DFID is also able to draw on experience outside Lebanon successfully supporting economic reform and economically-significant infrastructure investment in fragile and conflict affected countries with complex political economy dynamics. We will continue to draw on global evidence and make use of the full range of HMG resources in the development and implementation of this programme.
This programme is fully in line with DFID and UK Government priorities in Lebanon, including the National Security Council (NSC) Strategy for Lebanon, 2015 UK Aid Strategy, DFID’s Building Stability Framework and Economic Development Strategy. It also a key part of our DFID Lebanon Business Plan, complementing our existing portfolio of economic development projects in Lebanon. Existing UK programmes, including investment in municipal level infrastructure and support to SMEs are an important contribution to the ambitious job creation targets set out in the London Conference Lebanon Statement of Intent.[10] However, meeting these targets in full will require more fundamental improvements to the enabling environment for business, including the macroeconomic environment and addressing the infrastructure deficit.
[10] The Lebanon Statement of Intent is a joint document by the GoL and the international community setting out a series of commitments to support refugees and Lebanese host communities. The statement includes a target of 300,000 to 350,000 jobs to be created, 60% of which could be for Syrians.
The outcomes of a successful DFID programme would increase the chances that the Lebanese government implements key economic reforms and reaches agreement on the construction of key donor-financed infrastructure; and that such projects are well-built and operated. Intermediate outcomes might be a more sustainable medium term fiscal strategy, an enhanced business environment through the implementation of legislation, and more, cheaper electricity.
Impact-level success would be achieved if the combination of the international-community-financed infrastructure projects and government-led reforms increased economic growth, supported more inclusive growth, created significant levels of jobs, reduced the government deficit and debt dependence, whilst easing refugee-host and inter-sectarian tensions.
Donor coordination behind objectives owned by the GoL will be key. Although this programme, by blending DFID’s grant finance with loan finance from IFIs, could make over a hundred million pounds of lending for infrastructure investment more concessional, greater impact will be achieved if we can successfully coordinate with other donors, to support reform delivery by Lebanon’s political and economic establishment.
#### Compliance with the Gender Equality Act
Economic reforms and the provision of infrastructure have the potential to profoundly improve the livelihoods and developmental potential of all communities in Lebanon. This programme complies with both the UK’s Gender Equality Act of 2014, and the commitment in DFID’s Economic Development Strategy to tackle gender discrimination and to work to deliver safer, more secure and higher-return work for women. The programme will do this by focusing on sectors identified by DFID as priority transformation entry points for gender and inclusion on urban and infrastructure policy and programming. Within these, we will actively examine the impact of specific interventions on different genders (female and male) and identify, monitor and evaluate measures to reduce gender inequality in project design and implementation. We will also: ensure that women are well-represented in the governance arrangements for the programme, including the Independent Advisory Board; engage with female champions of change within GoL; and use the procurement process to ensure that the TA provider has strong gender expertise within the team.
The social appraisal section of the Appraisal Case provides more detail.
#### Compliance with Counter terrorism financing legislation
The risk of counterterrorism finance is assessed as low. Our preferred implementing partner for the infrastructure finance component is an EU institution with established Anti-Money Laundering and Combating Financing of Terrorism Framework, which is in line with relevant EU legislation. Our preferred implementing partner for the technical assistance component is a private management agent who would be contracted following a competitive tendering process. Compliance with UK counterterrorism legislation will be assessed through the supplier selection process and built into the contract between DFID and the supplier.
Appraisal Case
This section sets out a short analysis of the political economy of infrastructure financing and economic reforms in Lebanon. This informs a theory of change articulating how support from the international community might help achieve the desired macroeconomic outcomes and impact set out in the Strategic Case. It considers DFID best practice in working with partner governments to achieve development outcomes. These building blocks together suggest a structure for DFID’s support, and allow assessment of different delivery options. The section concludes with a summary of the value for money and risk of the preferred delivery option, relative to feasible alternatives.
#### The political economy of delivering economic reforms and infrastructure in Lebanon
As set out in the DFID Building Stability Framework, building stability is a highly political process, and our approach must be grounded in an understanding of how power is distributed, used and perceived. Implementing the required set of economic reforms and other measures necessary for infrastructure finance to be mobilised and built will be a challenging task. This is due to key characteristics of the Lebanese political and constitutional system. A sectarian division of constitutional powers, MP quotas and administrative positions guarantees a balance of power between Lebanon’s 18 officially recognised confessional communities. But this system has also allowed an extremely complex clientelism to develop, where the focus of public administration has become in many cases to ensure a ‘fair’ redistribution of state resources to elites and communities from each sect. This system of patronage politics, whilst it has delivered stability, has also created an environment conducive to high levels of corruption, as there is strong social pressure on individuals to vote along confessional lines, regardless of the policies or actions of the candidate. In this context, policy changes, investments or reforms are often blocked or vetoed by minority factions within Parliament if they are perceived as unfairly benefiting or dis-benefiting particular communities, vested interests within those communities, or as generating political leverage on other issues.[11]
[11] Le Borgne, Eric and Jacob, Thomas (2016), Promoting Poverty Reduction and Shared Prosperity: A systematic Country Diagnostic, World Bank Group, Report No. 103201, January 2016
In recent years, the complexity of negotiating agreement through this system has seen Parliamentary and Government processes move extremely slowly in some areas which could otherwise support higher levels of growth, prosperity, and public service provision. This complexity can also slow or stall donor support. The Global Concessional Finance Facility, an international initiative to provide donor finance to the GoL to support infrastructure and jobs, has almost $1 billion in fully-financed projects which would benefit Lebanese citizens and economy, but which only recently received partial parliamentary approval.[12] The Italian Aid Agency has only recently received Lebanese Parliamentary approval to disburse finance that was pledged at an emergency donor conference in 2007.[13]
[12] Two projects were passed by an extraordinary session of Parliament in September 2018. A further two projects still need approval from the Council of Ministers before proceeding to Parliament.
[13] This funding was pledged at the ‘Paris III’ conference to support Lebanese post-conflict reconstruction
In this context, the success of the previous GoL in forming a reasonably comprehensive Capital Investment Plan, and committing to an important set of initial economic reforms at the CEDRE Conference in April 2018 is notable. However, achieving sufficient and sustained support for their delivery will constitute a ‘wicked problem’[14] for champions of change within Government.
[14] A ‘wicked problem’ in this context means a problem that is difficult or impossible to solve because of incomplete, contradictory, and changing requirements that are often difficult to recognize. The use of the term "wicked" here has come to denote resistance to resolution, rather than evil.
DFID’s policy on supporting partner governments
DFID’s Framework for All Financial Aid to Partner Governments[15] was developed in 2016 based on a review of international evidence, and DFID’s experience providing finance to support partner Governments’ development priorities over the preceding two decades.
[15] Internal DFID ‘smart guide’
The Framework finds that financial aid to support partner governments’ priorities can be one of the most effective development tools available to us; but that a key condition for effectiveness is close alignment between the priorities of the Government and the donor. Without this alignment, financial aid is rarely successful. In addition, the Framework sets out that conditionality generally does not change the Government’s priorities to bring them closer to that of the donor. Finally, it is often very difficult to assess upfront, the degree to which a partner government is, or is not, aligned with a donor’s priorities, and there is often strong donor optimism bias.
The framework suggests that donors identify indicators which, if achieved by the partner government, would demonstrate clear ongoing alignment between the government’s priorities and that of the donor. Linking disbursement of donor funds to the successful delivery of such indicators could be a promising approach to improving the effectiveness of financial aid. This is not because it will significantly incentivise the partner to change their priorities, but rather because it will lead to an automatic and transparent reduction in disbursement if the partner governments’ and donors’ priorities diverge, as evidenced by indicators not delivered. This provides an automatic mechanism by which financial disbursement is reduced in an environment where it is unlikely to be effectively used.
What this implies for how we should approach our support
This analysis suggests that finance for a particular project should only be forthcoming once the reforms and other preparatory measures necessary for its success have been put in place by the GoL. It also suggests that donor finance for infrastructure will have to be patient.
In addition, a recent Public Investment Management Assessment (PIMA) conducted by the IMF highlights capacity and technical challenges within Ministries and other organs of government which will be critical for planning and implementing reforms and infrastructure.[16] This suggests that there could be a role for technical assistance to accelerate the preparation and delivery of reforms and infrastructure projects, financed by the international community.
[16] IMF, Public Investment Management Assessment (2017, unpublished)
Finally, and most importantly, the analysis set out above makes clear that any support from the international community for infrastructure finance, or for development and delivery of economic reforms, cannot be packaged around externally determined solutions. Given the complexity of the political economy in Lebanon, neither the international community nor reformers within government will be able to impose pre-defined technical solutions. Instead, decision-makers will need to identify problems which have potential to be addressed, and will need to own the search for, and testing of, solutions which could successfully be delivered through Lebanon’s existing confessional system of government and parliament. The international community, rather than predefining individual problems that must be addressed with technical solutions, will need instead to stand ready to address problems which have an emerging will to be solved by key decisionmakers within government, and which fit our strategic objectives, helping contribute to the impact and outcome set out above.
#### Theory of Change
The Theory of Change (ToC) summarised in figure 1 illustrates the process by which Lebanese economic reform and infrastructure investment could, if well designed and delivered, contribute to higher rates of inclusive economic growth and employment, improve the macroeconomic situation, and contribute to broader stability.
The arrows linking different components of the ToC are colour coded, with green arrows showing strong evidence of the link, amber arrows showing medium evidence, and red arrows showing weak evidence. Dashed amber arrows indicate connections which could be positive or negative. Solid red blocks illustrate potential inputs that could be financed by international donors. A number of features of the ToC are emphasised below, alongside our approach to addressing these in programme design:
The need to build consensus: Although both technical assistance and project finance will be necessary inputs for success, neither will be sufficient. Rather, the binding constraint is the ability of the political system to deliver the necessary reforms and permissions for technical assistance and project finance to be put to good use. This will require sufficient, and sustained, support from influential champions of change within Government, across political parties and communitarian groups, beneficiary communities and from the broader business and political elite. There is strong evidence to support this assumption but few examples of reform champions succeeding in overcoming political blockages. However, examples do exist e.g. improved enforcement of traffic laws and fine collection following concerted effort by one MP in brokering a deal between groups. Overcoming ‘blockers’ will also need to be a key element of a politically savvy reform approach. There are many examples, where the economically and socially preferable policy choice has been thwarted (sometimes at the last minute) by vested interests. Similarly, we need to take care not to fall into the trap of ‘consent and delay’ i.e. where a law is approved, but implementation is delayed or not enforced. An example is the passing of the Lebanese Access to Information Law which could have been a strong move towards greater transparency but has not been systematically implemented.

We should therefore ensure that our support not only provides technical assistance and project finance, but is designed to help promote and mediate sufficient consensus across these constituencies. And that this consensus translates into real progress, not just on paper.

Complexity: The complexity of the Lebanese political system implies that sufficient consensus on delivering reforms and projects will likely be slow and difficult to achieve, even if there is broad agreement on need and urgency. It also implies that to promote consensus, and avoid inadvertently making things worse, technical assistance and project finance must be designed to test and learn as much as possible about the underlying interests, incentives and disincentives for different stakeholders, whilst accepting that we will never fully understand everything which lies behind decisions from key stakeholders.

Sequencing: Some specific economic reforms, government investments and capacity building must be completed before specific infrastructure projects are able to succeed. The World Bank assessment of the GoL’s CIP sets out actions that must be taken before individual infrastructure projects become viable. Both from a financial perspective, but also from the perspective of maximising the benefits of the infrastructure to citizens.
Assumptions and evidence underpinning the ToC is summarised below:
Reducing the need for Government borrowing: The ToC assumes that, in addition to project-specific reforms, investments and capacity-building measures, if Lebanon is to improve the current macroeconomic situation, it must also implement reforms which reduce the Government’s borrowing. These can be done through higher revenues, reductions in expenditures, and/or through implementing reforms which boost business confidence and support higher rates of economic growth. This also assumes that measures to improve the fiscal situation can be achieved without a destabilising effect on Lebanese society.

Economic reforms and infrastructure investments will be sufficient to bring the economy back to a more sustainable path: The ToC assumes that this combination will be enough to reduce the fiscal and current account deficits. There is a direct effect: through the jobs created and economic benefit of infrastructure, and reduction in borrowing from Government, improved business environment from reforms; and an indirect effect: by improving the confidence in Lebanon of international and domestic investors and businesses, who in turn increase investment and financial inflows. Even if the reforms and investments are delivered in full, this programme must be flexible enough to respond to unexpected economic shocks.

External technical assistance can support the development and adoption of economic reforms: The above analysis – complexity, sufficient consensus – suggests that the development and adoption of economic reforms will be a difficult task. Navigating (and engaging with) the politics
Figure 1: A theory of change for international community support to economic reform and infrastructure investment in Leban
and vested interests will be a major challenge. The development and delivery of reforms must be owned by, and driven by, the Government itself. In addition, those within different parts of Government will be most adept at navigating vested interest and the political equities. DFID experience elsewhere shows that high-quality and demand-led technical assistance can, in the right circumstances, help champions of change within Governments build support for the adoption of reforms. The channels by which technical assistance could support the adoption of key economic reforms in such a complex political economy environment are explored in more detail below.

External technical assistance can support the Government’s delivery of infrastructure projects: The contribution of investment (public and private) to GDP has been low in Lebanon for many years, and has averaged at only 0.1 percentage points between 2011 and 2015. Of this, public sector infrastructure investment has been smaller still, at around $100 million per year. If the Capital Investment Plan was implemented in full this would see annual public sector investment volumes increase 100-fold. In addition, some Government legislation, technical systems and procedures are extremely out of date, or as yet untested.[17] This limits the current effectiveness of public investment, and poses challenges to the effectiveness and feasibility of a rapid increase in the volume of public sector investment. Given this, the ToC assumption that externally financed technical assistance could support the Government to increase its technical capacity to deliver infrastructure projects, in a volume and at a speed that can make a significant difference to the macroeconomic trajectory, appears reasonable and well-evidenced.
[17] Examples of outdated legislation include that for procurement, which was last updated in 1963. An example of as-yet-untested legislation is the new Public Private Partnership law, which has to date only partly been ratified by Parliament.

Concessional finance from international donors will have a positive impact on the fiscal balance: Lebanon’s high interest bills, as well as high public sector wage bills and electricity subsidies, have crowded out expenditure on infrastructure, and left little fiscal headroom for additional borrowing on commercial terms. Concessional finance (involving longer repayment terms and/or lower interest rates) is more attractive but still needs to be repaid. To have a positive effect on the fiscal balance, the benefits of the infrastructure must outweigh the fiscal costs in net present value terms. The government should also prioritise projects where benefits outweigh costs in terms of cashflow i.e. investments that will boost revenues more than they are expected to cost in interest and capital repayments in coming years – if not, the negative fiscal impact could worsen the economic situation.

Research and analysis, support to civil society, diplomacy, advocacy, media and communications work can support sufficient consensus for reforms, capacity improvements and infrastructure: the ToC for the international community’s support to GoL also assumes a role for these alternative channels in complementing TA, and supporting the development of cross-community and cross-stakeholder consensus. This is an area where the programme will aim to work with others, including the CSSF political reform programme, to better understand whether and how private sector, media and public demand side pressure can bring about change, and potentially identify areas that the UK (through this, or other programmes) or other donors could support.
#### Key principles for a UK intervention
The strategic case, political economy analysis, Theory of Change and assumptions outlined above suggest our intervention should adopt some key principles:

Interventions to support reform should be locally identified and designed, rather than designed around the implementation of donor-defined solutions: Lebanon’s political economy, and the past failure of multiple donor conferences and pledges of finance to incentivise reform suggest that the imposition of pre-defined solutions is unlikely to succeed. The international community, through technical and financial support, can nudge, but can’t force, the adoption of specific problems or the development of potential solutions. Our support should be ready to help key decision-makers address problems where there is a nascent will to solve them.

Recognising the vital importance of GoL ownership, the primary barriers to progress are political, and the complexity of the Lebanese political economy, interventions will need to be flexible, politically sensitive and opportunistic:
  - Interventions will need to be flexible enough to manage significant delays;
  - Interventions will need to be sensitive to the political environment and able to spot opportunities and avoid contributing to conflict;
  - Interventions will need to be nimble enough to quickly support opportunities when they arise, including opportunities to take preventative action before a particular economic crunch point bites;
  - Interventions will need to be problem- and demand-driven: supporting reform when there are incentives developing that make change beneficial to key decision makers.

Recognising the assumptions in the ToC and the weak evidence base for supporting reforms and building sufficient consensus in Lebanon, any intervention will need to test assumptions, and learn what works.

The programme must be flexible enough to pivot in response to major changes in Lebanon: The programme, if it is to be successful, will be a long-duration programme. Flexibility in activities to match the requirements of economic and political changes is the key attribute for the success of this program and the intervention.

The programme should aim to work collaboratively with other international donors. DFID’s finance for economic development in Lebanon is small relative to resources available to the GoL from elsewhere, including from International Financial Institutions (IFIs). The greatest impact that this can have is working in a complementary way with IFIs such as the WB, EBRD, EIB, ISDB and IMF. DFID’s comparative advantage in Lebanon is our staffing, and our experiences of supporting economic reform and catalytic infrastructure investment in equally fragile and complex environments. A close cross-UK Embassy approach is also a strong comparative advantage.
#### Economic and political economy appraisal
This section puts forward alternative options for delivering support to economic reforms and infrastructure finance, assesses these against the programme design principles set out above, considers their potential costs and benefits, and value for money.

The sections above have established that:
1. Government delivery of a subset of the proposed economic reforms is necessary before some infrastructure investment projects become viable;
2. Delivering reforms that reduce the government’s need for borrowing is necessary;
3. Delivering these reforms is a ‘wicked’ problem for the Government;
4. The political feasibility of different reforms and infrastructure projects is very difficult to assess. Rather, feasibility of reforms and projects will have to be tested, and support provided will have to adapt as we learn what works, and what doesn’t;
5. International support to progress reforms and investments will require technical excellence, will need to be informed by political economy analysis including a day-to-day understanding of the impact of political changes on project delivery; and, as with (d) must test how best to support progress within Government, and adapt accordingly.
Assessing Value for Money (VfM) in a complex and volatile environment
The overarching principles for this intervention (problem-led; flexible; politically-sensitive; opportunistic; adaptive; and collaborative) mean that identifying a specific set of reforms and projects which the UK Government’s resources could support under this programme is not practical at this stage. By extension, there is not enough information to inform a traditional option appraisal, which quantifies the expected social and economic benefits of alternative projects and reforms, against the expected costs of delivering them. This does not imply that the programme will not provide VfM for the UK taxpayer.[18] Rather, it implies that a pre-defined fixed plan would have a higher likelihood of failure. And that the key VfM questions to be considered at Business Case stage are:
[18] DFID defines value for money as maximising the impact of each pound spent on poor people’s lives. See ‘DFID’s Approach to Value for Money (2011) https://www.gov.uk/government/publications/dfids-approach-to-value-for-money-vfm

1. Selecting delivery partner(s) with the systems, experience and capabilities to navigate this uncertainty, rapidly test alternative approaches to making progress towards the impact and outcomes identified in the strategic case, develop evidence as to the success of those tests, and adapt on the basis of that evidence.
2. Designing governance and programme management structures to ensure that, as opportunities arise and evidence is created on what is effective, DFID’s resources are reallocated to workstreams which offer the greatest expected impact and VfM. What these are will change, as we learn through testing, and as the political economy environment shifts. This is covered in more detail in the Management Case.
3. Best practice[19] suggests that steps 1 and 2 will ensure best possible impact of the programme, in terms of contributing to the impact and outcome statements set out in the Strategic Case. In terms of benefit to Lebanon and to the UK’s national interest, we will also apply emerging best practice to ensure costs are controlled, efficiency, effectiveness and cost effectiveness are maximised, and so ensure VfM for the UK taxpayer. This is covered in more detail in the Commercial Case.
  [19] A summary of best practice and lessons learnt in DFID adaptable and flexible programming, was gathered through DFID’s Infrastructure and Cities for Economic Development (ICED) facility.

In line with HM Treasury best practice, before assessing alternative delivery partners we consider the costs and benefits of inaction. Under the do nothing option, DFID provides no financial or technical support to economic reforms or infrastructure finance in Lebanon.

The impact on the volume of finance available for Lebanese infrastructure investment would be marginally negative. In the context of potential financing available from the World Bank and others, DFID withdrawing £20m of grant finance for infrastructure will not make a significant difference to the total finance available, or to the impact or outcome statements. However, DFID is one of only a few bilateral donors who pledged new grant funding at CEDRE. A decision not to provide financial support could have a marginally negative effect, through reducing confidence of other donors.

The impact on the potential for critical economic reforms to be implemented would be negative. Although our financial contribution to project finance would be modest relative to others’, our potential to help the Government deliver meaningful economic reforms is more significant. DFID can bring experience and world-leading best practice in successfully brokering infrastructure and reforms in complex and fragile political economy environments. In addition, DFID is a leading member of the small group international donors active in Lebanon, and our engagement has scope to improve the efficacy of the broader international community’s support. Whilst we must be realistic and humble, and recognise that we are far from being the critical success factor for the implementation of a successful economic turnaround in Lebanon, if we were to disengage, the probability of Lebanon successfully implementing critical economic reforms would be somewhat lower. In a worse case scenario this could mean significant costs to the Lebanese population, to the 1.5 million Syrian refugees generously hosted here, and to the UK’s national security objectives, including those on development and humanitarian support. There would be no direct benefits. However, the £20m - £30m finance allocated to this programme could be invested in expanding programming elsewhere in DFID’s portfolio, to the benefit of the poor in both refugee and host communities.

Alternatives to ‘do nothing’
The options appraisal focuses on step (1) of our VfM approach: selecting delivery partner(s) with the systems and capabilities required to deliver the ToC set out above. We assess the feasibility of each option across the five criteria below. A summary of our assessment is provided in table 1.
1. Whether different delivery partners’ systems provide sufficient fiduciary assurance, given the elevated risks of investing in the construction of Lebanese infrastructure set out in the Strategic Case.
2. Whether different delivery partners’ systems offer the capability to identify the best routes to achieving outcomes and impact in this complex environment, and adapt accordingly.
3. Whether different delivery partners’ systems have the capability to deliver infrastructure finance, as and when conditions are appropriate.
4. Whether the delivery partner facilitates coordination with other donors, in line with the programme principles, and development effectiveness best practice.
5. Cost-efficiency of delivery partners, as measured by overhead costs.

Option 1: provide finance to the Global Concessional Finance Facility (GCFF)
The GCFF is World Bank-led multi-donor financing mechanism that provides cheaper loans to countries hosting large numbers of refugees. Four Lebanon GCFF projects have been approved under the facility since the London Syria Conference in 2016. Two have recently been approved by Parliament; a further two are awaiting approval. Other projects are in the pipeline and could be potential candidates for DFID support. However, it may be difficult to link UK support to progress on economic reform since this multi-donor facility is not currently set up to enable such linkages. Furthermore, this option would likely be at the limits of DFID’s fiduciary risk appetite. While World Bank systems employ a variety of fiduciary safeguards, finance is channelled through GoL systems and so is to some extent fungible. It could be time consuming to obtain agreement for, and costly to resource additional third party financial monitoring mechanisms for the Facility. Given this, we have decided not to pursue this option.

Option 2: provide bilateral finance for new infrastructure projects directly to the GoL
The highly variable quality of programme and financial management by government and poor scores in measures of corruption rules out direct sector budget support to the Government. Support through financial aid, in which UK finance was ringfenced for the construction of a specific infrastructure project and accompanied by very strong fiduciary controls, could be designed in a way to reduce fiduciary risk within DFID’s risk tolerance. However, UK finance available under this programme is insufficient to fully finance a single infrastructure project within the Government’s Capital Investment Programme, making a tightly-earmarked bilateral financing arrangement unviable. In addition, the transaction and management costs for setting up such a project would be very high relative to alternatives, as DFID would have to build or buy the capability to manage and deliver our support, and that of other donors. For these reasons this option is ruled out.

Option 3: contribute finance for new infrastructure via the European Investment Bank (EIB)
At CEDRE, the EIB pledged €800m to the GoL for infrastructure financing. By blending our grant finance with EIB loans, DFID could participate in the financing of larger infrastructure projects. DFID’s grant contribution would reduce costs to Government and/or to fee-paying end-users, relative to a case in which the project was wholly loan-financed. This is the rationale behind existing (central) DFID support to EIB’s Economic Resilience Initiative (ERI). EIB has strong fiduciary controls at HQ, although their model involves partial use of GoL systems which presents a degree of fiduciary risk. EIB does not currently have a local presence in Lebanon, which makes it difficult to navigate the complex political economy challenges, as set out in the ToC. EIB is recruiting one member of staff to be based in Beirut within the next six months, and will partner with other multilateral banks with greater capacity on the ground. However, as DFID has the option of partnering directly with others with greater presence and capacity in Lebanon, we have decided not to pursue this option.

Option 4: Provide finance for new infrastructure projects to the World Bank
This would see DFID’s financial contribution to infrastructure leveraged by blending our grant resource with World Bank concessional lending, allowing us to contribute to reasonably large infrastructure investments. Our support could be designed in such a way to connect our contribution with implementation of reforms, in line with Minister Burt’s pledge. However, as with Option 1, the financing mechanisms available through the World Bank (either via development policy loans or Payment for Results loans) would be a relatively higher fiduciary risk option in the Lebanon context, and we have decided not to pursue this option.

Option 5: provide finance for new infrastructure projects through EBRD.
DFID’s grant contribution to infrastructure would be blended with EBRD lending, allowing the UK to contribute to the financing of large infrastructure investments. EBRD disburses finance directly to the contractor constructing the project, meaning UK taxpayers money would not go through GoL systems, reducing the levels of fiduciary risk to the UK. DFID finance under this option could also support technical assistance, managed by EBRD, focused on preparing the project-specific feasibility studies and supporting specific government reforms or prerequisite Government actions that would be required for individual investment projects to be financially viable. This fits well with our theory of change: finance for construction could be released subject to the successful completion of prerequisite preparatory work, including on reforms, by Government, supported by technical assistance through EBRD. This option would present a strong link between Government delivery and specific project financing, in line with Minister Burt’s pledge.

Box 1: What sort of projects could be funded through EBRD?
EBRD is engaging with the GoL to design a pipeline of investments that will support private sector investment and contribute to delivery of the government’s Capital Investment Programme (CIP). Since starting operations in Lebanon in 2018, EBRD has signed four projects and has other projects in various stages of development including projects in wastewater treatment, industrial zones, highway construction, renewable energy and electricity. The majority of these projects in the infrastructure sector require Technical Assistance to be prepared and implemented.

Option 6: provide technical assistance to support economic reforms through the World Bank.
The World Bank are proposing a multi-donor trust fund (MTDF) to support the GoL in delivering critical economic reforms. Although at an early stage of development, the World Bank intend to take a problem-driven approach to this technical assistance package, working with Government to identify areas where progress might be feasible given the political economy context. The World Bank is well-established in Lebanon, with a track record of working with Government to achieve progress on difficult policy areas, and have a high-capacity in-country team supported by regional and Washington-based experts. However, DFID has mixed experiences across our international portfolio when it comes to maintaining oversight in MDTFs. Fiduciary safeguards are less of a concern for this option, as finance for technical assistance does not run through GoL accounts but directly to contracted specialists.

Option 7: provide technical assistance through private management agents
Under this option, a management agent would be commercially procured to manage a flexible budget for technical assistance and associated costs. The central advantage of this option is that DFID would be free to design bespoke governance and management arrangements which would best fit with the Lebanese context and with the opportunities to support the Government’s reform, investments and capacity-building work. This is a model which has achieved positive results, and represents emerging best practice in brokering catalytic infrastructure investment deals in fragile and extremely complex political economy environments.[20] An illustrative ToC for this model is set out in Annex B.
[20] ibid

The procurement process to identify the delivery partner is likely to mean longer lead-in times than those offered by EBRD or WB. Given this, best practice suggests factoring in ‘interim measures or precursor programmes, which can be smaller, easier to procure and provide inception work ahead of full programme inception’.[21] Under this option we would therefore also plan to set aside a small amount of money to fund preliminary analysis and small-scale TA whilst the larger procurement is underway. This TA could allow us to collaborate with other major donors/institutions in the first year of the programme to help strengthen relationships that will allow for greater coordination and influence later.
[21] Infrastructure and Cities for Economic Development (2017) The future of DFID’s infrastructure TA programmes p. 8

Box 2: What sort of reforms could be supported?
There is no shortage of potential reforms that could be supported through this programme. The challenge will be identifying those where there is sufficient political support, where the politics allows scope to make progress, where significant impact can be achieved, and where UK support can add value. The GoL set out a series of proposed reforms in the economic vision presented at the CEDRE conference. These centre around (1) fiscal reforms, primarily a reduction in the fiscal deficit to GDP ratio by 1% per year over the next five years; (2) structural reforms including anti-corruption measures, customs reforms, e-government, public sector restructuring, governance in the oil and gas sector, justice reforms and business investment climate reforms; and (3) sectoral reforms in electricity, solid waste, water and telecoms. The GoL has also commissioned McKinsey to prepare a five-year national economic plan focused on enhancing the potential of the productive sectors. We expect the McKinsey report to be consistent with the CEDRE economic vision, but potentially including additional reform recommendations. Other analysis and assessments e.g. the IMF-led Public Investment Management Assessment (PIMA) and World Bank-led work in the electricity sector is also expected to identify additional specific recommendations.

Table 1: Summary of option appraisal (*shortlisted options)
Opt.	Description	Level of fiduciary risk and degree of safeguards?	Ability to work adaptively to overcome political economy barriers?	Capacity to deliver infra finance?	Scope for donor coord.?	Cost-efficiency
1	Additional financial contribution to existing Global Concessional Finance Facility programmes	Finance channelled through govt systems presents some fiduciary risk. Challenging and potentially expensive to ensure sufficient safeguards to bring risks to the level presented by option 5.	Not yet demonstrated: existing programmes have experienced significant approval delays	Yes	Yes	GCFF fee is low (<1%); additional admin costs would apply and vary by project partner
2	Provide bilateral finance for new infrastructure projects directly to the GoL	Finance channelled through govt systems – relatively high fiduciary risk and untested safeguards. Difficult to bring within DFID risk appetite.	Not demonstrated. Lack of progress on reforms to date	Not clear	Partial	Likely to be higher cost
3	Contribute finance for investment in new infrastructure via the European Investment Bank (EIB)	Finance channelled through govt systems presents some fiduciary risk. Challenging and potentially expensive to ensure sufficient safeguards to bring risks to the level presented by option 5.	Lack of local presence makes this difficult	Good record elsewhere but mixed record in Leb.	Yes	Admin fee likely to average ~4%
4	Provide finance for new infrastructure projects to the World Bank	Finance channelled through govt systems presents fiduciary risk. Challenging and potentially expensive to ensure sufficient safeguards to bring risks to the level presented by option 5.	Not demonstrated – past investments have not been linked to reforms	Yes	Yes	Admin fee likely to be in the 2-5% range, depending on the project
5*	Provide finance for new infrastructure projects through EBRD	Acceptable – funds channelled to private contractor; good safeguards in place	Not demonstrated – new in Lebanon	Yes	Yes	Admin fee ~5% for TA, and 2% for other activities
6*	Provide technical assistance to support economic reforms through the World Bank (WB)	Acceptable – TA managed through WB systems	Not demonstrated. Proposed approach looks good but WB systems may not be as flexible as option 7.	n/a	Yes	Trust fund admin fee likely to average 2-5%
7*	Provide technical assistance through private management agents	Acceptable – TA managed by private contractor	Not demonstrated in Lebanon context but good examples from elsewhere	n/a	Yes	Will depend on selected bidder but competitive process should drive VfM

Acceptable risk / positive evidence		Untested / mixed evidence		Unacceptable risk / negative evidence

#### Climate change and environment appraisal
The climate and environment assessment is summarised at Annex C. Impacts of specific interventions could be both positive and negative depending on which reforms, and projects, are supported by the programme and how they are taken forward.
The choice of reforms and projects will be made on grounds of political feasibility and potential impact on macroeconomic stability. However, to minimise climate and environment risks and maximise benefits we plan to: (1) conduct an initial ‘do no harm’ screening of potential reforms and projects to screen out any likely to have a net negative impact and/or pose reputational risk to the UK; (2) assess climate and environment risks and opportunities related to proposed activities; and (3) ensure actions identified in the risk assessment are taken, and performance is monitored. If appropriate, we would look to track one or more International Climate Fund (ICF) key performance indicators and count a proportion of programme spend towards DFID’s ICF commitments.
#### Conflict and stability appraisal
HMG conflict analysis has identified economic factors as a key source of conflict and instability risk in Lebanon, and a recent update highlighted the risks of economic failure critically undermining Lebanon’s stability including risks of generating increased tensions between Lebanese and Syrian refugees. Providing inclusive economic opportunities, and building cross-confessional/cross-party political and societal consensus around reform will contribute to stability if delivered in a conflict-sensitive manner.
The selected implementing agent(s) will need to demonstrate a robust approach to conflict sensitivity, including ensuring the requisite expertise within delivery teams, and understanding of Lebanon’s political economy. The results framework and risk management strategy will need to incorporate conflict sensitivity indicators. Monitoring should include sources such as media monitoring and survey data to understand the perceptions and reactions towards reforms and infrastructure initiatives. The chosen option(s) will need to provide DFID with sufficient agility and oversight to seize opportunities and manage risk, generate evidence and lessons to inform the intervention in Lebanon as well as to feed into DFID and wider international learning on supporting economic reform and infrastructure investment in conflict-affected and fragile states.
#### Social appraisal
The social impact assessment is summarised at Annex D. Challenges and opportunities to maximise the benefit for vulnerable groups (women and girls; refugees; low-income; youth; persons with disabilities) will vary according to the project or reform undertaken. While the choice of intervention will be primarily driven by political feasibility and macroeconomic stability, we plan to mainstream gender and inclusion through the programme by: 1) ensuring we have a good understanding of social outcomes, why they exist, how they are perpetuated and where there is scope for positive change; 2) working with partners to conduct project-specific social impact assessments and consultations; 3) where possible, ensuring disaggregated data is collected and analysed; 4) being robust on safeguarding risks; and 5) working collaboratively to maximise our influence and understand barriers that are preventing national level outcomes for the inclusion of vulnerable groups.
On gender equality specifically, we will give greater weight to interventions which will reduce gender inequality (all other things being equal). There is evidence that some infrastructure improvements are relatively more beneficial for women and girls. For example. provision of modern energy to homes where women and girls do most household work and improvements in public transport where women and girls can be particularly vulnerable to violence and harassment. DFID’s Infrastructure & Cities for Economic Development (ICED) facility identifies 7 priority entry points for transformation on gender and inclusion: 1) Energy 2) Transport 3) Water and Sanitation 4) Formal sector workers 5) Informal sector workers 6) Safe Space & Security 7) Land and Housing Rights. We will give greater weight to projects that fall within these categories. For each project proposal, we will require implementing partners to provide a plan to ensure gender impacts are identified, monitored and evaluated.
We will also systematically incorporate gender into LERII’s governance framework including by ensuring that women are represented on the Independent Advisory Board, whose terms of reference will include a commitment to reducing gender inequality. We will also engage with female champions of change within GoL and include evidence of relevant gender expertise as one of the criteria for evaluating bids for the TA provider.
#### Summary of Options Appraisal
Of the seven feasible implementation options outlined above, no single option would deliver the combination of support to economic reform and infrastructure investment outlined in the programme’s ToC. To maximise our chance of success, we have therefore decided to pursue two distinct, though linked, components with different implementing partners. The additional administrative and coordination resource this will require has been factored into the programme and our approach outlined in the Management Case.
In relation to the infrastructure finance component, the level of fiduciary risk varies across options. Option 5 is assessed as having the strongest fiduciary controls, with funds channelled to private contractors rather than government. A bilateral arrangement with EBRD would also likely provide DFID with greater oversight than an MTDF (option 1) or working with a partner with limited local presence (option 3).
The World Bank (options 1 and 4) and EBRD (option 5) are assessed to have the strongest capability to deliver infrastructure finance, as well as coordinate with other donors, helped by their strong teams in country. Whilst EBRD are new to Lebanon, they have a good track record elsewhere in the region and their approach of blending TA with infrastructure funding aligns well with our ToC. None of the infrastructure options showed strong evidence of having worked adaptively to overcome political barriers, although recent success by the World Bank in gaining Parliamentary approval for several GCFF projects speaks in their favour. On cost-efficiency, administrative fees look comparable across options, but additional monitoring of fiduciary risk under options 1-4 would likely push up costs relative to option 5.
None of the options raise significant concerns from a social, environmental, conflict or stability perspective at this stage; all potential options (except option 2) are assessed as having appropriate policies and processes in place to manage risks, although risks, as well as opportunities, will depend on the specific projects selected. On this, option 5 again performs well: EBRD specialise in climate finance and have a strong focus on green investments, including renewable energy, which also shows potential for gender equality and inclusion. On balance, option 5 (provide finance for new infrastructure projects through EBRD) is the preferred option for preparing, financing and project managing new infrastructure projects, if the prior conditions are met.
In relation to the Technical Assistance (TA) component, both option 6 and option 7 could be equally feasible options for supporting economic reform, relative to the criteria set out on page 16. Options 6 and 7 both provide opportunities for TA to support sector-specific reforms that have a positive impact, whether related to climate and environment, gender equality, conflict or stability. However, DFID will likely have a stronger influencing role under option 7. Fiduciary risk and administrative costs would likely be comparable and within DFID’s appetite, and both options offer scope for donor coordination. However, experience from other countries in DFID’s portfolio, including Nigeria, Somalia and Nepal suggests that the additional flexibility and ability of a privately-contracted facility such as under option 7 to rapidly learn, adapt and respond to opportunities can lead to greater impact. Option 7 (TA through private management agents) is therefore our preferred option for this component.
Commercial Case
What are the procurement/commercial requirements for the intervention?
The two main elements of the programme will require different commercial approaches:
1. Technical assistance to prepare individual infrastructure investments, and finance for infrastructure construction, delivered through a Cooperation Agreement with EBRD;
2. Flexible and adaptive infrastructure advisory facility for the GoL, delivered via a competitively tendered contract to select a private management agent.
Separate processes will also be followed for contracting other work related to the programme (third party M&E, recruiting a programme-funded member of staff, complementary analytical work). The cost of these contracts falls below the threshold where procurement must be led by DFID’s Procurement and Commercial Department. These smaller items will therefore be procured and managed locally by the DFID Lebanon Delegated Procurement Officer (DPO), following DFID rules.

Cooperation Agreement with EBRD
UK financing will initially be used by EBRD to support project preparation activities. A decision will then be taken whether to release additional finance to support large infrastructure investment, based on a DFID assessment of whether sufficient progress has been made on the sectoral and cross-cutting reforms needed for the viability and sustainability of these investments.

What assurance has been obtained on EBRD’s capability and capacity to deliver?
EBRD is a newcomer to Lebanon, receiving ‘Country of Operation’ status in late 2017. However, the Bank has a good track record of delivery elsewhere in the region and have made quick progress in Lebanon, already entering into agreements with Lebanese commercial banks to support trade finance, credit to SMEs and green investments. EBRD has quickly established an adequate in-country presence with the ability to draw on a wide range of expertise as required.

DFID Lebanon has undertaken a comprehensive Due Diligence Assessment of EBRD systems and processes. Our assessment indicates that EBRD has a strong ability to deliver, with previous experience of implementing projects in politically and economically uncertain contexts, and knowledge of delivering similar DFID programmes elsewhere in the region (i.e. Jordan). EBRD has robust systems for identifying and mitigating risks throughout the project lifecycle and thorough due diligence systems in place for downstream partners.

Approach to managing costs and ensuring Value for Money (VfM)
All project proposals and funding requests, including for TA provision, will be submitted to DFID for review and approval, prior to work starting. The DFID Deputy Director will consider the VfM assessment of all infrastructure project proposals and have final say on whether they should be supported through this programme. EBRD will provide six-monthly progress updates including performance against planned activities, indicators in the logframe and, where possible, the associated receipt and utilisation of the resources used to deliver these. EBRD will submit a completion report describing the outcome of the activity within three months after completion of each activity. The format of reports will be in line with DFID requirements and agreed in an annex to the Cooperation Agreement.

EBRD sets and monitors performance of its projects using a standardised Compendium of Indicators (see Annex E). Projects are monitored on a semi-annual or annual basis depending on their risk profile, and transition impact is measured annually against the objectives, outcomes and outputs identified at internal approval stage. Once specific TA needs and projects have been identified, DFID will agree with EBRD which of these indicators we will track in the logframe and how performance will be measured. DFID and EBRD may choose to track additional governance indicators to ensure costs and effectiveness are monitored through delivery.

Flexible and adaptive infrastructure advisory facility, delivered via a commercially-procured management agent.

How does the intervention design use competition to drive commercial advantage for DFID?
This will require direct procurement of a management agent. The management agent will be selected through a competitive tendering process to maximise VfM. Procurement of this contract is expected to begin as soon as possible following Business Case approval and be completed by December 2019.

Traditionally, using competition to maximise VfM in programme delivery requires careful specification of the outputs which are to be delivered. However, the political economy analysis above suggests that specifying a full suite of outputs in advance would undermine the potential benefits of this programme. The complexity of the problems to be addressed mean that a continuous process of testing, learning and adapting will be required to discover the most effective interventions. This means that a traditional approach to competitive procurement, where outputs are clearly specified in the tender documents, is inappropriate.

Instead, in line with emerging best practice in adaptive programmes,[22] tender documents will be drawn up specifying the properties, capabilities, and governance and commercial structures that the supplier will require if they are to be effective in this complex environment. Specifically, the supplier will need to provide:
[22] DFID (11th September 2018) ‘Commercial Solutions for Adaptive Programmes’ (unpublished powerpoint presentation)
- a core team with the technical skills - and critically - influence in country to: develop action-oriented theories of change to support economic reforms; and identify and scope opportunities across the GoL – including in collaboration with other donors, civil society and academia etc – to deliver and test these theories of change;
- capacity and skills to encourage and facilitate constructive dialogue and consultation processes; and advise on effective communications on reform and infrastructure;
- dedicated capacity to undertake continuous political economy analysis to inform the team’s work, and capacity apply a conflict- and gender-sensitive approach;
- a learn-adapt methodology by which workstreams are designed so that their success or otherwise can be monitored, rapidly established, and amended as required;
- commercial processes to rapidly recruit and mobilise task-teams with the right technical skills and influence to respond to opportunities as they arise;
- a commercial offer (including offering different combinations of staff and day rates) that allows DFID to monitor costs and drive commercial efficiencies throughout the delivery period of the programme – not just at point of competitive procurement.
- a governance offer (including semi-independent governance board to review milestone adjustments and approve the commercial and technical proposals for new workstreams as they arise) that allows DFID to monitor costs and drive commercial efficiencies throughout programme delivery – not just at point of competitive procurement.

Assessment of the market for technical assistance in Lebanon
The Lebanon office held a supplier event in November 2016, at which around 40 international and local organisations expressed an interest in planned economic development work. This event provides some assurance that an effective competition can be undertaken and there would be sufficient interest to deliver and demonstrate VfM through commercial competition. However, since we will be looking for a specific sub-set of skills and expertise to deliver this programme, DFID Lebanon will conduct a programme-specific Early Market Engagement (EME) exercise to test this assumption.
The EME will be run in London and Beirut in close succession and advertised widely through local networks in Lebanon, and notices on DFID’s supplier portal and the EU procurement website. The aim of the EME will be to raise awareness in the market, present the high-level requirements and get feedback from suppliers. We plan to set specific questions in advance to encourage maximum engagement from potential suppliers. Since suppliers may not feel comfortable revealing information in the presence of their competitors, we will also seek confidential views through the online DFID supplier portal.
There are a growing number of international organisations who have experience in delivering flexible and adaptive programmes. There are also a number of local companies and organisations with detailed knowledge of the local context and political economy challenges. Given how important it is for supplier to understand the political economy of operating in Lebanon, we see it as critical that bidders build this expertise into their teams, potentially through partnering with local organisations. We anticipate that the EME exercise will help facilitate this.

What is the intended Procurement Process to support contract award?
The programme team are working closely with Procurement and Commercial Department (PCD) in developing the Sourcing Strategy and procurement documents and agreeing timelines. Potential suppliers will be invited to bid competitively against tender documents specifying the properties, capabilities, and governance and commercial structures that the supplier will require if they are to be effective in this complex environment. Bidders will be assessed against these technical and commercial criteria.
We intend to follow a ‘competition with negotiation’ approach, following good experience elsewhere in DFID on using this procurement route to secure the right skillset for delivering flexible and adaptive programmes. As this approach is more time consuming than a standard procurement, we have allowed for an additional three months in the procurement process and plan to bring our programme-funded post on board early, to help lead the technical aspects of the process. We anticipate the procurement process taking between 9-12 months from the point of Business Case approval to contract award.
Management fees included in commercial bids will be evaluated to ensure that costs are set at an appropriate level and benchmarked against other flexible and adaptive programmes.

Contract structure and supplier performance management
The Terms of Reference (ToRs) will clearly set out what success looks like, and how we plan to measure this, elaborating on the outline results framework set out in the Management Case. It is envisaged that the performance of the supplier will be measured using Key Performance Indicators (KPIs) proposed during bid stage; refined and agreed in the contract; and reviewed at break points. The programme team will ensure the contract has clear break points and a comprehensive exit strategy.

The nature of the programme means that the main cost drivers will be the day rates of consultants. The DFID team will continuously assess the performance of the supplier in terms of driving down unit costs and delivering results. We will do this through regular meetings with the supplier, reviewing quarterly reports and use of external review points such as annual reviews, logframe updates and audits. Annual Reviews will include team members external to the programme team and the supplier will respond in writing setting out an action plan for addressing review recommendations within a specified timeframe. Value for money indicators will be included in the programme’s results framework.
Financial Case
#### What are the costs, how are they profiled and how will you ensure accurate forecasting?
The proposed budget for this programme is up to £32.5 million. The expected spending profile is set out in table 2. The expenditure profile takes account of procurement timeframes: we expect to start the procurement process for an implementing partner for component 2 in early 2019 and for work to begin in late 2019/early 2020.
Table 2: Indicative expenditure profile
Programme component	£m
	18/19	19/20	20/21	21/22	22/23	23/24	Total
Component 1: Contribution Agreement with EBRD: / TA for project preparation / Infrastructure finance	- / -	£1.2 / -	£1.3 / £2	£1.3 / £10	£1.2 / £3	- / -	£5.0 / £15.0
Component 2: Competitively tendered TA facility	-	£0.5	£2	£3	£3	£1.5	£10.0
Component 3: Other costs including third party M&E, analytical work and programme-funded post[23]	£0.1	£0.5	£0.5	£0.5	£0.5	£0.4	£2.5
Total cost	£0.1	£2.2	£5.8	£14.8	£7.7	£1.9	£32.5
[23] This estimate includes up to £900k for cost of programme-funded post; up to £1m for third party evaluation and up to £600k for complementary analytical work, spread over five years.

EBRD will submit six monthly financial forecasts using a pre-agreed template. Informal discussions between the DFID programme manager and EBRD finance manager will happen on a monthly basis to check work is on track, and forecasts remain accurate. The above spend profile is indicative and based on discussions with EBRD on their emerging pipeline.[24] However, project financing will depend on what project or projects are supported, and the pattern of construction / invoicing. DFID will maintain regular discussions with EBRD on the extent to which the GoL is delivering on its economic reform commitments, and will not move forward with infrastructure finance unless sufficient progress has been made. This financing line will also include EBRD’s administration fee which will be deducted as a percentage of each payment.
[24] Feasibility study work is estimated to cost between €300m and €1m per project supported.
The manager of the TA facility will submit a quarterly budgeted work plan for DFID approval containing detailed estimates for fees and reimbursable expenses. Performance will be tracked through the provision of quarterly narrative and financial reports. These reports will contain details of forecast spend, spend to date, and estimated total spend for the year, including an explanation for any marked deviations from expected spend. These will help DFID assess SP budget utilisation rates and further inform our own forecasting. Again, the flexible and adaptive approach means that the pattern of funding might be subject to some fluctuation.
#### Mitigating the risk of underspend
The flexible and adaptive approach to the TA facility, and linking our infrastructure finance to progress on reforms makes it harder to provide accurate upfront forecasts and increases the risk of underspend. To mitigate this risk at the DFID Lebanon portfolio level, we are looking to build flexibility into our other programmes in order to absorb additional spend if needed. For example, in our municipal infrastructure programme we plan to conduct project preparation work for a larger number of potential projects, allowing us to quickly scale up our funding if more money is freed up from this programme. We are also considering how our SME support programme may be able to flex to absorb more funds in outer years.
#### How will it be funded: capital/programme/admin?
The programme will be funded from DFID Lebanon’s existing framework, and expected future allocation under the next Spending Review (SR) round. 18/19 and 19/20 funds have been profiled under DFID Lebanon’s programme resource (RDEL) budget, and included in the Operational Plan. For outer years (20/21-23/24), anticipated spend falls within acceptable levels for Country Office spending commitments before SR outcomes are known. In these outer years, we anticipate around £15m of total programme spend will count as CDEL with the remainder classified as RDEL.
#### How will funds be disbursed?
Under all components, DFID will ensure payments are not made in advance of need. Costs will be accrued based on regular checks on progress. Payments will be processed following proper documentation of expenses and provision of satisfactory delivery of milestones and project progress reports. Payments will be made on a quarterly basis to the TA service provider. With EBRD we plan to enter into an initial contribution agreement for project preparation work, making payments on a six-monthly basis, as need is demonstrated. Funding agreement(s) for larger infrastructure investment(s) will be signed later, once project preparation is complete and more information is available to inform decisions on project viability and impact. This will also be dependent on progress on the government’s economic reform commitments. Funding for large infrastructure investments could potentially be provided through one (or possibly two) promissory notes, following a similar approach to a comparable DFID project with EBRD in Jordan. This would allow EBRD to enter into loan agreements with private sector partners and draw down on DFID funds when needed.
#### What is the assessment of financial risk and fraud?
Financial risks are considered to be low. No funds will be channelled through GoL financial systems, either directly or indirectly. A comprehensive Due Diligence Assessment has been conducted on EBRD. Our assessment is that they have strong financial management processes and robust systems for managing fraud, corruption and terrorism financing risks. As part of the commercial evaluation of tenders for the TA component, bidders will be assessed to ensure that their own financial management systems are sufficiently robust to absorb funds and deliver the activities.
#### How will expenditure be monitored, reported, and accounted for?
Expenditure will be monitored through regular financial reports (six monthly for EBRD; quarterly for the TA provider) which will be scrutinised by the programme manager to ensure value for money principles are being met and unit costs are appropriate. To ensure that funds are used for their intended purpose, DFID will:
- Monitor financial forecasts and expenditure through ARIES;
- In relation to the TA provider, only pay for expenses invoiced against the purchase order. The TA provider will be required to keep all original documents for audit and DFID will reserve the right to request original documents before payment;
- Review narrative and financial reports submitted by EBRD and the TA provider;
- Conduct annual reviews to assess progress against the programme objectives and logframe indicators;
- Request and review audit reports within six months of the end of each fiscal year covered by the programme.
Management Case
#### DFID Internal Management
The core programme management team will consist of the DFID Lebanon team based in Beirut, including the Head of DFID Lebanon leading on high level political engagement locally, the head of the Economic Opportunities team (who will take on the SRO function), an A2L Economist, B1 Programme Manager. The core team will also draw on support and collaboration with FCO’s Economist and the FCO Political Team in Beirut as well as Commercial, Infrastructure, Conflict, Economics, Statistics and Social Development Advisers for procurement, delivery, analysis and monitoring and evaluation. The team will work closely with the Beirut CSSF Team to maximise synergies.

Given the ambitious nature of the programme, its adaptive approach, and the inherent challenges, management of the programme is expected to be above average in its demands on DFID staff time. This is particularly important on the TA side, where strong staffing levels within DFID Lebanon will be needed to closely monitor and collaborate with the TA, course correct, minimize moral hazard and ensure value for money in a situation where a private provider is operating opportunistically within a very fluid environment. To respond to this challenge we propose embedding a DFID member of staff in the TA programme team. This is in line with best practice experience across DFID’s portfolio and the literature.[25]
[25] LearnAdapt – lesson learnt note on adaptive programming: embed DFID staff in the programme

The SRO and core team will participate in board meetings and monitoring to ensure regular performance management of the programme and chosen implementing partners. The team will manage the ongoing risks to delivery using the delivery plan and risk matrix, which will also be used to clarify further roles and responsibilities. The division of responsibilities will be kept under regular review. As projects and reforms are identified, DFID Lebanon’s core programme team will map existing resources in the team and assess where additional support is needed, particularly on specialist areas such as infrastructure and WASH.

Reporting will feed into DFID Lebanon portfolio quality management systems including monthly programme management meetings chaired by DFID Lebanon’s Head of Better Delivery Team. The MENAD Deputy Director for Lebanon will monitor risks of this programme in the Lebanon country risk register and escalate critical risks to the Director, Director General Country Programmes and Ministers as necessary.

In delivering this programme, DFID Lebanon will work closely with FCO and DIT colleagues in Beirut as well as DFID’s International Financial Institutions Department (IFID) and Her Majesty’s Treasury (HMT), which is responsible for the UK’s institutional relationship with the European Bank for Reconstruction and Development (EBRD). The UK is a member of EBRD’s Executive Board which provides an oversight function.
#### Coordination with other donors
As outlined in the Appraisal Case, DFID’s finance for economic development in Lebanon is modest relative to resources available to the GoL from elsewhere, including from multilateral development banks. In this context, the programme will have greatest impact when working collaboratively and complementing others, including donors and major international financial institutions such as the WB, EBRD, EIB, ISDB, IMF.

DFID’s comparative advantage in Lebanon is our staff and expertise and a key component of the programme will be how we influence others to build support and momentum behind economic reform and catalytic infrastructure investment. As well as continued diplomatic and political engagement, UK officials will continue to use existing fora to influence a wide pool of stakeholders and improve efficacy of existing structures, including:
- CEDRE Conference follow-up mechanisms to influence discussions on reforms and making the link to infrastructure projects;
- Lebanon Development Forum (chaired by UN Special Coordinator for Lebanon);
- Informal Economist Donor Working Group;
- Livelihoods, Social Stability (and other) sector Working Groups under the Lebanon Crisis Response Plan (LCRP); and
- Post London/Brussels High Level Steering Committee.

We will make use of our participation in these fora to ensure other donors and IFIs are aware of the ongoing work under this programme, to coordinate our activities to avoid duplication and maximise complementarities; and share lessons as appropriate.
#### Management arrangements for the different components
The overarching principles for this intervention (problem-led; flexible; politically-sensitive; opportunistic; adaptive; and collaborative) are described in the Appraisal Case, and set the basis for how the programme needs to be managed. Different management arrangements will be required for the different components. However, to maximise impact, the two components will need to work together to identify synergies and share learning.

Component 1: provide finance for new infrastructure though EBRD (Option 5)
DFID finance under this component will initially support TA, managed by EBRD, focused on project-specific feasibility studies and supporting specific government reforms or prerequisite government action required for individual investment projects to be financially viable, and yield successful social and economic returns. Release of further funding will be dependent on progress on the government’s economic reform commitments. The programme’s Independent Advisory Board (see table 3 below) will help decide whether sufficient progress has been made to justify release of DFID funds.

EBRD will be responsible for the management and administration of all resources received. They will work closely with GoL counterparts to design and implement projects. All project proposals will be submitted to DFID for consultation and approval prior to implementation. Finance for construction would be released subject to successful completion of preparatory work, including on reforms, by Government, supported by TA from EBRD. The programme SRO within DFID Lebanon will have responsibility for day-to-day engagement with EBRD, supported by the DFID Lebanon programme manager.

Component 2: Provide technical assistance through private management agents (Option 7)
Under this component, DFID will procure a management agent to manage a flexible budget for TA and associated costs. To be successful, this component needs to be problem-led. This requires a flexible and adaptive management approach allowing TA to test hypotheses and pivot in response to emerging opportunities as they arise. An example of what this would look like in practice is provided in Annex B.

In the initial phase of the programme, the TA will need to consider its ‘entry strategy’ – how it builds reputation and credibility, which could in turn open doors to potential opportunities for further, and potentially more successful intervention. Equally each workstream will need a clearly articulated ‘exit strategy’ – setting out how hoped-for positive effects of the intervention would be sustained after the TA’s support ends.

Critical to the success of this component will be ensuring (1) the chosen supplier has the right mix of people and skills to navigate the steps set out above; (2) the right management platform; and (3) the right incentives. The procurement process, as set out in the Commercial Case, will be critical for ensuring the right mix of people and skills. The process must yield an extremely high skilled team which can generate demand for their services, and traction for reform delivery within the Lebanese political economy environment.  The continuity of TA facility staff is a key risk: loss of key staff could drastically reduce effectiveness. The management platform will need to be able to recruit and mobilise new workstreams quickly to respond to opportunities, whist exercising sufficient cost controls and delivering quality. Drawing on experience from other flexible and adaptive programmes, the proposed governance structure is designed to ensure the right incentives are in place.

Table 3: Actors involved in the governance structure
Actor/entity	Role
Government Ministries and agencies	Government should dictate which reforms the programme should support, and participate in the review of whether or not support has delivered a successful outcome
TA Management Unit (MU)	To design, implement, learn and adapt workplans for individual reforms, bringing in additional TA specialists as needed.
DFID secondee to the TA MU	Embedded within the TA management unit, this individual will support M&E, lesson learning and coordination between the supplier and DFID.
DFID programme team	SRO and programme manager input to decision on which reform to pursue; review and approve workplan; review evidence of what has (not) worked and why (not); and approve changes to workplan. SRO will bring in other DFID advisory staff as needed.
Independent advisory board (IAB)	A critical part of the governance structure. The IAB will support DFID in assessing the feasibility of the workplan, and evidence of success and failure. They will provide informed challenge and mitigate against risks of group think and optimism bias. Members will comprise a mix of experts on flexible and adaptive programming, as well as experts on Lebanon. A representative from EBRD will also sit on the board to foster learning and information exchange across the two components.
Independent M&E specialist	At various points in the programme we may want to bring in an independent, third party monitoring specialist to provide an independent perspective on performance
Other donors and stakeholders	It will be important to ensure coordination with other donors and IFIs working on economic reforms and infrastructure. We plan to work through existing coordination structures to achieve this (see above)

#### How will progress and results be monitored, measured, and evaluated?
The impact statement for the programme is: Government reforms strengthen the macro economy and support social cohesion. We would look to measure this with macroeconomic indicators (economic growth, trade deficit, inward investment flows etc.) and/or measures of the enabling environment for business (e.g. consumer confidence indexes, business surveys, sovereign risk rating etc.). We will also look to incorporate data on perceptions of governance, social tensions and resilience.

The outcome statement for the programme is: Economic reforms and their linked infrastructure improvements are implemented and build private sector and investor confidence. We would look to measure this for example by tracking investment flows and jobs created in sectors which are the focus of reforms, we could link the logframe to extent of progress in implementation of the Government’s CEDRE reform vision.

Outputs and output level indicators will be linked to the different programme components: (1) EBRD and (2) TA support. For component 1 (support to EBRD), we will aim to draw indicators from EBRD’s standardised Compendium of Indicators (see annex E), once it is clear which projects and activities will be supported. These may be supplemented by additional indicators akin to the ‘performance’ based indicators described below. Qualitative indicators (e.g. ‘agreement signed with GoL’, ‘feasibility study conducted for project X’) will be important to capture progress in the early stages of the programme.

Setting indicators for component 2 (TA facility) is more challenging. The usual approach to monitoring and evaluation is to pre-determine outputs, and score the programme positively if these are achieved, and negatively if they are not. However, this approach does not work well for assessing the performance of a TA supplier operating in the way set out above. In this component, we are explicit that we don’t know, at the beginning of the year, which interventions or approaches will work. The programme, and supplier, could perform very well, but if interventions do not succeed, the programme could be negatively scored.

DFID’s Better Delivery Department has developed an alternative results framework / Annual Review process which assesses performance, rather than achievement of pre-defined results. Scoring uses the same rating system as with a standard annual review, but the word ‘outputs’ is replaced by ‘performance.’ We propose ‘nesting’ this framework within the broader logframe. This approach suggests four areas to score performance against:
1. Delivery: A successful programme will use resources efficiently, deliver any specific milestones that have been agreed, to the right quality, and in a timely fashion.
2. Innovation and actionable learning: All adaptive programmes have an element of testing and learning. A successful programme will generate learning that can guide future action.
3. Contribution to meaningful change: A successful adaptive programme will use learning to contribute to meaningful development outcomes – constantly testing and revising its theory of change.
4. Fit for purpose: A successful programme will reassess, based on the three other performance areas, whether the approach is still the right one to achieve the programme goals.

Indicators for each performance area will be developed in the initial phase of the programme. Methodologies for tracking progress against each of these indicators will be elaborated, drawing on emerging best practice in DFID and elsewhere. One aspect we are keen to capture is political access and influence, which will be an important – but difficult to measure - component of what the technical assistance does. Illustrative examples of what expectations we should set are outlined in Annex F.

Whilst the TA approach will require built-in monitoring, evaluation and learning systems which allow the facility to rapidly learn what works in a complex environment, and adapt support, we also see value in recruiting an independent M&E specialist to bring an external perspective and maximise learning. This M&E specialist would lead an independent mid-term evaluation of the programme framework to test the analytical underpinning, the programme’s theory of change and the adaptive approach itself.
#### Assessment of risks and how these will be managed
The risk register will be maintained and updated by the DFID programme manager on a monthly basis, or more frequently as needed. DFID Lebanon’s overall net risk appetite, after mitigation measures, is moderate. Key risks, appetites and mitigating measures are summarised below:

- External Context Risk: DFID Lebanon has a high appetite for external context risks. A core activity of the programme will be supporting the delivery of key economic reforms and a clear economic vision to help put the economy on a more sustainable footing. We will continue to monitor the political and security situation closely and use the flexibility built into the programme to respond to changes in the economic and political situation;
- Delivery Risk: DFID Lebanon has a moderate appetite for delivery risk. Key delivery risks for the programme are associated with outputs (TA support and infrastructure) translating into outcomes (meaningful economic reform; increase in economic growth). To treat this, we will ensure procurement yields a highly skilled TA team that can build credibility and navigate the local political economy. We will ensure infrastructure projects are approved by the relevant ministry/authority and exit plans are put in place to maximise sustainability. Overall, treating this risk successfully will require flexible, adaptive and opportunistic delivery. We will encourage implementing partners to leverage multiple partnerships and communication channels to aid this approach.

Operational Risk: DFID Lebanon has a low appetite for operational risk. Given the ambitious nature of the programme, the key operational risk is staff capacity. Based on lessons learnt from other flexible and adaptive DFID programmes, we will embed a DFID member of staff in the TA programme team. This will allow DFID to monitor implementation more closely, help foster a close collaborative relationship with the partner and allow day-to-day decisions to made quickly. Throughout the programme lifecycle, we will seek to capture and act upon lessons learned and ensure high quality handovers to avoid loss of institutional knowledge.

Fiduciary Risk: DFID has a low appetite for fiduciary risk. DFID has a zero-tolerance approach to fraud and corruption and requires all partners to adhere to UK and international law relating to counter-terrorism financing. Enhanced due diligence conducted on EBRD - with deep dives on safeguarding and counter-terrorism financing - assessed the risk of counter-terrorism financing as low. We will conduct the same level of due diligence on all future partners; ensure delivery chain maps are in place; and ensure partners are compliant with DFID’s fraud policy and reporting procedures.

Reputational and Safeguarding Risks: DFID Lebanon has a low appetite for reputational and safeguarding risks. For this programme, we will seek to avoid harm to people, to the environment, and to DFID’s reputation by operating within our international obligations including those covering human rights and environmental conservation and protection. In line with DFID's commitment to the ‘Do No Harm’ agenda, we will work closely with partners to apply robust safeguards and reporting measures, through their own processes. Managing risks around extremism, violent extremism and terrorism (EVET), and ensuring compliance with counter-terrorism legislation will be a key part of our risk management with partners.

## Annexes
#### Annex A – Draft risk register
#### Annex B – Illustrative theory of change
#### Annex C – Climate and environment assessment
#### Annex D – Social impact assessment
#### Annex E – EBRD standardised performance indicators
#### Annex F – Illustrative examples of indicators to track performance of the TA provider