Project Completion Review for projects below £1m that were approved prior to January 2011.

Project Title: 105577 Harbour Reconstruction
Date Project Started: September 2006
Date Review Undertaken: March 2013

Why was UK support required and what did we provide?
Calshot Harbour connects the remote island of Tristan da Cunha with the outside world. It is a conduit for passengers and supplies to and from the island, as well as an essential facility for the local fishing industry. Without such access the small community of 270 people could not easily survive. In January 2006 DFID produced a concept note, the purpose of which was to safeguard the existing harbour/breakwater structures ensuring that a secure means of access to and from the island was maintained. / DFID proposed to carry out two phases of work. The first phase was to carry out additional studies recommended by earlier reports, and to develop designs and robust cost estimates for the rehabilitation of the harbour. / The second phase was (depending on finance being available) to prepare contract documents for rehabilitation/strengthening works, evaluate tenders and supervise and administer the construction works. / The contract for these two phases was awarded to Halcrow Group Limited (HGL). Work started in September 2006 and the budget was £945,935.62. / A final phase 3, depending on successful completion of the first two phases and a cost benefit analysis to improve the harbour further was never sanctioned for implementation.

Did the actual results achieved meet those we expected to achieve?
Phase 1 Results – In October 2007 HGL issued their final report Rehabilitation of Calshot Harbour – Phase 1. This report confirmed the need for urgent works to remediate the breakwaters and other harbour structures, and also recommended a number of improvements. The report prioritised the work required on the breakwater as emergency, rehabilitation, improvements and maintenance. / The Halcrow Report stressed the need for emergency repairs to be carried out before the next austral winter storms which were forecast to build from April 2008. DFID and Halcrow tested the market for possible contractors to carry out the works, but were unable to source a civilian contractor, and sought military assistance in December 2007. It was agreed that the repairs would be carried out in two stages. / Stage 1 – Emergency military led repairs to be complete by 31 March 2008. / Stage 2 – Commercially implemented repairs to be implemented from Sept 2008. / Both sets of work were supervised by Halcrow, although due to the nature of military and civilian contracting, the role of Halcrow’s for each differed. / The Halcrow “Draft”[1] Final reports from stage 1 – states that all emergency works have been successfully carried out. It goes on to emphasise that the works are primarily emergency works to ensure that the harbour survives until September 2008, when they will be incorporated into stage 2 works. The stage 2 Halcrow report states that the second stage of work was successfully carried out by Sea and Shore Construction Pty Ltd under contract administered by Halcrow. Unfortunately, in the winter storms of July and August 2010 the harbour sustained considerable damage.
[1] No Final version of this report found on DFID records.

Value for Money Assessment.
The harbour suffered considerable storm damage following the completion of all repairs. This was not expected. Expert opinion told DFID that the harbour should be able to withstand a one in a hundred year storm event. In the event this did not happen but we had no basis to disbelieve that expert advice. / Tristan da Cunha’s extreme isolation will always present major procurement and technical difficulties even in the course of regular maintenance, much less major rehabilitation efforts such as this project. We have worked hard to ensure that costs were reasonable and that work undertaken on the harbour offered value for money as far as possible. The work with Halcrow was based on full competition. Appropriate efforts were made to ensure value for money also in terms of fees and services provided for this work. / OTD has conducted a lessons learned study on this complicated project to make sure that future investments in harbour improvements are fully informed by experience.