Annual Review – Post April 2018

Title: Support for the Economic Recovery of Somalia (SERS)
Programme Value £ (full life): £69.4 m		Review Date: May 2017 -June 2018
Programme Code: 204313	Start Date: 4th July 2014	End Date: 31st May 2020

Summary of Programme Performance
Year	2014/15	2015/16	2016/17	2017/18
Programme Score	A	A	B	A
Risk Rating	High	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204313/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204313/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)
Outline of the programme
1.	Support for Economic Recovery in Somalia (SERS) is the programme vehicle through which the UK provides funding in support of the World Bank (WB) administered Multi Partner Fund (MPF). SERS’s performance measurement indicators and targets[1] are largely borrowed from the World Bank’s Project Approval Documents (PAD) and the MPF’s Portfolio Results Framework. Therefore, SERS Annual Review (AR) directly assesses the performance of the MPF.
[1] vault no 13156356
2.	The MPF provides expert knowledge/analytics, capacity building and financing in support of (a) core government functions and staffing, (b) improved economic governance and policies, (c) public financial management and (d) private sector development. The MPF supports a broad portfolio of projects designed around the Somali government’s National Development Plan (NDP) and the New Partnership for Somalia (NPS) priorities. It operates under Somalia’s aid coordination architecture, the Somalia Development and Reconstruction Facility (SDRF) chaired by the Federal Deputy Prime Minister of the Islamic Republic of Somalia.
3.	The MPF is funded by eleven donors (the UK, EU, Sweden, Norway, Denmark, Italy, Switzerland, Finland, USAID, Swiss Agency and Germany). Donors have committed a total of $317m and paid in $270m, of which $201m (74%) have been committed and $164 (61%) disbursed.. The Bank estimates that the Fund needs a total of £293m over the period 2019-22 (excluding the $140m PACF funding and any possible IDA over this period), of which Donors have committed $116m. DFID has cumulatively committed $97.12 over the period 2014-20, of which $69.54m has been disbursed and $27.58m is yet to be disbursed by DFID to WB. This financial overview includes the recently signed additional contributions by Germany UK, EU, Norway and Sweden. The MPF is initially intended to run up to 2024. The UK is the second largest contributor to the MPF after the EU, which together account for over 65% of the MPF funding.
4.	The UK’s funding through SERS is not earmarked for any specific programme with a few exceptions: £2.4m to enhance integrity and security of the UK-Somalia remittance corridor; and £3m for a new International Finance Corporation (IFC) managed Trust Fund (IFCTF) to accelerate private sector development in Somalia. The MPF became operational in July 2014 and the IFCTF in November 2017.
5.	This is DFID’s fourth AR of SERS/MPF, carried out by the team of advisers and programme managers working on the programme as per the ToRs[2] agreed with the World Bank Group (WBG).
[2] Vault 31582370
What are the expected results?
6.	The WB is the UK’s main partner for delivering development support in Somalia. The MPF is the key vehicle for funding WB world in Somali and as such the UK’s objectives and asks from the MPF are political and strategic as well as operational.
7.	At a political level, the strategic objective of the MPF is to support Somalia’s re-engagement withthe International Finance Institutions (IFI), , and longer-term economic recovery through Somalia’s eventual debt relief and access to concessional financing. Somalia is in arrears to its international creditors, including the International Development Association (IDA), and does not have access to bilateral and multilateral concessional loans. The MPF is not simply a project based trust fund but it provides a platform for the World Bank to engage in the absence of IDA funding in Somalia.
8.	At an operational level, the MPF is expected to contribute to a more stable and prosperous Somalia by supporting the establishment of effective core public institutions and policies. It is expected to strengthen fiscal discipline, domestic resource mobilisation and access to international capital markets which Somalia desperately needs for sustaining and scaling up economic reconstruction. It is also expected to support income and job creation through an inclusive, transparent and competitive private sector.
9.	The Fund is expected to yield quantifiable economic impacts well beyond its intended lifetime. By 2020 quantifiable results include ; (i) 2000 additional direct jobs, (ii) roughly £48m of additional annual federal government revenue, (iii) nearly 1100 additional civil servants will be recruited transparently and at least 4000 officials will be paid regularly (iv) the federal government will be on a sustainable fiscal path and likely cover all civil servants salaries by 2020 , (v) £5m additional direct private sector investment, and (vi) nearly 1 million beneficiaries of infrastructure services such as roads, water supply, street lighting etc.
What is the context in which UK support is provided?
10.	Somalia is still emerging from over two decades of conflict and anarchy with a dysfunctional public sector and a narrowly-focussed private sector captured by business elites. The last five years have seen small but significant gains, which are remarkable in the context of severe fragility. Stability is emerging based on a new political settlement, a provisional constitution and two transfers of power established on elections based on limited vote. Much remain to be negotiated and agreed, however, with the agreement on the distribution of power between FMS and FGS; assignment of revenues/spending, and natural resource agreements still pending. The MPF is specifically set up to support progress on the federal model, using, for example, the process of transfers from FGS to FMS level to cement the financial model. The government’s revenue is growing ($113m in 2016 to $143m in 2017) but still remains insufficient to maintain basic administrative structure and security.
11.	Since the last AR in July 2017, there have been a number of significant developments with implications for the MPF which are considered throughout the AR. These include:
- A major drought, which highlighted yet again Somalia’s vulnerability to climate related shocks and the urgent need for durable solutions. The WB-UN-Federal Government of Somalia (FGS) jointly conducted extensive assessments of the impact reported in Drought Impact and Need Assessments (DINA) launched in January 2018. This has led to the development of a Resilience and Recovery Framework (RRF) setting out priorities and approaches for finding longer-term and durable solutions.
- Continued progress by Somalia of the IMF Staff Monitored Programme (SMP), including agreement of a 3rd SMP with targets.
- WBG completion of a comprehensive Systematic Country Diagnostic (SCD) as well as development of its first Country Partnership Framework (CPF) which will be supported by a pre-arrear clearance grant finance (PACF) for Somalia, both expected to be approved by the WB Board over the summer 2018. The SCD, CPF and PACF priorities will influence the future shape of the MPF on which the Bank has started consultation with its donors.
- Announcement by the EU of a budget support package of over 100m Euros over a period of three years starting from later this year.
- Continued disagreements between FGS and FMS, exacerbated by the Gulf crises and looming decision points on key areas, including elections.
- Mounting pressure on the government to deliver visible progress touching the lives of the Somalis on the ground, including service delivery, jobs and inclusive growth.
Summary of Progress since the last AR
13.	The programme is assessed as an A, with milestones on average meeting the output targets relevant for this AR. The score reflects the good progress the MPF has made since the last AR on the political/strategic objectives at outcome level, as well as delivery of the expected outputs.
14.	At the strategic level, following four years of strong and productive engagement of the WB in April 2018, the Board signalled a willingness to consider PACF, likely to start this year. This is sooner than was previously anticipated; and is in part attributed to good progress on the establishment of core state functions, budget management and controls, and economic policies supported by the MPF. The PACF will bring additional funds that the Bank has decided to use through the MPF and will help scale up the WB’s activities and engagement in a number of areas critical for economic recovery and resilience. It will further support specific areas needed for reaching the tougher SMP benchmarks to come (see below), and future IDA re-engagement and, over a period of time, concessional financing to fund Somalia’s massive reconstruction needs.
15.	The MPF has also supported the federal government in meeting the benchmarks of the second International Monetary MPF Staff Monitoring Programme (SMP) concluded in May 2018 and formulation of the benchmarks for the third SMP (2018-19). The FGS’s success in delivering on the third SMP will take the Somali government closer to starting the process of debt relief under the High Indebted Poor Countries (HIPC) process.
16.	At the individual Trust Fund programme level, the MPF has made significant progress in a number of areas, including those directly contributing to milestones in the New Partnership for Somalia’s (NPS) Mutual Accountability Framework (MAF) between the donors and the Somali government.
For example:-
Core state functions
17.	The MPF has helped the government formulate and implement wide-ranging reforms on fiscal and budget management. Last year, the MPF introduced an innovative incentive scheme linking additional funding to results on policy reforms (see details under Output 1).The government successfully delivered on 12 out of the 13 policy milestones relating to tax harmonisation, revenue collection, expenditure controls etc. and as a part of the deal the MPF was able to allocate the additional funding of $6m to the federal and member state governments to implement visible service delivery projects expanding their legitimacy.
18.	Revenue collection of the FGS has increased from $113m in 2016 to $143m in 2017 although this currently barely covers basic administrative salaries with most of the security budget covered by external finance and with limited spends on service delivery or investment. The MPF has cumulatively supported recruitment of over 100 new staff. Recurrent cost financing has rebuilt government payroll and is progressively regularising salary payments for over 4,000 civil servants. For the first time since 2014, the FGS was able to pay all 2017 monthly civil service salaries, and did so within the calendar year 2017 and sliding financial support from the MPF.
19.	Financial management and accountability systems are progressively improving. For example, the MPF-supported oversight mechanism (Financial Governance Committee) has provided 28 confidential assessments of government concessions and procurement contracts. Of these, 15 were either stopped or cancelled and others were recommended for re-negotiation. Whilst oversight through the FGC has resulted in savings in potential loss of revenue through loosely negotiated contracts, overall follow-up on the FGC’s recommendations remain slow and patchy.
20.	The MPF is also financing fiscal transfers for service delivery e.g. health and education through inter-governmental financing system. There is growing automation of payments and receipts across all federal (and some member state) public institutions under the Somalia Financial Management Information System (S-FMIS). The MPF’s support in inter-governmental dialogue on natural resource management and resource-sharing has seen some success with an historic agreement in February 2018 between the federal and member state governments on issue of Tuna Licenses in the fishery sector.
Core economic institutions and policy reforms
21.	Good progress has been made on establishment and functioning of core economic institutions and policies. The Central Bank of Somalia’s (CBS) functions are regularizing and increasing its function: carrying out inspections of all Money Transfer Businesses (MTBs); and providing supervision of the newly established core banking system. Somalia’s financial and mobile phone sectors are integrating fast, opening up new possibilities for scaling up access to finance. The MPF has supported the CBS in preparing a road map for financial sector development launched in February 2018. The CBS, with the MPF’s support, is working on setting up a National Payment System which will support interoperability of services across the banking sector in Somalia.
Private sector development
22.	After some delay, the Somali Business Catalyst Fund has successfully concluded the first round of applications and has started disbursing grants to businesses across Somalia. Over 5000 new jobs will be created over the next two years by some 110 grantees in manufacturing, agriculture and fisheries sectors.
23.	The IFC Trust Fund has established a Somalia Public Private Dialogue, overseen by the Federal President. This is now embedded within the FGS’s policy making structures and has helped unlock important economic legislations e.g. the Communication Act, Foreign Investment Laws, and Companies Laws.
24.	The FGS has also initiated measures to expand international markets for Somali products – trade is a big part of the Somali economy with imports accounting for a third of the food consumption and livestock, fishery and cash crops are growing exports. These include the Joint Economic Cooperation Agreement with the Government of Turkey, signing of the east and southern Africa regional trade agreement, COMESA, and beginning of the process for WTO accession.
Urbanisation
25.	There has been good progress in the MPF’s support for urban infrastructure. The MPF’s well-informed analytics have helped in raising the profile of urban development in economic recovery as well as resilience. The MPF has provided small grants to local bodies and municipalities in eight regions supporting development of street lighting, drinking water and local roads. The urban component of the MPF has expanded in scope with new funding from Germany in support relatively bigger urban infrastructure e.g. Mogadishu community roads project initiated in 2018.
Knowledge and analytics
26.	The MPF has also marked good progress in ways of working, in particular the number, frequency and quality of engagement of the Bank with the donors has significantly gone up. For example, the MPF Consultative Group meetings have happened regularly and have involved qualitative consultations involving the FGS, WB and donors in key challenges and opportunities facing the MPF. The Bank has involved donors in shaping the recommendations of its Mid Term Reviews (MTR) in 2017/18 of key MPF projects e.g. SCORE, RCRF, CIP and PFM.
Key recommendations for the year ahead
Strategic level
27.	Engage with the Bank on improved coordination with new sources of funding and instruments in Somalia. The emerging contexts, following the development set out in paragraphs 11-12 above, in particular PACF, EU budget support and funding from non-traditional donors (Turkey, Qatar, UAE and Saudi Arabia) offers opportunities as well as risks surrounding (a) absorption capacity, (b) sustainability, (c) alignment of spending with RRF priorities and (d) fiscal transfers to FMS and to Somaliland, Somalia’s region with aspiration to be an independent country not recognised by the international community.
28.	DFID team should commit time and energy to engage with the WB’s planned Public Expenditure Review, an important tool to reduce risks around absorption, spending allocation and fiscal sustainability. DFID’s focus should be to ensure that:-
- The new sources of funding do not encourage the Somali government to take on spending and liabilities that it cannot finance nor does it reduce the pressure on the government to pursue reforms necessary to raise domestic revenue mobilisation. Expenditure needs to be sustainable and balanced against the Government’s ability to raise revenue as well as absorption capacity, given that governments systems, although improving, remain rudimentary.
- Increased funding is used to develop the federal structure and deliver fiscal federalism.
- Any planned expansion of service delivery, including health and education, is built around a well-articulated vision of the Somali Government on the roles of the state and the private sector which presently plays an important role in provision of basic services.
29.	Engage with the Bank in providing thought leadership and coordination of the policy dialogue with the Somali government. The policy dialogue around the EU budget support and PACF will need to include bilateral donors. The Bank, IMF and EU recognise that the quality and leadership of the policy dialogue will be important in shaping Somalia’s future, and will therefore need to broad and inclusive. Some policy coordination is already happening across the three agencies and this will need to intensify and include bilateral donors.
30.	In addition, the policy coordination and dialogue will need to include non-traditional donors who currently put nearly two-thirds of their monetary contributions through government systems. The reach and influence of traditional donors on the non-traditional donors remain limited, and policy dialogue can be severely undermined and diluted if large pots of funding from non-traditional remain outside of the dialogue. One way of ensuring better coordination could be for the Bank and donors to explore if and how non-traditional donors’ funding could be routed through the government’s aid architecture and the MPF.
31.	The MPF’s core state function, public institutions and enabling environment work has rightly focused at upstream activities and actors over the past four years. But this upstream work will need to be balanced with support at the meso and micro level. For example, a Communication Act will be ineffective without institutional capacity (e.g. a regulator) and support for enforcement of the provisions of the Act. A strong Central Bank will be ineffective without strong, compliant and formal financial services providers to expand financial access for businesses as well as individuals. As a part of the expanded MPF following PACF, the focus has to move to middle and micro level institutions and capacity building.
32.	DFID should increase its focus on developing the path towards concessional financing for private sector development e.g. from IFC and CDC. This will be a slow-burn, given the context, but the IFC TF can be a meaningful vehicle for promoting this, especially working with IFC to lay the foundations for DFI engagement. There is growing reference to ‘blended financing; in the context of the RRF and innovative financing instruments to finance Somalia’s reconstruction needs in the infrastructure sectors. DFID’s continued engagement on this will be needed at different levels, including through IFID and UkDel, to shape thinking at the WB and IFC’s Boards.
33.	DFID will need to consider how to engage with the WBG in a new context of PACF. Our SERS contribution finishes in 2020, and given timeframes for approvals and the lifetime of the MPF, it will be important to engage the WB to discuss life beyond 2020, perhaps more targeted funding on e.g. financial and economic governance, financial sector and productive sectors to strengthen recovery and resilience over a period of time.
34.	It is important to note that the review judges that the MPF will remain relevant going forward mainly (a) as an instrument for pooled funding for donors (and entry point for donors in the policy dialogue), (b) coordinating policy dialogue – the WBG is better placed to lead and coordinate this, (c) continue to define and test entry points in new areas/sectors e.g. service delivery and infrastructure development, and (d) the Bank is going to mix the PACF (and possible IDA) funding with MPF funding.

Operational level
35.	DFID to agree on three to five top strategic and operational objectives to be pursued through funding through the MPF and continue holding periodic (six weekly) structured internal discussions to monitor progress against the agreed objectives, identify challenges and opportunities, and agree on approach for tackling identified challenges.
36.	DFID should continue to contribute to strategic discussion over the design of the “Surge” additional financing component of the RCRF – the innovative incentive scheme to encourage challenging policy reforms. Funding through the RCRF component has been relatively light on reforms and policy milestones used are basic. Going forward the policy milestones can be made more sophisticated.
37.	DFID should continue to engage with the WBG to build on recommendations of the Bank’s MTR of the SCORE project to strengthen the project’s focus around supporting systemic changes, especially for scaling up financial access as a means for strengthening economic recovery.	DFID to continue to provide technical leadership to donors in engaging with the Bank and IFC and agree on the division of roles and responsibilities between the Bank, IFC and other actors (e.g. IMF and market development programmes) in financial sector development.
## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Strengthened fiscal and public finance management capacity
Output number per LF		1	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator	Milestone	Progress
Federal government finances an increased share of its civil service wage bill (non-security sector)	40%	Overall A+ / 70% (54% if include new “surge” funding through RCRF)
Fiscal federalism dialogue facilitates FGS- FMS agreements. / (i) # of annual intergovernmental fiscal dialogues and knowledge sharing events / (ii) Evidence provided of FGS-FMS decisions and agreements made at fiscal dialogues (qualitative).	(i) 3 / (ii) qualitative	Overall A / 4 / Mixed evidence of quality and impact of the FGS-FMS discussions.
Foundations for fiscal federalism strengthened as demonstrated by increased inter-governmental transfers. / (i) # of FMS receiving transfers / (ii) % increase in total volume of transfer compared to previous years outturn	(i) 3 / (ii) 20%	Overall A+ / 4 / 150% (from a very low base)
Improved treasury management, budget execution and procurement in FGS, regional member states and SL	(i) donor funds delivered on treasury included in annual financial reports / (ii) Newly installed core banking system goes live	Overall A / Met - $104m of external grants delivered on-treasury were recorded in the FGS Summary of Government Revenue and Expenditure for 2017. / The development of the core banking system is ongoing

Briefly describe the output and provide supporting narrative for the score
38.	This output provides knowledge, capacity building and financial support (not through the budget but on reimbursement basis) to the government at federal and member state levels to establish and progressively strengthen systems of public finance management with a view to improve integrity, transparency and effectiveness of public finance. This output is scored at A, with two of the four indicators exceeding expectations. The review notes that establishing and strengthening core state functions in a highly fragile environment will be gradual and slow, and the MPF is showing good progress.

39.	Eligible civil service salaries are reimbursed upon prior review by the Monitoring Agent and in accordance with agreed payment procedures. For the first time since 2014, all 12 months of salaries due to civil servants were paid on a timely basis, marking an important milestone in strengthening PFM. Uptake under the non-salary recurrent cost component however remains very low as a result of procurement and cash-flow challenges.
40.	The federal and state-level Finance Ministers’ Fiscal Forum meetings are now held in regional capital cities on a rotational basis, helping to build trust and ownership of the process. These meetings have helped progress on tax harmonisation on selected products (such as ‘Khat’ and cigarettes). Through working closely with DFID’s PREMIS programme, which is instituting from scratch PFM systems in new FMS, last year RCRF made intergovernmental transfers to the regions (totalling $2.7m in 2017, up from $1.5m in 2016).
41.	The core banking software went live in Dec 2017 and has been operational since alongside the CBS old manual system. The CBS has been undertaking a gradual data migration to the core banking software, as staff familiarise themselves with the software and also to make sure that the capacity needed to operate the system is there.
42.	The Somalia Financial Management and Information System (S-FMIS) is now deployed throughout the FGS, supporting on-line processing of revenue and expenditure transactions and enabling direct payments into authorised bank accounts of the suppliers and civil servants. At the FMS level, Somaliland and Puntland have been supported to develop their own FMIS and officials have been trained in operating on the new system.
43.	The Office of the Accountant General also benefited from TA that has enhanced its capacity to perform day-to-day treasury functions (e.g. scrutiny of payment transactions to ensure alignment to budgetary and commitment control framework). This has been an important contributory factor to the positive IMF review against agreed SMP benchmarks. Similarly, treasury management and budget execution functions are being supported in Somaliland.
Lessons identified this year, and recommendations for the year ahead linked to this output

44.	Fiscal affordability of the wage-bill remains an issue with recent trends pointing to an increasing share of the budget being absorbed by compensation of employees e.g. this year’s budget committed 84% of domestic resources to civil service pay bill compared to 49% in 2016. An increase in the on-budget wage bill is mostly a reflection of wages coming on budget, but also reflects an expansion of the civil service itself to deliver broader responsibilities and services. The expansion in size of the civil service needs to be calibrated to longer term affordability and sustainability.

45.	Progress on more politically contentious issues e.g. introduction of a harmonised sales tax nationwide and agreement on guiding principles for customs harmonisation have been understandably slow and patchy. Little progress has been made to date around revenue/functional assignments, and other core issues of fiscal federalism. DFID should intensify engagement with the Bank and EU on if and how the additional funding through the proposed budget support and PACF can be leveraged to energise the political processes to solutions to more complex issues such as functional and revenue assignments at federal, state and district levels.

46.	Despite good progress, financial accountability and systems of checks/balances still remain rudimentary. This is understandable given that Somalia is transitioning out of absence of state and government system for over two decades. Any attempts to push for reforms and modernisation beyond the government’s absorption capacity can be counter-productive. These risks need to be carefully assessed and monitored, especially in the context of the proposed EU budget support.

47.	The approach to leverage funding to incentivise policy reforms through the ‘surge’ mechanism has been relatively successful over the past one year. RCRF and other projects under the MPF could be leveraged to initiate a serious policy dialogue between the WB, donors and FGS on the medium-term reform priorities e.g. on (a) role and size of public sector, including the wage bill and (b) implementation of the road map for revenue mobilisation prepared as a part of the Bank’s Second Economic Update launched in August 2017.

49.	Build on the fruitful collaboration across RCRF/PFM programmes and with DFID’s PREMIS programme in strengthening Public Finance Management systems at the FMS level. DFID should work with the Bank towards building greater consensus and convergence around reform efforts at federal and state levels. This may require a more structured approach than is currently the case.

Output Title	Strengthened public sector management capacity
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator	Milestone	Progress
2.1 Staff appointed to key positions in FGS and regional member states through approved CIP procedure (cumulative, % women)	FGS: 90 / PL: 50 / (20%)	Overall A+ / FGS: 97 (24% women) / PL: 76 (26% women)
2.2 Ministries/agencies with operational HR / FM functions[3]	FGS: 1 / PL: 1	Overall A (see explanation below) / FGS: 10 / PL: 9
2.3 Improved civil service management functions	• Comprehensive payroll audit completed in Puntland / • Firm contracted for payroll audit at FGS level.	Overall A / The audit in Puntland has been completed / A firm has been contracted for the FGS audit
Transparency & Accountability: / i) # of monthly payroll reports published on the MoF Website. / ii) # of fiscal summary reports published on the MoF Website	12 / 12	B / 11 monthly payroll reports published and 6 fiscal summary reports.
[3] A ministry/agency is considered to have an operational HR and FM function in place when at least three of four criteria are met: i) organigram developed, ii) Unit staffed (at least 60%) iii) staff are trained iv) unit produces key outputs (e.g. financial reports, HR records).

Briefly describe the output and provide supporting narrative for the score
50.	This output is mainly delivered through the Capacity Injection Project (CIP) which is the second largest within the MPF portfolio after the RCRF. It is aimed at helping the government at the federal and member states levels improve transparency and efficacy of public service recruitments, and also build capacity of the government departments and institutions in delivering core state functions, including policing, tax collections, and enforcement of economic laws. This output is scored at A, with two indicators exceeding expectations (but one against the same targets as for 2016), one meeting expectations and one falling below expectations.
51.	Merit-based recruitment is increasingly becoming the norm, and the harmonized salary scale has widely been adopted. Whilst targets for total number staffs recruited and share of women have been exceeded, representation of women in senior leadership positions remain a concern. Retention rate for the newly injected personnel is high (90%). The scope of the project is rightly being expanded to cover government departments responsible for basic service delivery such as health and education which are likely to receive greater funding (under EU budget support and PACF) and will need enhanced capacity.
52.	All 10 beneficiary institutions in FGS and 9 in Puntland have gone through the reorganization and change management process with the exception of the Ministry of Finance in Puntland. CIP-supported institutions (9 in Puntland and 10 at FGS level) have also been helped to establish HR and financial management functions, including support on organizational restructuring and change management e.g. defining tightly defining staffing roles and hiring plans to reduce ad-hoc hiring. The HR audit in Puntland, resulted in a cleaned-up payroll (with reduction of eligible staff from 7,651 to 5,588). Puntland civil servants were also issued with biometric IDs and proper staff personal records are now in place, as part an HR Management Information System (MIS) also funded through CIP.
53.	It should be noted here that the targets for indicator 2.2 are retained at the same level as in 2016, and the results reported are the same as those reported in July 2017 review. Hence this indicator is marked down at A.
54.	After a protracted process, partly as a result of the political transition, a firm was awarded the contract for the FGS HR audit and the process was formally launched by the PM in April. Work is currently underway and is expected to be finalised this year.
Lessons identified this year, and recommendations for the year ahead linked to this output
56.	The level of ambition and progress of this output needs to be viewed in the context that reforms in this area are known to be both politically sensitive and technically complex. Implementation requires long timeframes especially in intra-governmental coordination and collaboration. Focus needs to be on replicating Puntland success in HR Audit at FGS level which can then be linked to a fully automated payroll. This will in turn allow a degree of strategic workforce planning in accordance with government priorities and revenue projections, which is currently absent.
57.	The Bank’s Mid Term Review of CIP points to a number of challenges with CIP’s project-based interventions as against a more comprehensive and more strategic approach to Public Sector Reform (PSR) in Somalia. The review recognises a more strategic approach is challenging at this stage and can be calibrated to progress on the political settlement around administrative and fiscal structures (e.g. revenue and spending assignments).
58.	DFID should continue to focus on greater transparency around the government’s budget and other fiscal processes. Limited fiscal transparency was confirmed by an Open Budget Index score of 8/100 (one of the lowest in the world) awarded to Somalia after its first ever Open Budget Survey (an internationally recognised benchmarking tool). The survey also found that Somalia provides few opportunities for the public to engage in the budget process and that oversight by legislature and audit is weak.
Output Title	Enhanced economic and sectoral policies and enabling environment for economic development.
Output number per LF		3	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	NO

Indicator(s)	Milestone(s) for this review	Progress
O3.1. Operationalisation of the SBCF and SMEF: / (i) grant applications received; and / (ii) awarded, by region / (iii) Private sector investment (committed as co-payment) by Catalytic fund recipients	i) South Central: 500 / PL: 500 / SL: 500 / ii) Granted : 85 / iii) $1,000,000	Overall A / (i) SC: 522 / PL: 476 / SL: 752 / (ii) Granted: 101 / (iii) $7.7 m committed / $643k mobilized. (to update before review).
O3.2 Training: / i) # of individuals receiving subsidized BDS, TVET or other forms of training financed by the SCORE project / ii) Total annual increase in revenue of firms supported by SBCF and SMEF that received training and advisory services	i) 200 / ii) 0	Overall A+ / 1062 / (ii) 0
O3.3 Improvements in the regulatory environment for private sector development / i) # of diagnostic reports on legal, regulatory, institutional and infrastructure setting aimed at supporting private sector development (cumulative) / ii) # of new business licenses issued under the Licensing Act during the SCORE project	i) 4 / ii) 20	Overall B / 5 / Data not available
O3.4 Supervisory capacity within the remittance sector: Trusted Agent operations, including # MTBs supervised (on or off-site)	4 key regulations drafted for Money Transfer Businesses (Customer Registration, AML/CFT/Operational).	Overall A / 5
O3.5. Greater contribution of ICT sector (through taxes and license fees) to public treasury enabled.	Communications Act Passed	Overall A / Communications Act Passed / And US$ 5.7 million revenue collected in 2017.
O3.6 Feasibility and preliminary design studies for specific urban investments completed. / (Primary roads in Mogadishu and Garowe; secondary roads in Mogadishu; solid and liquid waste in Hargeisa.	3 completed design studies	Overall A / 3 studies completed
O3.7 Total number of direct jobs created in enterprises supported by the SCORE project (Cumulative) / i) Total / ii) Women / iii) Youth	i) 100 / ii) 30 / iii) 40	Overall B / no direct jobs supported but speculative estimates are that supported enterprises may result in nearly 5000 jobs by 2020”

Briefly describe the output and provide supporting narrative for the score
59.	This output includes a portfolio of projects aimed at enhancing economic growth. This output is focused mainly on (a) creating an enabling environment for economic growth, (b) spurring growth in the productive sectors, (c) increasing access to finance and sustain remittance flows, (d) supporting inclusive resource sharing arrangements, and (e) support development of urban infrastructure. This output is scored at A, with of a total number of 7 indicators; one exceeding expectations, four meeting expectations, and two missing expectations.

60.	The Somali Core Economic Institutions and Opportunities (SCORE) project after much delay launched its flagship business grants scheme, the Somali Business Catalytic Fund (SBCF) in this review period. It has selected 110 businesses out of total applications of over 1700 applications for matching grants with a total value of $7.4m. These businesses are spread across the three regions of Somalia and come from manufacturing, agribusinesses and fishery sectors. Whilst job target for 2017 has been missed, through the grantees, the SBCF is forecast to directly create nearly 5000 jobs by 2020. Under the Skills Training and Entrepreneurship Pilot Project (STEP), young women are increasing their skill set, 40 percent of which have been employed as a direct result of STEP in Hargeisa alone.

61.	The MPF continues to support financial sector development through a combination of analytics, diagnostics, and capacity building activities. For example, the MPF has supported preparation of a Financial Sector Development Roadmap launched by the Central Bank of Somalia (CBS) in February 2018 year and a detailed diagnostic of the supply and demand of financial services in Somalia launched in May 2018. It is also supporting implementation of inter-bank payment, clearing and settlement systems by the CBS and Somali Financial Institutions (SFIs) which will modernize payment systems in Somalia. Six commercial banks have sought and received licenses from the CBS.

62.	The MPF has also supported formulation and implementation of crucial economic legislations. For example, The Communications Act, approved by Parliament in October 2017, provides the basis for issuing licenses to mobile operators and levying taxes, generating additional tax revenue for the government. The MPF is also supporting the FGS in implementation of key provisions of the Act, including establishment of an independent regulator.

63.	The PPD process has provided a strong platform for wider consultations and is now embedded within the FGS’s policy making structures. It has helped unlock important economic legislations pending in the Parliament due to vested opposition e.g. the Communication Act. The Parliament has also approved the Foreign Investment Law and the FGS has constituted a Foreign Investment Board responsible for promoting and approving all projects involving foreign investment in Somalia. The Board has started meeting every month and is taking a more structured and transparent approach in approving FDI in to Somalia. Following the London Conference in May 2017, several sectoral meetings have been organised, including on key economic legislations such as the Energy Bill that could open up the market for investments and Companies Law which could streamline the business registration process in Somalia to ease doing business.

64.	With support from the IFC TF, the FGS has also initiated measures in expanding international markets for the Somali products – trade is a big part of the Somali economy with imports accounting for a third of the food consumption and livestock, fishery and cash crops are growing exports. The FGS signed a Joint Economic Cooperation agreement with the Turkish government, securing concessional access for select Somali produce in to Turkey. The FGS recently signed agreement to become a part of a regional trading system, Common Markets for Eastern and Southern Africa (COMESA). It has appointed Chief of Party for negotiations of terms on accession to the multilateral trading system of the World Trade Organisation.

Lessons identified this year, and recommendations for the year ahead linked to this output

65.	The review period saw considerable challenges to economic growth and highlighted the importance of a more diversified economy for economic recovery as well as resilience.

68.	Firstly, prolonged drought was exacerbated by a temporary ban on livestock exported to the Gulf. Somalia’s vulnerability to climate related and other shocks got exacerbated by an economy narrowly focussed on rain-fed activities and few export items. Economic diversification will be crucial and will require (a) strong and efficient financial sector, (b) stronger linkages to international markets, (c) improved competitiveness of the existing productive sectors, (d) improved water resource development and management, and (e) innovative financing instruments and partnership to meet Somalia’s large project financing needs.

69.	These issues are sufficiently analysed and captured in the as suggested in the Drought Impact and Needs Assessment (DINA) reports and Recovery and Resilience Framework (RRF). DFID’s engagement on the RRF and thinking about policy and programmes in the economic development space should be looked through the lens of economic diversification. As the Bank is thinking hard about priorities for PACF and as the consultations on the WBG’s CPF for the next five years progress, DFID should explore with the World Bank Group about if and how it DFID and the WBG can jointly conceptualise, design and fund more targeted programme to address some of the challenges identified in the WBG’s SCD and the RRF.

70.	Secondly, incomplete legal and regulatory frameworks, combined with high cost of compliance with regulations and elite control of key sectors in Somalia, has skewed the performance and pace of regulatory reforms. Whilst the MPF makes good progress in establishing key economic legislations, a focus on implementation of those legislations will be equally important. DFID’s engagement with the Bank and IFC in supporting implementation will be crucial for example technical support for establishment of the telecom sector regulator, One-Stop-Shop for investment approvals etc.

71.	Economic empowerment of women remains a major challenge facing Somalia. This has been a relatively light focus of the MPF in general and the private sector development component in particular. DFID team should engage with the WB and IFC in exploring how to strengthen the gender focus by integrating interventions specifically targeted at women and including women business leaders in the PPD.

Output Title	MPF is effectively managed
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress
O4.1 Implementation of an effective MPF wide approach to risk management [revised] / i) # of annual Risk Management Group meetings ( for the three SDRF funds) / ii) # of quarterly reports and corresponding donor briefing sessions by Monitoring Agent / iii) Evidence of risk management response to issues raised / iv) External review of Joint Risk Management Strategy (JRMS) conducted / v) DfID and World bank work collectively to improve strategic implementation of JRMS (qualitative) / O4.2 MPF disbursement and commitment ratios / of signed project grants (signed more than 4 months prior to the end of the calendar year. / i)Disbursement ratio of signed project grants( signed more than 4 months prior to the end of the calendar year) including RCRF/ Excluding RCRF / ii) Commitment ratio of paid in donor contributions ( transferred more than 4 months prior to the end of the calendar year)	i) 6 / ii) 4 / iii) Yes / Additional qualitative indicator: External review of Joint Risk Management Strategy conducted / i) 55% / 45% / ii) 70%	Overall A / 6 / 4 / Yes / External review conducted / Overall A / 73% / 58% 75%

O4.3. Consultation and transparency / i) # of consultative group meetings held with both donors and Minister of Finance / ii) Publicly available documents available on the MPF website / iii) # of annual consultative group meetings with donors addressing fund, sector or project-level issues / iv) Annual consultation on the quality of dialogue and fund management between World Bank and donors hosted and minuted by DfID (Introduced in 2018)	i) 1 / ii) Yes / iii) 12 / iv) none	Overall A / 1 / Yes / 17
O4.4 MPF portfolio is gender and conflict sensitive / i) % of RE projects with WB gender flag and accompanying justification / ii) % of MPF projects that utilize conflict analysis to inform project management, going beyond basic World Bank requirements for project preparations	i) 70% / ii) 30%	Overall A+ / 75% / 100%

Briefly describe the output and provide supporting narrative for the score
72.	The focus of this output is on the effectiveness of the management and implementation arrangements of the MPF and its portfolio of projects, including the Bank’s procedures and ways of working. The output as reflected in choice of indicators covers risk management, the MPF’s financial performance (proxy for pace design and implementation of activities), integration of cross-cutting issues such as gender and conflict, donor engagement and inclusion etc. The output is scored at A. Out of a total of four indicators, three have met expectations and one exceeded expectations.

73.	The MPF relies on the Bank’s apparatus and policies and procedures for managing fiduciary and other risks related to implementing the Fund’s projects. The Bank has done well in coordinating its approach to mitigating risks associated with the overall operating environment with approaches of administrators of other Trust Fund Windows in Somalia through the Joint Risk Management Strategy (JRMS) forum. This group has been effective in helping to develop a common level of risk appetite. An external review of the JRMS has recommended a more focused approach, with discussion around identified risks. Based on this the group has planned for four deep dives in 2018 and a further internal review of the JRMS at the end of CY18.

74.	The MPF’s annual disbursements have persistently increased as projects moved to full implementation: from $24.4m in 2015 to $38.1m in 2016 to $62.46m in 2017. All the 15 MPF projects are in implementation. The MPF’s disbursement ratios relative to funds committed and paid in by the donors have also significantly increased. At the end of December 2017, the donors had committed $320.5m of which they had paid in $244m. The MPF had committed $185m to signed projects which was 75% of the paid in amount. The MPF had disbursed a total of $ 137.2m, representing 54% of all paid-in contributions, an increase from 44% of the corresponding funds at the end of 2016. A majority of the disbursements have been for project grants (US$ 120.4m, 88%). Of these grants, most have been recipient-executed (US$ 98.3m, 82%) and implemented by Somali authorities.

75.	The frequency and quality of donor consultations have improved significantly since the last AR. The Bank has done well in reaching out to donors on bilateral as well as collective basis on a number key and strategic issues such as the WBG’s SCD and CPF, MTRs of important MPF projects. Whilst some of these consultations have been open to fundamental suggestions from the donors (e.g. the SCORE MTR where the Bank took on board the donors’ suggestion to refocus the project on systemic changes), some others (e.g. on SCD) has so far been very high level. The frequency of consultations on some pillars could be improved: in our consultation, some donors highlighted that the governance pillar of the MPF has not met for a long time and that follow up actions on discussion on the SCORE MTR has been slow.

76.	The MPF projects and analytic activities are reviewed and assessed by the Bank to systematically consider and address gender inequalities. Projects are self-tagged by the Task Team Leader at project concept stage and updated at the appraisal stage when the project is fully developed. The gender tag gives operational teams an active role in identifying activities that are critical to closing key gender gaps and helps corporate reporting. All the MPF projects are closely analysed from a conflict sensitivity lens, but more could be done on sharing information on if and how political economy analysis and conflict analysis are used to inform the MPF’s project design and implementation.

Lessons identified this year, and recommendations for the year ahead linked to this output

77.	Consultations with donors have significantly increased since the last AR both in terms of frequency and quality. However, follow up on issues discussed in many cases have been slow e.g. the SCORE MTR discussions. Making consultations more focussed and action oriented should be a focus. There have been improvements in flow of information and more efforts are needed on the part of the Bank in coordinating efforts with other relevant programmes on the ground. This will be particularly important on policy based dialogue as the EU starts its budget support and the PACF allows the Bank its activities in a number of areas.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)
Summarise the programme’s theory of change and any major changes in the past year

78.	The programme’s theory of change (ToC) is currently specified at a very high level. This programme is premised on the assumption that Somalia’s low level of income and wide-spread poverty is down to low levels of investment. This, in turn, is due to a dysfunctional state, weak governance, poor security, unregulated private sector, low-level of human capital, and in-efficient financial intermediation. The programme is also premised on the judgement that a capable and well-functioning state is the single most important precursor to Somalia’s economic stability and prosperity.

79.	This ToC leaves a number of important questions unanswered, especially those around prioritisation and sequencing of (a) security, (b) capable and well-functioning state, (c) business enabling environment and economic governance, (d) infrastructure development, (e) public sector financing (including IDA funding) and (f) private sector financing (including DFI investments).

80.	The last AR recommended development of a core ToC to inform the MPF’s forward look. Following discussion with the Bank it became clear that timeline of the ToC revision had to be aligned with the Bank’s own process on development of the Systematic Country Diagnostic (SCD) and a five year Country Partnership Framework (CPF). DFID team therefore have agreed with the Bank that the ToC revision should be located within the Bank’s consultation with donors around the SCD/CPF which the Bank has started only recently. We expect discussions around ToC will start taking shape in the coming months.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

81.	The overall output score of the programme is A (Outputs meet expectation)

	Outputs	Score	Weighting %
1	Strengthened fiscal and public finance management capacity	A	40%
2	Strengthened public sector management capacity	A	20%
3	Productivity of high priority sectors enhanced	A	30%
4	MPF is effectively managed.	A	10%

82.	The programme is intended to support “more effective economic institutions contributing to socio-economic recovery” of Somalia. Overall progress towards outcome seems on track, but accelerated economic recovery will need more tightly defined and targeted support especially in harnessing the power of private sector in driving growth, job creation and revenue mobilisation all of which will be critical for stability and sustainable state.

83.	The previous section (B) sets out the progress mainly on (a) civil service building and modernisation; (b) establishment and improvement in functioning public institutions; (c) improved revenue collection; (d) management of the federal budget with progressively increasing integrity, transparency and oversight mechanism, (e) improvement in economic policies and enabling environment, (f) a strong analytical foundation for planning and growth of urban and economic infrastructure, including financial sector.

84.	With regard to outcomes related to socio-economic recovery, progress is understandably slow. This is very much in line with existing evidence that driving economic growth and job creation through structural and policy changes is a long haul project in any developing country and it will be even more so in a country transitioning out of conflict with severe state fragility. As pointed out by the Fragility Commission Report launched in April this year, trying to push too many changes far too quickly can be counter-productive. Hence, international community’s support for structural and policy reforms need to be calibrated with Somalia’s absorption capacity. The MPF has done well in progressing the structural and policy reforms in small steps and outcome level milestones are on track.

86.	Somalia’s entrepreneurial private sector represents one of its strong economic assets. The IFC TF has made a good beginning in raising the profile of the PSD agenda and engaging the Somali private sector in shaping Somalia’s future. Somalia’s access to international capital will be crucial for its private sector development and this seem like an opportune time for DFID and international community to start thinking hard about how Somalia can work towards accessing DFI financing much the same way it has through the MPF worked towards accessing concessional financing. As DFID thinks about its future pipeline, we should explore if and how we can support enhancing competiveness and productivity of Somalia’s existing productive sectors and help to economy to diversify in to less water dependent economic activities.

Explain major changes to the logframe in the past year (1/2 page)

87.	The last AR concluded that the programme’s outputs and outcome indicators are disconnected and it recommended revision of logframe. The AR also suggested refinement and more tight articulation of the ToC which will also necessitate changes in the logframe. Since work related to ToC had to be located within the Bank’s on-going work on its five year Country Partnership Framework (CPF) and the MPF’s forward look, the DFID programme decided to address some of the more immediate challenges in the logframe, pending the work dependent on the CPF and MPF’s forward look.

88.	The revision to the logframe includes additional indicators at the output and outcome levels to reflect and incentivise the expected policy support and influencing role of the WB through their policy analysis/dialogue. This accounts for a big part of the Bank’s time and resources and its impact. This also helps assess progress made against key public sector and institutional reforms in support for Somalia’s economic recovery.

89.	The revision process also concluded that targets were not sufficiently realistic and benchmarked against Somalia’s difficult political economy, risky operating environment and weak institutions and governance capacity. As a result, existing targets for some indicators were reduced by up to 70% (the Vfm implications are set out in Section D of this review.

90.	Key changes to the logframe included:-
- Agreed the WB proposal to remove the revenue indicator from the Outcome level (because the MPF’s activities are less focussed in this area)
- Inclusion of additional indicators on policy analysis and dialogue:-
1. Quality of design and execution of macro-fiscal policy, as evidenced by tangible progress against RCRF AR benchmarks”.
2. Proactive identification and analysis of systemic and strategic issues and challenges.

Describe any planned changes to the logframe as a result of this review

91.	The revision to the logframe following the 2017 AR as has been explained was partial and has not addressed some wider issues surrounding the gap between the output and outcome indicators. This work will therefore need to carry forward, including in the context of the forward look of the MPF.

92.	Much of the focus of the Fund is on strengthening policy, institutions and governance which are hard to measure and quantify. DFID needs to develop its logframe further to better capture the qualitative and policy engagement aspects of the MPF in its logframe. Whilst IFI re-engagement is a key consideration in DFID’s funding to the MPF and a top UK priority in Somalia, the logframe currently completely misses this aspect. The logframe should include an indicator at the outcome level that helps capture progress towards IFI re-engagement.

93.	The current outcome indicators are focused on progress of the country systems as facilitated by the RCRF, a measure cash management which also reflects strength of systems and ability to pay on time; and FGC recommendations taken on by the Government. These are quite specific about MoF systems and interest power of top Ministers to reform. The MPF programme is of course much wider – includes a lot of the support targeted at meeting the IMF SMP benchmarks – which cover fiscal and real sectors. There could be more on revenue, more on security sector payroll, more on the enabling environment and financial sector regulation at the outcome levels.

94.	The indicators in the logframe have all been selected from the World Bank’s own M&E systems. Given the pooled funding, there is good reason for DFID’s logframe indicators to stay within the Bank’s Results Monitoring Framework for the MPF. However, as the outputs don’t directly relate to the outcomes, DFID will need to explore further how best its logframe could be strengthened whilst staying within the indicators already monitored by the WB. The review believes there are possibilities for further improvement, including:-

At outcome level:
Broaden the scope beyond PFM (wage bill, fiscal credibility and contracts oversight) to include economic governance more broadly; this could make reference to financial sector reform, Central Bank capacity, agreement of Federal Structure and Revenue collection.
Consider including other areas of work that the MPF works on that also match DFID’s priorities – for example their urbanisation work .
At output level:
In general output and outcome indicators could be better aligned. There are several outputs that don’t directly relate to the outcomes as currently defined:
  - Fiscal federalism under output 1
  - CIP related indicator under output 2. These are important but not related to PFM outcome indicators
  - Output 3 on SCORE outcomes also not related to PFM outcomes

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
Financial performance
95.	Donors have committed a total of $317m and paid in $270m, of which $201m (74% of paid in funds) have been committed and $164 (61%) disbursed. DFID has committed $97.12 over the period 2014-20, of which $69.54m has been disbursed and $27.58m remains to be disbursed by DFID to WB.

97.	DFID has been monitoring this balance before making further disbursements, in line with the Smart Guide on World Bank Trust Funds, to ensure that no payment in advance of need is made.
Overall actual spend on project activities reached 81% of the total funds committed ($164m disbursed of $201m committed)– this represents a striking improvement since the last Annual Review where disbursement had reached only 52% of the total funds committed. Spend has largely improved due to improvement in the Government’s ability to meet reimbursement requirements through the Recurrent Cost and Reforms Financing (RCRF) II. The speed of spend in some other projects e.g. Somali Core Economic Institutions and Opportunities (SCORE) projects has remained slow, although the Bank is adapting the scope of the programme given the difficult political economy and concerns so far.

Key cost drivers and performance
98.	The main cost drivers for the programme remain the same as last review i.e. staff costs, security, travel, and procurement. DFID Somalia and the Bank have sought to contain these costs, for example by developing a harmonised approach to pay of advisers placed within externally funded projects.

VfM performance compared to the original VfM proposition in the business case
99.	Overall, the Fund continues to represent good VfM. The review judges that the Fund has initiated activities in a range of areas, some of which if consolidated further, hold good prospects to deliver the intended outcomes of stronger economic governance institutions for Somalia. The MPF has made important contributions to building stronger public finance management, increasing Government revenue collection , and civil services reforms all of which a critical for state builcing, stability and economic growth in Somalia. These benefits will reach Somalia well beyond the life of the Fund.

100.	Given the Bank’s technical expertise and management bandwidth, the MPF remains the strongest vehicle available in Somalia to deliver on the UK’s objective to build public institutions, and in particular economic governance institutions necessary to formalise and regulate the economy. This is because of (i) political reasons e.g. the Bank’s convening power across range of donors and its credibility with the host government and (ii) technical reasons e.g. the Bank’s management bandwidth, thought leadership and technical expertise that comes with its presence and track record of working in challenging environment. Equally, the robust fiduciary framework of the Fund as well as ability for pooled funding offset the challenges highlighted in this review.

101.	Limited availability of reliable and timely data, which is gradually improving with the Fund’s efforts, and the expansive focus of the Fund make it challenging to do a comprehensive and meaningful assessment of the Fund’s VfM on standard lines of Economy, Efficiency and Effectiveness. However, available quantitative and qualitative information demonstrates a reasonable VfM of the Fund. For example;-
Economy
The Fund’s management cost of roughly 6.5% to manage the MPF is significantly lower than the management cost of other programmes. This is consistent with the Bank’s policy on hybrid trust funds which include both bank and recipient executed funds. The pooled funding mechanism also enables scale benefits and ability to buy into a wider set of results than would be possible with individual funding. The impact of pooled funding on unit cost is difficult to measure, given the expansive nature of the Fund’s activities and challenges around quantifying some benefit streams. There is also leveraging beyond the Fund e.g. the PACF and the EU Budget Support which would not have happened but for the progress on building core state functions and civil service through the Fund.

Efficiency
The disbursement ratio has improved considerably, reaching 73% (or 58% not including the RCRF) by December 2017. This demonstrates an improvement particularly for the RCRF which represents the bulk of MPF payments.

Effectiveness
The programme has done well in progressing the state-building agenda, which is commendable given Somalia, is starting from a very low base. The impact of the state building measures will take time to be felt on economic development and will continue well beyond the life of the MPF. The ideal measure of economy is a calculation of unit costs.
However, the breadth of the Fund’s focus and its expansive activities compound the challenge of aggregating the Fund’s impact and hence developing meaningful unit cost indicator to represent the Fund’s portfolio, especially given the lack of meaningful comparators.

Equity
The fiscal transfer component of the MPF, although relatively small at this stage, has helped in progressing equity considerations, especially the MPF’s outreach to different Member States of Somalia. Fiscal transfers to the regions are likely to scale up with new funding from the proposed PACF. Access to civil service jobs for women is being monitored through the CIP component. While still low, this component has over-exceeded its target of 20% of all new staff being women.

E: RISK (½ to 1 page)

Overview of programme risk and mitigation

Overall risk rating: Major

102.	Overall we assess the risk as major. Operational, reputational, financial and political factors inhibit achievement of project purpose in this highly fragile context in which this programme operates.

103.	Enhanced controls applied to the management of this programme do work to bring the overall level of risk down. Some of the key control measures include (e.g. third party monitoring, RCF payment on reimbursable, monthly donor consultation groups where administrative agreements are discussed as well as risk mitigation). World Bank has adopted risk based approaches in identifying and assessing country, implementation entities and project specific financial management risks. In line with accounting and reporting requirements, project financial managements have been designed to facilitate and promote sustainable development of the capacity of country institutions and implementing entities. At the project level the Auditor general are responsible for project audits.

Overview of programme risk

103.	Support to the Economic Recovery of Somalia is a complex intervention in a highly fragile and challenging operating context that carries a number of risks, including political instability and partial political settlement, weak government and institutional capacity, constrained monitoring and supervision access, and fiduciary and corruption risk.

104.	DFID maintains a risk matrix developed as part of the business case of the programme which is reviewed at monthly programme team meetings and updated as necessary. In August 2017 the risk matrix was updated. We will continue to review the risk systematically. DFID is also an active member of the Multi-Partner Risk Working Group that is led by the WB and the UN. The group meets on a quarterly basis, and identifies high level risks to both the WB MPF and UN Fund. In addition, it is within the mandate of the Third Party Monitoring Agent to monitor and escalate risks to the WB when they arise.
Outstanding actions from risk assessment
105.	There are no outstanding risk actions from the risk assessment.

Update on partnership principles

106.	DFID Somalia’s relationship with the WB has been good. DFID was the first and largest donor to the MPF and has a lot of relevant technical expertise and therefore has a strong voice among the donors. The SRO and lead DFID adviser for each project have good relationships with counterpart WB officials and there is regular informal information sharing at each level, as well as broadly good attendance in the SDRF architecture of Donor Consultation, project and sub-working groups meetings.
107.	The objectives and priorities of the MPF are aligned with the Somali government’s National Development Plan. The MPF is accountable to the Somalia Development and Reconstruction Facility (SDRF) co-chaired by the Federal Prime Minister. Nearly 75% of the MPF’s funding are allocated to projects implemented by the Somali government making use of and progressively strengthening the government ownership and systems. Whilst emphasis on working through the government system is significant, this has also led to delays in some cases given the government’s weak procurement capacity, policy systems which the MPF is trying to address.
108.	Annual reporting by the World Bank on the MPF follows standard procedures, with the production of Implementation Status Reports for individual projects, as well as 6 monthly progress reports at fund-level. Though the May progress report was not available in time for the April Annual Review fieldwork, the WB provided the review team with evidence of all the necessary logframe indicators and project narratives in draft form.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)
Performance of partners and DFID, notably on commercial and financial issues (1-2 pages)

109.	The total budget for the SERS programme is £69.4m with £45.2m having been spent to date being 65.1% of the total business case approved budget. The budget is distributed as follows: World Bank £64.4m and upto £5m to IFC, of which the current IFC TF Administrative Arrangement signed by IFC and DFID in November 2017 includes only £3m.

110.	The total cumulative budget for the review period (June 2017 to June 2018) was £11.9m. The total spent during the review period (July 2017-June 2018) is £6.9 the forecast is on track with £5m due to be released in July 2018. Currently there are no anticipated spending risks; the forecasted amounts are likely to be spent. We anticipate a large payment of £5m to go out in July to the World Bank. Overall the financial management has been satisfactory to date with accurate forecasts being met.

111.	The programme is on track to fully execute its budget for the review period. The breakdown of spend by component during the review period is as per the table below:

Component	Component Description	Partner	Budget June 2017 - 2018	Spend to date June 17- June 18

204313-101	The Business Case has approval of £5m to be allocated to the IFC TF of which DFID has signed an agreement for £3m in November 2017. The remaining £2m will be agreed with IFC after satisfactory completion of the current grant.	IFC	2,000,000	0
204313-102	World Bank Multi- Partner Fund for Somalia	World Bank	10,000,000	5,000,000
204313-103	World Bank Multi-Partner-Safer Corridor Initiative Project to support remittance flows to Somalia	World Bank	476,376	476,376
204313-105	International Finance Corporation (IFC) Trust Fund	IFC	1,500,000	1,500,000
			11,976,376	6,976,376

112.	As of June 2018, all donors have committed $317m and paid in $270m. Of the total$270m already paid in, the Fund has committed $201m (74%) and disbursed $164 (61%). There is a balance of $116m in the Fund that remains to be committed/allocated to existing and/or new projects. The Bank estimates that the Fund needs a total of £293m over the period 2019-22 (excluding the $140m PACF funding and any possible IDA over this period). DFID has cumulatively committed £69.4m or roughly $97.12 over the period 2014-20. Of this, $69.54m has been disbursed and $27.58m is yet to be disbursed by DFID to WB. This financial overview includes the recently signed additional contributions by Germany UK, EU, Norway and Sweden. Annual disbursements increased in this reporting period as all projects moved to full implementation.

113.	These recent contributions are strategically significant to the MPF as a tool for government-led development and for the overall engagement of the World Bank moving forward. This injection of resources into the trust fund has allowed for a comprehensive forward-look, in line with the strategic process of defining the World Bank Group’s next country strategy. These additional resources allow for a discussion about the role of the MPF in supporting the country’s longer-term development and eventual re-engagement with IFIs.

Quality of financial management

114.	The quality of fiduciary management by the administrator is judged to be of a high standard. The WBG’s financial policy and standards apply to spending through the Fund. Where spending is done through the Recipient Executed projects, those are subject to stringent fiduciary risk control measures designed and applied for the Fund projects. There are also wider efforts through the PFM projects under the Fund to enhance transparency and integrity of government spending.

115.	World Bank provides six monthly reports which are accessed through the World Bank portal and are used to compare actual rates spend against the original rate. We continue to assess the WB financial management as robust and offering good fiduciary assurances. Currently we are not facing any risks on exchange rate given we are disbursing funds in pounds as set out on DFID system.

116.	Some of the measures the WB take to ensure good financial and fiduciary management include:
- Expenditures are deemed eligible for reimbursement on the basis of actual amounts expensed
- Advance thresholds are based on risk assessment
- Risk Unit reviews payments and risk level on a regular basis
- Funds held in separate Designated Account in Central Bank to prevent mixing of funds
- Third Party Monitoring of payment requests through an external consultancy, only 100% eligible requests approved for reimbursement
- Use of external audit firm to conduct audits. We anticipate obtaining the next audit in September 2018. From the last review there were no specific concerns on the audit details provided by WB.
- Use of an externally staffed External Assistance Fiduciary Service (EAFS) to prepare withdrawal applications, reimbursements and procurements
- Regular Financial Management supervision missions
- Salary payments paid in cash on the basis of biometric identification

117.	The MPF’s spending rate has improved particularly on the RCRF. This is largely due to increased systems and capacity from the Government to meet the eligibility criteria required for salary reimbursement. In other programmes the Bank has assessed progress so far and gone through a process of reprioritisation with a view to scale back funding to projects where absorption is slow and to reallocate funds saved to projects with greater needs (e.g. SCORE).

118.	As the Bank moves ahead with the Pre-arrears Clearance Grant the Bank, Government of Somali and the Donors will have to consider how to prioritise and focus the MPF. To ensure there is no payment in advance of need, the DFID programme team continuously reviews the level of funds uncommitted prior to making disbursements by reviewing financial reporting and the allocation of funds as outlined on the World Bank’s donor portal.

Date of last narrative financial report(s)	June 2018 - Vault Number 32329827
Date of last audited annual statement (s)	September 2017 No particular issues raised in this audit statements

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)
Monitoring
119.	DFID directly engages with the Bank at different levels, including through DFID Somalia’s Senior Leadership Group, to shape the strategic focus as well as performance of the Fund. DFID’s programme team engages with the Bank and other donors through quarterly reviews, the MPF Consultative Group Meeting (some involving the Somali government), meetings organised by the Bank around the MTRs of the various MPF projects and the WBG’s SCD and CPF. In addition, efforts have been made to meet with FGS and federal member state who are implementing the projects either in Nairobi, through the regional flyaway meetings, and in Somalia.

120.	The MPF’s results are measured through a compilation of indicators drawn from project-level reporting by the Bank. The results framework distinguishes two levels of indicators in line with standard World Bank procedures: Project Development Objective (PDO) level indicators and Intermediate Indicators. The former tends to be more outcome focused, while the latter are often related to outputs. The Fund’s operational performance is measured through indicators measuring operational and organizational efficiency and effectiveness such as those included in Output 4 of the DFID Logframe.

121.	Systematic reporting requirements are also in place to monitor financial management, quality, progress and risks. The financial information related to the MPF can be accessed through the Bank’s Clients’ Page, including periodic audit statements. The Bank provides detailed annual progress reports setting out areas of achievements, challenges and emerging priorities.

122.	MPF uses a management consulting and monitoring agent to provide external third party monitoring and assurance to complement the Bank’s internal supervision of the MPF projects. The agent is directed to report on how MPF funds are executed by the Somali authorities, confirm utilization for the purposes specified in MPF grant agreements, and monitors the flow of MPF funds from the World Bank through the government systems. The monitoring agent also advises the World Bank on trends, developments, and emerging issues that relate to the MPF portfolio.

Evidence

123.	The Fund’s knowledge and analytical work products also serve as useful backdrop for monitoring the country-level outcome and impact indicators also provide useful monitoring of impact level indicators and serves. These include periodic surveys and reports of the Bank (e.g. Somalia Economic Updates, Somali Poverty Profile) or products prepared with the support of the World Bank (e.g. annual Aid Flow Analysis), the DINA reports etc.

124.	The Bank’s knowledge products and analytics are important in progressively strengthening the evidence base in Somalia. The Bank has also played a significant role in strengthening the government’s statistical systems, including support from the IMF and other agencies, although the systems still remain very rudimentary. The Fund has rightly planned for more targeted support to the FGS in building its capacity for statics and economic planning.

125.	Although a number of the Fund’s large and strategic projects have gone through midterm reviews in the last one year or so, those reviews have focussed more assessing performance rather than evaluating underlying project design.
As we approach into the fifth year of the Fund (which will be the half way mark of the Fund originally intended life span), it will be good opportunity for all the donors to jointly commission an independent third party review and evaluation of the fund, taking a close look at some of the high level and strategic objectives, how the various investment decision fit within those objectives, the key lessons and what could have been done differently.
Learning
123.	The last AR included a number of key lessons surrounding challenges of delivering a large and complex technical programme in a post conflict context where the supplier market is very limited and attracting large and reputable suppliers on the basis of small and fragmented contracts makes things even more challenging. These challenges and the associated delays and cost implications need to be adequately factored in in any umbrella programme such as the MPF in fragile and conflict environment.

124.	Implementing matching grants is complex and politically difficult. It is more so, if it involves the government in decision making, especially in countries where public sector institutions, oversight mechanisms, political economy, and clan dynamics are weak. Nor can matching grants provide any systemic fix to credit and capital constraints. Whilst matching grants can be a temporary fix a clear and concurrent focus on systemic changes in the financial sector is equally important.

125.	Equally, upstream public sector policy and capacity building support need to be balanced with support at the meso and micro level in order for the upstream changes to bear fruit on the ground. Planning and design of macro, meso and micro level interventions should be current rather than sequenced.

Progress on recommendations from previous reviews (1/2 page)
126.	The last AR made a set of broad and substantive recommendations relating to Fund’s (a) focus, (b) ToC, (c) rationalisation, prioritisation and sequencing, (d) revision of the logframe and (e) management, procedures and ways of working. The logframe revision was completed in December last year and rationalisation of some of the large and strategic projects e.g. SCORE is taking place in within the Bank’s MTR. For example, the Fund has decided to drop the planned second round of the business grant schemes and has engaged with donors in reshaping the SCORE projects to focus on systemic changes needed for strengthening the financial sector.

127.	There has good progress on recommendations related to management and procedural aspects of the Fund. The quality and frequency of the Bank’s engagement with donors have significantly improved. The Bank has reached out donors on bilateral as well as collective basis on a number of important issues such as financial sector development, digital IDs, and RRF. Consultations through the MPF Consultative Group meetings has also more frequent and including the government counterparts. Occasionally, the Bank has invited the donors to participate in its review missions, and sharing of Aide Memoires and Review Reports has also improved.

128.	Follow up on some other recommendations e.g. (a) and (b) had to move alongside the Bank’s work on the Systematic Country Diagnostic and its Country Partnership Framework both which provide a firmer information and analytical base needed to inform the MPF’s focus as well as the ToC. Since March this year the Bank has started consulting donors on high level findings of the SCD and more recently on the forward look of the MPF as part of its consultations on the CPF.