Project Completion Review

Title	Tax Administration Diagnostic Assessment Tool
Programme Identification Number	204114
Total Programme Budget	£1,781,000
Start Date	15 May 2014
End Date	23 Oct 2018
DevTracker Link to Business Case	Business Case
DevTracker Link to Logical Framework	Logical Framework
Project Completion Review Date	23 Jan 2019

Summary of Programme Performance and Risk Rating

Financial Year	2014/15	2015/16	2016/17	2017/18
Review Score	B	A	B	A+
Risk Rating	Major	Moderate	Moderate	Moderate
DevTracker Link	Annual Review	Annual Review	Annual Review	PCR

Summary of the Logical Framework

Level	Descriptor	Score
Impact	TADAT contributes to strengthened tax administration systems and domestic revenue mobilisation efforts globally.	N/A
Outcome	TADAT assessments improve tax administration knowledge, and inform tax reform discussion and decision-making.	N/A
Output 1 / Weight: 60%	TADAT is the preferred tax administration diagnostic and performance assessment tool globally.	A+ / Moderately exceeded expectation
Output 2 / Weight: 20%	TADAT assessments are of a high quality and effective in identifying the relative strengths and weaknesses of tax administrations.	A / Met expectation
Output 3 / Weight: 20%	TADAT facilitates enhanced understanding by key stakeholders of international good practices in tax administration through training and impactful outreach activities.	A+ / Moderately exceeded expectation

1. Summary and Overview ………………………………………………………………………………………. 2
2. Detailed Output Scoring ………………………………………………………………………………………. 4
3. Theory of Change and Progress Against Outcomes ……………………………………………… 8
4. Value for Money ………………………………………………………………………………………………….. 13
5. Risk ………………………………………………………………………………………………………………………. 17
6. Delivery, Commercial and Financial Performance ………………………………………………… 18
7. Monitoring, Evaluation and Learning …………………………………………………………………… 19
Annex A: TADAT Results Framework – Phase I …………………………………………………………… 22
# A. Summary and Overview

The Tax Administration Diagnostic Assessment Tool (TADAT) is a global tool, designed to provide an objective performance assessment of key components of a country’s tax administration system. TADAT scores performance from A-D on nine key areas; a scoring mechanism aligned with other similar public finance system diagnostic tools. To date, 71 assessments have been completed, 60% of which were in lower-middle and lower income countries.

TADAT is funded by donor agencies from Germany, Japan, the Netherlands, Norway, Switzerland and the European Union, as well as the UK. DFID is the largest donor, providing just under a quarter of all contributed funds. The World Bank and the International Monetary Fund (IMF) also contribute staff time and resources. All of the above sit on the Steering Committee, which DFID currently chairs. TADAT also benefits from a Technical Advisory Group (TAG) which provides technical guidance and participates in the quality assurance of TADAT assessment reports.

DFID has been a key partner in TADAT since its inception in 2013/14. In 2014, DFID approved £1.8m in funding over four financial years (2014/15 to 2017/18) for the first phase of TADAT. The majority of the funding was designated to support the central functions of the TADAT Secretariat, based in the IMF building in Washington DC, with a small amount budgeted for DFID-led assessments in priority developing countries, although the latter was never utilised (the TADAT Secretariat did not have access to these funds and this indicator was removed from the logframe accordingly). Assessments are requested by the revenue authority, and donor-funded teams of trained assessors are deployed to countries on a voluntary, case-by-case basis.

The Theory of Change follows the rationale that countries need effective and efficient tax administration systems to more sustainably raise domestic revenue and reduce aid dependence. Better tax systems require policies and processes of reform and improvement, built on robust evidence, skill and discussion.

As such, the expected impact of this work was that the use of TADAT assessments would help improve the effectiveness of countries’ reform efforts and that this improvement could be monitored through repeat assessment. As only two of the 71 jurisdictions assessed have undergone a repeat assessment, it is too soon to evaluate whether this has been the case. The use of repeat assessment scores as a monitoring and evaluation source is perhaps not the best indicator of TADAT’s success as a diagnostic tool, as this is largely outside the operational scope of the TADAT Secretariat, and has therefore been replaced in the next phase of our work with TADAT.

The expected outcome of providing funding for TADAT was based on the rationale that TADAT assessments would facilitate discussion among country authorities and donors about tax capacity building and serve as the basis for setting the direction of reform of tax administrations. There is significant evidence to suggest that this outcome target has been achieved.

At the outset of the programme, indicators in Output 1 centred on the establishment of TADAT’s core mechanisms and documents, and later, on monitoring, assessment, incidence and uptake. This is the primary function of TADAT, and therefore has a weighting of 60%. Targets for assessment numbers overall, and in developing countries, were both met and exceeded slightly.

Output 2 focuses on systemic quality assurance, particularly that the TADAT Framework and Field Guide (guidance for assessments) reflect current best practice in tax administration performance, and that the performance assessment reports (the document compiled at the conclusion of a TADAT assessment) are quality assured. Both of these indicators’ targets were met, and thus, this output scores an A. This carries a weighting 20%.

Output 3 covers TADAT’s outreach and training work. This work utilises the largest category of budget and a great deal of Secretariat resource. The training workstream was initially established to train TADAT assessors but has since expanded its offer to include non-assessor training. This is seen as a type of indirect capacity building for tax administration officials, and is for those who wish to learn more about the TADAT performance areas and learn good practice. Many such ‘TADAT-trained persons’ do not undertake this with the intention of becoming TADAT assessors. This output also carries a weighting of 20%, and expectations have been exceeded, scoring an A+. Further detail on all the above outputs can be found in section B.

This document reviews the extent to which TADAT, at the point of programme completion, has met expectations as described above, both as a programme and as a tool. The review process draws upon the monitoring framework put in place to support delivery and the evidence provided by stakeholders in line with this.

DFID has committed to funding the next phase of TADAT work, through the ‘Supporting IMF’ programme (project ID.: 300381), so this document makes a number of recommendations to shape the continued engagement with TADAT over the coming years.

Summary of Recommendations

The TADAT Secretariat should consider how best to give a voice to lower-income country officials, to foster a more inclusive approach to the design, strategic focus and management of TADAT. (See p. 5)

There should be an examination of the various relevant diagnostic tools to ensure donors can avoid double-funding similar tools, and to reduce the risk of conflicting advice being issued to developing countries. This could be done by the Platform for Collaboration on Tax. (See p. 10)

Clear targets and an upper limit to the number of trained TADAT assessors should be established in order to achieve good value for money and reduce the risk of a surplus of underutilised assessors. (See p. 8)

TADAT should develop a pre-TADAT assessment of the motivations and expectations of countries requesting TADAT assessments. (See p. 9)

TADAT should explore ways to ensure that a country’s performance assessment review (PAR) results are properly embedded in wider capacity development providers’ work and PCT support package. (See p. 9)

TADAT should explore how best to monitor and evaluate post-TADAT impact to capture impact on revenue authority strategic objectives, and to follow operational, legislative and policy reforms. The next mid-term evaluation exercise should take account of the qualitative impact of TADAT in recipient countries. (See p. 8)

# B: Detailed Output Scoring

The programme logframe for 2018 was revised substantively to align more closely with TADAT’s Results Framework and to remove outdated mobilisation indicators. The outputs that follow relate to 2018. A summary of the changes to the logframe can be found on page 11.

Output 1	TADAT is the preferred tax administration and performance tool globally
Impact weighting	60%	Impact weighting % revised since last AR?	Yes / (from 70%)	Output Score	A+

Indicators	Milestones (2018)	Achieved
1.1 Cumulative total number of TADAT assessments that are carried out globally (national and subnational).	70	71
1.2 Cumulative total number of TADAT assessments undertaken in low-income (LICs) and lower-middle income countries (LMICs).	35	41
1.3 Number of institutional groups and technical providers using TADAT.	All	All

This output seeks to measure the extent to which TADAT had been established as the most recognised and utilised framework for assessing tax administration performance. Indicators of this output as set out in the 2018 logframe assess TADAT’s performance on three levels: the number of assessments completed; the number of assessments completed in LICs and LMICs and the extent to which relevant stakeholders are using TADAT to inform delivery of their objectives.

Despite a slow start in terms of assessment numbers in its early years, the programme has met its expectations for this output, having completed 71 assessments over the life of the programme, two of which are repeat assessments. The total number includes 41 assessments in LICs and LMICs (58%). Of these 18 were completed in DFID countries, representing 25% of all assessments to date. Evidence of TADAT’s usage by all institutional groups and technical providers also meets expectations.

Evidence of assessments provided suggest 2018 was a stronger year than 2017 – a total of 20 assessments were conducted compared to 14 in the previous year. 2016 saw the same number of assessments completed as 2018, a greater number of which were done in LICs or LMICs (13 vs. 11). Use of TADAT by assistance providers was first monitored following recommendation in the 2017 annual review and therefore has no baseline or prior results; however, feedback suggesting all providers use TADAT supports the output having met its expectations.

Lessons identified this year linked to this output and recommendations for future programmes

As we can see on the graph above, TADAT assessments by countries in the lower-middle and lower-income brackets (58% of all assessments). Yet there appears to be more representation from higher-income countries in the management and design groups within the TADAT structure.

Although the TADAT framework is intended to simply provide a good, objective benchmarking tool, we need to ensure that the voices of those who benefit most from it (LICs/LMICs) are able to influence how the diagnostic is designed to ensure it provides the most useful benchmarking possible/ is easily accessible to these stakeholders.

In its initial design, the TAG, for example, had roughly equal numbers from high-income and lower-income countries, however if the proposal to include several new members from OECD countries passes at the next Steering Committee meeting, this will be thrown out of balance.

The TADAT framework was deliberately designed to measure performance of tax administration performance against standards that are within the reach of any tax administration and those to which they might aspire. The term ‘good’ rather than ‘best’ practice is used in TADAT documentation for this reason. Many tax administrations want to undergo a TADAT assessment simply to be able to use an objective framework to establish a baseline from which they can develop informed reform programmes. Therefore, it could be argued that representation on the TAG itself doesn’t matter.

However, balanced representation is important to ensure not only that TADAT remains the most relevant tool possible, but also to ensure that those countries which have most to gain from use of TADAT (LICs/LMICs) are able to provide feedback to keep TADAT an accessible tool.

Recommendation: We recommend that the TADAT Secretariat should consider how best to give a voice to lower-income country officials, to foster a more embedded inclusive approach to the design, strategic focus and management of TADAT.

Output 2	TADAT assessments are of a high quality and effective in identifying the relative strengths and weaknesses of tax administrations.
Impact weighting	20%	Impact weighting % revised since last AR?	N/A	Output Score	A

Indicator(s)	Milestones (2018)	Progress
TADAT is regularly maintained to include good practices that are tested, proven and applied by the majority of leading tax administrations.	Framework and Field Guide adapted to reflect evaluation recommendations	Delivered
Proportion of TADAT PARs selected for quality assurance that comply with the standards set out in the Field Guide.	All assessments	Met

The expectations of this output were met over the life of the programme. The TADAT framework has been developed within a context of continuous feedback and improvement based on lessons during delivery. This is evident in the development of recommendations and amendments forming elements of the design framework for the second phase of the TADAT programme. Discussions around new areas of consideration in the next phase of TADAT’s work represent examples of this approach to ongoing refinement.

Similarly, across the span of the programme all performance assessment reports (PARs – the final report following a TADAT assessment) were subjected to quality assurance reviews by the Secretariat as a standard element of the assessment process. Prior to sign-off of every assessment report, a draft is sent to the Secretariat for a review of consistency and quality. This has contributed to a high level of consistency in the quality of completed PARs and lends credibility to the tool.

Lessons identified this year linked to this output and recommendations for future programmes

As noted previously and linked also to this output indicator, we recommend that the TADAT Secretariat should consider how best to give a voice to lower-income country officials, to foster a more embedded inclusive approach to the design, strategic focus and management of TADAT.

Output 3	TADAT facilitates enhanced understanding by key stakeholders of international good practices in tax administration through training and impactful outreach activities
Impact weighting	20%	Impact weighting % revised since last AR?	N/A	Output Score	A+

Indicators	Milestones	Achieved
Cumulative total of trained TADAT assessors and team leaders	350	439
Extent to which TADAT outreach is significant and impactful at international, regional and country levels	Outreach activities continuously undertaken, evaluated and improved	Delivered

This output has been consistently met across the life of the programme. The TADAT programme has placed significant emphasis on training of assessors and officials in tax administrations in the TADAT framework. TADAT assessors and ‘TADAT trained persons’ undertake online or face-to-face training and are tested and certified.

Questions were raised at Steering Committee about the variance between the number of assessors trained and the proportion of this number who actually carried out assessments (300 vs 121 as of April 2018). The Secretariat explained the low relative cost of training assessors and the need to ensure availability of assessors to carry out assessments where existing assessors where not likely to be available. The value of tax officials being trained as being an asset to tax administrations was also discussed as a form of capacity building.

TADAT outreach has been outlined in successive editions of the programme’s newsletter and discussed at Steering Committee meetings. Examples include training, newsletters, website content, and presentations at conferences. Feedback from DFID country offices (Ghana and Rwanda) speaks positively of the professionalism and strong engagement of TADAT assessors and officials providing post-assessment support to countries.

Lessons identified this year linked to this output and recommendations for future programmes

Recommendation: While recognising that TADAT trained persons are an asset to their home revenue authorities when they are used as a source of good practice knowledge, training and outreach is the largest part of the TADAT budget and we recommend some clear targets and an upper limit to the number of TADAT assessors (perhaps weighted by region, population, etc.) as an effective balancing mechanism to achieve good value for money and reduce the risk of a surplus of undeployed or underutilised assessors.

Recommendation: TADAT should explore how best to monitor and evaluate post-TADAT impact to capture impact on revenue authority strategic objectives, and to follow operational, legislative and policy reforms. The next mid-term evaluation exercise should take account of the qualitative impact of TADAT in recipient countries.
# C: Theory of Change and Progress Against Outcomes

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

Impact Level

The expected impact of this programme was that developing country revenue authorities would be supported towards improved performance as a result of undertaking TADAT assessment and utilising that in their reform planning.

The indicators for determining improved performance are based on the results of repeat TADAT assessments; however, as repeat assessments are typically undertaken 4-5 years after the initial assessment, this places the timing of repeat assessments largely outside the life-span of this programme (two have been conducted to date). As mentioned on page 2, the use of repeat assessments is perhaps not the best indicator of TADAT’s success as a diagnostic tool, as this is largely outside the operational scope of the TADAT Secretariat, and has therefore been replaced in the next phase of our work with TADAT.

Mixed patterns are emerging from the two repeat assessments conducted thus far (Kosovo and Zambia). Common areas of improvement include: feedback from taxpayers to the tax administrations, stronger use of electronic filing of declarations/returns, and use of tax withholding methods. Areas of deterioration include: accuracy of the taxpayer registration database, timely filing of personal income tax and PAYE, tax debt/arrears management, and the investigation of suspected wrong-doing and maladministration. Uganda and Rwanda will have repeat assessments in February and April 2019 and the results will provide further insights.

The second phase of the TADAT programme is expected to include many more repeat assessments. The results of these repeated assessments compared to initial ones will provide evidence with which to measure the expected impact.

In summary there is not yet sufficient repeat assessment data to determine whether this impact target has been achieved. This does not constitute or suggest failure but, in this case, is a question of timing of available evidence, and this will be monitored through the next phase of the programme.

Outcome Level

At business case stage, the expected outcome of this programme was that TADAT assessments would improve knowledge of the performance of a country’s tax systems and facilitate discussion amongst stakeholders (country authorities, international organisations and donor countries), and be the basis for the setting of the direction of tax administration reform.

Using the indicators within the framework, evidence points towards the programme having met its expected outcomes. The Nov 2016 TADAT Survey Report indicated that the TADAT results are increasingly being used to refine tax administrations’ strategic and annual work plans. A repeat survey will be conducted in early 2019, the results of which should be available for publication by the June 2019 steering committee meeting.

Countries using formal TADAT assessment results to refine their tax administration reform plans are increasing—for example, Albania, Fiji, The Gambia, Ghana, Georgia, Guatemala, Kyrgyz, Liberia, Malawi, Malaysia, Namibia, Nigeria, Peru, Sierra Leone, Trinidad and Tobago, Rwanda, Sierra Leone, Tanzania (as well as Zanzibar at the subnational level), Uganda and Vietnam. The subnational entities of Brazil (Alagoas, Brasilia, Goiás, Rio de Janeiro and Sao Paulo) are being supported to implement reforms, based on assessment results, by the Inter-American Development Bank.

Regarding facilitation of dialogue among stakeholders, it is clear that TADAT is a driver of increased engagement among tax officials and providers of assistance. This dialogue insofar as it is more focused on the performance outcome areas (POAs) covered in TADAT assessments represents a qualitative shift in the nature of dialogue.

The convergence on standardised measures could be taken as a sign of progress where it drives more structured analysis of tax systems. However, to ensure TADAT is sensitive to developing country contexts, our recommendation is for a greater balance of representatives in the design and management of TADAT, and by ensuring follow up actions/programmes are sensitive to these issues going forward.

Feedback on the extent of reform activities points towards TADAT having significant impact on the direction of change in tax administrations that have undertaken TADAT assessments. While some feedback points directly to change being attributable to TADAT, in other cases it is not clear to what extent TADAT versus other drivers of reform is acting as the basis for dialogue. Anecdotal evidence from Ghana suggests TADAT is referred to in reform discussions, but at varying degrees of depth and quality.

Sufficient time has not yet passed to fully determine TADAT’s impact in improving tax systems of the countries undertaking assessments. Even with time, specific methodologies aimed at assessing the nature of reforms over time and the role of TADAT in realising change would need to be established in order to evaluate impact. The next mid-term evaluation exercise should take account of the qualitative impact of TADAT in recipient countries.

However, it should be remembered that TADAT is a diagnostic tool. In terms of impact, TADAT assessments should best be considered as useful for promoting discussion with the revenue authorities and ministries of finance, and with development partners about what the findings actually mean and what is driving them.

Recommendation: TADAT should explore ways to ensure that a country’s PAR results are properly embedded in wider capacity development providers’ (including DFID, IMF and World Bank) and PCT support packages.

Summary of the Theory of Change

The business case outlined the theory of change (ToC) as follows:
[TADAT] will allow standardised assessment that objectively measure tax administration performance and it will ultimately become the principal global assessment tool for evaluating the institutional performance of countries’ tax administrations. […]

TADAT assessments will be the basis for a dialogue between tax administrations and donors about reform priorities and the sequencing of tax capacity building projects. This dialogue will then provide the foundation for the development of reform strategies for a tax administration.

Repeated application of the assessments will provide information on the extent to which a country’s tax administration is improving as a result of post assessment responses by the government and donors.

Ultimately, the implementation and use of TADAT will mean more effective tax reform in developing countries, which will lead to higher tax revenues, better governance and provision of services to the public and less dependence on aid.

This Theory of Change has not been amended since the programme’s inception, and this logic still holds in the logical framework (logframe).

TADAT designed their own Results Framework, which is attached at Annex A. This covers similar areas to the DFID logframe and is reported against twice annually before each steering committee meeting (in Dec/Jan and Jun/Jul).

Note on the Underlying Assumptions in The Theory of Change

It is important to note that TADAT is a diagnostic tool- an assessment of a tax administration system at a point in time. Performance assessment reports (PARs) do not include a set of recommendations, so we cannot track progress in that way. Essentially, how a TADAT assessment is used by a country is currently only marginally within TADAT’s own scope to influence. TADAT assessments do, however, offer a good basis for tax reform discussions, and repeat assessments offer a way to monitor changes over time in a standardised way.

In the reports provided to DFID and other TADAT donors, there can at times be conflation between positive TADAT development (in terms of its own management, strategy and delivery) and the impact this has on output activity (the assessments and wider training and outreach work), and subsequently, whether this is beneficial for particular countries. There is an implicit assumption that TADAT development benefits recipients, which could be the case but is not explored. This does not take account of potential new/other diagnostics nor of the quality of fit for TADAT use in various countries.

Recommendation: We recommend therefore that there should be an examination of the application and use of various relevant diagnostic tools, such as the World Bank’s Tax Diamond, the OECD’s Maturity Model, and so forth, to ensure donors can avoid double-funding similar tools, and to reduce the risk of conflicting advice being issued to developing countries. This could be done by the Platform for Collaboration on Tax (PCT).

Key Changes to the Logframe in the Past Year

The 2018 logframe was amended to align more closely with the results framework used by the IMF and to strip out outdated indicators and targets. The table below outlines the key changes.

2018 Logframe			Previous Logframe (2016)	Reason for Change
IMPACT
TADAT contributes to strengthened tax administration systems and domestic revenue mobilisation efforts globally.	Impact Indicator	Extent to which TADAT-influenced reform programmes lead to improved tax administration performance in developing countries.	No change.	No change.
OUTCOME
TADAT assessments improve tax administration knowledge, and inform tax reform discussion and decision-making.	Outcome Indicator	Extent to which TADAT assessments facilitate dialogue about tax administration reform and directly influence donor programmes and tax administration reform plans.	No change.	No change.
OUTPUT 1
Preferred Assessment Tool: TADAT is the preferred tax administration diagnostic and performance assessment tool globally.	Indicator 1.1	Cumulative total number of TADAT assessments that are carried out globally (national and subnational).	1.1 Extent to which the assessment tool and the indicators are finalised	Mobilisation indicator. Now not relevant. / Number of total assessments included for context.
	Indicator 1.2	Cumulative total number of TADAT assessments undertaken in low-income (LICs) and lower-middle income countries (LMICs).	1.2 Extent to which management structure is in place	Mobilisation indicator. Now not relevant. / New 1.2 slightly reworded version of old indicator 2.1.
	Indicator 1.3	Number of institutional groups and technical providers using TADAT.	N/A	N/A. Not present in old logframe. / 1.3 added as per 2017 AR recommendation.
OUTPUT 2
Systemic Quality Assurance: TADAT assessments are of a high quality and effective in identifying the relative strengths and weaknesses of tax administrations.	Indicator 2.1	TADAT is regularly maintained to include good practices that are tested, proven and applied by the majority of leading tax administrations.	2.1 The number of assessments undertaken by TADAT in developing countries	Slightly reworded and moved to output 1 (1.2).
	Indicator 2.2	Proportion of TADAT PARs selected for quality assurance that comply with the standards set out in the Field Guide.	2.2 Number of TADAT assessments facilitated and funded by DFID	Removed as per 2017 AR recommendation.
	Indicator / 2.3		2.3 TADAT is recognised as the principle assessment tool for objectively assessing tax administration performance	Moved this indicator to output level as seemed at wrong framework level.
OUTPUT 3
Effective Dissemination: TADAT facilitates enhanced understanding by key stakeholders of international good practices in tax administration through training and impactful outreach activities	Indicator / 3.1	Cumulative total of trained TADAT assessors and team leaders	N/A	Added because this is a significant part of the budget and activity.
	Indicator / 3.2	Extent to which TADAT outreach is significant and impactful at international, regional and country levels	N/A	The efficacy of this work is at the heart of what DFID wants from TADAT, particularly in priority developing countries.

# D: Value for Money

All values are in GBP unless otherwise indicated. The TADAT Secretariat provides financial reports to DFID and all other donors in USD; where these figures have not been converted, this will be noted.

TADAT Funding by Financial Year - DFID only (GBP)

Financial Year	Committed	Disbursed	Variance
2013/2014	2,000	1,758	242
2014/2015	426,000	424,801	1,199
2015/2016	353,000	253,000	100,000
2016/2017	500,000	500,000	0
2017/2018	250,000	250,000	0
2018/2019	250,000	250,000	0
Grand Total	1,781,000	1,679,559	101,441

TADAT Funding by Financial Year – All Donors

Partner	Amount Pledged			Date agreement signed
	Currency 1		USD Equivalent
Germany	Euro	500,000	603,653 (6%)	December 16, 2013
Japan	USD	1,000,000	1,000,000 (10%)	June 5, 2014
The Netherlands	EUR	1,000,000	1,373,000 (13.6%)	December 11, 2013
Norway	NOK	10,000,000	1,312,142 (13.2%)	February 6, 2014
United Kingdom	GBP	1,775,000	2,383,780 (23.6%)	May 19, 2014
Switzerland	USD	1,250,000	1,250,000 (12.4%)	August 13, 2014
European Union	EUR	2,000,000	2,151,473 (21.4%)	October 8, 2016
Total signed and pledged			10,074,047
Revised Program Budget 2			10,074,047
1/ Received contributions in Euro, British Pound and Norwegian Krone are accounted for based on actual exchange rates. Exchange Rates as of April 30, 2018 are used for remaining contributions/pledges. 2/ Revised from original budget in Program Document of US$8,402,710.

Summary of Programme Budget

The TADAT subaccount received total cumulative pledges of US$ 10.1 million over 2013-2016. (The strength of the U.S. dollar compared to other currencies slightly eroded the value of the signed and pledged contributions -previous estimated total resources were US$ 10.3 million).

As of end-April 2018, cash inflows into the TADAT subaccount totalled US$ 8.5 million. Cumulative TADAT expenditure for fiscal years 2013/14 – 2017/18 to end-April 2018 (Years 1 – Year 5) totalled US$ 7.5 million. Outstanding pledges are currently being provided by TADAT partners.

Total expenditure during Year 5 (2017/18) was US$ 1.9 million or 86% of the endorsed budget of US$2.2 million. The slightly lower than expected expenditure outturn is a result of less-than-budgeted payment for the mid-term review, less use of short-term experts, and prudent financial management to align expenditure to the cashflow.

Value for Money (VfM) compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

The VfM proposition outlined in the TADAT business case was predicated mainly on TADAT’s low cost relative to PEFA while offering a similar framework of benefits specifically on revenue mobilisation. The business case states the following:

DFID will be able to monitor the Value for Money of TADAT through central donor monitoring tools and also as an end user, through its own tax programmes. DFID already has a good view of the Value for Money of the project through its close involvement in the running of the programme so far. As a TADAT partner (along with the IMF, the World Bank and other donors) the UK (DFID and HMRC) has worked to establish the objective and scope of the programme, defined the content of the tool and the criteria for its use and provided institutional support for its implementation.

DFID is able to monitor relevant information on the status of the TADAT Programme through the IMF’s Donor Gateway. The Gateway provides financial information, and will be a central repository of information on donor arrangements, including legal documentation, project documents, progress reports, project status and self-assessments. The trust fund will operate on results-based management principles in line with the IMF logframe which can be found in TADAT programme document. The TADAT Secretariat will report on results annually, following endorsement by the Steering Committee.

After three years of the operation of TADAT, an independent evaluation of the work under the trust fund will be conducted. External experts will assess the effectiveness of the work and formulate recommendations. The findings will inform discussions on operations for the remaining two years of the programme. DFID will also be able to monitor value for money as a member of the TADAT Steering Committee, which directs the operations of the programme. The Steering Committee meets annually and additional meetings may take place as needed. The UK has also supplied a technical representative, from HMRC, to sit on the technical advisory group (TAG), which provides ongoing technical advice and guidance to the TADAT secretariat, and can also act as another means for monitoring value for money.

IMF Value for Money Metrics

DFID subscribes to the IMF’s methodology for costs incurred in the delivery of this programme. This provides common benchmarking for DFID programmes that rely on IMF delivery. In 2016, the IMF developed a new Results Based Management (RBM) system, which substantially improved tracking the delivery of milestones, outputs and objectives, and provided the groundwork for an improved understanding of cost versus impact. In 2017, DFID agreed a set of VFM metrics to be reported annually across all DFID-funded IMF vehicles, including TADAT. At the time of this report, only figures for 2017 were available (table below).

Economy

The key cost drivers throughout the programme were training of assessors, salaries and related costs of assessors conducting assessments where relevant (mostly paid for by the requesting body for TADAT assessments), travel and subsistence payments. The frameworks for these costs are determined centrally at the institutional/corporate level for the IMF, rather than negotiated at the level of individual projects like TADAT. The UK exerts oversight of the IMF’s wage and expenses policies (as do other Board members) through its membership of the IMF Executive Board. The UK receives information on these costs via annual IMF papers entitled, ‘Administrative and Capital Expenses and Output Cost Estimates’ and ‘Output Cost Estimates and Budget Outturn Paper’.

TADAT Budget by Outcome - Phase I (USD)

Outcome Area	Total
Outcome 1: Preferred Assessment Tool / Framework development and maintenance, and research and outreach work streams.	3,821,339

Outcome 2: Effective Dissemination / Assessor accreditation and training, and stakeholder engagement and outreach work.	3,109,442

Outcome 3: Systematic Quality Assurance 1 / Monitoring and quality assurance, and external evaluation work streams.	1,048,317

Outcome 4: Assessments are impactful and facilitate a shared view of tax administration reform baselines and priorities by all stakeholders.	1,346,585

7% Thematic Fund Management Fee	652,798
Total	9,978,481

In terms of outcome spend versus original budget, the table above shows projected spend outturn of 9.98 million USD. This is in line with cashflow outturn of 10 million USD. Due to exchange rate variations, the Secretariat has been able to fit spending within the cashflow versus originally projected 10.4 million USD. Additional value has been realised through cost-effective spending particularly on translation/interpretation costs given the range of languages TADAT is operating under.
Source: TADAT Steering Committee Consolidated Binder, January 2019

Efficiency: From 2017, the efficiency of TADAT has been measured by two indicators:
1) Average cost of a capacity development day, that is, the average cost for TADAT staff to spend one day completing capacity development work (including fees, travel, accommodation and any other costs); and
2) Average cost of a participant day, that is, the average amount of expense required for an individual to receive a day of TA from TADAT.

As can be seen in the capacity development day table below, TADAT has the second-lowest cost per capacity-development day amount. In comparison to other IMF-based thematic funds conducting similar work therefore, TADAT is keeping its costs within reasonable VFM parameters.

In terms of cost of participant day, as we can see from the table below, TADAT has, by a wide margin, the lowest average cost per participant day. This shows good value for money in comparison to other DFID-funded IMF-based thematic funds.

Effectiveness: This is measured by the proportion of TADAT milestones / outcomes / objectives which are fully or largely achieved. Over FY2018, 100% of milestones targeted by TADAT were rated as completed, and some were exceeded.

It can be said that TADAT costs are in line with other IMF regional technical assistance centres, and that TADAT has taken active steps to reduce costs and improve efficiency of delivery. For example, the TADAT Secretariat stated in Steering Committee meetings that funds allocated to translate the TADAT Field Guide were not spent in light of more affordable options for translation being met. Greater attention is still needed to demonstrate whether TADAT has contributed to improvements in reform activity.

# E: Risk

Overview of programme risk during the past year and over the life of the programme

Overall risk rating: Minor/Moderate
Overall, the programme has represented only minor risks given the administrative nature of the programme, where the risks around demonstrating efficacy and Value for Money were the most relevant. Over the last year, the programme’s performance has been in line with expectations. All outputs identified within the 2018 TADAT logframe have been achieved or slightly exceeded, and evidence suggests the programme has achieved the desired outcome.

Overview of programme risk
The table below outlines the risks associated with the programme. These are carried forward from the 2017 annual review where risks remain relevant and assessments have been updated based on evidence and analysis undertaken as part of this review. New risks have been identified and are recommended to be incorporated into Phase 2 of the TADAT programme (see*).

Risks	Current Rating	Assessment 2018
The impact of TADAT on countries’ tax systems is not robustly evaluated.	Rating: Minor / Impact: Minor / Likelihood: Likely	We note TADAT is a diagnostic tool, but further follow-up work is needed to properly assess the impact TADAT assessments have on developing country revenue authorities and tax policies.
Tax authorities in TADAT countries have insufficient capacity to implement necessary reforms.	Rating: Major / Impact: Major / Likelihood: Possible	There are signs that TADAT countries are developing action plans/programmes with donor countries to implement reform. The risk remains that many countries do have the capacity to implement reforms but the risk will be mitigated as donors scale up resources through their ATI commitments. The extent to which donor support is effectively coordinated will influence the impact of increased support.
Too few assessments are carried out in DFID priority countries.	Rating: Major / Impact: Moderate / Likelihood: Possible	Several DFID priority countries have had assessments exceeding the target number within the logframe. However, the risk remains that the focus of TADAT undermines its integrity or does not take full advantage of its potential to support improved tax administration reforms.
Take-up of TADAT by developing country tax administrations is low.	Rating: Major / Impact: Major / Likelihood: Unlikely	The majority of assessments are in developing countries; however, uptake has reduced over the past year. Secretariat should continue to promote TADAT in developing countries. Donors (including DFID) should continue to promote in their countries.
Insufficient ownership of TADAT assessment by tax authorities within developing countries	New risk / Rating: Moderate	*The risk is around how developing countries interact with the process of the TADAT assessment/process. To mitigate this risk, it is important to clearly identify to beneficiaries what the benefits of undertaking a TADAT assessment are, ensuring that ‘change champions’ are involved in the process within local Revenue Authorities and capable/experienced Team leaders used. Furthermore, communication on the risks around revenue should continue to be communicated ahead of assessments, and the tool should continue to seek feedback, incorporating and improving the tool to capture the realities, tailoring, as much as possible, to different countries’ systems.
Donor countries are not engaged in TADAT assessments thereby diminishing their impact.	Rating: Moderate / Impact: Minor / Likelihood: Likely	There is a risk that TADAT assessments happen without the knowledge of donor country offices; to mitigate this, it is important that the Secretariat and donors reach out to country offices in advance, where it knows an assessment will take place. The potential development and uptake of Medium Term Revenue Strategies in developing countries will mitigate this risk as they will allow countries to take ownership of reform processes and provide a structure for all donors to engage with development of reform plans (including diagnostic).

Outstanding actions from risk assessment
Risks continue to be treated in line with the Risk Matrix. There are no outstanding actions from risk assessments. However, it is recommended that the DFID team continue to monitor the risks closely, in line with the second phase of the TADAT programme, and seek feedback from DFID country offices where assessments are being undertaken as much as possible.

# F: Delivery, Commercial & Financial Performance

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Performance of partnership (s)
The working relationship between the TADAT Secretariat and DFID is good; DFID attended Steering Committee meetings and was engaged in programme deliverables. The TADAT Secretariat noted that the governance structure in place over the past year has worked very well for the programme, and that the model used is being advocated for other IMF Trust Funds. DFID took up the role of Chair of the Steering Committee in mid-2018.

Asset monitoring and control
DFID is in regular contact with the TADAT secretariat. DFID receives annual account information about programme spend and monitors progress in the programme as a member of the Steering Committee.

Date of last narrative financial report	Jan 2019
Date of last audited annual statement	2018 Annual Report
IMF Quarterly Financial Reports	Quarterly Reports

# G: Monitoring, Evidence & Learning

Monitoring

Programme Completion Review
This review was carried out by an HMRC Tax Policy Adviser independently of the programme team, and quality-assured by the DFID Senior Responsible Owner (SRO). Evidence from reports on progress, together with supporting documentation, was provided by the implementing partners. The reviewer also interviewed DFID and HMRC staff who have had experience with TADAT as assessors and tax programmes within DFID country offices.

Monitoring progress throughout the review period
The programme sits within the Public Finance and Tax (PFTD) department at DFID. DFID monitors progress through its membership of the TADAT Steering Committee, which it currently chairs. An HMRC official has also attended TADAT Advisory Group (TAG) meetings.

The team monitored progress through:
- Bi-annual Steering Committee meetings
- Progress reports (narrative and financial)
- Regular engagement with the TADAT Secretariat

The secretariat also produced a bimonthly TADAT newsletter that was made available to the public on the TADAT website (www.tadat.org).

Evidence
Evidence was provided mainly in the form of narrative contained in programme reports. DFID annual reviews for each year of the programme, an external mid-term evaluation (commissioned by the Secretariat) and two independent surveys were also used to provide independent evidence of delivery, feedback and performance. The limitations of existing data to definitively assess the effectiveness of TADAT (impact) mean this level cannot be evidenced fully yet. There remains scope in the second phase of the Programme to address this in the M&E framework.

Overall, evidence supporting the meeting of expectations around outputs is overwhelmingly positive. In some TADAT reports, there were inconsistencies in statistics but this is largely down to various overlapping reporting periods. Similarly, feedback on the distribution of TADAT assessments across country classifications highlighted at times the need to focus on developing countries while in other areas it was emphasised that the TADAT tool is for both developed and developing countries.

Supporting evidence for outcomes and impact in line with the programme’s theory of change is by contrast less clear due to the timing of available evidence; the absence of repeat assessments and other forms of longitudinal evaluation aimed at identifying technical progress correlated with TADAT’s existence results in disproportional reliance on feedback around the delivery and take-up of TADAT’s methodology as opposed to the results of such activity on countries’ tax systems.

Learning

As noted earlier the TADAT programme has demonstrated significant focus on refining the TADAT tool and Field Guide to reflect learning through delivery and feedback. This has meant the Tool and its delivery has been refined over the life of the programme.

Progress on recommendations from annual reviews for this programme
Recommendation	Update
Logframe: It is recommended that DFID consult with the TADAT Secretariat on the suggested indicators to outputs 1 and 2 to reflect work being conducted by the TADAT Secretariat and better aligned to the TADAT Logframe: / Add indicator 1.2: TADAT is kept up-to-date with good practices that are tested, proven and applied by the majority of leading tax administrations. Target 2018: Position/guidance notes issued as necessary following approval by TADAT Steering Committee and Technical Advisory Group / Modify indicator 2.1: is recommended that DFID work closely with the Secretariat on agreeing a shared indicator outlining a) the total number of assessments it sets out to undertake and b) of those, how many are in developing in countries. / Add indicator 2.4: Number of institutional groups, and technical providers using the TADAT. Target 2018: All TADAT partners using the tool in assessments. / Add indicator 2.5: TADAT Secretariat ensures that assessments are of high quality. Target 2018: All TADAT Performance Assessment Reports go through certification process.	Completed. / The logframe has been comprehensively amended and updated. All the recommended indicators have been included.
Risks: It is recommended that some risks are revised, and new ones added, and that they be monitored quarterly by DFID. New Risks: / Insufficient ownership of TADAT assessment by tax authorities within developing countries / TADAT assessments do not respond to developing countries’ ways of working / DFID country offices and other donors are not engaged in TADAT assessments	Completed. / All recommended risks have been included in the risk register.
Value for Money / It is recommended that DFID works closely with the Secretariat, following the results of the Mid-Term Evaluation to assess the overall VfM of the programme, including a comparison of costs of similar tools. / It is recommended that the Secretariat conduct a VfM assessment to determine whether the cost and effort that they have put into training of assessors matches the demand that exists for assessors. This can either be done as part of the evaluation or by a quality assured Secretariat VfM assessment. / It is recommended that the Secretariat set out clearly to donors the rationale, purpose and value for money (including objectives of the project, costs and results etc.) of the development of e-TADAT and accompanying mobile application.	Completed. / In 2017 DFID and the IMF worked together to develop value for money metrics. This has now been implemented.

# Annex A: TADAT Results Framework