Department for International Development

Nigeria

Expansion of the State Accountability & Voice Initiative (SAVI) Programme

Business Case

        August 2012

Contents	Page number
Intervention Summary	5-7
Strategic Case	8-11
Need and context for DFID intervention	8-10
Impact and Outcome that we expect to achieve	10-11
Appraisal Case	11-18
What are the feasible options that address the need to set out in the Strategic case?	11-13
Assessing the strength of the evidence base for each feasible option	14-15
What are the costs and benefits of each feasible option	16-17
What measures can be used to assess Value for Money for the intervention?	17
Summary Value for Money Statement for the preferred option	17-18
Commercial Case – Direct Procurement	18-20
Clearly State the procurement/commercial requirements for intervention	18
How does the intervention design use competition to drive commercial advantage for DFID?	18-19
How do we expect the market place will respond to this opportunity?	19
What are the key underlying cost drivers? How is value added and how will we measure and improve this?	19
What is the intended Procurement Process to support contract award?	1
How will contract & supplier performance be managed through the life of the intervention?	20
Financial Case	20-22
What are the costs, how are they profiled and how will you ensure accurate forecasting?	20-21
How will it be funded?	21
How will funds be paid out?	21
What is the assessment of financial risk and fraud? / How will expenditure be monitored, reported, and accounted for?	21 / 21-22
Management Case	22-24
What are the Management Arrangements for implementing the intervention?	22
What are the risks and how will these be managed?	22-23
What conditions apply?	24
How will progress and results be monitored, measured and evaluated?	24
Annex / SAVI Logframe / SAVI Expansion summary / SAVI Economic Appraisal

Glossary

CBO	Community Based Organisation
CSO	Civil Society Organisations
DSA	Daily Subsistence Allowance
DFID	Department for International Development
DDIN	Deepening Democracy in Nigeria Programme
ENABLE	Enhancing Nigerian Advocacy for a better Business Environment Programme
ESSPIN	Education Sector Support Programme
FGN	Federal Government of Nigeria
GDP	Gross Domestic Product
GEMS	Growth and Employment in States Programme
GoN	Government of Nigeria
HMG	Her Majesty’s Government (UK)
IMEP	Independent Monitoring and Evaluation Programme
IRR	Internal Rate of Return
J4A	Justice for All Programme
LGA	Local Government Area
MDAs	Ministries, Departments and Agencies
MDGs	Millennium Development Goals
MDGs CGS	Millennium Development Goals Conditional Grant Scheme
M&E	Monitoring and Evaluation
MNCH	Maternal, New-born, Child Health Programme
MTSS	Medium-Term Sector Strategy
M4M	Mobilising for MGDs Programme
NGO	Non-Governmental Organisation
NPV	Net Present Value
NSRP	Nigeria Stability and Reconciliation Programme
PATHS2	Partnership for Transforming Health Systems Phase 2 Programme
PRRINN	Partnership for Improving Routine Immunisation in Northern Nigeria Programme
SAC	State Advisory Committee
SAVI	State Accountability and Voice Initiative Programme
SG	State Government
SLPs	State Level Programmes (UK)
SP	Service Provider
SPARC	State Partnership for Accountability, Responsiveness and Capability Programme
SPRM	State Peer Review Mechanism
SUNMAP	Support to Nigeria Malaria Programme
TA	Technical Assistance
ToC	Theory of Change
USAID	United States Agency for International Development
VfM	Value for Money
Intervention Summary

Title: Expansion of the State Accountability and Voice Initiative (SAVI) Programme

What support will the UK provide?
How much does the UK expect to provide? / The UK will provide an additional £10 million to the State Accountability and Voice Initiative (SAVI) programme. This will increase the total funding provided to SAVI to £31 million. / Period of Funding / The programme will now run for a period of 7 years (2008-2015) representing a one year extension from the original timeframe (2008-2014).

Why is additional UK support required?
What need are we trying to address? / More than 100 million Nigerians (64% of Nigeria’s 158 million people) live in poverty. In northern Nigeria, poverty rates are 77% and the current context is one of poor service delivery and little progress towards the Millennium Development Goals. Nigeria’s remaining poverty and underdevelopment are often attributed to poor governance. / Within Nigeria’s Federal system, State and local government are responsible for delivery of core public services and spend around 50% of the total budget. Effective spending at state level is essential for service delivery and poverty reduction. However, public resources are often mismanaged. / The mechanisms for Nigerian citizens to hold government to account for public spending and service delivery are often weak at state level. State Houses of Assembly often struggle to oversee the work of the executive and in proposing and passing legislation. Civil society and the media also have limited capacity to monitoring the work of government and to lobby and contribute to policy reforms. / What will we do to tackle this problem? / SAVI was designed as one of a suite of State Level Programmes (SLPs) to leverage improved governance, service delivery (health and education) and private sector development at state level. SAVI was set up in 2008 to start to strengthen mechanisms for Nigerian citizens to hold government to account, supporting State Houses of Assembly (SHoA), media and civil society. SAVI currently works in five focus states in a full-scale way (Kano, Kaduna, Jigawa, Lagos and Enugu). It was envisaged that the programme would expand and an inception phase has been conducted in the states of Katsina, Yobe and Zamfara since 2011. / The independent mid-term review in 2011 found that SAVI efforts have so far led to improvements in budget and policy processes in most SAVI states, as a result of civil society policy advocacy and budget tracking. For example, due to CSO efforts in Kaduna the government made a saving of N31billion (approx. £124million) for the 2010 Kaduna State budget. SAVI’s partner, the Lagos State Civil Society Partnership (LACSOP), successfully lobbied Lagos SHoA to increase the allocation for primary education in the 2012 budget by N1.15billion (approx. £4.6million). SAVI has also generated 17 advocacy partnerships which have successfully brought about 11 demonstrable changes in policy in response to public demand. / The rationale for expanding SAVI is: / DFID Nigeria’s Operational Plan, approved by Ministers in 2011, requires a scale-up of DFID’s work in Northern Nigeria. Seven of the 10 SAVI focus states (including 4 of the 5 new states) are in Northern Nigeria where poverty rates are 77%. / SAVI has been performing well and there are notable opportunities to achieve additional results. The extended programme will increase coverage of the population from 23% to 37%. / Expanding SAVI at Federal level will help leverage broader impact beyond the states SAVI is working to replicate successful lessons. / The additional year will allow SAVI to deepen engagement and results in all 10 states but also ensure the programme fits with the Nigeria electoral calendar (elections due in 2015). / The main proposed changes to the scope of the programme are to: / Expand geographic coverage to fully cover 10 states. This comprises: / Deepening the intensity of support in 5 existing states, / Scaling up in 3 states currently completing inception phase; and, / Setting up the programme in 2 new states which have progressive governments. / Add new areas of focus in response to updated political economy analysis and opportunities for reform identified in the mid-term review: / Growth sector, especially in engagement around youth employment and resulting insecurity; / Media strengthening; and, / Federal level work to help replicate lessons and lever broader impact. / Extend the implementation by one year to ensure newer states have enough time to deliver reforms and for all state programmes to better fit with the electoral cycle. / Who will be implementing the additional support we provide? / SAVI’s implementation is currently contracted out to a consortium of service providers led by GRM International Limited.
What are the expected results?
The impact of the intervention is expected to be the efficiency and effectiveness of selected state level governments’ use of public resources is enhanced. The programme outcome is State houses of assembly, civil society, media and citizens demonstrate more effectiveness in demanding better performance from government and holding government to account. / With additional funding and a one year extension, SAVI will strengthen state accountability mechanisms and achieve the following specific additional results: / passage and implementation of at least 7 more key pieces legislation that underpins good governance; / 20 more demonstrable changes in policy and implementation (linked to improving service delivery and attainment of MDGs) by state government; / 10 demonstrable changes in growth-related policy and implementation; and, / improved quality of media coverage of state budgets and policies. / What will be the approach to monitoring and evaluation? / SAVI’s performance will be assessed by internal monitoring of the programme and external scrutiny. The Independent Monitoring and Evaluation Programme (IMEP) provides independent monitoring and evaluation of the SAVI programme through annual and mid-term reviews. IMEP will also conduct an end of project evaluation.

Strategic Case

A. Context and need for a DFID intervention / More than 100 million Nigerians (64% of Nigeria’s 158 million people[1]) live in poverty. Nigeria has a quarter of Africa’s extreme poor, 10% of the world’s children out of school, 10% of child and maternal deaths and 25% of global malarial cases. Nigeria’s human development indicators are worse than comparable lower middle-income countries[2]. In northern Nigeria, poverty rates are 77% and the current context is one of poor service delivery and little progress towards the Millennium Development Goals. / Poor governance is a major challenge and contributes to these poor development statistics. Thirty years of military rule and dependence on oil revenues has weakened the social contract in which government is accountable and responsive to citizens. Although oil provides Nigeria with disposable income, public resources are often mismanaged and corruption remains widespread. / Within Nigeria’s Federal system, State and local government are responsible for delivery of core public services and spend around 50% of the total budget. Effective spending at state level is essential for service delivery and poverty reduction. However, the various mechanisms for Nigerian citizens to hold government to account are particularly weak at state level. The state legislature is seen as a ‘rubber stamp’ for the Governor. Civil society and the media still lack both the capacity and the resources they need to truly engage with government and advocate for change. All are rarely accountable to the people themselves. These factors contribute to a generally weak state of governance with limited ability of citizens to claim rights. The result is poor service delivery and little progress towards the MDGs. / Why scale up SAVI? / SAVI was designed as one of a suite of State Level Programmes (SLPs) to leverage improved governance, service delivery (health and education) and private sector development at state level. SAVI was set up in 2008 to start to strengthen mechanisms for Nigerian citizens to hold government to account, supporting State Houses of Assembly (SHoA), media and civil society. SAVI currently works in five focus states in a full-scale way (Kano, Kaduna, Jigawa, Lagos and Enugu). It was envisaged that the programme would expand and an inception phase has been conducted in the states of Katsina, Yobe and Zamfara since 2011. / The independent mid-term review in 2011 found that SAVI efforts have so far led to improvements in budget and policy processes in most SAVI states, as a result of civil society policy advocacy and budget tracking. For example, due to CSO efforts in Kaduna the government made a saving of N31billion (approx. £124million) for the 2010 Kaduna State budget. SAVI’s partner, the Lagos State Civil Society Partnership (LACSOP), successfully lobbied Lagos SHoA to increase the allocation for primary education in the 2012 budget by N1.15billion (approx. £4.6million). SAVI has also generated 17 advocacy partnerships which have successfully brought about 11 demonstrable changes in policy in response to public demand. / The rationale for expanding SAVI is: / DFID Nigeria’s Operational Plan, approved by Ministers in 2011, requires a scale-up of DFID’s work in Northern Nigeria. Seven of the 10 SAVI focus states (including 4 of the 5 new states) are in Northern Nigeria where poverty rates are highest. / SAVI has been performing well and there are notable opportunities to achieve additional results. The extended programme will increase coverage of the population from 23% to 37%. / Expanding SAVI at Federal level will help leverage broader impact beyond the states SAVI is working to replicate successful lessons. / The additional year will allow SAVI to deepen engagement and results in all 10 states but also ensure the programme fits with the Nigeria electoral calendar (elections due in 2015). / The main proposed changes to the scope of the programme are to: / Expand geographic coverage to fully cover 10 states. This comprises: / Deepening the intensity of support in 5 existing states, / Scaling up in 3 states currently completing inception phase; and, / Setting up the programme in 2 new states which have progressive governments. / Add new areas of focus in response to updated political economy analysis and opportunities for reform identified in the mid-term review: / Growth sector, especially in engagement around youth employment and resulting insecurity; / Media strengthening; and, / Federal level work to help replicate lessons and lever broader impact. / Extend the implementation by one year to ensure newer states have enough time to deliver reforms and for all state programmes to better fit with the electoral cycle. / Link with Nigerian Government and DFID Strategic priorities / The SAVI programme in line with the Nigerian Government’s Seven Point Transformation Agenda and Vision 2020, which emphasizes key governance areas as priorities, including the rule of law and combating corruption. The programme also aligns with the joint donor Country Partnership Strategy 2010 -13 for Nigeria which sets out improving governance as a core and cross-cutting theme. SAVI’s activities are in support of the priorities set out in the DFID Nigeria Operational Plan 2011-2015 with an emphasis on scale-up plans for the North. Further SAVI has strong links and works with other DFID programmes as part of a complementary suite as shown in Fig 1. / Fig 1: Related DFID Programmes / Legend: / SPARC – State Partnership for Accountability, Responsiveness and Capability / SAVI - State Voice and Accountability Initiative / PATHS2 – Partnership for the Transformation of Health Systems (Phase 2) / ESSPIN – Education Sector Support Programme in Nigeria / GEMS – Growth and Employment in States / How does SAVI make a contribution to addressing conflict and/or fragility? / There are long standing political and economic grievances in Nigeria that can lead some of the population to seek radical alternatives. One of these grievances is the perception that state systems are corrupt and unfair. SAVI helps to address this concern by supporting moves towards more accountable and democratic governance. SAVI through its partners and the State Houses of Assembly engage with affected communities and this can contribute to defusing the drivers of discontent. The programme has already engaged with DFID’s Nigerian Stability and Reconciliation Programme (NSRP) and will endeavour to collaborate on supporting local partners to tackle the issue of inter-communal conflict through advocacy related activities. Such activities have already been piloted in Kano (after the 2011 election violence), and are being planned in Kaduna. Where the need and opportunity arise in others states, similar activities may be undertaken. / SPARC supports State public finance and administration / reforms, and assists central ministries / ESSPIN / supports State education planning and resource use & drives reforms / PATHS2 / supports State health planning and resource use & drives reforms / SAVI – Provides support to civil society and media groups across all four programmes, and also to State Houses of Assembly, to increase demand, transparency and accountability for service delivery and citizen’s rights. / GEMS / supports / State business climate reforms and growth sectors (value chains)
B. Additional Impact and Outcome we expect to achieve / The impact of the intervention is expected to be the efficiency and effectiveness of selected state level governments’ use of public resources is enhanced. The programme outcome is State houses of assembly, civil society, media and citizens demonstrate more effectiveness in demanding better performance from government and holding government to account. / The programme aims to deliver the following 5 outputs: / 1 Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy and monitoring; / 2 Civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes; / 3 More open and inclusive communication and improved understanding between citizens, civil society, the media, State Houses of Assembly and government. / 4 Improved state houses of assembly systems for transparency, public engagement and financial oversight; / 5 Lessons routinely identified and other development partners take a more sustainable approach to strengthening voice and accountability. / With additional funding and a one year extension we expect SAVI to have the following results: / For the 5 existing lead states: Kano, Kaduna, Jigawa, Lagos and Enugu, (total population: approx. 32.3 million – 23% of national total), working in partnership with the full suite of SLPs (SPARC, ESSPIN, PATHS2 and GEMS) – intensifying efforts and extending them by one additional year will result in further improvements in governance reforms already being targeted by the programme including: / further progress on the passage and implementation of 10 key pieces of legislation relating to good governance / 10 more demonstrable changes in policy and implementation linked to improving service delivery and attainment of MDGs – covering at least 3 sectors: health, education and growth in the majority of states. / For the 3 “inception” northern states: Zamfara, Katsina and Yobe (total population: approx. 11.4 million – 8% of national total) – scaling-up to a full state programme with much wider scope and one additional year means the expectation has significantly changed from one of ‘exploratory engagement’ to delivery of similar results to those expected in the 5 existing lead states including: / further progress on the passage and implementation of 6 key pieces of legislation relating to good governance / 6 more demonstrable changes in policy and implementation linked to improving service delivery and attainment of MDGs – covering at least 3 sectors: health, education and growth in the majority of states. / For the 2 proposed “more progressive” new states: Anambra and Niger (total population: approx. 8.1 million – 6% of national total) – initiating a full programme for 2½ years in states where SAVI has had no previous engagement, aiming to fast-track midterm results equivalent to those achieved in the 5 existing lead states after 3 years. / Through strengthening of federal-state linkages, the results of SAVI’s engagement with state houses of assembly and the media in all 10 lead states will be extended to a number of non-lead states through national platforms and regional networks. For example: wider public awareness and engagement in budget scrutiny across the nation through engagement of regional and national media houses in state level advocacy partnerships with civil society for making strategic use of evidence on budget performance from a range of sources (such as ‘open budget index’ surveys, state citizens perception surveys, state government’s own self-performance assessments and the Nigerian Governors Forum’s peer review mechanism). / Detailed quantification of the results described above can be found in the attached SAVI logframe at Annex 1 which has been endorsed by the Independent Monitoring and Evaluation Programme (IMEP). A summary of key additional results in comparison to additional resources is provided in Annex 2. / How will we determine whether the expected results have been achieved? / Impact, outcome and output indicators will be monitored throughout the lifetime of the programme by IMEP. Data will be obtained through routine programme monitoring tools and processes. An Independent mid-term review has been conducted and informed this proposed scale up. Further an end-point evaluation of the programme will be carried out. Both the review and evaluation assess the overall impact effectiveness, cost efficiency and economy achieved, and test assumptions underpinning the theory of change.
[1] See UN Population Division’s World Population Prospects: 2010 revision and Nigerian Living Standard Survey (NLSS), NBS & World Bank, 2006.
[2] All figures are from the “Gender in Nigeria Report 2012”, British Council, May 2012.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The options considered in the appraisal are: / Option 1: Alternative use for resources (do nothing) / The counterfactual is to ‘do nothing’ and invest resources in an alternative programme or not at all. Under this scenario SAVI would continue with the programme’s original resource allocation of £21million and a scale-up of funding and an additional year’s extension would not occur. / Option 2: Scale-up of SAVI in 10 states / DFID expands SAVI programme funding by £10 million, bringing the total to £31 million. This will be undertaken by deepening engagement in the 5 existing states (Jigawa, Kaduna, Kano, Enugu and Lagos) and scaling up the whole programme in another 5 states (Niger, Anambra, Katsina; Yobe; Zamfara,) and extending the programme by 1 year to 2015. / Considered and discarded Option / A third possible option would be to tender for a new State level accountability programme. This option was discarded due to i) the strong overlap between SAVI’s work and potential duplication of work in any new programme: ii) the fact that SAVI has considerable experience and contacts at state level in Nigeria and has achieved results in the areas to be addressed; iii) staff resources not being available to identify, design and manage additional programmes; and (iv) it would delay expansion by 18 months. / Theory of Change / The SAVI programme’s intervention logic consists of three inter-related components: / implementation of strategically aligned, mutually reinforcing activities under each Output by local partners with facilitative support from the programme; / the development of effective partnerships for improving voice and accountability within and between each Output; and, / the facilitation of this through a stepped-down process of empowerment. / SAVI’s approach to facilitating each stage in the process, requires building local ownership, sustainability and replicability into the approach to demonstration from the very outset, i.e. an ‘exit strategy’ that starts on day one, fostering a mind-set of ‘diminishing dependency’ on SAVI over the lifespan of the programme. This requires putting local partners in the driving seat, building on existing local capacity through the formation of local partnerships and pooling of local resources – human, financial and technical – supplementing only where necessary and helping them to overcome the constraints they face in project implementation. / To ensure that local ownership, sustainability and replicability remain guiding principles throughout the process, SAVI provides support to local partners in the form of capacity building that serves to ‘empower’ them by highlighting and harnessing their collective potential. The role of the programme is restricted primarily to promoting strategic thinking and planning by partners, brokering constructive relations, catalysing appropriate action and supporting ‘learning by doing’ together (action learning/ research). Where technical inputs are required these are mostly provided through behind-the-scenes ‘mentoring’: i.e. the stepped-down transfer and contextual adaptation of knowledge and skills from programme advisers to staff, staff to local partners, and local partners to other key stakeholders. / Theory of Change in Practice (see diagram below) / Putting this theory into practice starts with the programme identifying and engaging local partners – key individuals and groups in civil society, media and state houses of assembly committed to and potentially capable of improving voice and accountability. Through a variety of inputs (e.g. organisational skills) partners are supported to get their own respective houses in order before seeking the support of one another. The programme guides them through a process of partnership formation, situational analysis, consensus building, objective setting, capacity self-assessment, workplanning & budgeting, strategic planning, monitoring & reflection, and key skills acquisition through local networking & active learning to demonstrate that they are inclusive, responsive and accountable to citizens of their state. / Building on the credibility gained from this initial engagement, SAVI then supports them to overcome the main barriers and establish good working relations between civil society, media and the state house of assembly. This comes mainly in the form of behind-the-scenes support to broker relations, strengthen their partnership and strategize their advocacy, to demonstrate that they can effectively work together in support of each other on behalf of their state’s citizens. Partners are then supported to capitalise on these relations and their increased public credibility this gains them, to overcome the barriers to a more constructive engagement with government – actively supporting state government to demonstrate its responsiveness and accountability to citizens through changes in policy and implementation in response to public demand in key sectors (primarily health, education and growth), as well as the passage and implementation of key legislation that underpins good governance. / Partners are then encouraged by SAVI to further capitalise on their successes, to consolidate their achievements, sustain their approach and support its replication by others with additional behind-the-scenes support to strategize the process of replication towards generating a ‘critical mass’ of effective partnerships facilitating participatory governance. Finally, the programme focuses partners’ attention on linking all these successful demonstrations and replications together, through central networks, platforms and agencies, to institutionalise this new way of working with government. / Serving as entry points/vehicles for facilitating this process of change, above, SAVI provides this supports to partners through a number of mutually supportive broad areas of activity: / Issue-based policy advocacy and monitoring through civil society (CS) partnerships; / Facilitating public involvement in government budget and planning processes through CS partnerships; / Strengthening the role of the media in V&A, promoting gender & social inclusion and improving communication and understanding between citizens, CS, media, SHoA and government; / Strengthening the role of SHoA in V&A – improving their systems for transparency, public engagement (constituency relations) and financial oversight of government; and / Advocating SAVI and its local partners’ approaches to other development partners to promote synergy and replication. / These all come together in the course of demonstrating the partnership approach, each one effectively reinforcing the achievement of the other, the final product of which – a more inclusive, open and responsive form of governance – is far greater than the sum of each individual part.
B. Assessing the strength of the evidence base for each feasible option / The options are whether or not to provide State Accountability and Voice Initiative (SAVI) with additional funding of £10 million to fully cover 10 states. / Option 1: Alternative use for resources (do nothing) / Under this scenario SAVI would continue to operate until 2014 with a full programme in the 5 initial states (Enugu, Jigawa, Kaduna, Kano and Lagos) and a scaled down programme in 3 other states (Katsina, Yobe and Zamfara). It is expected that SAVI will achieve the results agreed in the original SAVI programme logframe. However, our assessment is that if nothing is done, it would adversely affect DFID Nigeria operational Plan commitments to support Northern Nigeria. For instance SAVI would not be able to work on removing the governance blockages faced by other DFID programmes to improve education and health outcomes of the poor particularly women and girls. This would hold back our support for Nigeria to make progress on the MDGs. / Additionally, other DFID programmes are establishing a presence in the same states as SAVI. A lack of additional funding would mean that planned linkages with these programmes would be lost. Further benefits that would be missed include: / Greater momentum to achieve results – increasing the likelihood of reaching a ‘critical mass’ of demand for governance reforms – in the 5 existing lead states. / Increased time and resources for engagement and delivery of key results from work with state houses of assembly, the media and sectors beyond health in the 3 new northern state offices. / Engagement with 2 new progressive states – further increasing the potential for greater scale-up of results and providing a mechanism to balance the risk of not being able to work on the ground in the northern states if the security situation there gets worse in the longer-term. / Enhanced engagement in the ‘growth’ sector in all states to address problems of youth employment and resulting insecurity. / More work on ‘media development’ to strengthen their role in V&A in all 10 states beyond improving their relations with CS, SHoA and citizens. / Ability to support transition from the present administration to the next (post 2015 national elections) with state houses of assembly in all 10 states and with the 6 outgoing (second-term) state governors looking to leave a legacy. / Option 2: Expansion of SAVI to fully cover 10 states / The preferred option is to provide SAVI with £10 million additional funding so that the programme can be extended until 2015 and reach 5 additional states. Under option 2, there will be a quick scale-up of SAVI activities in response to emerging opportunities for additional results. / SAVI has performed well so far, as noted in the independent mid-term review (MTR). A lot has been learned from the MTR to drive improved performance even further going forward. The MTR found that SAVI has been particularly successful in demonstrating a replicable and sustainable approach to issue based policy advocacy and monitoring. SAVI has succeeded in bringing together civil society organisations into partnerships that are increasingly capable of engaging in effective policy, advocacy and monitoring. It also complements other state-level programmes, particularly State Partnership for Accountability, Responsiveness and Capability (SPARC). / Highlights of the results delivered to date include: / Progress on improving the functionality of State Houses of Assembly as agents of voice and accountability demonstrated by the passage and implementation of key legislation relating to good governance - fiscal responsibility bill, public procurement bill, freedom of information bill, house service commission bill. For example in Lagos, all 4 bills have now been passed and signed into law and are in the process of being implemented and in Jigawa and Kaduna Fiscal responsibility legislation has been passed signed into law and given budgetary provision. / The passage of the Public Procurement Law in Enugu as a result of SAVI’s and SPARC’s intervention will potentially save more than N580million (£2.3million): >10% of the total capital budget of Enugu per annum through better procurement. / Progress in improving the functionality of civil society (including the media) as agents of voice and accountability. For instance in Kaduna civil society intervention led to a book-saving of N31billion (approx. £124million) on the 2010 Kaduna State budget and in Lagos an increase in the allocation for primary education in the 2012 Lagos State budget by N1.15billion (approx. £4.6million). / 11 changes in policy and implementation judged to be in part attributable to SAVI's work. These include: in Enugu deployment of more staff to primary health centres; in Kano: new legislation for decentralised water management ;and, in Jigawa: the Free Maternal and Child Health Bill at Second Reading and a scaled-up state response to shortage of female personnel in health and education sectors. / In addition, an extension of the programme will enable DFID to reach 37% of the population rather than 23% covered during the first phase. 7 of the 10 states SAVI will operate in (including 4 of the 5 new states) are in Northern Nigeria, where 77% of Nigeria’s poor live. / Rating the quality of evidence for each option (Strong, Medium or Limited) / Option Evidence rating / 1 Medium / 2 Medium / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / The environmental screening was completed as a part of the original programme approval. There is no evidence to suggest that the proposed programme will place a significant additional impact on the environment or climate change. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C

C. What are the costs and benefits of each feasible option? / Rational for Intervention / The development rationale for a voice and accountability programme is that enabling people to have a stronger say in decisions about policies and the distribution of resources potentially increases poor people’s access to the services and resources they need for their own development.[3] This should lead to better development outcomes. There is currently limited ability of citizens to claim rights and hold Government accountable in many Nigerian states. Accountability, responsiveness and capability of state government in the use of public resources to provide basic public services are general weak. / The economic analysis is judged against the do nothing counterfactual. The benefits are assumed to be additional to any other benefits flowing from earlier streams of SAVI. A detailed summary of costs and benefits are presented below in Table 1. / Table 1 – Costs and Benefits / 2012/13 2013/14 2014/15 2015/16 2016/17 / Costs / DFID Spend £800,000 £1,400,000 £5,400,000 £2,400,000 - / Discounted Spend £800,000 £1,272,727 £4,462,810 £1,803,156 - / Benefits / Enugu - £609,110 £553,736 £503,397 £457,633 / Jigawa - £776,671 £627,210 £627,211 £570,192 / Kaduna - £1,453,088 £1,453,090 £1,453,087 £1,320,988 / Kano - £900,287 £818,443 £744,039 £676,399 / Lagos - £3,646,070 £3,622,308 £3,697,007 £3,360,915 / Katsina - £2,168,853 £1,971,685 £1,792,441 £1,629,492 / Yobe - £1,414,113 £779,256 £795,836 £723,488 / Zamfara - £1,016,034 £1,016,018 £1,016,003 £923,639 / Anambra - £758,697 £689,725 £627,023 £570,021 / Niger - - - - - / Total - £12,742,925 £11,531,471 £11,256,044 £10,232,767 / Benefits are all shown discounted at 10% / However, given the uncertainty around monetising the benefits of the project a thorough sensitivity / The base scenario presents a Net Present Value (NPV) of £37,424,513 and a Cost- Benefit Ratio (CBR) of 4.58. However, given the uncertainty around monetising the benefits of the programme a thorough sensitivity analysis is presented in Table 2. / Table 2 – Sensitivity Analysis / Scenario NPV BCR / 1) Actual budget is only 75% of forecast £23,241,391 3.28 / 2) Actual budget is only 50% of forecast £14,840,662 2.19 / 3) Actual budget is only 25% of forecast £2,439,934 1.4 / 4) Scale up in 5 existing states has no impact £8,304,954 2.16 / 5) Scale up in 5 existing states only has 50% of expected impact £20,973,536 3.85 / 6) Programme in 2 new states has no impact £31,237,151 4.12 / 7) Actual budget is only 50% of forecast and scale up in 2 new states has no impact £172,079 1.08 / 8) Actual budget is only 50% of forecast and scale up in 3 pilot states has no impact. £5,910,272 1.46 / The cost benefit analysis and sensitivity analysis provide a strong case for supporting this project. Additionally given the uncertainty around some of the returns, the conservative nature of the analysis ensures there is a large margin before the appraisal becomes misleading. Scenarios 1-3 act as catch all scenarios which can encompass lower actual budgets as well as lower than expected impact on state budgets. For the purposes of the appraisal we have assumed annual returns of 0.5 per cent or 0.25 per cent, however, if the returns were half of this the project would still represent good value. / Using the most complete forecast for all states (2012) the project would have to improve budget efficiency by 0.23 per cent over 4 years to break even. / Given the uncertain impact of scaling up the project in the 5 existing states scenarios 4-5 serve to test the levels the returns would have to fall to before compromising the value of the project. Scenarios 6-8 provide similar assurance for the 3 states where full scale up will be applied and the two new states. / Balance of Costs and Benefits / The cost benefit analysis and the sensitivity analysis provide a compelling case for funding the expansion of SAVI. The base scenario provides a return of almost 4.4 times the initial investment. Additionally the mid-term review of SAVI provided a number of high impact outcomes that are attributable to the programme. Additionally there are a number of benefits that cannot be monetised or quantified. A strong well organised civil society able to hold government and state houses accountable will have a number of other benefits as well as improved budget allocation and efficiency. / The full economic appraisal is attached as Annex 3
D. What measures can be used to assess Value for Money for the intervention? / We will carefully track SAVI’s progress in each component against results and milestones in the logframe as an overall guide to whether expected benefits are being achieved. This will include: / Evidence of the economy of inputs being sourced through SAVI procurement systems / Justification of management costs and further negotiations during contract amendment stage / Monitoring of output levels against agreed results framework / Focusing on key case studies where the project has demonstrable impact.
E. Summary Value for Money Statement for the preferred option / The Mid Term Review found that SAVI offers good value for money at each of the three levels of economy, efficiency and effectiveness. There were indications that SAVI has been able to deliver its outputs in an economical and cost-efficient manner. / We are confident that SAVI continues to offer good value for money. The following examples provide evidence of actual impact to date of SAVI’s approach: / Know Your Budget (Kaduna) – SAVI spent £6,700 on a series of activities in support of a budget tracking CS partnership which called ‘Know Your Budget’. The interventions of this group led to a more credible 2010 Kaduna State budget and a book-saving of £124 million. / Lagos State Civil Society Partnership (LACSOP) – SAVI spent £6,000 over the course of more than 2 years on a series of activities aimed at strengthening the partnership. The partnership successfully lobbied Lagos SHoA to increase the allocation for primary education in the 2012 Lagos State budget by £4.6 million. / Project Monitoring (Jigawa) – SAVI spent £6,000 on 2 trainings on budget tracking and project monitoring. The Babura Patriotic Movement discovered unauthorised variation from a public works contract leading to the arrest of the culprits and a saving of £2.5 million for the Jigawa State Government. / Public Procurement Law (Enugu) – SAVI and SPARC spent £12,800 to support of CS groups to influence the passage of the Public Procurement Bill. When implemented, Enugu state government will save > £2.3 million per annum through better procurement. / The extension of SAVI represents good value for money, not only because of the projected return of almost 4.4 times the initial investment but also because it is building on already existing infrastructure and relationships, meaning it will benefit from economies of scale. The initial SAVI proposal had the potential to reach 23% of the Nigerian population for £21,000,000, or £913,043 per 1% of the population. For an additional £10,000,000 SAVI has the potential to reach 37% of the Nigerian population or £714,285 per additional 1% of the population reached. / On the management side, numerous cost savings have been identified in the scale up. For example The ratio of use of national long term-TA to use of international short term-TA will increase further to 88.3%:11.7% of the TA budget. Further, 88% of the additional budget will go to frontline delivery compared to 12% spent on admin costs. / Additionally SAVI is one of a number of complementary projects that all act to reinforce one and other, which should generate greater and more sustainable returns than a stand-alone project. As well as scaling up into additional states, the extension of SAVI will also deepen engagement in all 10 states. This means that for an approximate 48% budget increase, not only are the number of full programme states doubling from 5-10 (i.e. 100%), but the scale of key results is roughly increasing by 100%.
[3] McGee, R. and Gaventa. J. (2011) ‘Shifting Power? Assessing the impact of transparency and accountability initiatives.’ IDS Working Paper no. 383.

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / The procurement process has already been undertaken through competitive open tendering in accordance with the EU Public Procurement Directives. The scale-up is within EU guidelines which specify that contracts awarded can be increased by up to 50% before they need to go out to tender again. In these circumstances, extending the contract with the existing supplier makes better value for money unless poor performance dictates a change of supplier is required.
B. How does the intervention design use competition to drive commercial advantage for DFID? / It does not. Instead, better value would be obtained by negotiating an extension to the current supplier’s contract. This judgement is based on: / the supplier’s performance so far; / the real and opportunity costs – and the time taken – that would be incurred in returning to the market and potentially “changing horses in mid-stream”; / and the reality that unless it were common knowledge within the relevant market that SAVI’s performance was below par, few if any other potential service providers would judge the cost of bidding to be worth it, because we would be unlikely to make a change at this juncture in the life of the project.
C. How do we expect the market place will respond to this opportunity? / Not applicable. We are recommending extending an existing contract. / We know GRM will welcome the opportunity to extend the SAVI contract Negotiations will offer a single tender route highlighting the immense ‘goodwill’ value for GRM’s portfolio if successfully executed. PrG will negotiate any revision to existing fees in the context of the significant incentive for it and a single tender opportunity without competition. / GRM will raise increasing security costs, particularly as scaling -up into some new states carries new or increased risks.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Consultancy fee rates, where the specific factors are levels of responsibility, duration of engagement, difficulty of the post, credentials and CV and past performance, unique issues related to the market position of each professional group, and regional or local market factors for national consultants; / Direct consultant overhead costs relating to the provision of a consultant (e.g. medical insurance, visas, etc.) / Indirect overhead costs. These will include amounts within each fee to contribute to the costs of being in business, such as corporate operations, managed costs, recruitment, back office administration, headquarters, Nigerian office, etc.) / The profit margin. / Our ability to influence the cost drivers is limited, although we have made progress in the past year in strengthening our negotiating position with our key suppliers. But living costs in Nigeria are high, and while insecurity continues, these become higher factors and a major driver of consultancy costs, as is the perception of Nigeria as a difficult environment to operate in. / Many of the results expected in the extension period involve high level policy change, and in some cases legislative change. In this context the experience and effectiveness of key consultants is paramount. Value for money is not driven simply by least cost, but by the best ratio of effectiveness to cost, and this has to be assessed on a case by case basis. Whenever interventions are not delivering the expected results, and we assess that this is due to the limited effectiveness of individual consultants, we will either agree personnel changes or discontinue the intervention.
E. What is the intended Procurement Process to support contract award? / We will liaise with PrG to write to SAVI seeking a proposal for an extension to the existing contract, and emphasise that we are looking for a revision that reflects the factors set out above in section C. Once we have this we will meet to negotiate an outcome. Our emphasis will be on obtaining improved value for money for both parties, without unduly delaying the process of the next phase of work.
F. How will contract & supplier performance be managed through the life of the intervention? / We will continue the quality-focussed approach so far deployed, but will seek GRM’s interest in an increased focus on payment by results, possibly by payment of higher fees for over-performance a mid-level fee range for standard delivery, and means to reduce fees in the event of under-performance and failure to meet the programme’s logframe targets.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / SAVI will require provision of additional financial support of up to £10m bringing the total resource envelope for the programme to £31m. Note that £1m has not yet been programmed in the tables below and will be used for strategic opportunities if they arise. / Tables 3 and 4 below outline a total Programme Budget based on these assumptions. Table 4 gives an outline, whilst Table 5 details including a breakdown of the programme technical assistance by state. Both tables give provisional allocations for each of the forward years to 2014/15, all programmed to the SAVI Programme year August to July. Table 4 also shows how the additional funding is allocated and phased and how this maps against current funding. Annex 2 sets out the scale-up summary, including an overview of programme funding, outcomes and results matrix for additional funding. / Table 3: Outline budget including scale up / ITEM Inception to date (2008- Sep.12) 2012/13 ( Q3 & Q4) 2013/14 2014/15 2015/16 ( Q1) / Core delivery costs (programme and technical personnel) 8 2.65 5.24 5.24 1.67 / Project admin costs (including procurement of equipment through Crown Agents) 3.2 1.17 1.28 1.28 0.27 / Total 11.2 3.82 6.52 6.52 1.94 30.00 / Table 4: Detailed SAVI budget profile after scale up from September 2012 / 2012/13 2013/14 2014/15 2015/16 Total / £m £m £m £m £m / Program Activities 1.16 2.25 2.25 0.93 6.59 / Reimbursable Management Costs 0.09 0.09 0.09 0.03 0.31 / Offices 0.55 0.61 0.61 0.14 1.91 / Travel 0.28 0.30 0.30 0.07 0.96 / Equipment 0.18 0.20 0.20 0.02 0.61 / Living Costs 0.06 0.07 0.07 0.02 0.21 / Total Reimbursable costs 1.08 1.18 1.18 0.25 3.69 / Long Term TA / Abuja 0.45 0.89 0.89 0.22 2.45 / GRM (Abuja) 0.05 0.09 0.09 0.02 0.25 / Kano 0.11 0.22 0.22 0.05 0.59 / Kaduna 0.11 0.22 0.22 0.05 0.59 / Lagos 0.11 0.22 0.22 0.05 0.59 / Enugu 0.09 0.18 0.18 0.05 0.51 / Jigawa 0.09 0.18 0.18 0.05 0.51 / Yobe 0.05 0.09 0.09 0.02 0.25 / Zamfara 0.08 0.15 0.15 0.04 0.42 / Katsina 0.08 0.15 0.15 0.04 0.42 / Niger 0.05 0.09 0.09 0.02 0.25 / Anambra 0.05 0.09 0.09 0.02 0.25 / Total LTA 1.29 2.58 2.58 0.65 7.11 / Pool Short Term TA 0.05 0.09 0.09 0.02 0.25 / Core Short Term TA 0.15 0.31 0.31 0.08 0.85 / STA 0.20 0.40 0.40 0.10 1.10 / Total budget excluding inception to date (£11.2) 3.82 6.52 6.52 1.95 18.80[4]
B. How will it be funded: capital/programme/admin? / The programme will be funded from programme resources and has been budgeted for in the Operational Plan for DFID Nigeria. There are no contingents or actual liabilities.
C. How will funds be paid out? / All programme funds will be managed by the lead service provider. The contracted lead service provider will be reimbursed quarterly in arrears on satisfactory performance and in accordance with contract terms and conditions.
D. What is the assessment of financial risk and fraud? / DFID will continue to conduct an independent annual audit of the programme. Assessment of the probability of financial risk and fraud is generally low though the probability of reduced financial management oversight and monitoring is significantly increased in areas where complete audits may not be possible due to security concerns at the time and auditors being unable to visit certain states, to mitigate this, DFID may explore the option of postponing part of the audit process. However SAVI main operation’s and head office is located in Abuja where majority of management and financial systems coordination exists. / SAVI funds will not be passed directly through government and therefore reduces this potential fiduciary risk. Since inception SAVI has had unqualified audits.
E. How will expenditure be monitored, reported, and accounted for? / Monitoring and accounting of expenditure will take place using the ARIES system and standard DFID Nigeria procedures for inspecting invoices to ensure VFM and compliance with agreed fees and reimbursement costs. / DFID will rely on: / Quarterly progress reports covering programme and financial issues / Year-end statement of actual expenditure / Independent annual audits of the programme / Quarterly narrative and financial progress reports to DFID will include reports against the logical framework and agreed results. Expenditure will be monitored/validated against quarterly financial and progress reports. Progress and financial reports will be submitted within 15 calendar days of the end of each quarter. / DFID will conduct annual financial audits of the programme and ensure that SPARC maintain up to date asset registers. DFID will decide on the disposal of assets at the end of the programme.
[4] Grand project total including inception to date is £11.2m+£18.8m=£30m.

Management Case

A. What are the Management Arrangements for implementing the intervention? / Project management is primarily the responsibility of GRM the service providers, but with close collaboration between them and the responsible DFID Governance Adviser. The programme will be managed by DFID Nigeria’s Abuja office, and report to the DFID Nigeria Governance Adviser. Project support is provided by a Programme Officer in the GSD Team. / SAVI, as part of DFID Nigeria’s State Level suite of programmes is also overseen by a DFID Steering Committee for the SLPs which meets on a quarterly basis. DFID State Representatives liaise closely with SAVI at state level. / SAVI has State Team Leaders in each state who manage the programme and there are quarterly meetings of all SLP Team Leaders at state level to ensure coordination between the different programmes
B. What are the risks and how these will be managed? / Risk Management Table / Risks Likelihood / 3=high 1=low Impact / 3= high 1=low Mitigation strategies / EXTERNAL RISKS / POLITICAL / Increased insecurity 3 3 Programme: SAVI will enforce recently updated security procedures (general security architecture for the programme) by hiring a full time (cost-shared) security manager. Additional security requirements are necessary given recent spread of Boko Haram attacks. / DFID: State Representatives, Advisers and DFID Risk Management team to proactively address potential security risks and mitigation response. Ensure partners understand the potential delay or termination if security risk threaten programme. / Inadequate autonomy of State houses of assembly 2 2 Programme: Engagement with National Assembly, Conference of Speakers, Association of Clerks of state houses, and Nigerian Governors Forum to advocate for the adoption of required Amendments to the Constitution previously blocked by the then incumbent Governors. / DFID: Leverage opportunities through policy and programme dialogue to lobby for required changes. / Political volatility 2 2 Programme: Adaptation of advocacy strategies, identifying opportunities to influence policy under the prevailing circumstances, while also implementing above-proposed management /mitigation measures against rising insecurity greater sensitivity in the selection of issues / DFID: Maintaining close working relations programmes on political analysis and high level engagement with political office holders and security personnel as appropriate / BENEFICIARIES / Intimidation of individuals and groups supporting reform. 2 2 Programme: The provision of a self-assessment of the House (OCA) and resulting change plan endorsed by the Legislature should provide “political cover” to individuals and minorities in the House in order to take forward the endorsed reform agenda and those supporting its implementation. Retribution levied on journalists for reporting more evidenced based reporting needs to be protected, help and guidance is expected from the Nigerian Guild of Editors. Where appropriate both formal and informal contacts will be required to establish confidence building measures through existing contacts at State Level. / DFID: Leverage opportunities through policy and programme dialogue to lobby for required changes and support for reform. Political engagement as required. / INSTITUTIONAL / Lack of SLP Co-ordination 1 3 Programme: An ‘expansion management plan’ has been developed to sequence the recruitment, induction and orientation of new staff in line with a tenable work-plan of activities in each state and as much as possible in tandem with other DFID programmes. / DFID: Ensure SLP Core group is functional and able to coordinate activity. / Impact not sustained beyond the programme lifetime 1 3 Programme: The “Theory of Change” and approach of SAVI with its engagement with Partners emphasise diminishing dependency on SAVI resources and an exit strategy is agreed with partners from day one. / DFID Validate approach in independent Annual Reviews with low profile field reviews undertaken by DFID State Representatives. / Risks Likelihood / 3=high 1=low Impact / 3= high 1=low Mitigation strategies / Fraud or corruption on the Programme 1 3 Programme: Ensure good quality financial management control systems in place. Monthly monitoring of financial implementation against activities. / DFID: Regular financial audits and reviews. / OVERALL 1.75 2.5
C. What conditions apply (for financial aid only)? / N/A
D. How will progress and results be monitored, measured and evaluated? / DFID Nigeria is intending to do an evaluation the SLP suite[5] as a whole. It has been chosen as candidate for evaluation using the criteria in the DFID Nigeria evaluation strategy. The principle rationale for this evaluation is to provide accountability, both to the UK taxpayer and the Government of Nigeria, for the £400 million that has been allocated for these programmes. It will also identify key lessons learnt to inform future programme development in Nigeria. / The evaluation questions are currently being consulted on. They summary evaluation questions are / Is there evidence that the suite of SLPs has had its anticipated impact? / Do the changes appear to be sustainable? / In the light of these two findings, does expenditure on the suite represent reasonable value for money? / Full evaluation questions, the SLP theory of change, and the methodological options being considered can be found in the draft design and approach paper[6]. / Given the focus within the evaluation on impact, options for understanding the counterfactual (what would happen in the absence of the SLPs) are being explored. The counterfactual will be partial due to practical and technical limitations. / The budget for whole SLP evaluation is currently being negotiated, and will affect the methodological options in the final evaluation. The current proposal in the region of £250,000.
Lograme / A Summary SAVI logframe is attached in Annex 1. A complete logframe is available in Quest. / Quest No of logframe for this intervention: (3618029) SAVI Logframe in Summary
[5] The evaluation will not cover GEMS due to its delayed start.
[6] Quest number 364 2396