Type of Review: Annual Review

Project Title:

Facility for Oil Sector Reform and Transparency (FOSTER)
First Annual Review

Date started:	Date review undertaken: March 2012

Introduction and Context

What support is the UK providing?
DFID is providing support to Nigeria through FOSTER to enable reform and greater transparency in Nigeria’s oil and gas sector. It provides an opportunity to reduce revenue leakage and stem corruption, by strengthening the governance of the sector and thereby reducing the many incentives for the abuse of power and capture of revenues which distort policy and politics in Nigeria and undermine the potential for oil revenues to be used to accelerate economic and social development. / The programme harnesses different strands of interest and commitment for reform in Nigeria, within government and other organisations and institutions working in the oil and gas sector. FOSTER will reach out to engage and support relevant stakeholders, and give them the tools and the voice to open up information and improve understanding of the obstacles to reform of the sector and to build the policy debate around potential pathways to change.

What are the expected results?
Improved governance of the Nigeria’s oil sector through: / improved transparency in the availability of relevant information / improved accountability through an increase in evidence-based policy recommendations and demands for accountability / Improved accountability through increased responsiveness from government agencies to disclose information, provide explanations for decisions, change policy or make commitments to action.

What is the context in which UK support is provided?
Corruption, abuse and malpractice in the oil sector in Nigeria have many adverse consequences, often described as the ‘resource curse’. The potential benefits of oil revenues are often not realised when used ineffectively (or when captured by elites). The rapid expansion of extractive industries poses stern challenges for even the strongest governance and market institutions, and recent research provides evidence of a strong negative correlation between mineral dependence and institutional development. / In Nigeria a broad range of negative impacts are witnessed that go way beyond the narrow economics of pushing up the real exchange rate so that it undermines growth in the non-oil tradable sector. The tendency for natural resources to generate rents which lead to rapacious rent-seeking and adverse political economy effects is also well documented. / Nevertheless, oil and gas revenues contribute a large proportion of government income and GDP and have the potential to drive growth, attract foreign direct investment, and expand public services and infrastructure. In a country with such huge internally generated revenues as Nigeria, even small increments in improvements in transparency and accountability over revenue streams flowing to government as affected through FOSTER offers tremendous development potential and value for money.

Section A: Detailed Output Scoring
Output 1: Generation of technical analysis of key oil sector governance issues
Output 1 score and performance description: / Score = A++ (Outputs substantially exceeded expectation as the milestone is 10 deliverables before the end of 2012) / FOSTER has made an excellent start to implementation, understanding and providing analysis on pertinent and complex issues and producing recommendations on areas where FOSTER may provide future support. These reports provide a solid platform for further hard work that needs to be done by the programme in order to make a real impact on the sector. The first year has been successful in FOSTER both understanding where key opportunities for reform in the oil sector exist as well as understanding its role vis-à-vis facilitating and producing reports. It is clear that FOSTER should not be trying to operate as a think-tank in its own right as its ability to then directly champion these findings is limited by the nature of a DFID programme. Rather, its role as a facilitator is crucial, making sure gaps in important analysis are filled and reports are distilled in ways that can lead to meaningful change. This understanding has been cemented in a recently developed communications policy that reflects the relative advantages of FOSTER, its partners and industry stakeholders. / Further FOSTER influence, going beyond the technical analysis, across all these areas will be crucial as to whether there is eventually any development impact. / Performance Description / Published a policy brief on governance around ‘Nigeria’s Petroleum Industry Bill: Improving sector performance through strong transparency and accountability provisions’. The publication makes concrete recommendations on which transparency and accountability provisions from drafts of Nigeria’s Petroleum Industry Bill should be retained and strengthened in final legislation. / Summary Note for National Assembly members on the Petroleum Industry Bill. The objective of this initial analysis was to provide updated reference information for Members of the House of Representatives on the major issues in the Petroleum Industry Bill. The Summary Note has been finalised and circulated to all members of the House and has established the basis for FOSTER to provide more detailed technical support through facilitated technical sessions and stakeholder consultations. / Legislative review and stakeholder analysis of the regulatory framework governing oil spills was conducted in collaboration with Stakeholder Democracy Network (SDN). The paper provides a comprehensive review of the scope, responsibilities and the reasons behind the failures of regulatory agencies, using powerful insights based on interviews from international and national oil companies and local communities in the Delta. / During the period under review, the project also conducted a contextual and stakeholder analysis of the fuel subsidy reform. The paper provides valuable contextual analysis on previous attempts to reform, comparative analysis from other countries, analysis on the interests and positions of key stakeholders, as well as recommendations for strengthening the evidence base around debating the removal of the fuel subsidy. / Survey of Non-State Accountability Actors in the Niger Delta. The survey’s primary focus was identifying civil society partners that the SEEFOR, Edo DPC and FOSTER projects could support through targeted capacity building and financial assistance. Consultants were asked to provide analysis of the political standings and governance priorities in the Delta and the respective activities around transparency and accountability issues. / Transparency Deficits in the Governance of Nigeria’s Oil Sector. Research conducted by CSEA to identify weaknesses in the discharge of statutory transparency roles by strategic regulatory institutions in the oil sector, particularly in the disclosure of information and data. This resulted in a policy brief providing comprehensive analysis of transparency deficits in the governance of Nigeria’s oil sector. / Assessment of the implications and potential for the Freedom of Information Act to increase transparency in Nigeria’s oil sector. This research was conducted to complete a situation analysis of current strategies for utilising new FOI legislation and exploring its relevance and opportunities for applying it to the oil sector through consultations with media rights, advocacy and oil sector focused civil society organisations and media channels. / Crude Sales Analysis. Completed analysis of governance risks in upstream chain of custody, export sales and use of revenues for refined product imports. Report contains many recommendations for future FOSTER support that will feed into client outreach and project development.
Progress against expected results: The above FOSTER activities make it a total of eight technical analysis outputs so far produced for FOSTER. By the end of 2012 the first milestone under this output requires that 10 of such information datasets must have been produced. / Recommendations: Although being able to produce high-quality analysis on specific sector issues is a key tool for FOSTER’s approach, the number of reports that FOSTER produces should not be a measure of its success. This output should be dropped from the FOSTER logframe and replaced with a higher-level result that better captures and reflects the quality and impact of their research and analysis. For instance, a better indicator might be the number of oil sector policy changes that result mainly from FOSTER’s engagement. / Impact Weighting (%): = 30 / Revised since last Annual Review? Y/N = N / Risk: Low/Medium/High = Medium / Revised since last Annual Review? Y/N = N

Output 2: Communication of NEITI audits and other key information about oil sector governance
Output 2 score and performance description: / Score = A (Outputs met expectation) / The Nigerian Extractive Industries Transparency Initiative (NEITI) remains an important partner for FOSTER and in this initial implementation period FOSTER’s engagement with NEITI has been pitched appropriately. Challenges with the backlog of NEITI audits not yet delivered risk diminishing the potential impact that NEITI can have on the sector, and in turn the value of FOSTER’s engagement with them. FOSTER has maintained a supportive engagement with NEITI but is not dependent on NEITI’s success in order to have impact on the sector. / FOSTER has done well in building relationships with other important Nigerian government partners such as the Department for Petroleum Resources (DPR) and the Ministry of Finance. An important area going forward will be how FOSTER works with these Ministries, Departments and Agencies (MDAs) to better communicate important information about oil sector governance that could potentially lead to reform. / FOSTER’s work on building the capability of local media and civil society to respond effectively to issues of oil revenue transparency is important, but is only one part of a broader need for Media and Civil Society to better understand complex oil sector policy issues. Changes in oil sector policies can have a major impact on the Government Budget or alternatively can have immense local environmental impact on communities. FOSTER has started to help bridge the gap between the complexity of some of the oil sector policy issues and the extent that the implications of these changes are understood by the public. FOSTER’s planned work on the Natural Resource Charter and driving this initiative from the ‘grass roots’ will provide a good platform for targeting demand for change across important industry governance reforms. / Finally, FOSTER has used this initial period to explore its role in direct media engagement on key sector issues. Reflecting on this the risks that come from FOSTER acting as a high profile voice for reform outweigh the benefits, as the programme tries to balance the difficult act of providing technical support to government whilst facilitating demand from civil society on reform. Instead, FOSTER needs to act as a facilitator of informed engagement between the government, industry and civil society. / Performance Description / As a prelude to effective public engagement with the latest NEITI audit report, FOSTER organized and ran a two-day training session on how to effectively use the NEITI audit reports to understand the Nigeria oil sector and as a result strengthen oversight roles by accountability actors. The training was for NEITI staff, civil society organizations, media and other key stakeholders in the oil industry. / FOSTER participates in TV debates. As a result of Africa Independent Television (AIT) journalists attending the NEITI audit training, FOSTER was invited to participate on a live TV debate at AIT (‘Diplomatic License’). The discussion provided FOSTER with the opportunity to communicate on prime-time television sections in the NEITI reports that explicitly referred to the debts owed by NNPC to the Federation. It also offered an opportunity to enlist the support of a Member of the House of Representatives as a potential change champion for FOSTER. Following the success of the first debate on oil sector transparency, another TV debate on ‘Democratic License’ was held a month later with FOSTER again invited. This time a representative of the oil marketers and another National Assembly Member participated (Chairman of the Committee on Local Content). / NEITI 10 years of audits. With FOSTER technical support, NEITI completed a review of the findings, conclusions and recommendations over successive audits covering the last 10 years of audited numbers. Initial findings from this analysis were featured in NEITI’s quarterly magazine and the detailed findings will be presented at the National Conference in 2012. / NEITI Sensitization and Strategic Plan Dissemination: NEITI in collaboration with FOSTER and the World Bank organized a two-day awareness raising event for its key partners to share the new strategic plan of NEITI and reiterate the key roles the main partners need to play in supporting NEITI implementation. During the two-day event work plans were drawn for NEITI and each of the partners. / PETROData: FOSTER supported CSEA to launch the PETROData website to enhance the dissemination of data and information on the Nigerian oil sector. The PETROData website is the first ever on-line information hub on the oil sector in Nigeria. It will provide real time information to the public on the key debates in the sector. The aim for the platform is to enhance data dissemination and communication of existing research and reports from duty bearing institutions in the oil sector. By using social media tools the platform will stimulate debate amongst diverse actors on strategic policy issues in the governance of the oil sector. / A four-page note on the governance environment around dealing with oil spills was circulated at the First Stakeholder Roundtable on Niger Delta Environmental Protection and Regeneration, with the theme: “Ensuring Niger Delta Environmental Sustenance” held in Abuja on 29 November 2011. The event was widely reported in the print and electronic media. FOSTER supported Chris Newsom from SDN to speak on managing and organising remediation, current capabilities and gaps, funding and new technological support.
Progress against expected results: The publication and dissemination activities around six pieces of information and events on oil sector governance mark the first of 10 events or datasets that FOSTER is expected to produce under its first milestone before the end of 2012. / Recommendations: / NEITI is an important government partner to FOSTER and FOSTER should continue to maintain this good relationship. However, for the programme to have a higher level of impact it needs to follow through with already initiated steps to widen its government partners and effectively communicate oil sector policy changes. It will be important to ensure effective communication of oil sector reforms from agencies such as the Ministry of Finance, Department for Petroleum Resources, as well as communicate important work around the Petroleum Industries Bill. DFID should consider broadening out the wording of this output to reflect the wider engagement. / FOSTER recently developed a new communication policy that changes the nature of FOSTER engagement to avoid trying to be a public voice for reform and instead focus on being a facilitator of sector reform by providing an informed basis for stakeholders to engage with each other. / Impact Weighting (%): = 30 / Revised since last Annual Review? Y/N = N / Risk: Low/Medium/High = Medium / Revised since last Annual Review? Y/N = N

Output 3: More effective institutions involved in oil sector transparency and accountability functions
Output 3 score and performance description: / Score = A+ (output moderately exceeded expectation) / This is the most important output for FOSTER. If Nigeria is going to make the most of its natural resources then it needs to have more effective institutions involved in the management of the oil sector. These institutions need to be continually striving for a better deal for the country and mitigate the negative impact on the communities directly involved in or affected by resource extraction. The programme has tested the water of a number of institutions during its initial phase of implementation, but a fast evolving political context in early 2012, with the attempt to remove the fuel subsidy and the battle to pass a version of the Petroleum Industries Bill (PIB) means that this work will likely have to step-up substantially in 2012. This may indeed be the make or break of FOSTER’s development impact. Progress so far has been very good with FOSTER responding very well to an opportunity of providing support to the Ministry of Finance’s revamped Oil and Gas unit. Building a strong unit within the Ministry of Finance will be key in helping the country better manage revenues from this sector. / Performance Description / Output 3: More effective institutions involved in oil sector transparency and accountability functions - Indicator 1: Number of demand driven organizational development outcomes developed with organisations involved in oil sector transparency and accountability. / NEITI MTSS: With FOSTER support NEITI has developed its first strategic plan and medium term sector strategy. NEITI featured a one page write-up of the strategic plan in Nov/Dec’s edition of Open Audit. / Performance Assessment of Revenue Mobilization, Allocation and Fiscal Commission (RMAFC): In collaboration with the RMAFC, FOSTER commissioned an assessment to ascertain their capacity in delivering on its mandate. The exercise covered six zonal offices of the commission. The findings identified weak capacity of the personnel and inadequate working tools as the key factors impeding the commission’s performance. The report will be presented to the RMAFC management and then reviewed by both teams (RMAFC and FOSTER) with a view to mapping out mutually beneficial areas of collaboration in 2012. / RMAFC Oil and Gas Department: With FOSTER’s support, RMAFC automated its monthly production and allocation processes. The information will go live on the RMAFC website in early 2012. / Output 3: More effective institutions involved in oil sector transparency and accountability functions - Indicator 2: Number of accountability actors provided with demand driven institutional development support. / Capacity Building for Effective Policy Advocacy: The first phase of collaboration between FOSTER and the Petroleum and Natural Gas Senior Staff association of Nigeria (PENGASSAN) and National Union of Petroleum and Natural Gas Workers (NUPENG) was successfully completed. FOSTER assessed the preparedness of the two frontline unions operating in the Oil and Gas Sector in conducting evidence-based advocacy that will bring about policy change in the oil and gas sector of the economy. Based on the findings, FOSTER will develop a strategy with the unions to build the capacity of the two bodies in evidence based advocacy and research. / Regional Extractive Industries Knowledge Summer School: With FOSTER support participants from six accountability institutions and one government agency attended a comprehensive technical training in analysis, advocacy and accountability for extractives industries. / Output 3: More effective institutions involved in oil sector transparency and accountability functions - Indicator 3: Number of government agencies and institutions provided with demand driven institutional support. / Review for the National Assembly Local Content Committee of the accountability and transparency challenges in Local Content: Scoping study on the accountability and transparency challenges to implementing the Local Content Act presented to the Chairman of the Local Content Committee. The study analysed what interventions and institutions FOSTER should support to improve transparency and accountability in the implementation and application of the Local Content Act. The National Assembly Committee on Local Content has requested FOSTER provide technical support and training to the Committee members in 2012.
Progress against expected results: Six activities on organisational/institutional development initiatives have been successfully completed with organisations involved in oil sector transparency and accountability. / Breaking the reporting down further: 3 activities were recorded against Indicator 1 against a milestone of 10; and for Indicators 2 and 3, six civil society institutions and one government agency received technical training in analysis, advocacy and accountability for extractives industries. This is against a milestone target of five civil society institutions and five government agencies to have received institutional development support by the end of 2012. / The overall milestone target for Output 3 by the end of 2012 is 20 deliverables. / Recommendations / This is currently the most crucial output to reforming the sector. However FOSTER’s outputs should be broadened from only looking at oil sector transparency and accountability to a broader focus on good governance of extractive industries. / With this change in the output the programme has full licence to engage in more general oil sector reforms such as the Petroleum Industry Bill beyond transparency and accountability provisions and consider the fiscal provisions. It should also look at how it can support the Ministry of Finance to better manage a revenue stream that accounts for over 75% of government revenues. / The programme should also have full licence to help build effective institutions for other extractive industries beyond oil in order to make sure that preventative measures are in place so that these sectors do not deteriorate as badly as the oil sector. / The impact weighting of this output may need to be increased and the risk reassessed. / Impact Weighting (%): 40% / Revised since last Annual Review? Y/N = No / Risk: Low/Medium/High = Medium / Revised since last Annual Review? Y/N = No

Section B: Results and Value for Money.

1. Progress and result

1.1 Has the logframe been updated since last review? Y/N / No- however, a key recommendation is that the log-frame is revised after this annual review. / 1.2 Overall Output Score and Description / FOSTER scores an A+ overall, having moderately exceeded expectations for its first year. DFID can be very proud of the efforts that this programme has made to quickly engage in the sector and build a strong foundation for its future work. This should provide DFID with the confidence to consider being more ambitious with what the programme can achieve. / 1.3 Direct feedback from beneficiaries / It is too early in implementation to start getting useful feedback from beneficiaries. However, the next annual review should pick up on this and engage with relevant Government Agencies and local civil society organisations to understand their view on how effective FOSTER will have been.
1.4 Summary of overall progress / Actual progress against FOSTER’s current logframe show the following: / Output 1 Milestone 1: Eight out of the 10 information datasets expected at the end of 2012 has been produced. / Output 2 Milestone 1: The publication and dissemination activities around six pieces of information and events on oil sector governance mark the first of 10 events or datasets that FOSTER is expected to produce under its first milestone before the end of 2012. / Output 3 Indicator 1: NEITI and RMAFC have been provided three successful institutional support interventions. A total of ten such institutional support interventions are expected to be provided by the end of 2012 / Output 3 Indicators 2 and 3: Six civil society institutions and two government agencies were provided with demand driven institutional support, against a milestone target of five civil society institutions and five government agencies to have received institutional development support by the end of 2012. / FOSTER’s successful first year should provide DFID with the confidence to expand the scope and expectations for the programme.
1.5 Key challenges / A fast-expanding programme like FOSTER needs to manage its roll-out well. In the short-term this could put a lot of pressure on the project management. Prioritising areas of work in the short-term will be important. In the longer-term the programme needs to make sure it has the capacity to develop across its strategic areas. / A UK Government programme engaging in the oil and gas sector in Nigeria brings many challenges. Perceptions and distrust about motives from other stakeholders need to be overcome. Particularly in some of the areas where FOSTER could have the most development impact. Appealing to the provisions of the UK International Development Act might go some way, but more importantly FOSTER needs to build a trusted track record.
1.6 Annual Outcome Assessment / It’s too early to measure the outcome of the programme. However, the programme has built a very strong foundation year that puts it on track to achieve a good outcome and make a real positive impact on how Nigeria governs its extractive industries. / The log-frame needs to be revised in order to make sure the outcome indicators are both ambitious yet realistic.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / FOSTER has exceeded initial expectations for spend in its first year due to the rapid implementation and widespread engagement across the sector. DFID has been actively encouraging this, and is pushing the programme to deliver more and to deliver rapidly. Whilst it is early days in implementation, if the programme continues to deliver results at a high rate and across the expanded areas of its new proposed scope, then DFID may need to increase its budget allocation to ensure the programme can meet expectations. / 2.2 Key cost drivers / Key cost drivers are the consulting rates of experts used by the programme. Two things DFID and the programme need to pay particular attention to are: / (i) Daily fee rates of long-term advisory support to institution; and / (ii) Industry specialists that attract very high daily fees given market demand for their services. / DFID/ FOSTER need to make sure the long-term fee rates for advisory support to institutions continue to be rigorously negotiated down whilst still retaining high-calibre of experts. Industry specialists that attract very high daily fee rates should only be used sparingly and in areas where they can make very high potential impact. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Given the nature of the sector that FOSTER works in, there needs to be regular assessments of the political economy and continual scanning for the risks and opportunities that the political situation offers the programme. Formal updates of these will be commissioned on a quarterly basis and will directly impact on the programmes operations. / 3.2 Where an evaluation is planned what progress has been made? / N/A

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / As the programme engages deeper in reform of the more sensitive areas of the oil sector the likely development results will get higher but the likely risk to the programmes’ delivery if not managed well will also increase. At the moment the risk mitigation strategies outlined in the risk log are adequate in the context of current process outputs and are being applied. The risks are still at the medium level as proposed in the project memorandum. No new risks have been identified so far, but these should be updated at the same time as political economy updates are provided. In the process of revising the log-frame and including more ambitious outputs these risks should be re-considered and may have to be revised upwards.
Risk of funds not being used as intended / Low- FOSTER does not provide funds directly to government and its support is completely through technical assistance. As the programme increases its direct engagement with funding activities of smaller local non-government organisations this risk may increase. The programme should ensure they have sufficient policies in place to minimise fiduciary risk with these smaller organisations. / 4.4 Climate and Environment Risk / Not applicable

5. Value for Money
5.1 Performance on VfM measures / Effectiveness / FOSTER could have incredibly high impact if they succeed in influencing important changes in how the oil sector is governed. If the programme is able to help plug revenue leakages either through cutting some of the opportunities for corruption, increasing competition in the sector through improved fairness and transparency in how licences are granted, or plugging tax loop-holes in legislation, then the benefits of the programme will far exceed the £10 million programme cost. / DFID Investment in FOSTER Expected Development Impact of FOSTER / (monetised) / £10 million over 5 years ? / Pinning down a reasonable target for the programme is difficult. The original log-frame proposed an estimate of an additional $2 to 3 billion a year made available for Nigeria’s national development (from 2014/15) as a result of the FOSTER programme. In terms of development impact, this would give DFID an extraordinarily high rate of return on its £10 million investment. It’s likely that this level of result will be too ambitious given recent estimates of the total size of revenue leakages across the sector. FOSTER has begun the process to revise its log-frame. DFID and FOSTER should seriously consider what is realistic to expect from the programme. This should still be ambitious and more than justify the cost of the programme but grounded on the knowledge and experiences they have gained in their first stage of implementation. / FOSTER need to continue to make sure they have the systems and methodologies in place to capture the effectiveness of the programme. At the time of the next Annual Review the reviewers should be able to see revised high-level results and have an ambitious yet credible expectation on the development impact for the FOSTER programme. / Efficiency / FOSTER has started tracking its spend against its outputs (shown in the table below) and this will help show which areas of the programme are having the most success, and possibly enable us to benchmark with other relevant programmes. The difficulty in making efficiency judgements on the programme with the current outputs is that they are pitched at too low a level of results. This does not give us the ability to make judgements on which areas are the most/ least promising for achieving results and whether they should be scaled-up or cut back. Under the current output one, ‘generation of technical analysis of key oil sector governance issues’, there were 8 reports produced with a total spend of £674,271. We would expect the programme to be working heavily in this area in the early stage of implementation as it tries to build an informed evidence base for its interventions. On average this works out as approximately £84,000 per report which seems expensive. However, this ignores the real results that this type of technical analysis is targeted at. For instance if the programme provides solid analysis on revenue leakages in crude sales, identifying potential areas FOSTER could work on to plug these leakages and then goes on to achieve this, then the £84,000 for the initial analysis will be a very wise investment and wonderful Value for Money. If it produces technical analysis merely for the sake of producing reports, then £84,000 is a very poor use of this money. Thankfully, the programme are taking an intelligent approach to this and operate with results in mind, however their outputs within their logframe needs to start reflecting this. / Logframe Output 1 Output 2 Output 3 / Generation of technical analysis of key oil sector governance issues Communication of NEITI audits and other key information about oil sector governance More effective institutions involved in oil sector transparency and accountability functions / Total Spend in inception and implementation £674,271 £336,460 £447,655 / Illustrative examples of FOSTER projects Crude sales analysis / Fuel subsidy analysis / PIB Transparency policy brief / Nigerian Local Content transparency and accountability challenges for NASS / Transparency Building Initiative and PETROData website (CSEA) / Freedom Of Information Strategy development / Natural Resource Charter Phase NEITI Report analysis training for accountability actors / PIB Summary Note for NASS Members / PIB Civil Society & Private sector roundtables / Oil spills situation analysis and dissemination NEITI Strategic Planning and MTSS / RMAFC ICT Development / RMAFC Capacity Assessment / Oil spills - engagement for reform / Extractive Industries Summer School / Advocacy support to NUPENG & PENGASSAN / Economy / As the programme is still early in its implementation, the most direct influence on Value for Money has been in trying to ensure good economy of the programme inputs. A large part of this is focused on the key cost driver, the technical advice and consultants that the programme uses. The oil industry poses a real challenge for a donor programme given that high quality specialist input into the oil sector has a very high market price. Making sure that the programme only draws on high-priced industry specialists sparingly and where there is a very high value-added to their input needs to be an important strategy in controlling overall costs and the extent to which this is achieved should be properly assessed at the next annual review. / The programme aims to ensure competitiveness and transparency in its procurement. To achieve this, FOSTER has put in place procurement processes as detailed in the funding process and conditions manual. Issues of economy are reviewed by benchmarking proposed input costs as contained in TORs to ensure good Value for Money. FOSTER will have to be careful that the effect of taking on high-cost industry specialists that have high value added in the programme does not distort their internal benchmarking and that more general roles reflect reasonable market rates for the type of work they will be doing. / Other approaches that FOSTER has adopted to capitalize on the opportunities to reduce costs are: / Adopting a ‘Making Markets Work for the Poor’ (M4P) approach with their partners. Making explicit their efforts to encourage them to develop alternative sources of funding for events and disseminating research. For example, CSEA were initially extremely resistant to the idea of seeking corporate funding for policy dissemination events. As a result of FOSTER efforts and insistence, CSEA began a process of resource mobilisation and developing relationships with potential corporate. / Making use of other seminars and workshops being organised and paid for by others to disseminate our policy analysis to save money. For example, the First Stakeholder Roundtable on Niger Delta Environmental Protection and Regeneration with speaker Bill Richardson who spoke almost exclusively on FOSTER recommendations. / Recruitment policies for staff and externals have taken into account considerations of cost, benchmarking these against comparable industry cost (locally and internationally) of consultants and staff. / Overview / It is clear that FOSTER has the potential to be an excellent value for money programme in DFID’s portfolio. Achieving one or two big improvements in the governance of the oil sector will more than justify the £10 million programme spend, and make FOSTER a highly effective programme. FOSTER appears to be operating efficiently although it is too early to see this reflected in cost per output metrics. As the outputs are currently set at a relatively low-level it’s difficult to show which areas of the programme are offering more value than others. A planned revision of the logframe should help correct this. The programme is aware of the challenges of attracting high-level industry experts to add value, whilst making sure costs do not spiral. How it manages this balance will be vital to the VFM of the programme. FOSTER have taken an intelligent approach to working with partners and continuing to use ‘Making Markets Work for the Poor’ approaches that encourage sustainability will help both the short-term economy of the programme and the long-term impact.

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
DFID’s FOSTER programme has had an excellent first year of implementation. It has provided good analysis of important sector issues and identified a number of areas for future work. It and has engaged widely across the sector and has proved adaptable to a fast changing political situation. It has made itself relevant with important stakeholders in the industry, such as the Ministry of Finance, Department of Petroleum Resources and NEITI and has the potential to achieve a very high impact if even a small number of its potential reforms come off. There are a lot of opportunities and risks to the programme as it delves deeper into reform of the oil sector, with the various vested interests. However, the potential returns from working in this area are high. The programme’s politically savvy approach is critical in a sector teeming with deep vested interests and as the programme goes further into implementation there will likely be tough choices to make about where to concentrate efforts and difficult trade-offs. The potential for major gains in Nigeria’s extractive industries are profound. Whether it is plugging some of the serious revenue leakages in a sector that contributes 75 to 80% of Nigeria’s government revenues or if it is trying to limit the local damage to communities caused by poor sector governance, the need for reform is clear. How much can be achieved depends on how savvy, results-focused and determined the programme continues to be. They have so far been well managed and have a very strong team of people in place. Early signs are very encouraging. / Recommended changes to the Scope of the programme / Oil Sector Reform is clearly the main objective of the FOSTER programme and this may be broader than only transparency which the programme was largely conceived around. It may also involve looking at fiscal elements, improved regulation and policy making. This should be aimed both at increasing the long-term revenues available for national development, as well as limiting damage of extractive industries at the local community level. / FOSTER should also look at what they can achieve in broader extractive industries (beyond oil). Here the emphasis should be on prevention rather than cure. Making sure these sectors with growing investment do not repeat the mistakes of the oil sector and are governed well. / Recommended changes to logframe / The logframe needs to be urgently redesigned to take account of changes to the programmes’ scope and to make sure that results (such as outputs) are lifted to a high enough level to be useful to monitoring and managing the programme. Indicators should be ambitious yet credible. / Recommended Value for Money steps / It’s important that the programme has a credible headline result on how much increased official revenues could be made available for national development as a result of reforms facilitated by the FOSTER programme. This will be an important step in the high-level value for money of the programme. It will also act as a target and help keep the programme strategically focused on where it can have the most impact. / The FOSTER programme face Value for Money challenges that exceed those of many development programmes due to high fee rates of industry experts in extractive industries. How DFID and the project management deal with this will be key to how much impact they can have with an increasingly ambitious programme.

8. Review Process
As the FOSTER programme recently had an inception review by an external team, and because it is still early days in the programme’s implementation this review was carried out by the DFID Nigeria Country Economist with the assistance of the FOSTER management team.