Type of Review: Annual Review

Project Title:

Facility for Oil Sector Reform and Transparency (FOSTER)

Date started:	Implementation phase July 2011

Date review undertaken: December 2012

Acronyms

DPR	Department of Petroleum Resources (Ministry of Petroleum Resources)

EI	Extractive Industry (ies)

FAAC	Federal Allocations and Accounts Committee

FIRS	Federal Inland Revenue Service

MITIE	Media Initiative for Transparency in Extractive Industries

MoF PU	Ministry of Finance Petroleum Unit

NEITI	Nigeria Extractive Industries Transparency Initiative (NEITI)

NNPC	Nigeria National Petroleum Corporation

NNRC	Nigeria Natural Resource Charter

NOSDRA	National Oil Spills Detection and Regulatory Agency

NR	Natural Resources

NUPENG	National Union of Petroleum and Natural Gas Workers

PENGASSAN	Petroleum and Natural Gas Senior Staff Association of Nigeria

PIB	Petroleum Industry Bill

PPPRA	Petroleum Products Pricing Regulatory Agency

PRSTF	Petroleum Revenue Special Task Force

RMAFC	Revenue Mobilisation, Allocation and Fiscal Commission

## Introduction and Context

What support is the UK providing?
DFID is providing support to Nigeria through its Facility for Oil Sector Transparency and Reform (FOSTER) to enable reform and greater transparency in Nigeria’s oil and gas sector. It provides an opportunity to reduce revenue leakage and stem corruption, by strengthening the governance of the sector and thereby reducing the many incentives for the abuse of power and capture of revenues which distort policy and politics in Nigeria and undermine the potential for oil revenues to be used to accelerate economic and social development. / The programme harnesses different strands of interest and commitment for reform in Nigeria, within government and other organisations and institutions working in the oil and gas sector. FOSTER will reach out to engage and support relevant stakeholders, and give them the tools and the voice to open up information and improve understanding of the obstacles to reform of the sector and to build the policy debate around potential pathways to change.

What are the expected results?
The impact of FOSTER will be that Nigeria’s natural resources are used more effectively and management of them is enhanced through: / Identification of increased extractive industry (EI) revenues; / Improved management and accountability of EI revenues; / Improved policy outcomes for local communities affected by natural resource extraction.

What is the context in which UK support is provided?
Corruption, abuse and malpractice in the oil sector in Nigeria have many adverse consequences, often described as the ‘resource curse’. The potential benefits of oil revenues are often not realised when used ineffectively (or when captured by elites). The rapid expansion of extractive industries poses stern challenges for even the strongest governance and market institutions, and recent research provides evidence of a strong negative correlation between mineral dependence and institutional development. / In Nigeria a broad range of negative impacts are witnessed that go way beyond the narrow economics of pushing up the real exchange rate so that it undermines growth in the non-oil tradable sector. The tendency for natural resources to generate rents which lead to rapacious rent-seeking and adverse political economy effects is also well documented. / Nevertheless, oil and gas revenues contribute a large proportion of government income and GDP and have the potential to drive growth, attract foreign direct investment, and expand public services and infrastructure. In a country with such huge internally generated revenues as Nigeria, even small increments in improvements in transparency and accountability over revenue streams flowing to government as affected through FOSTER offers tremendous development potential and value for money. / The context for reform of Nigeria’s oil and gas sector has also substantially changed since the programme was first designed providing additional opportunities to improve management of the EI. On the demand side, the Federal Government’s attempt to remove the fuel subsidy in January 2012, the subsequent mass protests, industry reports highlighting corruption and mismanagement, and the results from legislative and executive enquiry committees have all focused attention on the problems of the sector like never before. On the supply side, there have been important opportunities to help build oversight capacity of agencies outside of the core Petroleum Ministry, influence the Petroleum Industries Bill, and engage with key oil and gas institutions on issues such as oil spills.

## Section A: Detailed Output Scoring
The next milestones for the FOSTER logframe indicators are at end-2013, therefore results have been assessed against progress that could be expected with respect to these milestones by December 2012.

Output 1: Increase in extractive industry revenues identified
Output 1 score and performance description: A(outputs met expectation)
Progress against expected results: / Indicator 1.1 5 policy recommendations targeted at increased revenues have been made by December 2012 compared with a milestone of 2 by mid-2013, exceeding expectations. But no policy recommendations have yet been adopted although there are some signs that specific measures are being considered by the government (as part of the Petroleum Industries Bill (PIB) and other policy processes eg. Committee to draw up White Paper following the Petroleum Revenue Special Task Force (PRSTF) report, Extractives Industries Transparency Initiative (EITI) reporting on crude oil sales). This requires continued action by FOSTER and follow-up during future reviews. / Indicator 1.2 By December 2012 progress has been made towards completing capacity building interventions in 2 agencies targeted at increasing Natural Resource (NR) revenue capture [Revenue Mobilisation, Allocation and Fiscal Commission (RMAFC) and Nigerian Extractive Industries Transparency Initiative (NEITI)] although quantifiable results from these interventions are still emerging, compared with the milestone of 2 interventions by mid-2013. / Indicator 1.3 1 system in revenue generating and oversight institutions (Fuel subsidy verification process) has been strengthened by December 2012 compared with the milestone of1 such intervention and 1 to support transparency by mid-2013. The system to support transparency has not yet been introduced. Overall expectations are therefore met for this indicator as at December 2012. / Recommendations: / FOSTER could calculate actual savings achieved from the new audit approach for fuel receipts and subsidies in order to disseminate this information as evidence of improvements in management of the sector. / FOSTER could consider a comparative study of the extent to which NEITI and other transparency measures already cover proposals for a broader EITI standard and measures to introduce these (eg. oil sales, contract transparency) in order for Nigeria to be in the vanguard of delivering the new standard and delivering systems of greater transparency. / FOSTER could consider assessing the value and approach to using social media and other technology to make data on revenues and how the sector is managed more accessible, and in order to match supply of such data to users’ needs and demand (eg. for data from RMAFC, NEITI, oil spills platform). / It may be useful to weight the milestones further towards adoption of policy recommendations, use of newly built capacity and systems in use, in order to ensure that programme activities are not overly input-focussed. / Impact Weighting (%): 40% / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? N

Output 2: Improved management and accountability of extractive industry revenues
Output 2 score and performance description: A+ (outputs moderately exceeded expectation)
Progress against expected results: / Indicator 2.1 5 policy recommendations (concerning the NEITI Board, reforming the NNPC, the NNRC, the PIB and upstream licencing at the DPR) targeted at improved management and accountability of the NR sector have been made by December 2012 compared with a milestone of 2 by mid-2013, exceeding expectations. 1 policy recommendation has been adopted concerning the NEITI Board so that this aspect of the milestone was also met. However due to its recent appointment the Board had made limited progress in supporting accountability by December 2012 as is the milestone for mid-2013. / Indicator 2.2 By December 2012 3 substantial capacity building interventions targeted at improving management and accountability in the sector had been carried out (with DPR, NUPENG and PENGASSAN and MITIE), compared with the milestone of 2 interventions by mid-2013, exceeding expectations. / Indicator 2.3 Progress had been made towards strengthening 2 systems which support improved accountability of oil and gas revenue streams in revenue management and accountability institutions generating and oversight institutions (RMAFC) by December 2012 compared with the milestone of 2 such interventions by mid-2013. This met expectations as to where delivery could be by December 2012. / Recommendations: / Logframe milestones could be adjusted (for this and other outputs) to balance introduction of policy/legal/role recommendations, capacity building interventions and systems strengthening more with actual implementation and effect of these. / Work to strengthen reporting of revenues to RMAFC needs to be complemented by work to ensure that the templates are accurate and the data, once published on the website, is accessible and meaningful to potential users, including for comparison with other data sources eg, NEITI. / Impact Weighting (%): 40% / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? N

Output 3: Improved policy outcome for local communities affected by natural resource extraction
Output 3 score and performance description: A(Output met expectation)
Progress against expected results: / Indicator 3.1 2 policy recommendations (concerning oil theft and compensation regime) targeted at improved outcomes for communities affected by NR extraction have been made by December 2012 compared with a milestone of 2 by mid-2013, exceeding expectations. But no policy recommendations have yet been adopted compared with the milestone of 1 being adopted by mid-2013. / Indicator 3.2 By December 2012 some progress had been made with capacity building interventions. This includes support for the National Coalition on Gas Flaring and Oil Spills (against the milestone of 1 intervention by mid-2013). / Indicator 3.3 Progress had been made towards strengthening 1 system and process in institutions and agencies charged with improved policy outcomes for local communities - National Oil Spills Detection and Regulatory Agency (NOSDRA) by December 2012 compared with the milestone of 1 such intervention by mid-2013. This met expectations as to where delivery could be by December 2012. / Recommendations: Recommendation i. under the previous output applies equally here. If the logframe – and therefore progress discussions with DFID focus too much on achieving numerical milestones then FOSTER could be asked to propose more appropriate measures that capture the impact of various interventions. Calculating the savings from fuel duty reforms partially supported through FOSTER is a very interesting initial attempt to do this (and we encourage FOSTER to repeat this regularly and also attempt to quantify the FOSTER contribution to these savings as much as possible). Similar efforts could be made in other project-supported areas. / Impact Weighting (%): 20% / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y / The context for reform of Nigeria’s oil and gas sector has substantially changed since the programme was designed. On the demand side, the Federal Government’s attempt to remove the fuel subsidy in January 2012, the subsequent mass protests, and the fallout of industry reports highlighting corruption and mismanagement have focused attention on the problems of the sector like never before. On the supply side, there have been important opportunities to help build oversight capacity of agencies outside of the core Petroleum Ministry, influence the Petroleum Industries Bill, and engage with key oil and gas institutions on issues such as oil spills. None of these areas would have been sufficiently captured under the initial programme logframe. / FOSTER’s 2011 annual review highlighted deficiencies in the existing logframe. Outputs were judged to be ‘activity based’ rather than result based, focusing on issues such as generation of technical analysis and communication of reports. In practice, DFID has been encouraging FOSTER to do more to pursue fundamental reform in the sector in order to improve governance and reduce leakages. This evolution in the programme also reflects DFID’s growing central policy emphasis on support for reform of extractive industries in DFID focus countries. / The proposed ‘impact’ of FOSTER now better aligns with DFID Nigeria’s operational plan, with the intended impact of ‘More effective use of Nigeria’s Natural Resources’ and an outcome focused on ‘enhanced management’. The headline result target is the aim to have £300m additional revenues realised from Nigeria’s natural resources by the end of 2015. Not only is this target useful for ‘why’ DFID is doing this work, but it will help the programme prioritise its interventions and focus on delivering tangible change in the industry. Outputs reflect key reform areas that it is important for FOSTER to pursue and have been balanced with achievable indicators and milestones. The underlying theory of change is that improvements in policies, laws and roles together with the capacity and systems to implement these will lead to improvements in natural resource management, increased revenues and reduced leakages including for local communities. / 1.2 Overall Output Score and Description: / FOSTER scores an A overall with outputs meeting expectation at this stage in delivery of the project. The first formal milestones under the new logframe are set for mid-2013 and delivery of programme outputs is as expected, looking across the range of milestones, by December 2012. / 1.3 Direct feedback from beneficiaries / Direct feedback was obtained from several recipients of FOSTER support, both government agencies and non-state actors. Feedback was consistent that this is a high-performing programme, in terms of products, engagement with stakeholders and the quality of staff. This enables high quality technical analysis to be targeted effectively to influence policy and reform based on agility in spotting high-return opportunities. This approach has stimulated a significant increase in debate about sector management and reform options and increased demand for accountability from government.
1.4 Summary of overall progress / Progress against the revised FOSTER logframe by December 2012 was as follows: / Output 1 (milestone 1): With respect to measures to identify increases in EI revenues: 4 policy recommendations have been made compared with the milestone of 2 but none have yet been adopted. Progress has been made on capacity building in 2 agencies but the impact of these interventions (e.g. increased revenues) will need to be tracked. 1 system for revenue generating and oversight institutions has been strengthened but a system to support transparency has not yet been introduced. / Output 2 (milestone 2): With respect to measures to improve management and accountability of EI revenues: 5 policy recommendations have been made compared with the milestone of 2 and 1 has been adopted but limited progress has been made in supporting accountability so far. 3 capacity building interventions have been carried out compared with the milestone of 2. Progress has also been made towards strengthening 2 systems for improved accountability of oil and gas revenue streams. / Output 3 (milestone 3): With respect to measures to improve policy outcomes for local communities affected by NR extraction: 2 policy recommendations have been made meeting the milestone but none have yet been adopted. Limited progress has been made with capacity building interventions so far. Progress has been made with strengthening 1 system and process in institutions and agencies charged with improved policy outcomes for local communities. / In addition, within these workstreams there have been some key successes to which FOSTER has contributed, for example: / New controls over subsidy payments introduced reducing losses through fraudulent subsidy claims; / Analysis, briefings and consultations on the PIB to stakeholders leading to changes in key governance and transparency provisions; / Establishment of Nigeria’s Natural Resource Charter (NNRC) to benchmark management of the oil sector with an expert panel; / Establishment of a mapping and tracking platform for oil spills merging government data and citizen reporting; / A policy forum for stakeholders to review mechanisms for compensation to communities.
1.5 Key challenges / The programme includes a large number of small activities grouped into clusters, it will be important to prioritise these systematically in 2013 according to potential to deliver high impact, while allowing space for critical areas which may deliver more slowly and to continue to take advantage of new opportunities. This approach could be formalised into a forward strategy. / To maintain momentum in its influencing of policy while demonstrating results the programme also needs to consider introducing communication protocols which will ensure appropriate handling of data while allowing dissemination of lessons to a wider audience, including internationally. / To date, FOSTER has developed the programme based on the premise that its role is to provide high-quality evidence and influencing of policy by engagement with stakeholders in order to enable improvements in revenue collection and sector management. However there remains a challenge of how to build accountability for management of the sector based on this information. This needs to be addressed by exploring linkages with other DFID programmes, for example for civil society advocacy, through opportunities for regular exchange of information to leverage complementary work. However, FOSTER should assess carefully whether to not expand into this work itself in order to protect its operational space and credibility with a range of stakeholders. / Similarly, the impact of FOSTER’s work ultimately depends on the quality of implementation of policies, laws, roles, and the related capacity and systems that it supports. Therefore DFID also needs to explore complementary means to ensure actual implementation of reforms such as the PIB, while FOSTER can continue to support technical analysis to enable this. / FOSTER’s excellence in delivery depends on the quality of staff, therefore it is also important for the programme to retain key staff in order to maintain continuity in delivery and take advantage of opportunities to influence reform.
1.6 Annual Outcome Assessment / Progress toward the outcome of enhanced management of Nigeria’s natural resources is likely to have exceeded expectations according to the indicator of additional revenues received. Evidence for this could be more clearly documented if FOSTER calculated the actual savings from measures to reduce leakages in subsidy payments in 2012, which amount to $3.4bn pa, compared with a milestone of £150m by mid-2013 and £300m by the end of the programme in mid-2015. The programme is also on track with respect to the indicator on increasing the proportion of natural resource revenues regularly accounted for insofar as the RFAMC has put in place reporting templates for the PPPR, Customs, FIRS and solid minerals, although the NNPC and DPR have not yet agreed this (although the logframe refers to the FAAC as the relevant reporting mechanism) Work will continue to publish this information on the RFAMC website in 2013.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / As in the first year FOSTER has continued to spend ahead of initial forecasts due to rapid implementation and widespread engagement across the sector given the opportunities to influence reform during 2012. As at October 31, 2012, 2 years into implementation of the programme (including inception), FOSTER had spent £4.6m (52%) against an overall contract value of £8.9m. If the project continues to spend at this rate, the FOSTER team anticipates it will be close to 100% spend by the end of 2013, 18 months before the planned end date. / 2.2 Key cost drivers / Key cost drivers are the consulting rates of experts in this sector used by the programme. DFID Nigeria is active in reviewing rates and negotiating them down where appropriate while ensuring that the programme has access to high quality sector expertise as necessary. / 2.3 Is the project on-track against original timescale: Y / Given the opportunities for reform which have arisen in 2012, FOSTER has delivered at a pace to match these opportunities. If such opportunities are sustained DFID could consider further support to the programme while maintaining the level of opportunity under regular review, using FOSTER quarterly political economy analysis, to ensure value for money.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / FOSTER have proposed several new areas of work which could be explored through programming in 2013: / Local content: Analysis is underway to review Nigeria’s experience thus far (including the private sector response to the 2010 local content legislation) and to gauge opportunities for FOSTER to support the new Local Content Monitoring Board. This area is of significant interest to DFID programmes across Africa and lessons from Nigeria will be received with great interest. / Anti-corruption: FOSTER works on prevention, strengthening state capacity and targeted interventions, transparency and accountability work with civil society. It argues it is beyond the project’s scope to work on political and social mobilisation and enforcement. However, it plans to explore opportunities to expand work with core revenue oversight agencies and support civil society to improve sectoral understanding, investigative and advocacy capacity. There are also plans to work more closely with other relevant DFID programmes including Justice for All and FEPAR. / Gender: FOSTER proposes considering the structure and benefits of the oil sector with respect to their impact on women, for example through employment, and also reviewing the design and inclusiveness of support to civil society and briefing materials to ensure a greater gender balance. / Mining: A recently completed scoping analysis of the mining sector in Nigeria concluded that while solid minerals do not hold the same revenue potential as oil and gas they do offer significant scope to create economic activity and employment in many central and northern parts of Nigeria, not least because the regulatory environment is relatively strong by international comparison. A decision is required on what FOSTER’s incentives are to move into this area. / As part of a process of developing a formal forward strategy for 2013-15, these areas require careful consideration and consultation with DFID as to the additional impact to be expected from interventions in these areas compared with prioritising influencing reform and build capacity and systems through existing areas of intervention. / 3.2 Where an evaluation is planned what progress has been made? / N/A

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The logframe was updated in 2012 reflecting a refocusing of the programme and this requires a corresponding reassessment of the risks associated with the revised results and associated mitigation strategies compared with the original risk matrix in the Project Memorandum of November 2009. This should be a priority in 2013. / Additional risks identified during the AR were as follows: / Measures are needed to ensure continuity of existing programme staff to avoid risk of programme interruption or loss of quality; / The programme needs regularly to assess the balance of maintaining appropriate access to different stakeholders, eg, political access and influencing and working with civil society, to ensure it is sustainable. This includes reassessing regularly interaction and association with HMG.
Risk of funds not being used as intended / The original FOSTER PM states that programme managers will provide DFID with quarterly accounts and an annual audited set of accounts. These audits will include a random sample of accounts from FOSTER projects managed by other organisations. DFID reserve the right to conduct further audits at any time. In practice these accounts are not submitted but DFID conducts independent audits at particular stages of the programme. / DFID should discuss with FOSTER and document as part of regular management discussions, the approaches used to perform due diligence on potential funding recipients – whether TA or 3rd party organisations eg, Civil Society Organisations (CSOs). / 4.4 Climate and Environment Risk / N/A

5. Value for Money
5.1 Performance on VfM measures / For some aspects of FOSTER, it is more straightforward to trace a direct connection between the programme’s technical assistance (TA) support and evidence products and financial returns through reduced corruption and fraud or higher revenues (eg. physical audit systems for fuel imports which reduce fraudulent subsidy payments). However, for other aspects of the programme, the results chain is longer with FOSTER’s contribution being more difficult to quantify/attribute, especially in the short term, although the potential return through a better managed, more transparent and competitive oil and gas sector is transformational (eg, improved regulatory framework through PIB, open licensing regime, restructuring of NNPC. In this context a relatively small investment of £10m by DFID could yield disproportionately large returns in a sector which provides 80% of government revenues and £40bn pa in export revenues, even with current leakages and inefficiencies. / Effectiveness / As part of the revision of the logframe in 2012, an overall target of £300m additional revenues by 2015 was set as an outcome of the programme. Process changes are already identified as having significant savings which are expected to easily exceed the overall cost of the FOSTER programme of £10m. It is important that FOSTER systematically records costs and returns for the different components under the managed funds part of the programme to reflect these benefits across the programme. The initial attempt to calculate savings from fuel subsidy reforms (received after the review visit) is a welcome first attempt. / Efficiency / The FOSTER Annual Report states that expenditure by outputs was as follows for the period to October 2012: / Result area Key results / REVENUE IDENTIFICATION – Total spend: £1,134,582 Support to various agencies providing scrutiny of various oil and gas sector payments have potentially saved the country up to $3.4 billion per year. / Helped identify $1.5 billion in debt, and multiple billions in uncollected royalties, penalties and under-payments. / Analysis, briefings and consultations on the proposed Petroleum Industry Bill (PIB) provided by FOSTER to the MoF, National Assembly, national and international media channels, civil society organisations (CSOs), unions and the organised private sector have led to significant changes in key governance and transparency provisions in the Executive Draft presented to the legislature in August 2012. / REVENUE MANAGEMENT – Total spend: £1,246,244 Establishment of the Nigerian Natural Resource Charter (NNRC), a comprehensive benchmarking exercise around an Expert Panel, chaired by the former Minister of State for Petroleum (and Minister for Foreign Affairs) Henry Ajumugobia. / LOCAL COMMUNITIES – Total spend: £611,008 FOSTER’s work on oil spills has led to the establishment of a ground-breaking mapping and tracking platform that will merge government coordination data with an open platform for citizen monitoring and reporting, due to be launched by the end of the year. / Our briefing on the regulatory framework for the environment has been fed directly to the President and also to the Senate Committee for the Environment, which is currently reviewing draft legislation to strengthen the oil spill regulator. / FOSTER has established a policy vehicle with established participation of government, companies, and community representatives to review the mechanisms for providing compensation to communities affected by oil spills. / In order to make a systematic assessment of the efficiency of this expenditure, further analysis is needed by FOSTER of the actual and projected financial returns from these key results and other activities. Within the 3 output areas, the programme includes a large number of small activities grouped into clusters, beyond the key results listed above, it will be important to prioritise these systematically in 2013 according to potential to deliver high impact, while allowing space for critical areas which may deliver more slowly and to continue to take advantage of new opportunities. / Assumptions can be made as to the attribution of individual results for activities to FOSTER, so far there is a compelling underlying case which supports this. / Economy / The key cost drivers in FOSTER are the costs of consultants with appropriate skills and experience to provide high quality and relevant technical advice based on sectoral expertise. Market prices for such expertise tend to be high and this is reflected in 17% of FOSTER fees ranking in the highest rate fee band. However the returns to the programme outlined above already demonstrate the value added of industry specialists. / 5.2 Commercial Improvement and Value for Money / DFID is proactive in reviewing Terms of Reference (ToRs) and consultancy rates for all contracts over £40k and has successfully encouraged FOSTER to negotiate fee rates down in several instances. In addition there could be opportunities to explore further value for money with FOSTER by reviewing fee rates in the light of DFID’s recent internal review of VFM in the use of contractors for aid delivery. / Based on performance of the programme to date, there is a strong evidence base for DFID to consider scaling up the programme in order to maintain the pace of delivery and take advantage of opportunities for reform if they continue to emerge in 2013 as they have done in 2012. However this approach should be accompanied by a review of measures to ensure continued value for money in obtaining appropriate sector skills from consultants. / The original PM refers to FOSTER being required to conduct competitive tenders for TA over £50k. However, the approach implemented reduced the role of sub-grantees and increased direct Technical Assistance, through short term consultancies, to support reforms. / 5.3 Role of project partners / To provide a stronger evidence base for VFM FOSTER should more systematically record expected and actual returns from the activities within the programme. / 5.4 Does the project still represent Value for Money : Y / Given the significant returns already being recorded from FOSTER activities on a sample basis the financial benefits of FOSTER are expected to significantly outweigh DFID’s investment in the programme to date, even taking into account consultancy rates for sectoral expertise. Thus the programme represents value for money although there may be scope for further efficiencies through prioritising high return activities, and maintaining consultancy rates and related overheads under regular review. / 5.5 If not, what action will you take? / As above, when considering scaling up the programme, DFID Nigeria should undertake a review of consultancy rates for the programme in the light of DFID’s recent internal review of VFM in the use of contractors for aid delivery.

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
FOSTER has taken advantage of the key opportunities to influence reform of the oil and gas sector which have arisen in 2012 through effective and timely use of high-quality evidence products and technical assistance. The scale of resources and mismanagement in this sector is currently of such scale that even if FOSTER can eventually claim only a small (less than 5%) contribution to the benefits of reform for Nigeria, this will far outweigh DFID’s financial investment in the project. It is essential that the project team do more to track and quantify these contributions (building on the first attempt to quantify savings from fuel subsidy reforms supported by FOSTER), lessons learnt and the value for money gains they represent. / FOSTER supports a large number of activities grouped into clusters in order to maximise opportunities to influence reform. 2013 will require consolidation and greater focus on expanding activities with the largest potential to achieve the outcome and outputs agreed in the revised logframe. Prioritisation will be essential to create space for these emerging high-return opportunities within the FOSTER portfolio. This might best be achieved by articulating more clearly an explicit strategy for the next 12-24 months as a basis for regular management meetings with DFID. / Interviewees emphasised that 2012 has been a year where ‘people have started to ask questions’ about corruption and mismanagement in the oil and gas sectors, in part stimulated by FOSTER analysis and recommendations. FOSTER may have a further important contribution to make to continue to stimulate a more informed public debate about both sector management and the use of revenues which might entail reinforcing the capacity of key civil society actors. Thought needs to be given to whether this is a role for FOSTER or whether there are other complementary programmes within DFID or elsewhere which can play this role. / Evidence products produced by FOSTER or partners often represent important distillations of knowledge in this sector which could be seen as global public goods for wider dissemination and FOSTER and DFID should explore how best to share these lessons further if appropriate. / As in its first year FOSTER has continued to spend ahead of initial forecasts due to rapid implementation and widespread engagement across the sector given the opportunities to influence reform during 2012. Given the strong performance of the programme (scoring A+ at the 2011 AR and A for 2012), while reform opportunities remain there is a strong case for increasing DFID support to the programme to ensure support to reform is sustained.

8. Review Process
The Annual Review was conducted by 2 senior extractives advisers from DFID central Policy Division and Africa Regional Department. They conducted a desk-based review of FOSTER management reports including the Annual Report dated November 30, 2012 and FOSTER products and 4.5 days of interviews with FOSTER and HMG staff and funding recipients in Abuja in December 2012.