Annual Review – post April 2018

Title: Western Region Coastal Foundation (WRCF)
Programme Value £ (full life): £ 9,500,000		Review Date: 9 November 2018
Programme Code: 202476	Start Date:30/01/14	End Date:31/12/19

Summary of Programme Performance
Year	2014	2015	2016	2017	2018
Programme Score	C	A	A+	A	B
Risk Rating	Medium	Medium	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4269826.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/16344883.xlsx (2018 logframe yet to be published)

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The Western Region Coastal Foundation (WRCF) programme was designed to help deliver the G8-Ghana partnership between the Government of Ghana and the UK Prime Minister agreed in June 2013. The Business Case was approved in December 2013, and a service contract with DAI signed in October 2015. The programme was set up to leverage oil and gas corporate social responsibility (CSR) funding for development in the communities of operation. It envisaged a DFID contribution of £9.5 million and industry contribution of £16 million in the first 5 years of operation, and thereafter for the Foundation to continue operating independently for a minimum of 5 years, with the expectation that it would do so until the end of oil and gas activities in the Western Region. The programme has registered as a Foundation with a board of directors drawn from industry, government and community leaders. The contract value with DAI is £8,428,419, with a balance of £1,777,772 remaining as of September 2018.

Summary supporting narrative for the overall score in this review (1/2 page)

Following the Mid-Term Review (MTR) in November 2017 and Extended (MTR) in March 2018 the programme’s Theory of Change (ToC) and Logframe were revised in August 2018 and a key performance indicators assessment was agreed to ensure the programme was re-orientated in line with the new direction, following changes in the operating environment. To take account of these revisions, a business case addendum was approved by the DFID Ghana Head of Office in September 2018. The procurement and commercial department contracts board approved a contract amendment in November 2018, which will include a programme break clause following a Key Performance Indicators (KPI) assessment at the end of January 2019.

To achieve the KPIs the foundation was given until the end of January 2019 to secure an MoU with the Petroleum Commission and work with oil, gas and petroleum companies to secure funding for at least 95 percent of the foundation's annual operational costs. While an MoU has been submitted, WRFC has not able to secure its signing by the Petroleum Commission and no funds for the continuation of the organisation had been raised by the time of this review, leaving a great deal of uncertainty over the sustainability of the WRCF as an independent foundation. While WRCF has delivered satisfactorily against most of the other revised logframe indicators, the lack of delivery against the sustainability indicators has meant that the programme is scored a B in this review, and there is a serious risk that the programme will have to be terminated following the Key Performance Indicators (KPI) assessment at the end of January 2019. The programme team is, however, confident that funding uncertainties will be addressed through the implementation of their newly drawn stakeholder engagement plan, which proposes sustained engagement with industry and government to unlock the necessary funding.

On the other logframe indicators, data and evidence generated by the multi-stakeholder dialogue platform is continuing to positively impact corporate social investments in host communities and district planning activities. The Dialogue platform consulted with and prioritised issues of 7,995 (47% male and 53% female) residents in relevant host communities of which 3,101 were first time participants in 2018. In line with agreed revisions to the geographic spread of the dialogue platform, the 2018 dialogue conversations were conducted across 100 coastal fishing communities, rather than across the 300 coastal and inland communities in earlier consultations. Data sets that profile oil and gas Corporate Social Investments and their impact, as well as community issues across the 100 coastal fishing communities, have been shared with Industry and Government as a basis for influencing future investments. However, greater efforts are required to increase the WRCF’s influence on CSR funding overall, as we have seen several major CSR invests by major oil and gas companies, which were not directed toward WRCF priority areas/or in cooperation with WRCF (such as Tullow’s $10m allocation for the Government of Ghana’s public Senior High School programme; Tullow’s joint venture CSR funding for cassava production; and the International Finance Corporation’s (IFC) cumulative impact work on the effects of oil and gas on livelihoods in the Western Region coastal areas, among others).

Take up of the Economic Interventions has been positive and the programme's Technical and Vocational Education Training (TVET) intervention is now delivering well against the 2018 logframe funding target. The aquaculture pilots have received the most buy-in with Eni Oil providing resources for training 43 new farmers on alternative livelihoods in the Ellembelle district in 2018. The aquaculture pilot has been a success as it managed to lower the entry/exit costs for potential entrants to the market as well as successfully facilitated technology adaptation. About 74% of the direct beneficiaries from WRCF aquaculture intervention have now adopted aquaculture as an income generating business, and on occasions there have been secondary investments by beneficiaries to further strengthen the aquaculture value chain. Other districts in the Western Region have also approached beneficiary farmers for advice on the adaptation of aquaculture as livelihood opportunity for community members.

At the impact level, the poverty data collected suggest a reduction in poverty from 23.4% at baseline to 19.5% at end line, however poverty increased in the Ellembelle district, making it difficult to assess the programme’s impact on poverty reduction. It is possible that the impact of the WRCF interventions on community incomes will have a time lag, particularly for the TVET intervention, as it takes time to increase the skills level of local communities for increased participation in the oil and gas industry as well as other industrial value chains. The scale-up of the aquaculture interventions is now beginning to yield results, however, more effort and engagement is required to fully utilise the impact of the interventions of oil and gas companies in the communities. Economic livelihoods interventions supported by industry in the communities have so far had very mixed results with 47% of such projects not currently functioning according to the dialogue platform data.

The focus of the programme in 2018 was setting the conditions to become a self-sustainable foundation on withdrawal of DFID support. While there is evidence that the dialogue platform and TVET interventions are gaining traction with stakeholders, including the Petroleum Commission (PC) and industry partners, with the TVET interventions securing some funding from industry, the dialogue platform funding process requires additional attention including:
1. securing an MOU with the PC;
2. working with Tullow, as the lead of the Joint Venture (JV) partners, on funding for the dialogue activities, and
3. broadening the support base by securing funding from other industry players, including from new market entrants such as BP, Aker Energy and Exxon Mobil, among others.

In line with this annual review, DAI has reviewed its stakeholder engagement plan to accelerate progress towards the self-sustainability targets.
DFID will undertake a comprehensive key performance indicators (KPIs) assessment, focusing on whether the funding generated to continue the foundation as an independent organisation, at the end of January 2019 is adequate. Should this not be the case, DFID will terminate the project by the end of April 2019.

Recommendations for the year ahead (1/2 page)

In 2019, it is envisioned that the momentum gained through the dialogue and TVET activities during 2018 will be consolidated through sustained funding. Key recommendations include:

- Formalise an MoU with the Petroleum Commission (PC) and obtain resources for funding the dialogue structure. This will include full implementation of the newly prepared stakeholder engagement strategy with particular focus on engaging Tullow, IFC and the other JV partners and obtaining their support for the dialogue platform. Until the time of the January 2019 KPI review, it is recommended that DAI reports to DFID on a bi-weekly basis on progress regarding its stakeholder engagement and seek DFID's support in engaging with key stakeholders.
- The WRCF should strengthen its value addition proposition particularly regarding the economic interventions strand and set out how it plans to generate resources from industry and government to support these interventions. The WRCF can showcase their success with the aquaculture pilot to attract resources from industry for future pilots in other economic/livelihood sectors. This will contribute to the overall impact of poverty reduction as well offers opportunities to generate funding in support of the foundation’s funding base.
- The WRCF should increase engagement with the PC and industry players including utilising the Corporate Social Responsibility (CSR) forum organised by the WRCF and facilitated by the PC to set strategic direction for industry engagement in the communities affected by the oil industry and establish strategic partnerships on CSR.
- The WRCF should continue engagement with the Developing Industry Standards platform which has resulted in £200,000 of funding in 2018 for WRCF’s TVET activities.
- The WRCF should re-assess the role of the current board members and their contribution towards the foundation’s financial sustainability with the aim of ensuring its board composition support its drive towards financial sustainability.
- The WRCF should build on the successful TVET funding platform to generate funding for WRCF and other aspects of the foundation’s programme.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	An independent, self-sustaining, open and inclusive dialogue platform for communities, government and industry established
Output number per LF	ONE	Output Score	B
Impact weighting (%):	40	Impact weighting % revised since last AR?	Yes ↑

Indicator(s)	Milestone(s) for this review	Progress
1.1: WRCF Memorandum of Understanding (MoU) for funding executed (Government, Industry and donors)	1 MoU signed	Outputs substantially did not meet expectation: An MoU to support the Dialogue platform was submitted to the Petroleum Commission (PC) for discussion. A date for presentation and discussion has yet to be agreed. / Indicator Score: C
1.2: No. of CSR interventions informed and influenced by WRCF dialogue data to address community needs	5 CSR interventions informed and influenced	Met expectation / Ten low value CSR interventions in 2018 have been informed by data from 2016/2017 dialogue: / Three Economic Livelihoods enhancement activities funded by Jubilee Partners / Seven Water access interventions through boreholes funded by Cirrus oil, Volta River Authority-VRA, Ghana National Petroleum Company GNPC / Indicator Score: A
1.3: Non-DFID funds raised to sustain the dialogue	£100,000 committed by Jan 2019	Outputs substantially did not meet expectation No funds have been raised. A proposal submitted to the PC for Oil and Gas companies to commit to provide $500,000 per annum to sustain the dialogue is under review. Endorsement by the PC is seen as a pre-requisite to secure funding commitments from Oil and Gas companies. / Indicator Score: C
1.4: No. of relevant data sets collected and disseminated to partners as a result of community dialogue	3	Met expectation / Three community conversation data sets collected and disseminated. These are: / Profiling and Mapping of Social and Economic Corporate Social Investments / Community Satisfaction ratings and assessment of Corporate Social Investments / Assessment of safe access to sea by all users and livelihood issues among fishermen and fish traders / Indicator Score: A
1.5: No. of Western Region coastal district residents engaged in the Dialogue Structure (disaggregated by sex -50% male and 50% female and youth - 50% under the age of 30 years old)	New 2,610 directly reached. Indirectly reached 10,440	Expectations moderately not met / 3,101 residents have been reached directly, for the first time in 2018 of which 1,434 are females, representing 46% of total. / 936 youth participated in the dialogue representing 30% of total, of which 15% were female. / 12,404 have been reached indirectly. / The number of residents reached exceeded the target, however, the sex and demographic compositions targets were not met. / Indicator Score: A+

Provide supporting narrative for the score

This output is aimed at ensuring the foundation raises funds to become sustainable and independent and a trusted and sustainable platform for residents of host communities impacted by the activities of Oil and Gas companies to voice issues and agree on priorities, which are documented, analysed and shared with the Oil and Gas Companies and the GoG as a basis for decision making on corporate social responsibility investments and government expenditure.

Indicators 1.1 and 1.3 aim to ensure sustainable funding is available for sustaining the dialogue platform as the WRCF transitions into an independent foundation. The WRCF is yet to secure an MoU with the PC as well as attract funding for the dialogue platform and the organisation’s sustainability. Based on discussions with the PC and Tullow as the lead operator for the Joint Venture partners (which also include Kosmos, Anardako, GNPC and Petro SA), there is the possibility that the foundation will be able to attract industry funding in 2019. This, however, requires further engagement with Tullow as well as other industry players. The IFC is another potential partner as they are currently provide funding for an assessment of the effects of oil and gas on livelihoods in the Western Region coastal areas. To attract IFC funding, the WRCF will need to strengthen its value proposition and upscale its engagement with IFC. The WRCF team has now prepared a stakeholder engagement plan to carry out this engagement.

Indicators 1.2, 1.4 and 1.5 relate to progress regarding the dialogue platforms for community members, industry players and government to generate dialogue on pertinent issues related to oil and gas exploration as well as community development. They also measure the extent to which data from the dialogue is influencing corporate social responsibility activities funded by industry and government.

Ten CSR interventions recorded in 2018 worth GHC270,000 (£45,000) had direct links to issues raised on the dialogue platform in 2017 and shared with industry and the district assembly. These interventions responded to economic issues such as livelihoods skills training and provision of water infrastructure in selected communities. However, the interventions influenced are of low value, and there were several high value CSR projects which WRCF was not able to influence. The expectation is that the WRCF is also influencing high value projects going forward.

The WRCF has shared the datasets from the dialogue platforms with 13 Oil and Gas companies, the six Coastal District Assemblies and the PC the CSR Learning Forum held in Takoradi. It is, however, recommended that the WRCF uses the data more strategically with the senior management of the oil and gas companies to influence their CSR spending.

Lessons identified this year, and recommendations for the year ahead linked to this output

It is recommended that the WRCF expands engagement with the senior management of oil and gas companies – drawing in DFID or High Commissioner if required - to ensure buy-in for their work and better influence the CSR spending of oil and gas companies.

It is recommended that the WRCF follows up on its engagement with the PC, including signing of an MoU, and mobilises resources for the dialogue structure. This will include full implementation of the newly prepared stakeholder engagement strategy with particular focus on engaging Tullow, IFC and the other JV partners on supporting the dialogue platform. It is recommended that the programme reports to DFID on a bi-weekly basis on progress with stakeholder engagement and seek DFID's support in engaging with key stakeholders, at least until the decision point in January.

Output Title	Community livelihoods improved through Industry CSR support for economic development interventions
Output number per LF		2	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1: No. of OGPs and other funders committing / finance above £25,000 ($32,500) for scaling-up livelihood and economic development initiatives	1	Met Expectation / Under the Off-shore Cape Three Points (OCTP) JV Project - ENI, Vitol and GNPC through Technoserve, sponsored the construction of 43 aquaculture ponds, using the WRCF pilot model in their design. Per adopted pond model cost projections, x1 pond costs £800, the cost of 43 ponds was £34,000 / Indicator Score: A
2.2: No. of beneficiaries trained on new aquaculture, CSA and other economic development practices supported by industry	60	Expectations Moderately not met / The ENI livelihood project supported 43 beneficiaries with aquaculture intervention in 2018, but no other trainings took place. / Indicator Score: B
2.3: No. of relevant economic development publication reports produced and shared with stakeholders	2 publications	Expectations Moderately not met / Two evaluation publications produced on the aquaculture intervention and climate smart agriculture intervention. Only the aquaculture intervention evaluation publication has been shared with stakeholders / Indicator Score: B

Briefly describe the output and provide supporting narrative for the score

This output measures the WRCF’s contribution to community livelihoods through the implementation of pilot economic interventions and the level of beneficiary uptake and industry investment to support expansion. The aquaculture pilots have received more buy-in and funding from industry than the climate smart agriculture pilot, receiving £34,000 from Eni Oil for the construction of water ponds (other funds have supported training and management oversight and are not included here) for 43 new farmers on alternative livelihoods in the Ellembelle district in 2018. Given the WRCF’s successful conceptual design of the aquaculture initiative, Eni Oil/Technoserve modelled their Aquaculture project within their wider ‘Economic Diversification project in the Western Region’ on the WRCF’s aquaculture model. The aquaculture initiative had the highest uptake by community members in the Eni Oil enclave when presented with 27 livelihood options under the wider Economic Diversification project to alleviate job losses in communities with oil and gas operations. About 74% of direct beneficiaries profiting from the WRCF’s aquaculture intervention have now adopted aquaculture as an income generating business and we have seen secondary investments by community members in the aquaculture value chain (one of the beneficiaries invested about £5,000 into a hatchery to strengthen the value chain of the aquaculture industry and bringing aquaculture inputs closer to aquaculture farmers). An emerging risk for the WRCF is that industry might not provide any further direct funding to the WRCF for this intervention as knowledge about this approach has been widely shared, making reproduction much easier and cheaper for new up-takers. The WRCF will have to define its continuous value addition if it still envisages income from the economic interventions to support the foundation’s sustainability, for example by providing continuous advisory, outreach and M&E support to industry as well as using its success with the aquaculture pilot for attracting resources from industry for other pilots.

The WRCF also undertook the Climate Smart Agriculture (CSA) programme as part of its economic intervention pilots to provide alternative livelihoods and increase incomes for communities affected by the oil and gas industry. The evaluation of the CSA found that the number of farmers applying at least one CSA technology to their crops following the intervention increased from 38 (20.4%) to 107 (82.7%). For example, the number of farmers who had used improved seeds increased from 47 to 118, mulching increased from 28 to 116, composting increased from 23 to 61 and use of organic past control also increased from 20 to 117 respectively.

Lessons identified this year, and recommendations for the year ahead linked to this output

The WRCF should strengthen its value addition proposition particularly regarding the economic interventions strand and set out how it plans to generate resources from industry and government to support these interventions. The WRCF can showcase their success with the aquaculture pilot in attracting resources from industry for future pilots in other economic/livelihood sectors. This will contribute to the overall impact of poverty reduction as well offer opportunities to generate funding in support of the foundation’s funding base.

Output Title	Community TVET skills enhanced by facilitating dialogue and coordination with public and private educational and training institutions using a self-sustaining revenue stream to generate funds derived from industry
Output number per LF		3	Output Score	A
Impact weighting (%):		40	Impact weighting % revised since last AR?	Y↑

Indicator(s)	Milestone(s) for this review	Progress
3.1: No. of people trained on TVET skills related to the Oil and Gas sector and allied industries - disaggregated by students and artisans and industry employees (90% male, 10% female)	200	Met expectation / 328 people trained / 64 industry employees and artisans (from Takoradi Kokompe) trained in TVET skills related to oil and gas sector in 2018. 56 of these have been engaged in industry activities following the training. / 264 welding students trained and benefiting from improved instructor capacity and curriculum. 14% of beneficiaries in 2018 were female. / Indicator Score: A+
3.2: No. of Oil & Gas related courses supported by industry	3	Met expectation / 4 oil and gas companies provided oil and gas related training programmes in the following; welding, mechanical, electrical and hydraulic skills development / In 2018, 4 programs were supported by industry including welding, electrical, mechanical and hydraulics. Greenline Logistics, Newmont, AMS, Klloyds, Takoradi Gas provided support for welding through the corporate social investment skills program, training of employees and provision of consumables. Support was also provided for electrical, mechanical and hydraulics through support for instructor capacity and corporate training programs by Siapem, Metka, AMS, Harlequin, Mantrac and Group 5. / Indicator Score: A
3.3: No. of instructors trained to industry standard in OGP skills	20	Met expectation / 40 instructors trained. / 10 welding instructors from Takoradi Technical Institute, Kikam Technical Institute, Regional Maritime University and College of Technology, University of Education have been trained to industry standards. / 30 instructors have been trained in other skills (to industry standards) including; mechanical, electricity and hydraulics. / Indicator Score: A
3.4: Total finance secured from industry and other donors to support skills development	£200,000	Met expectation / $317,635 (£249,000) from Greenline Logistics, Siapem, Modec, Seaweld, Yinson, Newmont, AMS, Integrity Logistics, Marine Master Services, IPMC, Kkloyds, and Takoradi Gas. / The WRCF expects to secure additional contracts from Newmont, AMS and Siapem by end of the year. / Indicator Score: A+

Provide supporting narrative for the score

The TVET sector was identified as an avenue to create economic opportunities for communities adversely impacted by the oil and gas industry as well as as a long-term solution to local content and local supply chain development, addressing the issue of low employability of citizens in the coastal areas. So far, the WRCF has supported four Oil & Gas related courses with 4,000 students enrolled in such courses. Improved instructor capacity is improving the skills level of students and increases employability in the oil and gas industry. However the lack of training consumables during practical lessons continues to limit the impact of this training on student capacity and their readiness for industry engagement.

The TVET intervention has also made great progress in raising resources to fund TVET activities as the WRCF transitions into an independent foundation. The hosting of the first edition of the National Developing Industry Standards conference which brought together industry players, education institutes, regulators and policy makers to implementing industry standards in technical training institutes and the launch of the Corporate Social Investment Skills Programme have all proven to be successful in creating a common platform to discuss industry-government-educational institute linkages.

The total finance secured in 2018 to date from industry toward sustainable skills development is $317,635 (£249,000), which is made up of eleven contracts including
- $84,000 from Siapem for basic, intermediate and advanced welding training for 28 employees
- $71,3250 from Modec and Seaweld for Level 1 welding inspection and welding lab test centre certification at Regional Maritime University and assessment of TTI and Kimtech welding facilities
- $56,000 from Newmont Foundation for training 24 Newmont project impacted communities in 2019

Based on these resources, the TVET work strand has trained 40 educational instructors who are transferring skills to about 1,000 final year technical students. The WRCF has also trained 64 artisans from the Takoradi Kokompe area and industry employees and secured industry attachment for some of the participants, with two participants gaining employment with one of the oil and gas companies with a starting salary of GHC2,000, about three times their initial earnings. Other participants won contracts in other industries for the first time. The TVET team plans to increase beneficiary attachments to industry in 2019.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Securing industry support for TVET interventions requires long term engagement to build trust, including discussions with various departments within companies and a consistent level of engagement. The WRCF has put the building blocks in place with over 70 companies and is expecting positive returns in 2019.
- The Developing Industry Standards Conference has shown that the partnerships required between industry, government TVET implementers and technical institutes can be built through facilitating dialogue and providing technical assistance, as described in the TVET theory of change. The momentum gained, and the relationships built need to be sustained in 2019.
- Raising funds for the training of industry employees and artisans should be matched with raising resources for TVET training and teaching in classrooms as students are a larger pool and the cumulative impact of raising their technical skills for industry engagement will be higher. The WRCF should engage the Ministry of Education, Ministry of Energy and GNPC for funding for practical TVET lessons to maximise impact of student training in oil and gas related TVET skills.
- The WRCF should support schools to facilitate industry attachment for students and instructors to maximise skills gain.
- There is the need to engage industry to commit to ensuring training consumables are available to use during practical lessons. This is a risk to the sustainability of the TVET programme; hence the WRCF needs to monitor this closely.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES(1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year(1/2 page)

The programme’s theory of change (ToC) is built around institutionalising the ‘dialogue platform’ by establishing an independent Western Region Coastal Foundation, using DFID support to both leverage increased amounts of oil and gas industry corporate social responsibility (CSR) funds, and to help ensure that oil and gas CSR funds are being used to benefit people in the Western Region and respond to community demands. It seeks to ensure that the expectations of communities affected by oil and gas operations are being managed and met, and the credibility of regional and local government is sustained.

The programme objectives are to be achieved through three outputs:
1. An effective Coastal Foundation (CF) established;
2. An independent, open and inclusive dialogue mechanism for communities, government and industry established (CF managed); and,
3. A Coast Foundation Development Fund established and functioning.

Changes to the ToC in 2016/17 reflect changes in the reduction in oil prices at the beginning of the programme. The revised ToC centres on strengthening the WRCF as an independent, self-sustaining entity, influencing the CSR spending of oil and gas companies and directing government interventions towards community needs. In the programmes’ final year of DFID’s funding (2019), the Foundation will:
- Facilitate the delivery of services by engaging communities in shaping CSR funding (primarily from OGPs) through an open and inclusive dialogue platform,
- Facilitate the implementation of Economic Development Interventions (particularly in aquaculture) by scaling-up pilots through external funding, and
- Support TVET activities related to the Oil and Gas sectors to deepen local capacity to partake in the oil and gas value chain and industry development in general.

These will ensure progress towards the impact statement of ‘expectations managed and met and constructive relationships built between communities, government and industry, thereby improving stability and inclusive development prospects in the region’.

A service contract amendment to include a contract breakpoint in the absence of credible sustainable funding for the foundation from industry by 31 January 2019 has been approved by the procurement and commercial department contracts board. Should the programme not meet a set of pre-agreed KPIs, DFID will cancel the contract and close the project by 30 April 2019.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The programme Impact is “Improved stability and inclusive development prospects in Western
Region.” This is measured through two indicators:
 i) Average poverty rates in the Western Region coastal districts
ii) Citizen perceptions of local stability, development equity and economic prospects in the Western Region.

These two indicators have been in the logframe from programme onset. The poverty rate is measured every two years while the Citizens perception of local stability, development equity and economic prospects has been measured yearly since 2016.
The Citizens Perception and Socio-Economic Survey (CPSES) baseline and end line conducted in August 2016 and August 2018 respectively suggest a reduction in poverty from 23.4% at baseline to 19.5% at end line. However poverty increased in the Ellembelle district, making it difficult to assess the programme’s impact on poverty reduction. Households in the end line sample also had an average Poverty Probability Index (PPI) score of 2.5 points more than households in the baseline sample. (The PPI runs from 0 to 100, with higher scores meaning less likelihood of poverty). Households in the end line sample were 4% less likely to be poor than at baseline. It is likely that impact of the WRCF’s interventions on community incomes will have a time lag particularly for the TVET intervention as it takes time to develop the necessary skills level in local communities for increased participation in the oil and gas industry as well as other industrial value chains. The scale-up of the aquaculture interventions is now beginning to yield results, however, more effort and engagement is required to fully utilise the impact of the interventions of oil and gas companies in the communities. Economic livelihoods interventions supported by industry in the communities have so far had very mixed results with 47% of such projects not currently functioning according to the dialogue platform data.

Poverty Likelihood in six coastal districts – Baseline to Endline
	Jomoro	Ellembelle	Ahanta West	Nzema East	STMA	Shama	Total
Baseline Poverty likelihood	28.2%	26.2%	25.7%	26.8%	11.4%	22.7%	23.4%
EndlinePoverty likelihood	22.3%	27.1%	21.7%	20.4%	8.3%	18.7%	19.5%
Baseline average PPI score	42.0	43.1	42.8	42.5	58.1	45.8	45.6
Endline average PPI score	45.9	41.4	46.7	46.5	58.5	48.3	48.1

Source: Citizens Perception and Socio-Economic Survey 2018

Households in the endline sample had an average PPI score of 2.5 points more than households in the baseline sample. (The PPI runs from 0 to 100, with higher scores meaning less likelihood of poverty). Households in the endline sample were 4% less likely to be poor than at baseline.

Measuring citizen’s perceptions of local stability, development equity and economic prospects in the Western Region at endline suggest a positive change with the development equity indicator. Political stability and economic prospects remained unchanged since 2016.

Socio-political development in 6 coastal districts – Baseline to Endline
	Political stability	Development equity	Economic prospects
Baseline (Aug 2016)	21.0%	20.0%	10.0%
Endline (Aug 2018)	20.8%	25.5%	10.0%

Source: Citizens Perception and Socio-Economic Survey 2018

The programme is off track regarding the main outcome level indicators, the establishment of a ‘sustainable and functioning foundation’. While the foundation has been established, so far the WRCF hasn’t been able to raise non-DFID funds to cover its operational cost. The programme is set to enhance its engagement with the PC and with oil, gas and petroleum companies to raise funds to cover the foundation's annual operational costs. DFID will review progress early in January 2019 against a set of pre-defined indicators. If these are not being met, the programme will end by April 2019.

Explain major changes to the logframe in the past year (1/2 page)

The programme logframe was amended during the year to respond to the recommendation of the programme mid-term review, ensuring the programme adjusted to changes in the operation environment as well as promoted the sustainability of the foundation after DFID funding will have come to an end. One of the biggest changes was the removal of reporting on direct jobs and incomes, which is now captured by an indirect measure.

Describe any planned changes to the logframe as a result of this review (1/2 page)

No major changes are envisaged as a result of this review.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year(1 page)

The programme’s VFM framework was updated in September 2018 in line with changes suggested at the programme’s mid-term review to ensure the programme continues to deliver value for money.

Economy - The revised framework includes three indicators to assess the programme’s delivery on economy which are: evidence that the WRCF has secured value in the procurement of goods and services, the ratio of national staff time to international staff time, and average daily fees.

As in previous years, in 2018, the programme adhered to its procurement guidelines. 80% of total procurement of £339,505[1] has been managed through open or limited competition and the remaining through single sourcing for purchases of less than £500. Important elements of single sourcing such as hotels and air tickets have been based on pre-qualified vendor selection.
[1] Up to September 2018

Between December 2017 and September 2018, the ratio of national to international staff time inputs was 11.6:1 compared to a ratio of 7:1 in DAI’s programme budget and a ratio of 9.5:1 in 2017. Average daily fee rates over this period were £265 compared to a budget provision of £305 and a figure of £282 in 2017.

Efficiency - The updated framework includes three indicators to assess efficiency during the remainder of the programme: the ratio of expenditure on fees and expenses to expenditure on programme activities; the proportion of output milestones achieved; and the cost per beneficiary of WRCF interventions.

The ratio of expenditure on fees and expenses to expenditure on programme activities is assessed as an approximate indicator of productivity[2]. Between December 2017 and September 2018 DAI’s invoices show that the ratio of expenditure on fees and expenses to expenditure on activities was 2.96:1 compared to 1.81:1 as provided for in DAI’s overall contract and an outturn of 1.87:1 in 2017. Importantly the high ratio in 2018 reflects a slowdown in activity expenditure while the implications of the mid-term review and DFID’s follow-up were considered, and the log-frame revised. The ratio is expected to fall significantly in the final two months of the 2018 programme year as activity spend accelerates.
[2] The revised VfM framework document highlights that in this context it might be preferable to adopt an indicator that monitors the allocation of staff time between management functions on the one hand and technical support and implementation on the other but notes a time recording system to make this possible is not in place. The framework document questions the WRCF’s high “administrative spend”, however, the analysis underlying these concerns classifies all fees and related expenditure as administrative and is based on comparisons with other programmes without taking account of variations in programme design and context.

Cost per beneficiary is also included in WRCF’s VfM framework as a common over-arching indicator of programme efficiency (although one that is also difficult to compare across programmes, for example because of wide differences in the way beneficiaries are defined and in the nature of benefits). Here, focusing specifically on the WRCF’s dialogue process and adopting the method of calculation favoured by DFID’s follow-up to the mid-term review[3], costs per dialogue beneficiary in 2018 are estimated to have been £15.56. This figure compares to £17 per beneficiary in 2017 (estimated on a comparable basis).
[3] The calculation includes the full programme costs of the dialogue platforms apart from the WRCF staff costs. Beneficiaries include both “unique” participants and participants who have already benefitted in previous years.

Effectiveness - The programme’s revised VfM framework measures four effectiveness indicators: non DFID resources secured for the operation of the WRCF; the resources leveraged by the WRCF; the increase in incomes secured by the beneficiaries of economic interventions; and the programme’s success in building constructive relationships between communities, government and industry as highlighted by the programme’s annual Community Perceptions and Socio- Economic survey (CPSES). Evidence on indicators below shows an improved value for money performance:
- By September 2018 WRCF had secured £220,000 of non-DFID funding to support TVET activities
- Evidence from the evaluation of economic intervention pilots and TVET follow up surveys illustrates that the beneficiaries of the WRCF’s programming have secured increases in incomes.
Equity -Equity indicators in the revised VfM framework cover both participation in the WRCF’s interventions and the distribution of benefits. Participation data shows that programming targets covering gender and age have been largely met. In particular, in 2018 there was a high degree of inclusivity in the dialogue process where the target of reaching at least 1,305 female participants for the first time was exceeded by 10%. In total 46% of all participants in the dialogue process, including those who had previously been engaged, are female.

The CPSES will cover equity considerations in the context of the WRCF’s success in building constructive relationships between communities, government and industry. The programme will provide detailed analysis of the equity indicators in the new CPSES data for future reporting.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The programme’s value for money performance is assessed to be positive as presented above with the results suggesting a moderately positive return for investment. Achieving the programme’s objective of establishing the programme as a sustainable self-financing foundation would further strengthen the value for money proposition of DFID’s investment into the programme. There are, however, significant concerns around WRCF’s ability to raise industry resources to fund the sustainability of the foundation by the January cut off date. The industry engagement strategy, recently developed by the WRCF, is designed to address this and sustain engagement with government and industry to be able to attract funds for the foundation.

The current prospects for leveraging industry resources for the TVET intervention in 2019 and beyond provide an overall positive outlook for the cost benefit analysis (CBA), ensuring the programme will continue to represent value for money if these resources materialise.

DFID in agreement with DAI has approved a contract amendment which recognises a new break point clause in January 2019. In the absence of credible funding projections to sustain the programme as an independent entity, the programme will be closed down by the end of April2019.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Major

The 2017 Annual Review rated the programme as Major Risk reflecting the uncertainties surrounding the sustainability of the Coastal Foundation beyond DFID funding, as well as the innovative nature of the programme. There is no change to the programme Risk rating for 2018.

As at October 2018, the WRCF still seeks commitment to external funding for the Foundation beyond the end of the projected DFID support. The team’s stakeholder engagement plan developed in November 2018 seeks to sustain industry and government engagement to enable sustainable funding outside of DFID. Acknowledging the major programme risk has let to DFID instigating a contract amendment with a new break point clause in January 2019 to be activated in the absence of credible funding projections to sustain the programme as an independent entity. Should that risk materialise, the programme will be shut down by the end of April 2019.

The programme team maintains the risk register, updates it quarterly and communicates feedback to DFID through the programme quarterly reports. There are currently no ‘severe’ risks at the residual risk level (post mitigation assessment). The table below presents the five risks identified as severe prior to their respective mitigation strategies.

Risk	Rating	Mitigation	Rating after mitigation (residual risk)
Resources mobilised are inadequate to fund core Foundation operations	Severe	DAI/WRCF has developed a value proposition and stakeholder engagement plan, which is being used to engage the Petroleum Commission and oil and gas companies for buy-in and investment. / The WRCF Governing Board has a committee on government and corporate engagement to support DAI/WRCF efforts.	Major
The Petroleum Commission and/or Oil Companies may not commit to funding the Foundation's Dialogue Platform due to low interest	Severe	At the request of the Petroleum Commission, WRCF has drafted and submitted a MoU with the Petroleum Commission requesting support for Community Engagement and CSR Impact Assessments in the seven coastal districts of the Western Region. / In addition to engaging the PC and oil companies, WRCF will engage the Western Region House of Chiefs and other key high-level government officials to advocate supporting the Foundation. The new stakeholder engagement plan will form the basis of this engagement.	Major
Funding from Industry for TVET and/or livelihoods may not be able to sustain operations of Foundation	Severe	The WRCF has developed and submitted proposals to Industry to fund further and more substantial skills development projects, which could help to sustain the foundation more broadly. / The WRCF will engage the Western Region House of Chiefs and key high-level government officials to lobby for boarder support from industry.	Major
Transitioning from a programme to an independent organisation will have implications for staff, resource mobilisation, operations and stakeholder relationships	Severe	The Foundation will develop a change management plan to ensure smooth transition from a programme to a sustainable entity	Major
The programme will lose crucial programme staff as a result of uncertainties surrounding DFID’s continuance of the programme beyond April 2019	Severe	The WRCF is communicating openly with team members and good teamwork is enhancing continuity. However, the current Team Leader has now given his notice and will leave the organisation in due course. DAI will be consulting DFID and the foundation board on his replacement. In the meantime, DAI has provided immediate cover within the team and from DAI to limit the impact on the programme.	Major

F: DELIVERY, COMMERCIAL& FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Delivery against planned timeframe
The programme has so far utilised about 80% of the available budget however 91% of fees has been spent. Overall the phasing of spend is progressing as planned with the exception of the fees component.
Delivery is broadly on track in terms of log-frame milestones, with the notable exception around funding for the sustainability of the foundation.

Programme activity spend was generally low at the beginning of the year partly due to the ongoing mid-term review.

The WRCF is preparing a financial/business plan to transition from being a DFID funded programme to a self-sustaining foundation funded by external funding sources. The Transition Plan will be submitted for DFID approval during the last quarter of 2018.Among other elements, the Transition Plan will set out the timetable for transferring the WRCF (DFID funded) programme staff to the WRCF, the Foundation. During this period of transition (and perhaps beyond), the WRCF may invoice the WRCF programme for services, including staff costs, in much the same way as any vendor retained by the programme to deliver services.

The contract with DAI was signed in September 2014, before the recent revision of DFID’s overall contractual framework. There have been six contract amendments to date. The overall contract value and end dates have remained consistent throughout these amendments.

DFID in agreement with DAI has put in place a contract break clause that allows DFID to give three months’ notice for the programme closure should it not meet a number of milestones related to establishing the foundation as a self-sustaining entity by early 2019. Should the WRCF not meet pre=agreed KIPs, the programme will close at the end of April 2019.

DAI and DFID-Ghana have a good working relationship and have worked in collaboration on the revision of the Logframe, Theory of Change, the addendum to the original Business Case and the contract amendment, capturing the terms of the above break clause. Regular calls have been held between the project’s management and leadership and DFID to discuss strategic and commercial issues.

Financial

DFID is satisfied with the quality of financial management. The narrative and financial reporting requirements set out in the contract between DFID and DAI have been adhered to.

PwC concluded an independent audit of the WRCF on November 30th 2017. The final management letter was agreed on 5th March 2018. The findings showed that DAI had robust financial management systems and processes and that these systems have been cascaded to implementing partners. The report also found that WRCF’s due diligence was satisfactory and in line with the contractual expectations of DFID. There were a few recommendations and accounting notes to be followed up on by DAI emanating from the report. These were closed out in June of 2018. An independent audit of WRCF’s financial management for the period December 2017 will again be conducted by PwC from January of 2019.

Programme funding includes a grants component covering agreement with ‘Conversation Managers’ (CMs) for the provision of facilitation services under the programme’s Dialogue Platform component. Grants are processed and paid quarterly. However, Conversation Managers are required to provide monthly financial reports to the WRCF. These reports are reviewed by the Finance & Operations Manager and feedback is provided to individual CMs where necessary. At the end of each quarter, quarterly activity and financial reports are submitted and reviewed by the Dialogue Lead and the Finance & Operations Manager.

Asset monitoring and control

The assets of the WRCF consist of office furniture, office equipment and two project vehicles. All programme assets are systematically recorded and reported in the comprehensive assets register, which is regularly updated and shared with DFID on a quarterly basis. As part of DFID Ghana’s risk management, regular assessments are carried out on the effectiveness of the control systems and physical existence of the assets. 90% of assets acquired under the project were verified in August 2018, however, it was observed that the some assets allocated to the CMs were not captured in the Asset Register.

There is a risk of missing assets allocated to the CMs as the register kept by the CMs do not correspond with the master register held by the WRCF. The DFID programme Manager is working with DAI to ensure this is rectified.

Recommendation:
The WRCF should update the assets register (in the recommended DFID format) by January 2019 with all assets held by CMs and economic intervention beneficiaries and all assets should be properly branded.

Date of last narrative financial report(s)	October 2018
Date of last audited annual statement (s)	30th Nov 2017

G: MONITORING, EVIDENCE &LEARNING (1-2 pages)

Monitoring (1/2 page)

Programme monitoring has been conducted satisfactorily and drew data from several sources as follows;

Quarterly Programme Update Meetings: DFID Ghana holds quarterly programme update meetings with the WRCF/DAI team to monitor progress on activities and to ensure appropriate linkages with related programmes. The DFID Ghana Lead Adviser/Senior Responsible Officer also has informal 1-2-1 meetings with the WRCF Team Leader and Technical Director. This has helped build trust and strengthen communication.

Feedback on reports: Since the last annual review, the team has submitted three quarterly progress reports (narrative and financial) covering progress towards achieving the log-frame milestones. Detailed feedback has been provided to help the WRCF Team improve and enhance delivery.

Structured DFID Ghana commissioned reviews: DFID Ghana conducted an expenditure verification on the programme in 2018. Findings from the exercise indicate progress on the majority of recommendations and improvement in the financial management of the programme compared to previous years. The expenditure verification exercise serves as a fiduciary risk mitigation measure given the nature of the project. DFID Ghana has also assessed the delivery mechanism and control of the programme and identified key risks and drawn up mitigation measures. An annual external audit is being planned for January 2019.

The WRCF PMT’s own Monitoring: Apart from DFID’s monitoring, the WRCF programme team also conducts quarterly monitoring visits to all CMs to assess progress of work and to provide technical inputs as required. An annual lesson learning event was also conducted with all key stakeholders including beneficiaries to assess progress and to share lessons on the programme.

Evidence (1/2 page)

There are currently no plans for DFID Ghana to carry out an evaluation of this programme.

The Citizen Perceptions and Socio-Economic Survey (CPSES) which is used to draw information against high level log-frame targets was conducted in 2016 and has been repeated in 2018 to gather evidence on poverty and citizen perceptions of local stability, development equity and economic prospects. Results from the data have been presented in earlier section of this annual review.

Learning (1/2 page)

The WRCF collects beneficiary feedback from communities which is used to tailor the programme and shared with relevant stakeholders to inform the design of community interventions.

Progress on recommendations from previous reviews (1/2 page)

The key recommendation from the previous annual review centred on sustainable funding for the WRCF post DFID funding. The focus of the programme intervention in 2018 has been to ensure financial sustainability after DFID funding. Progress has so far been made with the TVET intervention. The programme has developed a stakeholder engagement plan for sustained industry engagement to ensure sustainable funding outside of DFID funding going forward.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe.This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc.) as a result of the review and once agreed at the appropriate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g. costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g. Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan)or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg. accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback)and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’agenda and as far as possible disaggregate information by age, sex, disability, geography(update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided