## Project Completion Report

Project Title: Fair Trade, Employment and Poverty Reduction Research
Date Project Started: 2009 Date Review Undertaken: June 2014

Introduction and context

What support did the UK provide?
DFID provided an Accountable Grant of £692,958 to the School of Oriental and African Studies (SOAS) over 4 years (2009/10-2012/13). / The closing date of the grant was extended to 31st March 2014 through two no cost extensions (EDRM 3839646, 4272237) to allow for increased research time in-country, and initial testing and validation of findings and recommendations through participant feedback. / The grant was used to fund quantitative and qualitative (including some longitudinal) research to provide a better understanding of the prevalence of waged work in the study areas and the comparative benefits and disadvantages (especially for women workers) of agricultural certification schemes compared to non-certified production. The research took a labour market approach and was implemented in Ethiopia and Uganda and focused on two commodities in each country: coffee and cut flowers in Ethiopia, and tea and coffee in Uganda. The approach was characterised by a high level of field research time, as well as the use of new technology for data collection, as the project progressed.

What were the expected results?
The SOAS research project aimed to enable companies, certification bodies, governments and donors (including DFID) to have a better understanding of the income effects of fair and ethical trade for poor people engaged in wage labour. / The expected impact, outcome and outputs were: / Impact: Poverty reduction policies, company decisions and certification standards are shaped by high quality evidence of the impact of agricultural produce certification on poverty. / Outcome: Relevant stakeholders have a better understanding of comparative benefits and disadvantages (especially for women) - from a labour market and poverty reduction perspective - between special certification and non-certified production. / Output 1: Appropriate research methodology to assess effectiveness of certification schemes on poverty reduction among women and men is available. / Output 2: Longitudinal assessment completed of the comparative benefits and disadvantages (especially for women) - from a labour market and poverty reduction perspective - between special certification schemes and non-certified production. / Output 3: Research results and policy messages disseminated to donors, certification bodies and business.
	What was the context in which UK support was provided?
	Millions of poor people in developing countries are involved in exporting agricultural commodities, as waged workers on large and small farms. Certification schemes are based on theories of change that suggest they reduce poverty, directly or indirectly. / There has been little research on the results for the poorest households of certified production, relative to non-certified production, on waged workers compared with smallholder producers, or on the living standards of women dependent on wage employment in agricultural commodity production. / The June 2007 International Development Committee report on Fair Trade and Development concluded “we believe there should be more systematic analysis of the impact of Fair Trade on poverty and would urge DFID to contribute to this process”. In response, DFID supported this research by SOAS and provided an accountable grant to the Natural Resources Institute (NRI) for Assessing the Impact and Governance of Sustainability Certification and Labelling Schemes (EDRM 4209728).

Detailed Output Scoring

	Output 1: Appropriate research methodology to assess effectiveness of certification schemes on poverty reduction among women and men is available.
	Output 1 score: A (Outputs met expectations) / Target: positive peer review of literature on methodology as part of final report. This target has been achieved. The SOAS team wrote a paper on methodological approaches in 2012 which was peer reviewed and published in the Canadian Journal of International Development in January 2014. SOAS presented on their methodology at workshops with standards organisations (e.g. ISEAL June 2013) and academic conferences (e.g. Lisbon June 2013). The final technical report (received in April 2014) includes a comprehensive overview of the approach to selecting research sites, sampling, longitudinal studies and the inclusion of life work histories. As is common in academia, discussions around the findings of the report include debates on the methodological approach (see paragraph 2.9). Consensus on the validity of the methodology will evolve once the data has been made public and the FTEPR team publish their full report findings in peer-reviewed publications. / Target: positive review of field report as part of final report. This target has been achieved. Discussions with the research team indicate that they received positive feedback from workshops held in Uganda and Ethiopia in November 2013. They were able to provide detailed explanations of how their data are generated, in response to challenges that their findings are controversial. The final technical report includes analysis of the field reports and the draft report was shared with the Advisory Group, Fairtrade Foundation, Fairtrade International and key DFID colleagues for fact-checking. Some of these stakeholders contest some of the data analysis and findings, and this discussion can continue with the FTEPR team once the field report data is in the public domain. / Impact Weighting (%): 25% Revised since last Annual Review? No / Risk: Low Revised since last Annual Review? No
Output 2: Longitudinal assessment completed of the comparative benefits and disadvantages (especially for women) – from a labour market and poverty reduction perspective – between special certification schemes and non-certified production
Output 2 score: A (Outputs met expectations) / Target: completion of sex disaggregated data set with methodological and technical notes. This target has been achieved. The data set was generated through 1700 survey responses, with 401 longitudinal follow up survey responses. The sample was generated from 8349 GPS census data points and 4743 initial household survey interviews. The methodologies paper records that the research respondent data set has been disaggregated (p30, http://ftepr.org/wp-content/uploads/how-to-do-fieldwork-draft.pdf), and that the research samples were representative of the wider population sample. The data set has been analysed for sex disaggregated correlations between a number of characteristics. Further regression analysis and propensity score matching has been applied to key labour market data. Findings include daily wage rate levels for women and men in each sector. / Target: peer validation of research findings through academic conferences and workshops. This target has been achieved. The research team presented their methodology and an initial research finding at the Research Network session with standards organisations in the ISEAL conference on 11/06/13. The SOAS team reported that the audience was impressed by the methodology, including use of GPS technology to track farmworkers in each survey round of the longitudinal study, and the number of qualitative ‘life histories’ – a relatively large sample (more than 100 work history interviews). Fairtrade International expressed their concern that SOAS had not provided them with an indication of their findings, as a courtesy, before presenting an initial finding that shows a negative correlation between wage levels and certification in Ethiopian flower production sites. In June 2013, the SOAS team co-organised a seminar in Lisbon at the European Conference for African Studies and presented methodology and preliminary findings, which were discussed by academic peers. The research team also held three workshops to report their research findings and test their assumptions with stakeholders in the research countries; one in Uganda (04/11/13) and two in Ethiopia (07 & 08/11/13). One of the Ethiopia workshops was particularly targeted at a government audience. Participants in the Kampala workshop became very engaged in a debate on child labour, which is not an issue that the research can inform systematically (although it was clear at each survey site that children below the age of 15 are engaged in waged work). / The key findings of the report were that waged work was prevalent in researched rural areas producing agricultural export commodities, including small-holder sites. All workers/producers included in the research were found to be very poor, both in certified and non-certified sites. The research found that Fairtrade certification had no positive impact on wage levels of waged workers at the research sites, and there appeared to be a strong correlation between lower wages and certification which could not be explained by external factors such as gender or geography. The report states that the research findings cannot be extrapolated to imply causality and there are several hypotheses for this which require further investigation. / The methodology purposively does not include engagement with the standards organisations as part of the implementation process to ensure there was no research partiality, but Fairtrade Foundation and Fairtrade International were asked to fact-check the draft final report. In the longer term (beyond the lifetime of this project) the research team will also produce articles on their findings for publication in academic journals and other outlets. / Impact Weighting (%): 60% Revised since last Annual Review? No / Risk: Low Revised since last Annual Review? No

Output 3: Research results and policy messages disseminated to donors, certification bodies and business
Output 3 score: B (moderately did not meet expectations)
Target: Research team implemented dissemination strategy. This target has not been achieved. As noted above, the SOAS team undertook a range of activities both in the UK and overseas to disseminate and test their finding ahead of publication. Their draft dissemination scoping document (EDRM 3855206) mapped a wide range of indicative opportunities for media, visual communications and interactive learning. They committed to ensuring public open access to their data. The SOAS team received detailed comments on the scoping document from the Advisory Group in 2013. In subsequent follow up, DFID reiterated the importance of finalising a dissemination strategy and getting the data set into the public domain. The team did not finalise a dissemination strategy, which led to DFID staff trying to clarify the team’s dissemination plans through multiple email exchanges just prior to the end of the grant period. By the close of the contract, the data set was not yet available in the public domain, although SOAS remain committed to ensuring that this is achieved. / The SOAS team proactively approached media outlets, resulting in coverage in: / BBC World Service: http://ftepr.org/2014/ftepr-on-bbc-world-business-report/ CBC Radio: http://ftepr.org/2014/how-fair-is-fair-trade/ Observer: http://www.theguardian.com/global-development/2014/may/24/fairtrade-accused-of-failing-africas-poor Observer (SOAS comment piece): http://www.theguardian.com/global-development/2014/may/24/harsh-truths-are-necessary-fairtrade Daily Mail: http://www.dailymail.co.uk/news/article-2639135/Fairtrade-fails-help-poor-farmers-Damning-investigation-says-profits-sent-help-Uganda-Ethiopia-not-reach-workforce.html / As anticipated from initial feedback from stakeholders involved in pre-publication events, the publication of the final technical report generated debate and controversy. As well as debates over the methodological approach, some stakeholders felt that in media coverage SOAS extrapolated their findings out beyond the context in the researched sites in Uganda and Ethiopia to make comments about the Fairtrade system as a whole. The report and media coverage led to rebuttals from various organisations: / Natural Resources Institute, University of Greenwich: http://www.nri.org/news/2014/fairtrade-benefits-in-the-complex-world-of-sustainable-development ISEAL Alliance (standards systems umbrella body): http://www.isealalliance.org/online-community/blogs/fairtrade-and-poverty-reduction-iseal-alliance%E2%80%99s-response-to-the-soas-report / CGDev blog http://www.cgdev.org/blog/million-dollar-question-does-fairtrade-work / http://ftepr.org/wp-content/uploads/Response-to-Fairtrade-Statement-on-FTEPR-Final-Report-Posted.pdf / Fairtrade International: http://www.fairtrade.net/single-view+M5a2383b864f.html / On visual communications, the SOAS team presented their findings via a photo exhibition at SOAS, which was opened by the Ethiopian Ambassador to the UK on 16th May 2014. Other visual communications activities were not completed during the project funding period so while the research team aim to pursue these options independently, they have not been funded by DFID. For example, the team planned to produce education materials for use in secondary schools. However, this work was only partially complete by the end of the project funding period and so was therefore only partially funded by DFID. No progress was made regarding a documentary film pitch, due to time constraints and shifting priorities for the project. These changes to the dissemination approach is reflected in the underspend referenced in 3.6. / Impact Weighting (%): 15% Revised since last Annual Review? No / Risk: Low Revised since last Annual Review? No

Results, cost, risk and value for money

Achievements and results
Has the logframe been updated since last review? No / Final output score: A (Outputs met expectations) / Intended outcome: Relevant stakeholders have a better understanding of comparative benefits and disadvantages (especially for women) - from a labour market and poverty reduction perspective - between special certification and non-certified production. / Outcome score: B (moderately did not meet expectations) / Target: Four examples of companies, certification bodies, Government and donors indicating their intention to adapt policy, programming or organisational arrangements as a result of this research. It is too early to tell if the intended outcome of the FTEPR project was achieved. As outlined in output 3 above, this research has generated considerable debate. But it is too early to tell if it will influence the growing area of academic debate and discussion in the standards system sector. / There are some early examples of the FTEPR research findings contributing to DFID’s understanding of rural economic development in Uganda and Ethiopia. In Ethiopia this will inform colleagues delivering the Private Enterprise Programme Ethiopia (PEPE) programme which targets key economic sectors, including horticulture. In Uganda, this research is contributing to the evidence informing the development of a Northern Ugandan agribusiness development project. / Impact and sustainability / The intended impact of the FTEPR project is: ‘poverty reduction policies, company decisions and certification standards are shaped by high quality evidence of the impact of agricultural produce certification on poverty’. The FTEPR project has made a contribution to the body of research on standards systems and has been disseminated amongst standards bodies, donor governments, as well as in the public domain via press and radio. The research has caused controversy, with some standards stakeholder organisations publishing rebuttals addressing the communication of findings (see paragraph 2.9). The academic and standards sector debate around the impact of standards systems will continue, and FTEPR’s contribution will evolve as their findings are discussed in peer-reviewed literature and other researchers draw their own analysis from the data once it is publicly available.
Cost and timescale
Was the project completed within budget / expected costs: No / SOAS submitted a request for additional funds for this project in 2010, and the project budget was increased by £85,484. The request was based on two developments affecting the project: / The most significant was the adoption of the new research technologies (GPS and hand-held tablets) which led to additional equipment and unexpectedly high training costs. / The second was the higher than budgeted number of staff days in the field that were required to ensure the data was of sufficiently high quality, through additional capacity support to the field-based teams. Senior SOAS academics made a number of field visits to train supervisors and enumerators, and to support and advise the Research Officer leading the project. / DFID considered this request to represent good value for money, as it enabled the research team to collect much better quality data at larger scale, leading to a more representative sample, and less survey attrition for the longitudinal sample and life histories. It has long been recognised that data quality for longitudinal research on the impact of certification and similar schemes has been limited by difficulties locating participants in rural areas for repeat surveys. The new survey techniques used in this SOAS research went some way to addressing this issue during this particular study, enabling repeat surveys and qualitative life-history information of participants, with the potential to share lessons & improve data quality for future rural research projects. The data collected by SOAS will eventually be shared publically, contributing to the wider knowledge base and global debate on certification schemes (see paragraph 2.7). / Key cost drivers: / The majority of the budget was for research staff time, including senior SOAS academics based in London, a lead Research Officer, academics based in Addis Ababa and Kampala, and locally recruited researchers and enumerators. Other key areas of expenditure were fieldwork, international and domestic travel, and dissemination of research findings. As detailed above, additional funding was spent on staff days and equipment costs. / FTEPR budget breakdown* / *Projected total spend. Although all spending activities have been completed, the final invoice for this project is still outstanding, as the project financial end date is not until 30 Sept 2014, allowing the team time to compile their receipts and payments. Total spend reimbursed so far is £641,280.12, of the total accountable Grant budget of £692,958. SOAS have estimated that their final invoice will come to roughly £31,500, which will leave an underspend of roughly £20,000. / Was the project on-track against original timescale: No (see 1.2 regarding no cost extensions)

Evidence and evaluation
Assess any changes in evidence and what this meant for the project. / This research was funded in parallel with an accountable grant with Natural Resources Institute at the University of Greenwich. As outlined in paragraphs 1.7-1.8, both pieces of research were funded in response to a limited evidence base on the impact of standards systems. While other research has emerged during this time, the SOAS (and NRI) research have made a contribution to this under-researched area as a multi-country, multi-commodity longitudinal study. / Set out what plans are in place for an evaluation. / There are no plans for an evaluation of the SOAS FTEPR project, as the findings and quality of research will be interrogated through future academic debate.

Risk
Output risk rating: / Low (the risk rating did not change in the course of the project) / Risk funds not used for purposes intended: / Low (SOAS submit an annual audited financial statement of accounts for this project) / Climate and environment impact / The SOAS research project is expected to have a low impact on the climate and environment beyond the impact of researchers’ air travel, as the sole outputs are research papers and knowledge transfer activities.

Value for Money
Did the project represent Value for Money: Y / In the context of this project, value for money is best understood in terms of how effective and efficient the project is in delivering its intended results. / Research is one effective way of informing evidence-based decision making. DFID has a strong commitment to commissioning world class research, and ensuring that it is readily available to those who can use it around the world. DFID uses research such as this to inform its own programming on responsible business. / The research team identified weaknesses in existing approaches to study in this field, namely: largely qualitative, case study-based studies that collected data from producers rather than directly from waged or self-employed workers, with weak rationale for selection of study sites and use of inaccurate official household lists and often a lack of adequate research independence. By addressing some of the weaknesses that have characterised earlier approaches, the research team believe that they have developed a mixed methods fieldwork methodology that will be replicable in other research studies focusing on rural development economics research, and in particular in research on labour markets in developing countries. They have contributed to capacity building of local and international researchers by training them in how to apply the methodology. Evidence of this includes the training of enumerators in both Ethiopia and Uganda, and sharing the fieldwork methodology amongst SOAS PhD and MSc students as a learning tool. / A number of efficiencies have also been realised in the project that have improved the value for money of the research. For example, the project team was able to build on a tried and tested approach based on their previous experience of including life histories (‘nested’ in a quantitative survey sample) in rural labour market survey-based research in Mozambique and their many years of experience in designing rural labour market surveys in a number of African and other countries. They drew on research expertise from other disciplines and adopted new technological methods that included the use of GPS and hand-held computers for sampling. This increased the efficiency and significantly reduced the inputting and search costs of large scale data collection and will also potentially increase the value for money of future research. The use of easily accessible visual representation of data sampling and collection methods will also add value when demonstrating the impact of the project. See, for example, use of Google maps and Google earth (http://ftepr.org/research-sites/). / The research team also note that the high proportion of time spent in the field increases value for money, as it improves research quality, enables the team to adapt to circumstances and ensure good data collection, and increases the transfer of research skills to local researchers. / It should be noted that DFID’s internal management of the project could have been improved from a VfM perspective. This project required significant staff time which raised questions on whether the management arrangements for this research were the best value for money. This research project was initiated by the Trade Policy Unit and then taken forward by the Private Sector Department within DFID. Neither team has research experts. At times, colleagues needed to draw on the skills and expertise of the Research and Evidence Department (RED) and other departments to support the delivery of the FTEPR project. From a VfM perspective, large-scale research projects may be best managed from within the Research and Evidence Department. When projects are not managed from within RED, clear internal guidance and support is required to other departments managing research projects, when findings are controversial and there is not time for academic peer review and debate within the grant period. / It is too early to judge whether the debate, discussion and uptake of the research findings has been as constructive as hoped and therefore whether the research represents VfM from this perspective. Response to dissemination to date has focussed more on the interpretation of the data rather than the data itself. The public availability of the research data will add greatly to the value for money this project represents, as the dataset is broader than the analysis presented in the report and this will allow standards organisations and academics in this field to conduct their own analysis and interpretation, thus furthering the evidence base regarding standards systems impact.

Conditionality
Not applicable

Conclusions
As outlined above, DFID funded SOAS to undertake the FTEPR project researching the impact of standards system on poverty reduction, with particular regard to waged labour, in order to address a lack of evidence in this area. The research itself represents a longitudinal assessment of these comparative benefits and disadvantages in three commodities across two countries. The methodology, along with the research findings, is now being debated by academics in this field. The report has been disseminated widely through print and broadcast media, amongst standards organisations and donors, and the research team have plans in place for peer-reviewed publications. The publication of the final FTEPR report has provoked some controversy, both in public and standards system sector, generating increased debate and – hopefully - learning in this area. / The data will soon be publicly available; ensuring other researchers in this field can further debates on the impact of standards systems on poverty reduction. Colleagues in Private Sector Department will liaise with the SOAS FTEPR researchers to ensure this is completely in a timely manner.

Review process
This review was conducted by staff in PSD’s Business Engagement Hub. / This review draws on the logframe (EDRM 3678809), the 2014 annual review (EDRM 4305038), no cost extension documents (EDRM 3839646, EDRM 4272237), the final technical report (EDRM 4528178 and 4528178) and the SOAS dissemination strategy (EDRM 3855206).