Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	21 March 2016

Title: Public Private Partnership (PPP) Unit Support, Sierra Leone
Programme Code: 203819	Start Date 10/07/2013	End Date: 11/11/2015

Summary of Programme Performance

Year	2014	2015	2016
Programme Score	B	A	A
Risk Rating	Medium	Medium	Medium

Financial Position

Original Programme Value	£ 1.2 Million
Extensions/ amendments	None
Log-frame revisions (with dates)	August 2014 / June 2015
Total programme spend	£ 1,043,542.54

Follow up actions required following closure

Complete regular DFID project closure actions including reconciliation of finances based on final expenditure and disposal of assets. This will be completed by 30 April.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203819
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203819/documents

Outline of programme and what it has achieved

The Public Private Partnership Project (PPP project) was a two year project which ran from July 2013 to November 2015. Its purpose was to help the Government of Sierra Leone to build its ability to use Public Private Partnerships as an infrastructure financing/ management structure.
The aim of this project was to set the conditions and environment for PPPs in Sierra Leone, and to conduct a set of pre-feasibility studies. Significant progress has been made on creating these conditions within the PPP unit. That said, there has been little progress on finding and implementing PPPs. In part, this was due to Ebola, and the effect of the epidemic on investors. But post-Ebola, progress on finding high-quality investors and implementing PPPs has not materialised. This is at least partly due to weaknesses in the business environment. Without improvements to the business environment, and hence a deal flow, we have decided that further investment in the PPP unit will not deliver benefits on our shared, ambitious, timescale and to deploy our resources against other Government of Sierra Leone priorities.

The project had a total budget of £2.14 million. Of this DFID contributed £1.2 million, with the African Development Bank and UNDP providing the remainder of the funding (see table below). The programme was managed by IMC Worldwide.

Table showing donor allocations to the project 2013-15

Item	Funder	Amount
Staff salaries and running costs	GoSL	£490,000
International PPP Advisor	UNDP	£250,000
Financial and legal advisors and training	AfDB	£200,000
Equipment, technical assistance and studies	DFID	£1,200,000
Total		£2,140,000

DFID’s support contributed 56% of funding to the PPP Unit over the reporting period. UK support included £125,000 for office equipment and vehicles, £575,000 for a PPP Technical Advisor and a £400,000 fund for pre-feasibility studies.

Infrastructure remains one of the major development bottlenecks of Sierra Leone as outlined in the Agenda for Prosperity and 24 Month Post Ebola Recovery Plan. Sierra Leone has poor infrastructure which severely restricts economic growth and leads to highly unequal access to government and private sector services. The Government of Sierra Leone’s (GoSL) priorities under the 24 Month Post Ebola Recovery Plan include rapidly developing electricity, transport, water and sanitation infrastructure and establishing an improved environment for the private sector.

The GoSL recognised PPPs as a potential modality to mobilise both funding and expertise for infrastructure development and is committed to working with private investors to share the costs, benefits and risks of infrastructure development through PPPs. However GoSL has limited financial resources and technical capacity to undertake the necessary reforms to policies, legal and institutional frameworks for appraising and managing PPPs to develop major infrastructure projects. Prior to this project there was an estimated pipeline of $1.7 billion of proposals by foreign investors and the GoSL was investing significant resources in appraising and administering this pipeline, which mainly consisted of unsolicited proposals. The GoSL set up a central PPP Unit to help line ministries manage the appraisal of these proposals and the subsequent contracts. Given the UK’s extensive experience with PPPs, the GoSL requested that the UK support building capacity of the PPP Unit and this support was delivered under this project.

The PPP Unit was set up with the following objectives:
- Promote sustainable PPP solutions for infrastructure projects within the country and to foreign investors
- Align investment into priority areas laid out in the Agenda for Prosperity and the Public Investment Plan
- Ensure that employment creation and local sourcing objectives are adequately embedded in the large PPP contracts
- Bring in core expertise required to negotiate deals and attract investors
- Assist GoSL negotiate strong, sustainable deal terms that ultimately benefit the people of Sierra Leone
- Give investors the confidence that they are dealing with informed and professional counterparts
- Introduce strong process, transparency and governance standards into the often ad-hoc and opaque area of deal negotiation.

Following the outbreak of Ebola, the main technical adviser to the PPPU was evacuated in August 2014 and only permitted to return in May 2015. An interim strategy for work during the Ebola outbreak was agreed in September 2014, but not implemented until January 2015. The key outputs in the interim strategy were:

- Completion of Strategic Plan for PPPU
- Preparation of a paper for reorganisation the PPPU to that of a Project Management Office.
- Preparation of guidelines and presentations to advice local government and MDAs on PPPs.
- Amendment of pipeline study and review of PPP guidelines created by CRISIL (an infrastructure advisory service) to make them suitable for local use.
- Write high level Local Government guidelines for small PPP Projects
- Finalise presentation for MDA workshop and local Government.

In response to the Ebola crisis and changed economic context, the PPP Unit changed its focus from large scale investments to smaller scale community based investments, what were called PPCP (Public Private Community Partnerships) projects. The key PPCPs were: i) Road maintenance, ii) Low-Cost Housing, and iii) Waste collection Kenema & Makeni (supported by DFID).

The DFID funded PPP project had two components. The main component was a TA team that delivered the bulk of the project covering drafting of PPP legislation, conducting feasibility studies, capacity building and training. The second component was smaller and focussed on improving the capacity of the PPPU to facilitate, negotiate, and implement PPPs.

The overall impact targeted by the project was to deliver sustainable development and inclusive green growth: wide participation in, contribution to and benefit from economic growth, particularly in environmentally sustainable activities. The project outcome was to support the PPP Unit to accelerate economic growth through development of a sustainable infrastructure.

The project made some progress towards its outcome and contributed to its impact. Its greatest contribution is in terms of development of a policy, and the legal, regulatory and institutional frameworks for PPP implementation. PPP Unit has delivered its outputs as detailed below. The logical framework for the PPP Unit as a whole, including government investment and contributions from other development partners, sets out the key outputs described in Section C.

Key achievements of the programme:

The enactment of the PPP Act 2014. This piece of legislation has provided the right balance of reassurance to the private sector and procurement process. The PPP Act has set new standards for PPP procurement, based on delivery of service, risk transfer, and good governance process.

The passage of this Act has limited the vast majority of ‘unsolicited’ proposals being considered to a much reduced number, and it is expected that they will be eliminated for all large scale infrastructure projects in the future.

The PPP Unit has, with its workshop and sensitization programmes with MDAs (including local government) sent out a clear message of opportunities for investment in partnership with the private sector.

The conduct of the pre-feasibility studies added some impetus for potential PPP projects and was extremely useful to provide more practical guidance on PPP projects and to facilitate identification of high potential projects that would potentially warrant investment opportunities.

The result of the pre-feasibility studies will lead to identification of PPCP projects that could be implemented in the short to Medium Term. Based upon the conclusions of the PFSs projects that could be taken forward include:

- King Jimmy Mall & Market; construction, with support for Market Phase as PPCP
- Estuary Integrated Transport Study; Lungi Hovercraft Services & Sea Taxi Service
- Solar Projects: Identification of Projects on Grid and Off Grid, standalone
- Low-Cost Housing: PPCP project pilot pro-poor housing options
- Solid Waste Collection: Rollout of PPCP programme for Kenema & Makeni

The PPP Unit benefitted from high level PPP master-classes facilitated by British expertise with funds from the British High Commission in Freetown. In October 2014, the PPP unit reacted quickly to a strong steer to utilise DFID funds to focus on those PPP projects in the pipeline list that were pro-poor and could be taken forward as part of economic recovery. This included a number of interesting PPP solutions for building rural feeder roads, on rebuilding the health system and providing basic services, and job creation. The PPP Unit responded to a proposal from IFC that they help develop the PPPs on Health in line with IFC strategic objectives. Further work needs to complete to get these PPPs off the ground.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment: B - Outputs have moderately not met expectations

The outcome of the project is to support accelerated economic growth through PPPs to build infrastructure through development of a sustainable and an enabling infrastructure. Overall there was mixed progress towards this outcome. The Ebola outbreak and a major downturn in the extractives sector contributed to a significantly worse investment climate which meant that the GoSL’s had to change its focus from large scale infrastructure to smaller scale investments with local partners. A summary of progress against the outcome indicators is presented below.

Given this

Outcome Indicator 1. Cumulative value of private investment in infrastructure PPPs (US$850m) from PPP Pipeline & Direct Advice.

Progress was made against this outcome indicator of cumulative value of private investment in infrastructure and electricity production. Two projects, Bumbuna Phase II Hydro Power Project; and 128 MW CEC Thermal HFO Plant, attracted investment of $883 million, although this cannot be wholly attributed to PPPs for which this project is directly responsible. PPP Unit led negotiations on the Copperbelt project which involved procurement guidelines, to enable competitive negotiations. This represented best market criteria in line with other negotiations in PPP projects, and many concessions were agreed with the private partner as well as output deliverables and timescales for phasing implementation.

Outcome Indicator 2. Amount of electricity produced (120 Megawatt MW)

At the time of writing progress is measured at 98 megawatts, which is a 22 MW short fall from the agreed target.

Outcome indicator 3: The percentage of households connected to the water network in Freetown. This indicator could not be assessed due to lack of data.

Outcome Indicator 4: Number of PPPs for which transaction structuring and guidance was provided.

The PPPU advised on thirty eight projects during the reporting period, showing progress towards the 2015 target of 40 projects but not quite meeting it. However, given the circumstances created by Ebola and the concurrent economic downturn, progress was fair. An estimated 38 projects are under active advice and support across several sectors (energy, transport, fisheries and other MDA’s), and are beyond concept stage.

Output Score and Description

This project scores and ‘A’ – Outputs met expectations.

	2014 AR	2015 AR	2016 PCR
Output 1	B	A	A
Output 2	B	B	A

The PPPU delivered against both outputs, with Output 1 consistently recovering from underperformance in 2014 to score an A in this review. Output 2 has just about met expectations by the end of the project.

The PPP Unit Strategic Plan 2014 to 2019 and “Sustainability Report” (May 2015) and “Project Management Report” sets out a considered assessment of the PPPU’s future strategy and capability requirements, and there is a greater clarity about the role and responsibilities of the PPPU in the future, which does represent some evidence of the unit’s plans for sustainability beyond the end of DFID support.

Considerable progress has been made in improving the capabilities of staff in managing PPPs. In total ten staff were enrolled in the specialised PPP (“IP3”) qualifications. Five study tours benefitting 11 staff was organised, which has been beneficial to core and new staff members.
The PPP unit has within the reporting period held 4 joint seminars with other MDA’s and local authorities on PPPs; this is in addition to 6 individual workshops all geared towards enhancing the capacity of the work force.

Under the sustainability plan of the PPP, there are aspirations to extend PPP training and guidance to MDAs, which should reduce the resource demands of the PPP Unit staff.

The programme exceeded the target of five pre-feasibility studies supported. Seven pre-feasibility studies were conducted and that were prepared as templates for the appraisal of potential PPP projects.
These studies covered a number of sectors (water supply, waste and recycling, Affordable Housing, Transaction Support Facility, energy and roads).

Lessons and how these have been shared

This PCR summarises the lessons learned against the three main work streams: legal framework; training and capacity building; and feasibility studies. These will be shared with the partner.

Overall, the programme has been successful in meeting its targets and deadlines, despite a number of challenges. The slow start in the first year of the project and the Ebola mobilisation restriction has meant a heavy end of project workload and the preparation of projects that can go to market from May to October 2015.

Transaction Fund. This PPP Unit ‘Transaction Fund’ is a good way for ‘development agencies’ to fund specific PPP projects related to pro-poor strategies as donations can be ‘earmarked’ to the development partners mandate for conditional support. Indeed, this approach can accelerate the PPP start up stage of projects. Feedback from the PPPU reiterated the important role of DFID in getting this fund into legislation as part of the sustainability of the PPP.

The handling of unsolicited proposals. The PPP Act made unsolicited proposals the exception and not the rule. At the end of the first year of the PPP Act, the number of the unsolicited proposals had dropped from nearly 100% to approximately 10% of investment proposals. This was in part due to the PPP Act and capacity building of MDAs and political support from the President. This alone freed up the PPP Unit staff to undertake more productive work rather than assessing and reporting on unsolicited proposals for projects which were unlikely to reach implementation.

Capacity building and training. The training events and study tours were an important component of PPP capacity building strategy. As a result more technical advisory support could be provided to line ministries and Local Councils on PPP legislation, negotiation and management of PPPs.

Local and international consultants working together. As evident in the quality of the PFS reports the PPP Unit gives priority to local consultants to build capacity. However the local/regional capacity in this area is for now is very limited. The key lesson learnt is that it is important to recognise that local consultants alone in the early stages of PPP Unit life are not necessarily the best option. The combination of local and International consultants is highly recommended to get the balance right over the coming years, depending on the technical subject matter.

Living up to expectation and understanding the client. The lesson is to identify clients, manage expectations and build process and procedures at the very start of the project to ensure good and clear working relationships.

Working in partnership with the private sector on projects that support PPPs, through innovative development partner tools. The PPP Unit should make use of legal pro-bono advice from facilities such as the Africa Legal Support Facility run by the ADB, LASER – which is a UK CMP focused on TA for commercial courts to improve the investment climate, and the Herbert Smith Freehills and GoSL Fair Deal programme (HSF have provided support to the PPP Unit in the past).

## C: DETAILED OUTPUT SCORING

Output Title	Quality Assurance to PPP transactions provided: increase in a number of quality PPP transactions
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	50
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target	Progress
1.1: Number of feasibility (pre-feasibility) studies for PPPs completed	5	Seven pre-feasibility studies undertaken and completed by December 2015.
1.2 Evidence of VFM from pre-feasibility studies (review findings)	Positive / VfM	Evidence of value for money in that pre-feasibility studies were completed on time and there is evidence of impact available.
1.3: Number of line ministries and Local Councils requesting support from the PPP Unit	25	There are over 24 projects (emanating from MDA’s and Councils) at various stages of development and concepts for PPP processing. Projects are at the early development stage and active.

Key Points

Since the last annual review in June 2015, the PPP Unit has made accelerated progress in achieving in its outputs. Given the increased political and financial support for the PPPU, the unit is much closer to being a sustainable unit. However, ongoing support is likely to be required to ensure the Unit benefits from further technical expertise support on developing the PPPs to additional stages of development.

On the second indicator, the unit with support from the PPPTA has demonstrated a clear understanding of principles of value for money in PPP’s and have demonstrated how the principles of value for money, affordability, and delivering public services to a consistent standard in potential PPP projects is the most effective way of identifying all of the PPP relevant issues. The financial viability analysis in each project proposal added value.

Achieving indicator 1.3 is a key to the sustainability of the project; in this regard staff was enrolled on the rigorous and specialised PPP IP3 training course. This is complemented by commitment to on-the-job learning and shadowing of more staff including newly recruited personnel. The PPPU is committed to improving the management of unsolicited proposals and there is demand from MDAs for support and guidance.

Summary of responses to issues raised in previous annual reviews

Most recommendations on this output from the last annual review were followed through and achieved. Pre-feasibility studies were conducted and concluded before the end of the programme. Value for money was achieved at the advisory phase and it is expected to be demonstrated when the five completed pre-feasibility studies are taken to market.

Capacity building initiatives such as delivering training content to convey key awareness raising messages, identifying PPP opportunities are ongoing with MDAs and local councils, and this is evidenced by the sharp fall in the number of unsolicited bids and high levels of consultations between the PPP unit and local councils.

There is evidence to showing a clear demonstration of value for money in some of the completed PFSs.

Recommendations for future programmes

MDAs’ capacity and understanding of PPPs should continue to be increased so that the PPP Unit can support these MDA’s in the most effective way. This approach will mitigate against the risk of unaffordability.

The PPP Unit should establish stronger linkages with the Sierra Leone Export and Investment Agency (SLIEPA) to help to drive implementation of projects to the market and attract higher quality investment opportunities to support it feasibility studies.

There is a strong incentive for the PPP unit to realign the selection criteria for the PFS projects to secure the right balance of leadership between local and International consultants.

Output Title	Capacity to facilitate, negotiate, and implement PPPs improved
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	50
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target		Progress
	2014	2015
2.1 - Evidence of sustainability of PPP Unit beyond 2015 (review findings)		Sustainable Unit	PPP Act Section (v) provides for PPP Unit to achieve greater sustainability. / This is reflected in the five-year PPP Unit Strategic Plan 2014 to 2019.
2.2 - Number of staff trained and managing PPPs, including technical advisers	12	15	Distance Learning Programmes completed for up to 11 staff; 6 Workshops held staff; and / 4 Joint seminars with MDA
2.3: Successful regional study tour: links to regional partners established (number of links); number PPP project revisited	4	6	11 staffs in total benefitted from 5 study tours and clear partnerships links were established.

Key Points

This review has identified that performance against the indicators is mixed but there is some strong evidence that the PPPU has been sufficiently empowered and capacitated to facilitate, negotiate and implement PPPs. However there is also enough evidence to suggest that it will always be hard to ensure that the PPP unit retains expertise that has been built up through capacity building support provided by donors.

It is important to reiterate the point that was captured in the 2015 annual review that there has been an improvement in the legal and institutional frameworks in which the PPPU operates, making it more sustainable. The passing of the PPP Act marked an important milestone towards increasing the robustness of the process for agreeing PPPs. This Act requires for feasibility studies and Cabinet approval for any public sector organisation to enter into a PPP, giving an important level of scrutiny and oversight to this process. PPPU staff interviewed commented several times that the number of unsolicited PPP bids, and the time spent considering these, has subsequently decreased.

Summary of responses to issues raised in previous annual reviews

Some of the recommendations under this output were implemented. Capacity Building and the strengthening of the PPP Unit continue to be a priority; hence study tours were successfully conducted.
The GoSL is building on the existing organogram of the office structures and staff incentivisation is also being addressed. Three new staff joined the Unit and the three local consultants were incorporated into the GoSL payroll. The critical issue of staff retention has been addressed; PPP unit staffs have been awarded attractive contracts with competitive salaries in a bid to retain institutional knowledge. Furthermore the GoSL has increased its commitment to the unit by providing a Le 1.1 billion for administrative charges excluding salaries.

Recommendations for future programmes

The TA team has managed to successfully roll out several training programmes covering foundation/basic level courses which have benefitted over 8 staff, trained on various aspects of PPP such as project screening, legal aspect, financing models, project contracts etc. These courses are geared towards building the capacity of PPP staff to assume full responsibility for running a successful PPP outfit. The PPP unit should however, continue to secure commitment from the Government of Sierra Leone to ensure that sustainability of capacity of staff is retained.

The project, with DFID support, has achieved a significant increase in the capacity of the PPPU which should now prioritise promoting sustainable PPP solutions for infrastructure projects within the country and to foreign investors. The following recommendations are made to achieve this:

1. Ensure that employment creation and locally sourcing objectives are adequately embedded in the large PPP contracts
2. Bring in strong expertise required to negotiate deals and attract investors
3. Assist GoSL negotiate strong, sustainable deal terms that ultimately benefit the people of Sierra Leone
4. Give potential investors the confidence that they are dealing with informed and professional counterparts
5. Introduce strong process, transparency and governance standards into the often ad-hoc and opaque area of deal negotiation.

The establishment of PPP pre-feasibility fund by DFID helped to get the PPP Unit off to a good start. This in turn, led the PPP Unit to look at setting up a PPP Transaction Fund for long-term sustainability of the project.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key costs of the project were the costs of the technical assistance (TA) team. The TA was procured through DFID Procurement Group using a competitive bidding process.
The TA team has delivered all of the agreed outputs and has provided additional services beyond the end of the project.
A total of £1,043,542 (87%) of the total project budget was utilised during the project life cycle. The budget had three components. Component one is for the provision of office equipment for the Public Private Partnership (PPP) Unit. Component two was to provide three project vehicles as part of the implementation of the project and a third component for procurement of the PPP Technical Assistance (PPPTA) and payment for pre-feasibility studies. The period between the last annual review to the end of the project year saw a substantial utilisation of funds allocated for pre-feasibility studies, which resulted to increased overall budget usage to 87%. The planned pre-feasibility studies were completed during the remainder of the contract time from the last annual review.

VfM performance compared to the original VfM proposition in the business case

The business case proposed achieving value for money by delivering on the outcomes of improved electricity access, and by managing the project expenses for the PPPTA and pre-feasibility study (PFS) fund in an effective and efficient way. Previous annual reviews had revealed that financial reports and invoices were submitted on time, and that the pre-feasibility fund was efficiently managed; indicative of the fact that the service provider (IMC Worldwide) was meeting expectations to deliver value for money.

During the period of the EVD outbreak and the eventual evacuation of the PPPTA, progress on the project in general was slower than expected. However, this did not impact upon the value for money offered by the project as payments by DFID were based on reimbursement of actual expenditure.

Concerns were, however, raised in the previous Annual Reviews over the added value being delivered by IMC’s provision of more detailed technical input on the actual PPPs rather than limiting their role to only managing the PFS funds, procurement and payments and quality assurance to the work carried out by the PPPTA. These concerns were addressed by transferring the required skills to PPP staff and building relationships with Government and other MDA’s during the last quarter of 2015 resulting into an effective technical input by the IMC leading to a completion of the project deliverables on time.

Assessment of whether the programme represented value for money

Previous reviews of the project indicated that there was little tangible evidence that this project actually represented value for money, due to the lack of tangible progress towards implementing a PPP. However, the Value for Money argument outlined in the Business Case is still relevant. The total cost of running the PPP Unit itself is extremely small compared to the size of transactions that it could be involved in. It is expected that the efficiencies gained in the processing of PPPs and more effective PPP contract negotiations led to significant savings for the GoSL, although this cannot be quantified.

. There was a departure from a milestone based approach in order to improve VfM and financial controls for DFID whilst resources were being prioritised for the Ebola response. Irrespective of the loss in time due to the EVD outbreak, pre-feasibility studies were completed and reports submitted on time.

Quality of financial management during programme

Financial reporting requirements have been adhered to with all scheduled invoices for this project submitted on time, and to the required level of detail and accuracy. Invoices have been in line with forecasts, despite the exceptional circumstances in Sierra Leone in 2014 -15. The most recent audited annual statement of IMC Worldwide for 2013/14 Financial Year was submitted on 3rd March 2016 for the period ending 31st December 2014. The 2014/15 statement is yet to be received.

Date of last narrative financial report	19 June 2015
Date of last audited annual statement	8th May 2015

E: RISK (½ page)

Quality of risk management over the life of the programme

Over the course of the two years, the programme focused on supporting the PPP Unit in order to:

1. Promote sustainable PPP solutions for infrastructure projects within the country and to foreign investors
2. Align investment into priority areas laid out in the Agenda for Prosperity and the Public Investment Plan
3. Ensure that employment creation and local-sourcing objectives are adequately embedded in the large PPP contracts
4. Bring in the core expertise required to negotiate deals and attract investors
5. Assist GoSL to negotiate strong, sustainable deal terms that ultimately benefit the people of Sierra Leone
6. Give investors the confidence that they are dealing with informed and professional counterparts
7. Introduce strong process, transparency and governance standards into the often ad-hoc and opaque area of deal negotiation.

This project identified and mitigated against a number of risks, several of which were dealt with well, but others less well:

Political and governance risks. Conflicting priorities between State House and MDAs resulted in limited usage of the Unit and/or poor quality PPPs through ad hoc negotiations. The PPPTA was procured to help agree priorities and to address conflicting interests between State House and line ministries, promote transparency in the Unit operations and publication of PPP agreements. A steering committee was formed to assess the performance of the unit.

Environment risk and climate change resilience. Insufficient data on potential impact of poor planning and design of infrastructure on climate change (both inadequate preparation resulting in damage, and over-compensation resulting in excessive costs). Efforts were made to link with climate scientists (governments, universities and agencies) to assess the impact of climate change on infrastructure in Sierra Leone.

Programme Management Risks - Poor performance by Technical Advisor. A well-qualified individual was selected as TA to undertake this assignment. Monitoring was done to assess project progress and risks to delivery. DFID had the option to withhold payments and terminate the contract in the event of poor performance.

Sustainability Risk - PPP Unit becomes reliant on technical assistance and capacity is not built; Government also becomes reliant on private sector suppliers without considering longer-term options of public sector provision. Experienced short-term specialists worked with local staff to pass on expertise.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

This project was completed according to the planned timeframe of two years on 31st December 2015, despite the significant impact of Ebola on the project and GoSL operations. Most milestones in the logframe for this project were achieved irrespective of the impact of the Ebola crisis which resulted in the withdrawal of the PPP Technical Adviser to the UK and the subsequent difficulties agreeing a revised workplan for the second and final year. Travel restrictions due to Ebola affected plans for staff study tours under the second output.

The project was agreed in June 2013 but the procurement was not concluded until Autumn 2013. After this, IMC quickly deployed the DFID-sponsored Technical Adviser for the PPP Unit to Sierra Leone on 11th November 2013, at which point implementation began. Therefore this PCR actually only covers twenty months of implementation.

The procurement process for the TA, including the study tour and pre-feasibility fund, was undertaken through a framework contract. DFID Sierra Leone had previously experienced delays in similar programmes, and reviewed the process and actions when procuring for this project. The result was that the time from approval to mobilisation was reduced from almost seven months (for the Market Development Programme) to four months for the PPP Unit.

Performance of partnership (s)

A strong partnership between DFID, IMC Worldwide and the PPP Unit added value to the overall success of the project. It allowed for frank and technical discussions on delivery, and an effective approach to project management. The PPP Unit showed consistent willingness along to take on recommendations to deliver a high quality programme in a challenging governance environment.

An amicable solution to earlier tensions between IMC and the PPP TA on governance and oversight within the project was resolved with the timely intervention DFID.

Asset disposal and value obtained by DFID

A total of £101,697.11 of assets (including three vehicles, 45 KVA Pramac Generator, and office equipment) were procured and provided to the PPP Unit. A complete asset register for this project held by the PPP Unit was provided to DFID on 28 November 2014.
A Toyota Land cruiser 2011 costing $30,000 procured for the use of the IMC Technical Adviser was returned to DFID at the end of the assignment. An asset spot check conducted on the 5th August 2015 revealed that all assets bought for the PPP Unit were intact and in good working conditions.

The programme team will follow up on assets and prepare a submission to the Head of Office with recommendations on disposal plans, in accordance with the Smart Rules guidance on assets.

G: CONDITIONALITY

Partnership principles assessment

Sierra Leone is a recipient of general budget support from the UK.  This arrangement is guided by a memorandum of understanding between DFID and the Government of Sierra Leone that requires it to demonstrate commitment to the UK’s partnership principles, in line with the UK’s conditionality policy.
A comprehensive assessment is made each year and updated each quarter, prior to budget support disbursements.

The establishment of the PPP Unit by the Government of Sierra Leone, and its continuing support for the remit of the Unit can provide evidence to support delivery against two of the four partnership principles:

- Progression and completion of PPPs could be used as evidence to show that Partnership Principle 1 - a commitment to reducing poverty and achieving the Millennium Development Goals (MDGs), is being upheld
- Reduction in the numbers of unsolicited proposals by an approximately 10% of investment proposals in the first year of the project is an evidence to prove the PPP Unit is providing an additional check, and service to Government in quality assuring tendering, negotiation and implementation of PPPs and therefore GoSL delivery against Partnership Principle 2 - a commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption.

H: MONITORING & EVALUATION

Evidence and evaluation

There is evidence in many countries for the value of PPPs; similarly there is lots of evidence of poor quality and bad VfM PPPs also. PPPs are inherently risky for Governments and sometimes they are completely unaffordable for the public sector when set against other priorities.

Note that the PPP Unit existed prior to DFID funding in this project. Therefore, in our monitoring exercises DFID was looking for a positive improvement in the capabilities and process for managing PPPs.

DFID undertook a review of evidence of the costs and benefits for centralised PPP Units as part of the original Business Case for this project and although findings reveal no quantitative evidence, the findings did identify a number of factors which can contribute to the success of central PPP Units. These were incorporated into the design of the project.

Previous annual reviews revealed that the four key factors that were incorporated in the design of DFID’s support to the PPP Unit were being addressed. At the close of this project, the Unit can now be viewed to have a good level of authority at the centre of government and a transparent process is in place to assess PPP proposals. Irrespective of the progress made, technical expertise and capacity still needs to be enhanced if the PPP Unit should be truly able to manage complex PPPs for the Government of Sierra Leone going forward.

Monitoring progress throughout the programme

Monitoring of this project has been undertaken through the review of quarterly written progress reports provided via IMC worldwide from inputs provided by the PPP-TA and PPPU.

Further monitoring has been taken forward through DFID’s direct engagement with the PPP Unit staff (with PPP-TA in attendance), the IMC representative, and donors supporting the PPP Unit