Annual Review - Summary Sheet

Title: Public Private Partnership Unit Support in Sierra Leone
Programme Value: £1.2 million		Review Date: 30/06/2014
Programme Code: 203819	Start Date: 10/07/2013	End Date: 30/09/2015

Summary of Programme Performance
Year	2014	2015
Programme Score	B
Risk Rating	Medium

Summary of progress and lessons learnt since last review

The 2014 milestones for this project have not been met. Partly this is because they were set incorrectly as milestones to be achieved within one year of the start of the programme instead of from progamme approval. Since the contract was only awarded to IMC Worldwide on 16 October 2013 and implementation started in November, this review only captures eight months of support from DFID to the Public Private Partnerships (PPP) Unit. However, it is unlikely that the milestones will be met by the first anniversary of impelementation because other constraints have also affected progress on this project, particularly the delay of the World Bank funded PPP pipeline study which was due for release in January 2014 but was only completed in July 2014. There have also been challenges in the day to day running of the Unit caused by ICT infrastructure and budget constraints, and delays in the PPP Act being passed into law by the Government of Sierra Leone (GoSL).

DFID support to the PPP Unit through this project has played an important role in establishing the Unit itself, still represents Value for Money and should continue. This review has found that there is visible progress in meeting the key objective of this project which is to help establish an effective PPP Unit that can provide technical support and quality assurance across government in prioritising, negotiating and managing public private partnerships (PPPs).

The project now needs to accelerate progress towards meeting the results identified in the Business Case and logframe. Although the programme progress is assessed as B, it is not proposed to draft and implement a Programme Improvement Plan. The key factor resulting in the B is the late completion of the World Bank PPP priority study. This has now been completed and other actions can now continue as originally planned.

Summary of recommendations for the next year

The key elements that will help achieve the intended results of this project are:

1. A stronger results based focus by the PPP Unit that can develop and deliver against a strong list of high priority PPP projects. Now the WB pipeline study has been completed, DFID should work with other donors and the PPP Unit Steering Committee to ensure that this happens as soon as possible.
2. Review the role of the Technical Assistance and agree with the Unit and other donors if changes are needed to reflect the progress and the current situation better.
3. The PPP Unit should capitalise on its own status, working with donors where necessary, to help ensure that the PPP Act is passed into law by the GoSL. This is important as at the moment there is a risk that negotiations will be taken forward with private investors on high risk PPP projects on the basis of having good knowledge of what potentially will be in the PPP Act, rather than the solid basis of the law itself.
4. Now the Unit is fully staffed and operational, it is time to review issues around sustainability and to ensure these are addressed in the next few months.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3805179.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4048168.xlsx

Outline of the programme

Sierra Leone has poor infrastructure which severely restricts economic growth and leads to highly unequal access to government and private sector services. The Government of Sierra Leone’s (GoSL) priority until 2017 in the Agenda for Prosperity is to rapidly develop electricity, transport, water and sanitation infrastructure and establish an environment where the private sector can flourish. The need is urgent in order to take advantage of the current surge in the economy led by investment in mining and agriculture, and to improve poor people’s access to public and private sector services and income generating opportunities.

GoSL has neither the financial resources nor the technical capacity to develop major infrastructure projects. It is committed to working with private investors to share the costs, benefits and risks of infrastructure development through PPPs. There is an estimated pipeline of $1.7 billion of proposals by foreign investors and GoSL has set up a central PPP Unit to help line ministries to manage deals. GoSL created the PPP Unit in order to:

1. Promote sustainable PPP solutions for infrastructure projects within the country and to foreign investors
2. Align investment into priority areas laid out in the Agenda for Prosperity and the Public Investment Plan
3. Ensure that employment creation and locally sourcing objectives are adequately embedded in the large PPP contracts
4. Bring in core expertise required to negotiate deals and attract investors
5. Assist GoSL negotiate strong, sustainable deal terms that ultimately benefit the people of Sierra Leone
6. Give investors the confidence that they are dealing with informed and professional counterparts
7. Introduce strong process, transparency and governance standards into the often ad-hoc and opaque area of deal negotiation.

The Government, African Development Bank and UNDP are all providing resources and DFID was also requested to provide support. The UK agreed to provide £1.2 million over two years in order to establish, support and build capacity within a PPP Unit in the Government of Sierra Leone. This support, provided by DFID, includes £125,000 for office equipment and vehicles, £575,000 for a PPP Technical Advisor and a £500,000 fund for pre-feasibility studies. The overall contributions to the PPP Unit are shown in the following table:

Item	Funder	Amount
Staff salaries and running costs	GoSL	£490,000
International PPP Advisor	UNDP	£250,000
Financial and legal advisors and training	AfDB	£200,000
Equipment, technical assistance and studies	DFID	£1,200,000
Total		£2,140,000

DFID’s support therefore contributes substantially to the outcomes of the PPP Unit (56% of funding). The expected impact is inclusive green growth that leads to prosperity and improves human development. The expected outcome is accelerated economic growth through the development of a sustainable and an enabling infrastructure. This will be achieved more rapidly, at lower cost and with less risk to government. The key outputs for the PPP Unit are:

- Electricity generation rising from 76.5MW in 2013 to 120MW in 2015
- An additional 120,000 people with access to electricity by 2015
- Over $500m invested in PPPs in electricity, roads and other infrastructure in 2014 and 2015.
- An effective system of prioritising, negotiating and implementing PPPs

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The expected outcome of our support to the PPP Unit is accelerated economic growth through development of a sustainable and an enabling infrastructure. Until some PPP projects move in to implementation phase there will be no results to show progress against these indicators that are attributable to this project.
However there is evidence that the PPP Unit is making progress towards meeting the expected outcome through the provision of advice on legacy PPP projects and tendering of pre-feasibility studies to inform selection of new PPP projects for future implementation.

Overall output score and description

B - Outputs have moderately not met expectations

The PPP Unit has started well, it is now fully staffed and is taking forward a number of intiatives to develop several important potential PPPs identified by GoSL. This is a major step forward and attributable in part to DFID’s very rapid procurement of office equipment and mobilisation of TA. If the WB PPP pipeline study had been completed on time and released in January, it is likely that the Unit’s priorites could have been established and some pre-feasibility studies already completed now. This is the single biggest factor in the slow progress of the programme, and one which was outside DFID’s control.

Without the prioritised pipeline, the PPP Unit has run the risk of wasting its future efforts, energy and resources on a list of PPPs that may not be top priorities for the country in terms of generating economic development. DFID and other donors expect to see this risk mitigated effectively now that the delayed WB PPP pipeline study has been finalised as the study should provide strong analysis to prioritise potentially viable PPP projects for tendering and implementation.

There has been some steady though limited progress in building the capacity of the staff of the PPP Unit and this needs to be accelerated as does the capacity building of staff in key line ministries that will work alongside the PPP Unit on key PPP projects that they identify to be taken forward in their areas of focus.

Key lessons

The PPP Unit is dependent on support from no less than five donors. Coordination amongst donors on the provision of all inputs that support the workplan is incredibily important and coordination over the timing and delivery of inputs for the PPP Unit could have been better. IN particular, a Plan B” strategy could have been adopted when it because clear that the WB PPP pipelinestudy was likely to be seriously delayed.

It has taken GoSL and donors more than two years to operationalise the Unit and provide it with the staff and assets that it needs to take forward its role. There are a number of reasons, particularly around leadership in GoSL, but it would have been helpful to have a single lead donor coordinating support and helping GoSL address the leadership issues quickly. UNDP’s support was effective in beginning work on some specific PPPs but did not include the donor coordination. The African Governance Initiative (AGI) attempted to provide some coordination support but this was ineffective.

Much is expected from the PPP Unit by the Government of Sierra Leone and there is also pressure from the Private Sector to take forward 132 idenitfied PPPs totalling an conservative estimate of $1.7billion. Managing these pressures will take strategic leadership from the head of the PPP Unit and lessons might be learnt from this project on how Sierra Leone has dealt with this challenge in particular.

Key actions
It is unclear when the PPP Bill will be passed by Cabinet although it is expected that this will be passed very soon. This leaves the PPP Unit slightly exposed in terms of carrying out its mandate. Action: DFID and other donors may need to raise this issue with the Government if it is not resolved within the next quarter.

Prioritisation of PPPs is a key challenge and is not helped by the existence of two separate pipelines, and the frequency of facing further unsolicited proposals from Line Ministries and the private sector. Action: Although the (very late) arrival of the WB PPP pipeline study will help, GoSL still needs to agree their priorities. DFID, with the support of other donors, will still need to support the PPP Unit in that process.

Once a prioritised list of PPPs are agreed, the Unit will need a clear workplan for implementation. Action: DFID should work with all donors to support the Unit in drafting a realistic and technically focused workplan which will also maximise capacity building opportuntiies.

Both the capacity and experience of PPP Unit staff are starting from a low base, and a careful balance needs to be struck in terms of the use of the international TA provided by donors for both PPP development and capacity building in the Unit. The capacity will be needed in order to achieve longer term sustainability. Action: DFID will need to ensure that sustainability is a key focus throughout the rest of the life of this project.

ICT infrastructure is still a weak link in the Unit’s day to day operations and a key frustration to going about business efficiently and effectively. Action: DFID will need to consider whether to provide support for correcting this.

Has the logframe been updated since the last review?

It is recommended that the Logframe be updated as a result of this review.

Currently two logframes exist – one has been developed by the PPP Unit for the PPP Unit as a whole and DFID also has a separate Logframe to capture its particular support to the Unit. Both logframes are identical at the Impact and almost identical at the Outcome levels. This approach was intentional because the Unit should have a logframe which they own and feel accountable for. However, they have chosen to set this in the GoSL context of the Agenda for Prosperity which is extremely ambitious. It was felt therefore that DFID’s support could not realistically be measured against this ambition, and a second DFID-only logframe is being used to assess progress for this annual review.

The link between the two logframes has been questioned and some thought is needed on how the DFID logframe can be revised both to reflect changes in the project and to maintain a link with the Unit’s logframe for the future.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Quality assurance to PPP transactions provided: increase in number of quality PPP transactions
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	50
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (2014)	Progress
Number of feasibility (pre-feasibility) studies for PPPs completed	4	0
Evidence of VFM from pre-feasibility studies (review findings)	Postive VFM	Not assessed until Jan 2015
Number of line ministries and Local Councils requesting support from the PPP Unit	7	Met

Key Points
The three indicators suggest mixed progress. The first indicator (number of pre-feasibility studies) could not be achieved because of the lack of pipeline priorities and hence delay in all PPP preparation work. However work has been undertaken to enable the studies to go ahead rapidly once the prioritise have been agreed. In particular, the PPP Unit have played a role in progressing the following high priority PPP projects:
- The FCC Mall & Market project - the pre-feasibility study for this project has now gone out to tender, with 3 bids having being evaluated by the PPP Unit in partnership with Freetown City Council and the Ministry of Finance.
- The Deep Sea Port in Freetown project - the World Bank group are now funding pre and full feasibility studies.
- The Freetown Estuary Transport Proposals project - this is now ready to go to EOI stage
- The Large Scale Thermal Power Plant ‘bulk off take agreement’ project – a paper has been produced for the GoSL on a strategy for agreeing bulk power off-take to justify the building of a new 600MW thermal power plant. This paper has assessed the Value for Money of and appropriate risk sharing between public and private partners for the proposed project.
- Reviewing the potential of including a PPP project on the national roll-out of Fibre Optic Cable to support growth of the private sector and private investment.

The second indicator (VFM for the studies) is to be assessed at a set milestone once a number of studies have been completed. This milestone has not yet been reached, so no assessment was made of the indicator.

The third indicator aims to reflect the extent to which line ministries and local government recognise the new Unit as a provider of quality support on PPPs. This indicator was achieved. Seven line ministries have already requested support from the PPP Unit on a total of 33 potential PPP projects.

An underlying assumption in the logframe is that the Unit is operational and beginning to establish itself as a provider of PPP technical advice and support. Since this is not spelt out as an indicator, the logframe fails to capture the significant progress made over the last year. Despite the delay in the pre-feasibility studies, the Unit has successfully undertaken:
- Development of initial plans for scoping out PPPs delivered by local authorities
- Development of initial plans for scoping out PPPs on water network investment, and a number of projects that can also address youth unemployment: affordable housing, recycling of solid waste, road maintenance, and selling and marketing co-ops for local content.
- Official advice from the PPP Unit has been provided on the draft PPP bill.
- Guidelines on procurement procedures and writing ToRs for RfPs for pre and full feasibility studies have been produced.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first annual review of this project, therefore there are no issues from previous annual reviews to address.

Recommendations
1. In order to focus the Unit and protect the Unit from wasting energy on unsolicited bids from the private sector and line ministries, a prioritised list of PPP projects, which draws on the findings of the recently completed World Bank study, must be agreed between the PPP Unit, the Ministry of Finance, donors providing support to the PPP Unit and, ideally, sanctioned and approved by Cabinet.
2. A number of pre-feasibility studies must then be rapidly tendered and completed for priority PPPs.
3. Flexible and appropriate guidelines for implementing PPP projects by local government must be completed in order to accelerate progress on implementing PPPs in line with the Agenda for Prosperity
4. Capacity building for local councils and line ministries must start rolling out by the PPPTA, in line with the Terms of Reference for that position.

Output Title	Capacity to facilitate, negotiate and implement PPPs improved
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	50
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (2014)	Progress
Evidence of sustainability of PPP Unit beyond 2015 (review findings)	Sustainable Unit by 2015	To be assessed March 2015
Number of staff trained and managing PPPs, including technical advisers	12	Training plans for 12 set up but four dropped out
Successful regional study tour: links to regional partners established (number of links)	4	1 (through study tour) but other links also set up

Key Points
Despite the fact that milestones against the indicators for this output have not been met, there is visible progress on developing the capability and capacity of the PPP Unit to facilitate, negotiate and implement PPPs, this includes:
- A fully staffed and equipped PPP Unit with all donor provided TA advisors in place for capacity building is now in place.
- Plans are in place to have all staff undertake a formal certificate programme which will conclude in December 2014 for 12 staff in the PPP Unit. However four have dropped out so further work needed.
- A significant and successful UNDP led study tour to South Africa to learn from best practice on negotiating PPPs has completed.
- Staff from the PPP Unit led and supported Freetown City Council in managing the tendering process, and evaluation of bids for the pre-feasibility study to assess the feasibility of a PPP to design and build a new mall and market in Freetown.
- A review on behalf of the PPP Unit of a draft of the WB funded pipeline study has been completed – therefore assisting in bringing this important input to completion.

The study tour funded by DFID has been planned but not yet undertaken. The planning has benefited from planning of wider capacity building and training, and the decision to tie this to a formal certificate programme. The indicator aims to reflect links to other countries which are planning or implementing PPPs rather than the number of study tours per se. In fact a number of links have been established through other means so this indicator may no longer be applicable. The success of the DFID funded stuy tour should be assessed instead, probably in terms of the number of participants and the value they see from the tour in relation to their own personal capacity building.

Summary of responses to issues raised in previous annual reviews (where relevant)
This is the first annual review of this project, therefore there are no issues to address.

Recommendations
1. A formal certificate programme must be completed by the PPP Unit staff by December as this will enhance the confidence and credibility of the staff within the Unit.
2. The DFID funded and other regional study tours must be taken forward to deepen the experience of the staff of the Unit and prepare the staff for evaluations of tenders of PPP projects.
3. A pricing and charging arrangement must be developed by the PPP Unit that enables sustainability for the Unit beyong the life of donor support to the Unit. It is proposed that this should be linked to results in terms of investments delivered with help of the PPP Unit
4. The TA provided to the PPP Unit by different donors needs to be planned along lines of carefully coordinated exit strategies that transfer more and more responsibility to the PPP Unit staff.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Only £267,449 (22.49%) of the budget has been utilised to date, which is around 50% of what had been profiled to spend by this stage in the project lifetime within the Business Case. Just under half of what has been spent so far accounts for the full utilisation of the budget line for provision of office equipment and vehicles for the PPP Unit.

The costs of the second budget line, the provision of the PPP Technical Assistance (PPPTA) are regular and predictable, with this resource in place we will expect constant spend against this budget line.

The low budget utilisation rate can therefore only be accounted for as an underspend against the fund put aside for the financing of pre-feasibility studies, which in turn is an indicator of the slow progress of the PPP Unit in developing PPP projects. One of the principle cost driver’s for this project therefore has been the delay of the World Bank PPP Pipeline study which was intended to underpin the workplan of the PPP Unit and prioritise key PPP projects for Sierra Leone. Now that this is finalised, together with the PPP Unit beginning to refine procurement processes in line with international procurement rules, it is expected that the utilisation of the pre-feasibility fund will increase. However, it is important to note that it would not have been prudent to push ahead with the pre-feasibility studies before the prioritised pipeline was agreed. The process has delayed the disbursement, but it has also protected funds and helped ensure that they will deliver value for money.

VfM performance compared to the original VfM proposition in the business case

Value for Money performance has been effected by the fact that some of the PPP projects are taking a lot longer to progress than would be expected. Furthermore recruiting a full complement of staff to the PPP Unit took longer than envisaged and also that the capacity of the PPP Unit remains low. But additional to this and as referenced above, the Unit’s procurement procedure are being refinement and timelines will be reduced by bringing the procedure in line with international procurement rules.

It is also recommended that the Head of the PPP Unit is encouraged to focus on strategic issues only and begins to delegate less strategic day to day affairs to competent staff in the Unit.

Assessment of whether the programme continues to represent value for money

Despite the lack fo progress in getting PPP projects to implementation stage, this project continues to represent value for money.

The Value for Money assessment outlined in the Business Case is still relevant and has not been unduly affected by the delays and challenges to the project summarised within this review. For example, the total cost of running the PPP Unit is extremely small compared to the size of transactions that it will be involved with. Assuming that donor support is withdrawn after two years and GoSL continues to fund staff and pre-feasibility studies at the same level, the discounted cost over the first five years amounts to £3.17m (DFID’s contribution is £1.15m). The discounted value of pipeline transactions over that time amounts to £803m.

It is important to note as above that it would not have been prudent to push ahead with the pre-feasibility studies before the prioritised pipeline was agreed. The process has delayed the disbursement, but it has also protected funds and helped ensure that they will deliver value for money. Now that the WB pipeline study is complete, the utilisation of the pre-feasibility fund will accelerate.

DFID does need to ensure that it is getting maximum value for money from the contract with IMC worldwide. It is not clear to the PPP Unit at this stage that the added value they might expect from DFID contracting with IMC Worldwide, over and above managing procurement for DFID, is being realised and deployed fully. DFID should take this up directly with IMC Worldwide at the earliest opportunity.

Quality of financial management

Invoices have been submitted on time and are in line with forecasts, despite the low budget utilisation rate which is a result of extraneous factors which are discussed elsewhere in this review.

Date of last narrative financial report	10/04/2014
Date of last audited annual statement	FY 13/14 from IMC Worldwide remains outstanding

E: RISK (½ page)

Overall risk rating: Medium

The overall risk rating for this project has not changed since inception and is still assessed as medium risk overall in the likelihood of this project meeting its expected goals. There is a medium risk that DFID will need to enable a no-cost extension to this project because of delays in setting the PPP pipeline priorities due to the late completion of the WB pipeline study.

Overview of programme risk

The risk assessment on fidicuary and fraud risk is still assessed as low. Sufficient safeguards, as outlined in the business case, remain in place to protect DFID funds.

An update to the risk register for this project has been undertaken and two of the risks have been updated in the matrix based on the findings of this review:

Risk / Category	Risk	Impact	Probability	Mitigating / Actions	Residual / Risk
Governance	PPP Unit lacks authority to impose quality standards and to tackle corruption	M	L	Promote transparency in Unit operations and publication of PPP agreements. / Continue support to Anti-Corruption Commission. / DFID funds specifically safeguarded through methods mentioned earlier	M/L
Programme Management Risks	Poor performance by Implementing Partner	L	L	Initial procurement will select a well-qualified Technical Adviser Ongoing monitoring will assess project progress and risks to delivery. DFID will reserve the right to withhold payments and terminate the contract	L

One risk under Governance has been reduced from Medium probability to Low probability to reflect the likelihood that the PPP Act will be passed by the Government of Sierra Leone in its current form.

The risk under Programme Management should be changed from poor performance by the Technical Advisor to language that reflects that DFID will hold the Implementing Partner accountable for delivery of against the contract, not just the technical adviser.

Outstanding actions from risk assessment

There are no outstanding actions at this point in time.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The milestones in the Logframe for this project were based on the assumption that this annual review would be undertaken one year after the start of on the ground implementation. The Technical Adviser for the PPP Unit provided by DFID did not arrive in Sierra Leone until 11th November 2013, so this review only covers eight months of inputs.

The time from approval of the Business Case to the start of implement can be assessed. The five elements are: office equipment; vehicles; TA; study tour; and pre-feasbility funds.

Procurement of the office equipment was very efficient and was completed within two weeks of approval by starting the procurement process in parallel with the approval process. Once the BC was approved, the office equipment tenders were evaluated and a contract awarded, with delivery the following week. This highly efficient process gained praised from GoSL and enabled the Unit to set up quickly. The vehicles took much longer because they were compbined with another DFID Sierra Leone programme requiring similar vehicles. This enabled the costs to be reduced but delayed delivery until December.

The procurement process for the TA, including the study tour and pre-feasibility fund, was undertaken through a framework contract. DFID Sierra Leone had previously experienced delays in similar programmes, and reviewed the process and actions when procuring for this programme. The result was that the time from approval to mobilisation was reduced from almost seven months (for the Market Development Programme) to four months for the PPP Unit. Although there were some differences in the process, the more rapid procurement does reflect improved programme implementation in DFID.

Other factors that are outside of the Implementing Partners control have impacted on their delivery against the project milestones, particularly the late completion of the WB PPP pipeline priority study. These have been highlighted already within this annual review.

Performance of partnership (s)

The technical quality of the TA provided is of the appropriate level and well balanced with an understanding of institutional reform. His involvement in the recent study tour to South Africa appears to have resulted in study tour that exceeded expectations for the Unit staff. It is noted that the PPP TA has a good working relationship with the Head of the PPP Unit and the long standing Technical Adviser provided by UNDP to the PPP Unit since 2012.

DFID has asked the Implementing Partner IMC Worldwide to ensure that DFID does not become too drawn into management decisions that IMC Worldwide is contracted to take on our behalf. For instance, IMC Worldwide should work with the Head of the PPP Unit to iron out any confusion over the use of money available for supporting regional study tours and to agree ToRs for supervision visits.

Although the level of detail and frankness provided in the progress reports provided by IMC Worldwide is appreciated. The English used within reports would benefit from more editing and proof reading to improve readability and to ensure that the margin for misinterpretation of anything stated in the report is reduced.

The Steering Committee mechanism as identified in the Business Case for this project needs to be implemented more formally. It will help improve donor coordination with Government priorities and help manage pressure and expectations placed on the PPP Unit by line ministries and the private sector.

Asset monitoring and control

£125,000 of assets have been provided to the PPP Unit. Assets supplied included office equipment, generator for power and three vehicles. A complete asset register for this project held by the implementing partner was provided to DFID on 14 February 2014.

It is strongly recommended that as part of due diligence, a routine spot check is undertaken to check these assets.

DFID has received a further proposal from the PPP Unit to provide a further US$10,000 of funding to the Unit to develop its ICT networking and connectivity, and to design and launch a website to manage the PPP Units identity and improve transparency. It is clear from the request and from visiting the office that internet connectivity is a real challenge for the Unit, and this is not enabling the staff there to make the best use of the assets already provided by DFID. It is recommended that if possible DFID supports this proposal using underspend from other budget lines in the already approved indicative project budget.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Sierra Leone is a recipient of general budget support from the UK.  This arrangement is guided by a memorandum of understanding between DFID and the Government of Sierra Leone that requires it to demonstrate commitment to the UK’s partnership principles, in line with the UK’s conditionality policy.  A comprehensive assessment is made each year and updated each quarter, prior to budget support disbursements.

This review does not consider that the Partnership Principles are useful in monitoring or managing this particular project. This project is not categorised as financial aid to the Government. The PPP Unit does sit within State House (the Office of the President), however DFID’s contracts are with suppliers of goods and services, not directly with the Government of Sierra Leone.

However, the establishment of the PPP Unit by the Government of Sierra Leone, and its continuing support for the remit of the Unit reflects postively on two of the four partnership principles:

Private Public Partnerships are an innovative way to finance expensive infrastructure projects and provide affordable basic services to people. The Unit’s work is a positive indication of the Government’s consideration of Partnership Principle 1 - a commitment to reducing poverty and achieving the Millennium Development Goals (MDGs).

The role of the PPP Unit in providing an additional check, and service to Government in quality assuring tendering, negotiation and implementation of PPPs contributes to Partnership Principle 2 - a commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There is plenty of evidence in many countries for the value of PPPs. DFID undertook a review of evidence of the costs and benefits for centralised PPP Units as part of the original Business Case for this project and although finding that there is no quantitative evidence, the findings did identify a number of factors which can contribute to the success of central PPP Units and these were incorporated into the design of the project. This review found that the four key factors that were addressed in the design of DFID’s support ot the PPP Unit are still being addressed in the implementation of the project.

However during the design of this project it was also found that there is limited evidence for impact from this kind of intervention - the issue identified was whether there was sufficient evidence of whether Sierra Leone will benefit from the creation of a PPP Unit. This evidence is beginning to materialise through the PPP Unit’s involvement in assessing the Value for Money of PPPs and sharing of risk. On two PPP projects that were already agreed for tender prior to the establishment of the PPP unit - Bumbuna phase II Hydro Power project and the Freetown HFO thermal plant project - the role played by the Unit at this late stage has benefitted ongoing negotitations with the private sector by GoSL.

There are no plans for an evaluation of the project as it is relatively low in value and not a novel development concept

Monitoring progress throughout the review period

Monitoring of this project has been undertaken through the review of quarterly written progress reports provided by IMC worldwide with inputs provided by the TA provided to the Unit itself.

Monitoring has also been taken forward through DFID’s direct engagement with donors that are also supporting the PPP Unit, the PPP Unit itself and also through our day to day interactions with those Line Ministries which have had most engagement with the PPP Unit over this last period.

This Annual Review has been completed by the DFID Private Sector Development Adviser who has drawn from progress reports provided by the implementing partner for this project, and meetings with the Technical Adviser, PPP Unit and the Head of the PPP Unit, and feedback from other donors supporting the PPP Unit. DFID also participated as an observer on the panel for the opening of bids for a pre-feasbility study for a proposed PPP project, and has followed progress on the evaluation of bids closely.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process