Business Case and Intervention Summary

Intervention Summary

## Title: Public Private Partnership Unit Support in Sierra Leone

What support will the UK provide?
The UK will provide £1.2 million over two years in order to establish, support and build capacity within a Public Private Partnership (PPP) Unit in the Government of Sierra Leone. Our support will include £125,000 for office equipment and vehicles, £575,000 for a PPP Technical Advisor and a £500,000 fund for pre-feasibility studies.

Why is UK support required?
Sierra Leone has poor infrastructure which severely restricts economic growth and leads to highly unequal access to government and private sector services. The Government of Sierra Leone’s (GoSL) priority until 2017 in the Agenda for Prosperity is to rapidly develop electricity, transport, water and sanitation infrastructure and establish an environment where the private sector can flourish. The need is urgent in order to take advantage of the current surge in the economy led by investment in mining and agriculture, and to improve poor people’s access to public and private sector services and income generating opportunities. / GoSL has neither the financial resources nor the technical capacity to develop major infrastructure projects. It is committed to working with private investors to share the costs, benefits and risks of infrastructure development through PPPs. There is an estimated pipeline of $1.7 billion of proposals by foreign investors and GoSL has set up a central PPP Unit to help line ministries to manage deals. / Overall, the Government has created the PPP Unit in order to: / Promote sustainable PPP solutions for infrastructure projects within the country and to foreign investors / Align investment into priority areas laid out in the Agenda for Prosperity and the Public Investment Plan / Ensure that employment creation and local sourcing objectives are adequately embedded in the large PPP contracts / Bring in core expertise required to negotiate deals and attract investors / Assist GoSL negotiate strong, sustainable deal terms that ultimately benefit the people of Sierra Leone / Give investors the confidence that they are dealing with informed and professional counterparts / Introduce strong process, transparency and governance standards into the often ad-hoc and opaque area of deal negotiation. / The PPP Unit requires support in four areas: setting up an efficient office; prioritising, negotiating and closing deals; building local capacity in PPP management; and undertaking pre-feasibility studies to collect information and set priorities. The Government, African Development Bank and UNDP are all providing resources and DFID has also been requested to provide support. This Business Case covers that request. If approved, DFID will provide: / A PPP Technical Advisor who will provide technical expertise and advisory services to the PPP Unit and to line ministries, and manage a fund for pre-feasibility studies and a study tour; / A fund for pre-feasibility studies aimed at identifying the PPP proposals with the greatest potential to benefit Sierra Leone and providing information to GoSL for use in negotiations with foreign investors; and / Computers and communications equipment, a generator and three vehicles.

What are the expected results?
A logframe has been developed by the PPP Unit and this is used to present the overall impact and outcomes of the Unit. The logframe links to the Results Monitoring Framework of the Agenda for Prosperity, strengthening the coordination within Government and ensuring effective ownership by the Unit themselves. DFID’s support will contribute to the outcomes of the PPP Unit, but it is more difficult to attribute outcomes to DFID resources. The results are therefore expressed in terms of the whole Unit and we will use more specific indicators and targets for the PPP Technical Advisor recruitment and performance monitoring. / The expected impact is inclusive green growth that leads to prosperity and improves human development. The expected outcome is accelerated economic growth through the development of a sustainable and an enabling infrastructure. This will be achieved more rapidly, at lower cost and with less risk to government. The key outputs for the PPP unit are: / Electricity generation rising from 76.5MW in 2013 to 120MW in 2015 / An additional 120,000 people with access to electricity by 2015 / Over $500m invested in PPPs in electricity, roads and other infrastructure in 2014 and 2015. / An effective system of prioritising, negotiating and implementing PPPs.

Business Case

Strategic Case

A. Context and need for a DFID intervention / From Post-Conflict to the Prospect of Prosperity / Sierra Leone’s ten-year war, and the years of decay that preceded it, destroyed much of the country’s infrastructure, institutions and human capital. By the time the conflict ended, Sierra Leone had some of the worst human development indicators in the world, languishing at the bottom of the UN’s Human Development Index (HDI) in 2003. / More than ten years later, Sierra Leone has made notable progress and is often hailed as a success story. Peace and stability have been achieved, government institutions have been re-established and a nascent democracy is in place. The country’s third democratic elections since the war were concluded peacefully in November 2012, with the incumbent president re-elected for a second, and final, five-year term.[1] Improving institutions and the expected draw-down of the UN’s peace-building mission in 2013 signal the country’s move away from fragile state status.[2] / Human development has started to improve from its low base, with the help of substantial donor support. However, there is a lot more to be done. Despite achieving some of the biggest improvements in the HDI of any country between 2000 and 2010, it is still ranked 177 out of 187.[3] Gross national income per capita is only $340 – just two thirds of the low income average ($567) and far below the average for developing sub-Saharan Africa (SSA) ($1,255).[4] Excluding South Sudan and Somalia, only three countries in Africa are poorer. More than 60% of the population live on less than $1 a day and 79% of the rural population live below the national poverty line.[5] As well as one of the lowest HDI scores, Sierra Leone has the lowest life expectancy in the world and is unlikely to meet any of the Millennium Development Goals (MDGs) before 2015. / The Economy and Macroeconomic Management / The economy has grown at an average rate of 6% per year since the war ended, out-pacing the SSA average. Nonetheless, the economy has remained small at £2.4 billion.[6] Minerals such as gold, diamonds, iron ore and rutile play an important role in the economy, contributing over 7% of GDP and accounting for nearly all exports. Agriculture, forestry and fishing contribute more than half of Sierra Leone’s GDP, with services (mainly informal trading) contributing a third and industry and other sectors making up the remainder. / With the help of successive IMF programmes and donor support, the economy has been reasonably well-managed, albeit with some slippages. Sierra Leone scores a 3.5 for macroeconomic management in the World Bank’s CPIA, above the SSA average and on a par with Ghana and Rwanda. High global food and fuel prices have kept inflation consistently in double digits in recent years, averaging 18.1% in 2011, but new limits on central bank borrowing and improved monetary policy are expected to reduce this to 12.0% in 2012 and to 8.7% in 2013.[7] After a period of volatility, the real exchange rate has remained largely constant whilst the current account balance has fluctuated at around 10% of GDP. / The increasing political and economic stability has supported improvements to the investment climate. Sierra Leone recently jumped from number 163 to 140 in the World Bank’s Doing Business Index, making it one of the top reformers.[8] Investment has started to flow in, boosting the mining sector in particular. However, the level of investment remains low, and scaling up has been constrained by low domestic savings of 4% of GDP. With the support of remittances and foreign grants, investments have been maintained at 15% of GDP.[9] This has been insufficient to meet the vast infrastructure gap, with Sierra Leone in the bottom six of the African Development Bank’s (AfDB) Africa Infrastructure Development Index.[10] Many rural roads are impassable in the wet season (June to October), electricity provision is poor, forcing most enterprises to reply on generators, and reticulated water supply and waste disposal is largely absent, even in the larger towns. / On the Brink of Transformation / Post-conflict Sierra Leone is moving in the right direction, and is potentially on the brink of transformation. The re-start of iron ore mining after a thirty year gap resulted in real GDP growth of 15.2% in 2012, with production from two iron ore mines alone contributing around 6% of GDP from near zero before. However, the impact on government revenue and the wider economy will take time to materialise and needs to be carefully managed. Initial estimates suggested a revenue increase equivalent to 8% of GDP starting in 2013, as the mining companies start to re-coup start-up costs and turn a profit[11] - but falling iron ore prices and production delays are likely to defer this windfall for a few more years. Even with this additional revenue – and the strong non-iron ore growth rate of 6% in 2013[12] – domestic revenue would still be less than the regional average. / Sierra Leone struggles with high levels of corruption and opaqueness in contracts including in public services, procurement and contracting. Corruption was seen as a key contributor to the civil war. However it is also showing improvements as the Government of Sierra Leone (GoSL) systems are built up and attempts are made to improve transparency. The Transparency International Corruption Perception Index 2012[13] ranks Sierra Leone 123 out of 176, noting the improvement from 134 of 182 countries in 2011[14]. This compares favourably across West Africa, with Nigeria (139) and Guinea (154) but is not as good as Ghana (64) and Liberia (75). The Global Integrity Index 2011 suggests a low level of absolute performance on integrity, and a mismatch between the legal framework for promoting integrity and reducing corruption (moderate) compared to the record of actual implementation, which falls into the lowest category (very weak)[15]. Sierra Leone is ranked low in international indices of transparency of revenue from natural resources, and is not yet Extractive Industries Transparency Initiative (EITI) validated[16]. The PPP has the potential to become an additional tool in the fight against corruption. / The successful elections have given the President a new mandate to tackle poverty and build a prosperous country. His vision will be underpinned by a new PRSP – the ‘Agenda for Prosperity’ – being developed in consultation with donors and civil society. The new PRSP will set out the country’s strategic direction over the next five years (2013 to 2017) as the country moves away from being a fragile state and towards its goal of becoming a middle income country by 2035. It aims to capitalise on the economic opportunities from the mining sector to address some of the outstanding poverty and human development challenges. A defining feature of the new PRSP will be a prioritised investment plan and stronger results focus with a clearly defined framework for tracking progress and demonstrating results. / The Agenda for Prosperity has 8 pillars: / Economic diversification to achieve inclusive growth / Managing mineral resources / International competitiveness / Employment and labour / Accelerating progress towards the MDGs / Social protection / Governance and public sector reform / Gender / Green growth is mainstreamed throughout as a cross-cutting theme. / Inclusive Green Growth and the Role of the Private Sector / Four of the pillars of the eight Agenda for Prosperity relate to inclusive green growth, managing mineral resources, international competitiveness and employment (see box above). President Koroma reinforced this pro-growth, pro-private sector focus in his inauguration speech in December[17] and the Finance Minister reiterated the message when presenting the 2013 Budget to Parliament on 21st December[18]. The message has two themes: / Growth: the economy is small and based largely on informal and subsistence activities. Growth and investment are needed to generate productive opportunities for the large number of un- or under-employed people, / Inclusiveness: large enterprises, mainly in mining, can generate growth but could be isolated from the wider economy. Everyone needs opportunities for productive employment and most will be generated by the private sector. / Green growth is a theme of both the Agenda for Prosperity and the 2013 Budget. GoSL aims at environmental sustainability but progress on establishing the policies and institutions to address environment and climate change has been slow. The Environmental Protection Agency (EPA)[19] became operational in 2012 but the Environmental and Social Regulations for mining companies have not yet been passed by Parliament. The National Climate Change Secretariat[20] under the EPA has also not been formed yet. The level of public awareness of environmental issues is also low[21]. Despite these limitations, GoSL and development partners are focusing future programmes on environmental sustainability and climate resilience. / GoSL is committed to gender equality, and policy is guided by the Gender Strategic Plan (2010). This includes action on land and property rights for women (currently women have limited rights to own land under some customary laws), access to finance, training for employment, and promotion of formal employment opportunities for women. / GoSL recognises that they do not have the capacity or resources to build the economic and social infrastructure the country needs, particularly for electricity, transport, water and waste management. Domestic sources of investment will also not be sufficient to finance development. GoSL has therefore sought ways to attract foreign investment, including setting up the Sierra Leone Investment and Export Promotion Agency (SLIEPA)[22] in 2004 (initially called SLEDIC). The Government has also negotiated ad hoc agreements with investors, for instance to build and operate the Bumbuna hydroelectric facility which provides electricity to Freetown. / In a concept note on the establishment of a Public Private Partnerships (PPP) Unit[23], GoSL noted that infrastructure remains a major challenge that has limited private sector development and held back further improvements in Sierra Leone’s Doing Business rankings. While recognizing the challenge, the government has looked to alternative funding arrangements with a view to finding private sector solutions to the bottleneck. This has led to GoSL receiving an unprecedented number of unsolicited proposals from the private sector to establish PPPs. As such, Ministries have entered into a number of memorandum of understanding (MOUs) and contracts which have placed an unanticipated burden on the GoSL to assess and negotiate these agreements. This is because line ministries have inadequate capacity to process the large number of unsolicited bids they receive and limited access and ability to manage appropriate technical, legal or financial advice before signing the agreements. GoSL is keen to adopt a more proactive approach and the creation of the PPP Unit is one element in doing so. / The excess pressure and lack of capacity could lead to a number of unfortunate outcomes for GoSL: / The negotiated deal terms and pay-out structures are heavily weighted in favour of the investor and as such do not benefit the government and people of Sierra Leone as much as they could. / The intended impact in terms of local job creation from these large scale projects are often not felt because of extensive use of outside contractors. / The government recognises deal terms are not optimal after signing, and decides to re-negotiate, sending negative signals to the investor community. / The negotiations are rushed and less transparent, giving rise to the perception (and possibly practice) of corruption. / In a bid to further encourage and professionalize the process by which PPPs are established and to ensure that line ministries have improved access to the capabilities required to evaluate and negotiate proposals, the GoSL determined that it needed a PPP policy and implementation framework. With the assistance of a World Bank funded consultant, GoSL was able to prepare a public private partnership policy and implementation framework which was approved by the Cabinet in March 2009. / The President has now made the PPP Unit a key priority and the GoSL is seeking the support of the development partners. The role, structure and governance of the PPP Unit are set out in the Appraisal case paragraph 30 onwards. / Overall, GoSL has created the PPP Unit in order to: / Promote sustainable PPP solutions for infrastructure projects within the country and to foreign investors / Align investment into priority areas laid out in the Agenda for Prosperity and the Public Investment Plan / Ensure that employment creation and locally sourcing objectives are adequately embedded in the large PPP contracts / Bring in core expertise required to negotiate deals and attract investors / Assist GoSL negotiate strong, sustainable deal terms that ultimately benefit the people of Sierra Leone / Give investors the confidence that they are dealing with informed and professional counterparts / Introduce strong process, transparency and governance standards into the often ad-hoc and opaque area of deal negotiation. / The need for DFID Intervention / A recent DFID-funded growth study[24] found that the main impediment to growth at present is the failure in coordination, in part from a lack of government capability to implement the necessary policies and reforms. GoSL is trying to address the issue by establishing specialised units to coordinate the implementation of policies developed by line ministries and has the support of development partners, including DFID, in building the capacity of these units. One such unit is the PPP Unit which will be based within State House (the Office of the President) and provide technical support and quality assurance across government in prioritising, negotiating and managing public private partnerships (PPPs). / The World Bank, AfDB, IFC and UNDP have already supported GoSL in the development of PPPs and in establishing the regulatory framework. The NGO, the Africa Governance Initiative (AGI) has also assisted in the establishment of the PPP Unit. These development partners plan to continue support, with UNDP focusing on international links and assessment of private partners and AfDB providing advice and capacity building in financial, legal and business analysis. IFC has indicated a willingness to provide technical advice and potentially investment funds for specific transactions. However, IFC, UNDP and AfDB have confirmed that they cannot extend their support further and will therefore not cover the Unit’s coordination with and support to line ministries and local government. / A number of other development partners operate in Sierra Leone but none work in the area of PPPs. The European Commission is active in infrastructure, trade and export development. GIZ focuses on minerals, youth employment, and agriculture in the south east of Sierra Leone. AusAid, USAid, Irish Aid and JICA have small programmes and the Chinese Government supports a number of large scale infrastructure projects. / The PPP Unit will need support from another partner or divert resources from other government programmes. GoSL has considered the options and written to DFID setting out the gaps and asking for assistance. / The UK played a crucial role in helping bring the civil war to an end, and has since helped to maintain peace and stability and support growth and development. DFID contributes more aid per capita to Sierra Leone than in any other country and is Sierra Leone’s largest bilateral donor. This has allowed the UK to maintain a close and influential relationship with successive governments over the past decade. / Funding will rise over the next three years as a £270m Operational Plan for 2011-15 is rolled out. DFID’s work will continue to be a major part of the UK Government’s engagement in Sierra Leone, and the overall UK objective of reducing the potential for future conflict, reducing poverty, increasing prosperity and promoting democracy. Significant DFID programmes are underway in health, education and water and sanitation aimed at addressing some of the significant human development challenges (Figure 1). DFID programmes also support better governance and stronger democracy, as well as helping build a flourishing and well regulated private sector. / Figure 1: Current DFID Sierra Leone Programme 2011-2015 / MDGs GOVERNANCE WEALTH CREATION / Health / Education / Water and sanitation Security and justice / Public sector reform / Elections / Corruption / Revenue / Women / Civil society Economic stability / Public financial management / Extractive industries / Energy / Private sector development / £154m £70m £46m / The request for support to the PPP Unit at £1.2m is a relatively small share of the portfolio and fits well within the wealth creation/private sector development pillar. / In summary, despite progress on a number of fronts and exciting prospects, Sierra Leone still requires significant additional resources and a guiding hand to help it achieve its inclusive growth and development objectives. DFID is well placed to take a significant role building on our good relationship with GoSL and experience across Africa.
B. Impact and Outcome that we expect to achieve / A logframe has been developed by the PPP Unit and this is used to demonstrate the overall impact and outcomes of the Unit. The logframe also links to the Results Monitoring Framework of the Agenda for Prosperity, strengthening the coordination within Government and ensuring effective ownership by the Unit themselves. DFID’s support will contribute to the outcomes of the PPP Unit, but it is more difficult to attribute outcomes to DFID resources. The results are therefore expressed in terms of the whole Unit and we will use more specific indicators and targets for the PPP Technical Advisor recruitment and performance monitoring. / The expected impact is inclusive green growth that leads to prosperity and improves human development. This will be evident through wide participation in, contribution to and benefit from economic growth by poorer people, particularly in environmentally sustainable activities / The expected outcome is accelerated economic growth through the development of a sustainable and an enabling infrastructure. This will be achieved more rapidly, at lower cost and with less risk to government. The logical framework for the PPP Unit as a whole, including government investment and contributions from other development partners, sets out the key outputs: / Electricity generation rising from 76.5MW in 2013 to 120MW in 2015 / An additional 120,000 people with access to electricity by 2015 / Over $500m invested in PPPs in electricity, roads and other infrastructure in 2014 and 2015. / An effective system of prioritising, negotiating and implementing PPPs.
[1] These were the first elections managed by Sierra Leone. Previous elections were administered by the United Nations.
[2] Sierra Leone’s score of 3.3 on the World Bank’s Country Policy and Institutional Assessment (CPIA) exceeds the threshold for fragile situations. To fully graduate, three years must pass without a UN peace-building mission.
[3] UNDP (2013) Human Development Report
[4] World Bank, GNI per capita (Atlas Method) for 2011 (accessed 31 October 2012)
[5] Estimate from 2009 Sierra Leone Poverty Diagnostic, sourced from World Databank. Preliminary figures from a recent integrated household survey suggest this has fallen to between 52% and 55%.
[6] The Ministry of Finance and Economic Development reports Le16,459 billion for 2012
[7] IMF World Economic Outlook (April 2013) and subsequent review mission
[8] http://www.doingbusiness.org/data/exploreeconomies/sierra-leone/. Greater credit availability has driven this improvement. Electricity, registering property and dealing with construction permits remain static and difficult to address.
[9] The ratio of investment to GDP, both measured in Current US$ was around 16% in 2010.
[10] AfDB (2012) Infrastructure and Growth in Sierra Leone
[11] IMF (2011) Second and Third Reviews Under the Three-Year Arrangement Under the Extended Credit Facility.
[12] GoSL/IMF. Growth is projected to continue at between 7% and 13% until 2014. The discovery of off-shore oil could be another game-changer; if commercially viable, it could come on-stream by 2017
[13] Source: Transparency International Corruption Perception Indices for the years stated. Absolute score is on a scale from 0 to 10, with 0 = ‘highly corrupt’ and 10 = ‘very clean’. UK = 7.8 absolute score and 16/182 for 2011
[14] Data suggests that absolute levels of perceived corruption have remained at a high level in the post war period, with a noticeable decline in 2007/8. Relative rankings are more difficult to interpret given the changing size of the data set, but overall Sierra Leone has improved relative to other countries as the data set has progressively expanded. Year	2003	2004	2005	2006	2007	2008	2009	2010	2011 Absolute score	2.2	2.3	2.4	2.2	2.1	1.9	2.2	2.4	2.5 Source: Transparency International Corruption Perception Indices for the years stated. Absolute score is on a scale from 0 = ‘highly corrupt’ to 10 = ‘very clean’. UK = 7.8 absolute score for 2011.
[15] Year	2011 Global Integrity absolute score 64 (weak); legal framework 78 (moderate); actual implementation	52 (very weak) where 100 = highest value.
[16] Sierra Leone was suspended for one year in March 2013. The country failed to meet two criteria and is due to submit a supplementary validation on these two by September 2013.
[17] Speech at the swearing-in ceremony at State House, 23rd November 2012
[18] Government Budget for the Financial Year 2013 “Accelerating structural transformation and inclusive green growth for prosperity”, 21st December 2012.
[19] Set up under the Environmental Protection Act 2008
[20] National Adaptation Programme of Action 2009 (NAPA)
[21] UNEP: Environmental Governance and Public Awareness programme 2011
[22] Website www.investsierraleone.biz
[23] PPP Unit in Sierra Leone, Office of the President, December 2012
[24] Leonardo Garrido, August 2012

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The PPP Unit / GoSL has already made the decision to establish a PPP Unit. Staff have been recruited and the head of the Unit took up his post during May 2013. This Business Case therefore looks at whether DFID support is appropriate and, if so, the level required. However, there has been a debate for some time on the role, structure and governance of the PPP Unit, and DFID participated in this debate. Before considering options for DFID support, this section presents the approach adopted by GoSL and the reasons for doing so. / The PPP unit will be serving two broad functions across government: / Direct transactional support: The immediate task is to centrally manage the backlog of around $1.7 billion of unsolicited bids received by various line ministries, and establish a clear protocol for dealing with such proposals in the future, enabling GoSL to take a more proactive approach. Line ministries will retain responsibility for policy and sector strategies but by bringing PPP negotiation and technical expertise into the centre of government, the unit will enable line ministries to handle these proposals better and to arrive at mutually beneficial outcomes with private sector partners. Over the longer term, the unit will also work with line ministries to find PPP solutions where suitable and support the process up to deal close. / Creating an enabling environment: The PPP unit will promote PPP solutions across the country while improving the broader environment for such transactions. This includes establishing a strong regulatory framework, supporting Cabinet in the implementation of GoSL’s PPP policy and building capacity of various ministries and departments. / A key concern of development partners, including DFID, was whether this centralisation of technical support would result in conflicts between the Office of the President, where the PPP Unit will be located, and line ministries which are responsible for policy choices within their sectors. It was feared that ministries would have a reduced ability to implement their policies if all PPPs were centrally managed. GoSL recognised these concerns and has addressed them by limiting the role of the Unit to capacity building and advice. Decisions on priorities will be taken collectively by Cabinet. / The PPP Unit will also help GoSL ensure that PPPs are properly aligned with the Public Investment Plan and the Agenda for Prosperity. The ad hoc approach which has been evident until now means that projects are not selected and supported according to overall Government priorities, leading to some areas being neglected and others attracting too much time and effort. The need for alignment has been emphasised by GoSL and development partners. / GoSL is currently finalising the PPP Bill which will formalise the legal framework including the division of responsibilities between the PPP Unit and the line ministries and the Ministry of Finance and Economic Development (MoFED), the Cabinet and Parliamentary scrutiny of PPPs, and the role of the PPP Unit itself. The World Bank and IFC are supporting GoSL in the drafting of the Bill and ensuring international best practice. / The key roles and relationships for the PPP Unit are shown in figure 2 and as follows: / Building capacity within ministries in order to improve the environment for PPP deals and to enable the ministries to carry out such transactions on their own. It will provide training, templates and awareness of options as well as practice guidelines for all ministries to follow. / Serving as an advisory unit to ministries, linked to specific transactions. While ministries will be the ultimate owners of the process, they will be encouraged to reach out to the PPP unit, which will serve as coordinator and resource for deal evaluation and negotiation skills. / Providing oversight and monitoring during implementation of projects to ensure construction is carried out in line with the output specification and the contract is fully honoured. The unit will liaise closely with and seek approval of their client, the relevant ministry, at all stages of the PPP life cycle. / Contractual responsibility will lie with the contracting ministry and the responsible minister will seek cabinet approvals at various milestones in the life cycle. The Unit may also support the minister with submissions related to these approvals. / MoFED is ultimately responsible for management of GoSL’s financial resources and oversight of the budget. The PPP Unit will support MoFED in providing value for money calculations and affordability assessments. / The Unit will support Cabinet with PPP proposals. It will coordinate the Cabinet reports and advise on whether GoSL should proceed to the next stage of the PPP lifecycle. The unit will also support Cabinet to monitor projects and implementation of GoSL’s PPP Policy. / The Unit will assess all types of government deals including commercial joint ventures with private sector, management and maintenance contracts, design, build, finance, operate, transfers (BOTs, BOOs, etc) and concessions. / Figure 2: Technical Roles of the PPP Unit / The Unit will be composed of two teams: Project Development Unit (PDU) and Implementation Unit. In the case of new project, the PDU, along with the PPP Coordinator will be tasked with identifying and developing large scale infrastructure opportunities in the country, conducting feasibility studies and preparing Implementation Reports for those best suited to a PPP structure. / Once PPP projects have been identified, the unit will work with SLIEPA to promote the projects to international private investors. When private sector interest has been determined, a tendering process will be launched and external technical advisors appointed. This process will continue on through negotiations and awarding of contract and will be led by the relevant ministry and the Implementation Unit. The Implementation Unit will be expected to continue in its value for money evaluation, affordability assessment and monitoring and oversight role as the project enters construction phase and then the concession period. This cycle is set out in the diagram below. / The PPP Unit will be located within State House (the Office of the President) and report to a Steering Committee chaired by the Chief of Staff. The committee will include the Chief of Staff, representatives from each development partner supporting the Unit (AfDB, DFID, UNDP), MoFED and the PPP Unit Coordinator. / The core GoSL PPP Unit comprises of: the PPP Unit (Coordinator); the Implementation Unit with three permanent national staff specialising in PPP transactions (Assistant Financial Analyst, Assistant Business Analyst and Assistant PPP Lawyer); and the Project Development Unit with permanent national staff reporting to the PPP Coordinator. This structure is set out below. / During the initial period of two years, the Unit will be supported by five advisors and technical assistants. The Implementation Unit will include three advisors in law, business analysis and finance who will work with national counterparts to build capacity and build practical experience in the professional areas. The AfDB is funding these three posts. The diagram also indicates that the PPP Coordinator will be supported by two PPP specialists - a PPP Technical Advisor (PPPTA) and an International PPP Advisor (IPPPA). The two advisors have distinct but similar roles and will regularly work together in assessing PPP proposals and in providing training and capacity building to the Unit. More specifically, the PPPTA will directly support line ministries in all stages of PPP preparation and negotiation and provide training to the Line ministries in analysis of proposals and management of transactions. The PPPTA will also manage a pre-feasibility study fund aimed at enhancing the information available to the Line ministries and the PPP Unit in order to set priorities and plan detailed feasibility studies. The IPPPA will focus on capacity building in the PPP Unit and support the development of the overall PPP strategy for Sierra Leone. / The PPP Unit will need support from development partners for two years. During this period it will establish the capacity of the Unit itself and in ministries and begin work on priority PPP deals. After two years, support will only be required for specific transactions and will be provided by IFC, development finance institutions and specialist agencies such as PIDG and PPIAF. The Unit will continue to operate and be financed by charging a fee on transactions (depending on the transaction size and level of involvement), which will be added to total PPP project cost. These fees will also cover costs of transaction-specific external advice. / DFID undertook a review of evidence of the costs and benefits for centralised PPP Units as part of this business case[25]. The review concludes that there is no quantitative evidence but does identify a number of factors which can contribute to the success of central PPP units. These include / the unit’s position in government (influencing its authority and power); / its ability to positively address government failures in regards to the PPP procurement process; / its capacity to build up technical expertise; and / its ability to appropriately judge PPPs (i.e. quality control and risk sharing). / The report recognises that PPP Units need to be appropriate to the country and sectoral circumstances in order to meet different requirements. For Sierra Leone, the four success factors above have been addressed in the design of the Unit. In particular: / The Unit is situated in State House, giving it a high profile and authority directly from the President. The main alternative was to situate the Unit in the Ministry of Finance and Economic Development (MoFED). This could provide a suitable level of authority but since MoFED is also responsible for budget and financial resources, it could have reduced the role of line ministries. By establishing the Unit in State House, GoSL ensures a greater level of coordination and accountability across government. / Government is generally considered weak in Sierra Leone and there are a number of potential failures in the PPP process. This is especially evident when negotiations and implementation lie with line ministries which lack capacity to ensure appropriate sharing of costs, benefits and risks, and rushed deals can lead to the perception of corruption. The focus on transparent and professionally competent processes aims to achieve better deals and that these deals are recognised as good for Sierra Leone. / The Unit has an explicit focus on building technical expertise. This covers both the Unit itself and line ministries. / The Unit will set a higher standard than the previous ad hoc arrangements and will provide quality control. Appropriate risk sharing requires judgement based on experience, and the Unit will depend on well qualified experts for some time, but the central Unit will enable local experience and expertise to be build and to establish long term relationships with international experts. / As previous noted, the PPP Unit already exists. The options for DFID do not therefore include encouraging GoSL not to have a Unit. The issue is how to ensure that the Unit operates effectively and efficiently, delivering good value for money through promoting high quality public private partnerships which share costs and risks to the benefit of Sierra Leone. / Options / There are three distinct options to consider: / Option 1 – fund the gap in the PPP Unit resources as requested by GoSL, including the advisor (PPPTA), equipment and vehicles, study tour and pre-feasibility study funds. / Option 2 – provide resources for the operation of the PPP Unit only (ICT equipment, generator and vehicles) / Option 3 – decline to provide resources / GoSL has requested £1.2 million over two years. This is for office equipment and vehicles (£125,000), technical assistance including the study tour (£575,000) and pre-feasibility studies (£500,000). Option 1 would cover all the items. Option 2 would cover only the office equipment and vehicles (£125,000). The GoSL budget breakdown for the PPP Unit is set out in table 2. / Table2: Overall Budget for the PPP Unit / Item Funder Amount / Staff salaries and running costs GoSL £ 490,000 / International PPP Advisor UNDP 250,000 / Financial and legal advisors and training AfDB 200,000 / Equipment, technical assistance and studies DFID 1,200,000 / Total £2,140,000 / The PPP Unit is already partially formed, with office space allocated in Wellington Street close to State House and staff from GoSL assigned to the Unit. The long term IPPPA funded by UNDP was recruited in early 2012 and has already been supporting State House in establishing the Unit and negotiating PPP agreements. The recruitment of the business, financial and legal advisors began in April 2013 and they are due to start in July. However the Unit staff lack equipment and transport – staff already allocated use their personal laptops in the office – and there is limited capacity to support line ministries to ensure proper prioritisation of PPP proposals, and effective negotiations to ensure a high level of benefits to Sierra Leone. / The office equipment and transport is needed immediately. Using individual (and private) laptops restricts information sharing and official communication with potential investors. The Unit urgently needs a computer network to facilitate team work, particularly for coordination of appraisal work and establishing quality assurance of negotiating positions and agreements. The transport is needed to visit project areas, although the more regular and detailed monitoring of agreements will not begin until late 2013. / Terms of reference for the PPPTA have been drafted by GoSL. The PPPTA is crucial in helping the Unit to become operational quickly, and in supporting the establishment of working relationships with line ministries and donors. The role would include technical advice on individual PPP transactions and the advisor would be involved in negotiations but have no decisions making responsibility – all decisions will rest with Cabinet, the Chief of Staff and/or the PPP Unit Coordinator. Without the advisor, there is a likelihood that some line ministries will continue to negotiate ad hoc deals with investors, and that some of these agreements may not be in the best interest of Sierra Leone. In particular, there is a reduced safeguard against corruption since the Unit will have little capacity for quality control until it is fully established. / Setting priorities for PPPs depends on good information about the potential costs and benefits of individual transactions. The fund for pre-feasibility studies will enable to Unit to commission short studies on likely interventions on behalf of the line ministries. These studies – typically involving three or four weeks of information gathering – will help determine whether more comprehensive and costly feasibility studies are likely to be worthwhile. The information gained through the studies will strengthen GoSL’s position in negotiations and ensure better outcomes for the country. Without the fund for studies, either the Unit will need to spend time and resources in attracting funds from donors to undertake individual studies, or would enter negotiations at a disadvantage or reply on information provided by the potential investor. / Option 1, by incorporating all three elements – equipment, TA and studies – would allow the PPP Unit to become effective quickly. The ICT equipment and vehicles would be supplied directly through separate contracts in order to enable the office to function properly, and the TA procured through a TA tender process. The costs and benefits of Option 1 are considered below. / Option 1 is the only option which can promote the alignment of the PPPs with the Public Investment Plan. The additional capacity and enhanced liaison with line ministries will enable to Unit to provide more structured support across a wider range of planned and unsolicited proposals. The management of the fund for pre-feasibility studies will also help the Unit ensure that line ministries focus on priorities. / Option 2 would similarly be split into contracts for ICT equipment and vehicles. The lack of the PPPTA will limit the capacity of the Unit to support Line ministries and some transactions may go ahead without support. The lack of a fund for pre-feasibility studies will delay some transactions until GoSL acquires funds from other sources to undertake the studies, whereas others may go ahead with limited information for GoSL. / Option 3 offers no support to GoSL. The PPP Unit would still exist but would delay or restrict its operations. / A key issue when comparing the three options is the pressure on GoSL from investors. GoSL reports a pipeline of possible projects worth $1.7 billion mostly in energy but also covering water, waste management, trade and transport. / PPP Technical Advisor
B. Assessing the strength of the evidence base for each feasible option including delivery routes / In the table below the quality of evidence for each option is rated as either Very Strong, Strong, Medium or Limited (or no evidence). / Option Evidence rating / 1 Limited / 2 Limited / 3 Limited / All three options are assessed as having limited evidence for impact. There is plenty of evidence in many countries for the value of PPPs. However, the issue in this Business Case is whether there is evidence of the value of establishing a PPP Unit, or conversely the impact of not having one. Still more specifically, the issue is evidence of whether Sierra Leone will benefit from the creation of a PPP Unit. / DFID undertook a review of evidence of the costs and benefits for centralised PPP Units as part of this Business Case[26]. The review concludes that there is no quantitative evidence but does identify a number of factors which can contribute to the success of central PPP units. The four key success factors above have been addressed in the design of the Unit in Sierra Leone.
C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner? / Sierra Leone suffers a serious lack of capacity in many aspects of government. Setting up the PPP Unit aims to address this deficit, and the technical assistance from AfDB, UNDP and DFID is needed to build capacity. / It is unlikely that the capacity in the Unit will be sufficient after two years of support. However, once a pipeline of transactions is established, GoSL will be able to charge fees for the Unit’s services which will enable the Unit to hire expertise as needed. The Unit will also be able to access training and technical support from PPIAF, IFC and others.
D. What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C B / 2 C B / 3 B C / Options 1 and 2 are thought to have similar environmental risks and opportunities and are these are therefore discussed together below. / The focus of this business case is for technical assistance, pre-feasibility studies and ICT equipment and vehicles. The direct climate and environment impacts stemming from the programme are therefore likely to be low. Given this focus, it is also unlikely that environmental degradation or climate change will have a significant impact on the success of this programme. The risks have therefore been categorised as a C. / As with all DFID programmes, care should be taken to reduce energy use and travel where possible. Due diligence of partners should include climate and environment issues and any contracted organisations should have suitable environmental management systems and safeguards in place. / It should be noted that a potential second order effect of supporting the PPP unit will be to stimulate investments in the energy sector and this is likely to lead to an increase in CO2 emissions. However, energy security is a priority for Sierra Leone and we consider that the broader benefits of this programme outweigh this impact. These second order effects will also be influenced by a large number of factors including market dynamics, technological change and regulatory frameworks and in practice, given the size and nature of this programme, there is limited scope to mitigate these impacts in program design. / More broadly, DFID Sierra Leone is working with the GoSL on its energy policy. Sierra Leone is still at a stage where it can take decisions that will lower the carbon intensity of its development and in line with the green growth agenda described in the strategic case, GoSL is keen to maximise the potential for renewables (in particular solar and hydro). / It is expected that the majority of the early PPPs to be supported through the unit will be in the energy sector and the PPP unit is likely to leverage conservable private sector investment into this sector in Sierra Leone and there are climate and environment opportunities associated with this programme. However due to the size and nature of this particular programme, and the limited influence the PPU unit will have over the policy and regulatory framework, the Climate and environment opportunities for both options have been categorised as a B. / Support to the PPP unit will improve the quality of PPPs that are negotiated with the private sector and has the potential to ensure that best practice environmental and social standards are mainstreamed into PPP design, (including requirements for Environmental Impact Assessments (EIAs) and CC risk assessments), and that stringent environment and climate change monitoring and evaluation criteria are incorporated into deals. Assessing the CC risks of proposed infrastructure projects is particularly important given the life of infrastructure projects: any projects must be able to withstand future climate variability. / There could also be the potential to use the technical assistance to explore the development of standard PPPs for renewables in order to encourage greater investment in renewable energy in Sierra Leone in the future. / The do-nothing option 3, could potentially lead to PPPs being negotiated with weaker environmental and climate change provisions in place and has therefore been categorised as a B in terms of risks. There would be no opportunities to influence this.
E. If any, what are the likely major impacts on social development? / The initial focus for PPPs in Sierra Leone is on energy, water, and transport. All have social dimensions, particularly as current provisions is very low and the major increase targeted by PPPs will give many more people access to services. / PPPs may also be developed in health and education. However, it is unlikely that these will be included during the two years covered by this business case.
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / The PPP Unit has an ability to impact in two important ways: / Peace dividend. After its third peaceful democratic election, over 10 years of peace, and the high expectation attached to national income form natural resources, the population of Sierra Leone has high expectations of the Government. The PPPs will help the government achieve its poverty reduction strategy and achieve real results for ordinary people, and deliver the state-citizen contract. / Corruption was seen as a significant contributor to the civil war. Managed well, the PPP Unit has the potential to increase transparency, encourage value for money, discourage corrupt activities, and help GoSL achieve its ambitions for inclusive economic growth.
G. What are the costs and benefits of each feasible option? Identify the preferred option. / INCREMENTAL COSTS / The total cost of establishing the PPP Unit has been estimated at £2.14m over two years with contributions from GoSL and various development partners (Table 1). Of this, the total cost to DFID is estimated at £1.2 million and includes set-up costs for equipment as well as funding for technical assistance, a regional study tour and funding for initial pre-feasibility studies. Funding for TA will not be provided in the future and GoSL will need to fund subsequent pre-feasibility studies from the budget. / Table 1: Summary of Costs / Source Funding Year 1 Year 2 / GoSL Staff costs and salaries 245,000 245,000 / UNDP PPP Adviser 125,000 125,000 / AfDB Financial and legal advisers and training 113,750 86,250 / DFID Equipment, technical assistance & studies 700,000 500,000 / o/w equipment 125,000 / o/w technical assistance and study tours 325,000 250,000 / o/w pre-feasibility studies 250,000 250,000 / TOTAL (£) 1,183,750 956,250 / Additional costs to DFID relate to staff time; the estimated inputs from DFID staff are set out in the management case and involve management, oversight and support for procurement. Staff time is expected to be limited and is not costed as DFID does not accurately record the cost of staff time. / INCREMENTAL BENEFITS / The expected benefits from establishing the PPP Unit principally emanate from efficiency gains that a specialised unit will bring to PPP transactions and to the cost, risk and revenue profile of the country’s PPP portfolio. A centralised unit is likely to be able to manage multiple PPP risks over the longer term and ensure that these benefits accrue to Government in the form of lower expenditure and greater revenue from more efficient operations and fewer failures. They may also result in more infrastructure being built to a higher standard and in a shorter time. For private individuals, the efficiency gains are assumed to result in more and better provision of the infrastructure that will be funded by PPPs e.g. energy, roads etc. / The total value of pipeline PPP projects is estimated at $1.7 billion mostly in energy but also covering water, waste management, trade and transport. The PPP Unit is expected to conclude deals worth $500 million in the first two years of operation, although this will be increased if pre-feasibility and feasibility work can be concluded quickly. Efficiency savings on this would involve ensuring lowest costs (by keeping on time and on budget) for a prudent level of risk. / Estimating the reduction in costs and risks is a complicated calculation (it is why the Government has requested specialist help) and there is currently no basis upon which to make an estimate. The risks involve errors in project design that result in lower quality, selecting the ‘wrong’ PPP, inappropriately designed licenses or permits that increase the overall PPP cost, creating a mismatch between demand and supply and may create opportunities for corruption. / The GoSL concept note on establishing a PPP Unit suggests that without PPP advice, the negotiated deal terms and payout structures would be heavily weighted in favour of the investor with sub-optimal benefits for Sierra Leone. We assume that it is preferable that these benefits accrue to Sierra Leone rather than to private investors, who may also be based overseas. / Other Benefits / Other intangible benefits relate to the impact that a specialist unit on PPPs might have on the business environment, the provision of jobs for Sierra Leoneans and the impact that more and better infrastructure will have on the people of Sierra Leone. / Improved business environment: As discussed in the strategic case, Sierra Leone has made good progress in improving the business climate, though from a very low base. Evidence suggests that PPP Units can carry out market development activities that improve the environment for PPPs. For example, if GoSL is able to negotiate good deals that do not require subsequent re-negotiations, the private sector will be able to enter into deals with greater confidence about the potential returns. This should result in an improved business environment in Sierra Leone that attracts more and better quality investors (e.g. with different risk-return preferences). Greater competition is expected to result in even greater efficiency gains and the PPP Unit can also share information and best practices that may improve future PPPs.[27] / Economic growth: Infrastructure remains a key constraint to doing business and economic growth. However, it is not assumed that implementing the PPP Unit will have a game changing impact on the business climate and growth as the infrastructure projects are expected to continue anyway. There may be a slight improvement from the efficiency gains discussed above but these are not considered significant. / More jobs: The concept note suggests that greater oversight of PPPs will result in more use of domestic contractors with an associated boost to employment for Sierra Leoneans.[28] The causal link between establishing the PPP Unit and more work for domestic contractors is unclear and these benefits are not quantified here. / Counterfactual / If DFID does not support the establishment of a specialised PPP Unit, it is assumed that GoSL will proceed to negotiate PPPs but that the deals will be sub-optimal in terms of revenue and risk-sharing for Government and reducing opportunities for corruption, and that the services procured will be sub-optimal. The other benefits highlighted above will also not be realised with associated implications for the investor climate and business environment. / BALANCE OF COSTS AND BENEFITS / The total cost of running the PPP Unit is extremely small compared to the size of transactions that it will be involved with. Assuming that donor support is withdrawn after two years and GoSL continues to fund staff and pre-feasibility studies at the same level, the discounted cost over the first five years amounts to £3.17m (DFID’s contribution is £1.15m). The discounted value of pipeline transactions over that time amounts to £803m. / Without a firm basis upon which to estimate or quantify the scale of efficiency savings, it is difficult to compare costs with benefits. However, because the size of the transactions is so large, an efficiency gain of only 0.4% per year is required for the PPP Unit to break-even (i.e. when NPV=0 and BCR=1). If the costs to DFID over the five year period are compared to the benefits that could be attributed to DFID based on DFID’s share of the costs (33%), then the annual efficiency saving required to break-even increases only to 0.43%. / Given that the PPP Unit plans to charge a fee for advising on PPP transactions, it is likely that such efficiency gains will be realised because MDAs are expected to be willing to pay. In addition, the other benefits discussed above should also be considered in this analysis, though their contribution is assumed to be marginal. / RISKS AND SENSITIVITY / The main area of uncertainty in this appraisal is whether the establishment of the PPP Unit will lower costs and risks and result in a greater return for the Government and people of Sierra Leone from PPPs than without it. There is no empirical basis upon which to test the effect of a PPP Unit or quantify the extent of these benefits so the appraisal has been done on a break-even basis and it is judged that a specialised unit should be able to generate the savings required to pay for itself. / The greatest risks to this conclusion are that the PPP Unit is not able to source sufficiently skilled personnel to staff the unit in the long run and that the technical assistance will not be sustainable. The market for skilled lawyers and financial analysts is limited in Sierra Leone, particularly for those with experience with PPPs. Even with enhanced salaries, it will be difficult to retain them in Sierra Leone. Management of this risk is explored in the management and financial cases below. / COMPETITION ASSESSMENT / To the extent that there are limited foreign investors in Sierra Leone and that the investment climate has many challenges, the establishment of a PPP Unit may result in more competition to invest in Sierra Leone. As discussed above, this is expected to lower the costs and risks for the Government and generate a healthier return, since more efficient firms may be encouraged to participate. / MACROECONOMIC AND FISCAL IMPACT / The main macroeconomic impact is expected to be that the operation of a specialised PPP Unit will encourage: / More and better foreign investment into Sierra Leone will contribute to foreign exchange earnings and reduce the current account deficit. However, earnings from operating PPPs may also flow out of the country. / More and better infrastructure will provide an environment more conducive to GDP growth, a more efficient economy and more jobs with an associated rise in government revenue. / The main fiscal impact of the intervention is the recurrent cost to Government of maintaining the PPP Unit and funding the pre-feasibility studies. If the macroeconomic and fiscal benefits are realised, this should be affordable in the budget, particularly if fees are charged on the transactions. / Potentially adverse fiscal impacts should also be noted if, for instance, a PPP needs to be ‘bailed out’ or nationalised by the Government. These costs would not be insubstantial but, if it is assumed that there is a higher probability of failure without the specialist advice of a PPP Unit than with one, then this risk is lower and the net effect should be a benefit to Government.
H. Theory of Change for Preferred Option / The Theory of Change (ToC) focuses on the central role of infrastructure in providing services to people and enabling the private sector to thrive and create jobs. Seven key causal links underpin the ToC as set out below: / GoSL will establish a prioritised infrastructure development plan which will focus investment in areas which will have the most impact / A well-resourced and technically competent unit within GoSL will ensure investments are well structured and deliver benefits to Sierra Leone / Well-structured and delivered agreements will give confidence to high quality foreign investors and attract them to invest in Sierra Leone / More and better infrastructure will be constructed faster, providing immediate benefits to Sierra Leoneans in the range of and access to services. / Reliable electricity, transport, water and waste management services will attract private sector investment in other areas of the economy, including secondary processing of minerals and agricultural products, and a tipping point will be reached which will allow other sectors and markets to develop / As enterprises become more productive and profitable, they will expand and create jobs and opportunities for others to earn income through providing goods and services to these enterprises. / Many of the 1.2million people who are unemployed, underemployed or engaged only in subsistence activities will gain employment (broadly defined to include paid and self-employment) and participate fully in the economic development of Sierra Leone. This is inclusive growth. / Although the ToC relates to all forms of job creation and inclusive growth, by selectively promoting certain investments and discouraging others, the intervention will aim at gender equality, environmental sustainability and climate resilience. These will be addressed through the policies and systems adopted during implementation. / The key assumptions in the ToC are: / Foreign investors – particularly high quality investors – recognise the potential of Sierra Leone and are willing to invest in infrastructure / Corruption does not undermine the ability of GoSL to agree well-structured agreements that deliver benefits to Sierra Leone / The private sector responds to improved infrastructure by investing in business opportunities across all sectors of the economy / World mineral prices remain sufficiently high for GoSL revenues to increase and allow the Government to invest in infrastructure with foreign partners. / All four assumptions are relevant to the Sierra Leone context but the programme can be designed to mitigate the risks. / GoSL is active in promoting the image of Sierra Leone and the opportunities for business. SLIEPA undertakes regular trade missions and engages directly with potential investors. / Sierra Leone is 123 out of 176 countries in the Transparency International Corruption Perceptions Index 2012[29]. This compares favourably with Nigeria (139) and Guinea (154) but is not as good as Ghana (64) and Liberia (75). GoSL is committed to tackling corruption and is gaining support from development partners, including DFID, to do so. / The lack of infrastructure, particularly reliable electricity supply, has appeared regularly on surveys as a key constraint to business[30]. / Sierra Leone has a range of commodities – iron, rutile (titanium), gold, diamonds and possibly oil and gas – and is not dependent on a single market. Although prices have dropped as the world economy slows, mining remains profitable and prices would have to fall significantly further before operations are likely to cease. The pressure on prices also means that mining companies need to reduce production costs which will encourage more local procurement and employment provided that suitable local services are available. This in turn depends on improved infrastructure and private investment.
I. What measures can be used to monitor Value for Money for the intervention? / Value for money will be achieved by ensuring delivery of the results and monitoring and reducing costs throughout the two years of the programme. / The target results are ambitious, requiring rapid negotiation of PPP deals and immediate installation of electricity generating capacity and distribution systems. However there is also potential for exceeding targets, both in terms of the amount generated and the number of additional people with access to electricity. By focusing attention on delivery, we aim to ensure that the Unit provides value for money. / The two major cost areas are the PPP Technical Advisor and the fund for pre-feasibility studies. The cost of the PPPTA will be managed through a competitive procurement process which will include value for money criteria in the selection of the provider. / The pre-feasibility study will be used for a series of individual studies commissioned by the PPP Unit and managed by the PPPTA. This arrangement allows for careful selection of potential studies, drafting of terms of reference which minimise duplication with other studies and ensure the recruitment of expertise from within Sierra Leone wherever possible. All these measures will contain costs and enhance value for money. The studies will be monitored both individually and as a portfolio to check that they are delivering value for money.
J. Summary Value for Money Statement for the preferred option / The PPP Unit will deliver value for money by: / Increasing electricity generation to at least 120MW by 2015 / Giving at least an additional 120,000 people access to electricity by 2015 / Recruiting the PPP Technical Advisor through a competitive selection process using VFM criteria; and / Managing the pre-feasibility study fund in an efficient and economic manner.
[25] PEAKS Helpdesk, April 2013 (ODI)
[26] PEAKS Helpdesk, April 2013 (ODI)
[27] See Lemma (2013) Literature Review: Evaluating the Costs and Benefits of Centralised PPP Units for a summary.
[28] The Government is implementing a ‘Local Content Policy’ that seeks to encourage the use of local inputs. This is likely to impact on the structure of PPPs regardless of the presence of a PPP Unit but its presence may result in greater compliance.
[29] Transparency International http://cpi.transparency.org/cpi2012/results/
[30] Eg IFC Enterprise Survey (2009) where electricity was in the top three obstacles, and the World Bank Doing Business index 2013 where Sierra Leone was 176 for electricity, the lowest score the country achieved across all indicators.

Commercial Case

Direct procurement through a contracted supplier

A. Clearly state the procurement/commercial requirements for intervention / Direct procurement / Under the preferred option, DFID will provide three components of support, each of which will be procured in a different way through contracted suppliers to ensure value for money. / Office IT equipment (mainly computers) with an estimated total cost of around £25,000 and no individual item costing more than £5,000 will be procured locally through a single contract. A diesel generator to power the office will be procured locally through a separate contract of up to £20,000. / Three project vehicles will be procured by a DFID approved Procurement Agent, with a total value of approximately £80,000. / Technical Assistance including the PPP Technical Advisor will be responsible for providing technical expertise and advisory services for the overall operations of the PPP Unit, along with managing pre-feasibility studies and a study tour. This expertise will amount to around £1.05 million and will be procured through either DFID’s Wealth Creation Framework Agreement or the Professional Evidence and Applied Knowledge Services (PEAKS) Framework.
B. How do we expect the market place will respond to this opportunity? / Procurement of office equipment and diesel generators is common practice and there should be no shortage of potential suppliers in the local market. Similarly, there are numerous suppliers of 4x4 vehicles that can handle Sierra Leone’s terrain. The DFID approved Procurement Agent should have several experience suppliers who can provide these goods. / DFID has a range of Framework Agreements with suppliers that set out the terms and conditions under which specific procurements for technical assistance can be made through call down contracts. The Wealth Creation Framework Agreement includes suppliers with expertise in private sector and market development, and investment climate reform. Similarly, the Professional Evidence and Applied Knowledge Services (PEAKS) Framework includes suppliers who can provide Economics and Private Sector Development expertise. / DFID Sierra Leone will explore both of these options to understand how technical expertise can best be provided to the PPP Unit. Previous experience of procuring through both of these frameworks has shown that there are a number of well-qualified potential suppliers[31] with experience of working in Sierra Leone and thus we anticipate there will be competition in the market to supply this expertise to the PPP Unit.
C. How does the intervention design use competition to drive commercial advantage for DFID? / The local procurement of office equipment obtains a minimum of three quotes to ensure DFID can choose the option that provides best value for money. Procuring low value items locally avoids the added administration and import costs of international procurement and ensures short transportation pipelines for the provision of equipment needed urgently to allow the PPPU to function. DFID has also spoken to the PPPU to understand the IT systems that exist in the office to ensure that IT equipment procured is compatible. The selection process will also factor in the provision of after sales facilities backed up with a warranty period to ensure the quote provides value for money across the project life cycle, not just in the purchasing phase. / The procurement of vehicles will use a DFID approved Procurement Agent who has already gone through an EU competitive process in the relation to the services they provide. Quotations received by the Procurement Agent will be evaluated on the basis of value for money, including; price (both up-front and on-going running and maintenance costs), quality of the vehicles, delivery times, and the availability and cost of spare parts. / For the provision of technical assistance to the PPPU, a competitive tender will be conducted under DFID’s PEAKS or Wealth Creation Framework Arrangements to select the agency or consortium best placed to provide a PPP Technical Advisor. These Framework Agreements have already pre-qualified potential suppliers’ technical competence. The mini-competition for this specific intervention will assess experience and technical expertise of those bidding to deliver the requirements set out in the terms of reference and the commercial aspects of their bids to ensure that the successful bidder has the required skills and experience to deliver results in a cost-effective manner. Following a due diligence assessment of the preferred bidder a call-down contract will be negotiated. / Criteria to be used for assessment will include: experience in providing PPP transaction advisory services / development of large infrastructure projects on PPP basis; relevant expertise in infrastructure projects including power generation, road construction, tourism, and agri-fishery; experience of working in post-conflict countries and managing relations within and between government ministries and agencies; experience and understanding of pre-feasibility studies; negotiation, project and contract management skills; and the ability to deploy rapidly. These will be considered alongside financial and organisational criteria, including demonstrably robust financial management; and a credible and value for money proposal. / The terms of reference for the PPP Technical Advisor will be structured to encourage flexibility in how the programme is delivered, in order to achieve maximum results at reasonable cost in what is likely to be a changing context over the project lifecycle. However, changes in priorities to what needs to be delivered for the PPPU will need to be discussed with, and approved by, DFID.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The principle cost drivers will relate to the provision of technical assistance and the pre-feasibility studies, rather than equipment for the office which is a smaller component. Within the technical expertise the main cost drivers will be: / PPP Technical Advisor’s fee rates, where the specific factors are level of responsibility, duration of engagement, difficulty of the post, credentials and past performance. Given Sierra Leone’s post-conflict status and limited health care, combined with the need for a proven ability to work in a government setting, there may be limited room for negotiation with a supplier that meets the technical criteria. If the Technical Advisor is based here permanently the cost of living expenses for accommodation and related expenses will also be a key cost element. / Direct Implementing partner overhead costs relating to the provision of a technical expert, for example, accommodation, medical insurance, visas, flights. Accommodation costs will be the most significant in this category and DFID will encourage the use of rented accommodation over use of hotels. / Indirect overhead costs, including amounts within each fee to contribute to the costs of being in business, such as corporate operations, managed costs, recruitment, back office administration, headquarters, and the supplier’s profit margin. / Pre-feasibility studies and study tour managed by the PPP Technical Advisor. These could include looking at possible projects on roads, energy provision and water resources. / These feed into the wider consideration of the scale of resources required to manage the programme. As set out above, it is important that the right level of expertise is recruited and a balance is struck between gaining sufficient expertise and keeping costs down where possible. / Management costs will therefore be carefully scrutinised and challenged as part of the competitive tendering process. These costs will be regularly monitored, and compared with implementation rates and achievement of results.
E. How will the contract be structured and how will contract & supplier performance be managed through the life of the intervention? / The PPP Unit has developed a terms of reference for Technical Advisor. This includes defined outputs in assisting the Unit to prepare key documents and processes that will allow it to manage the backlog of unsolicited proposals. These outputs include pre-feasibility studies, legally compliant procurement policies, designing and administering of a pre-qualification process, a bid evaluation system and criteria; a request for proposals document; and a comprehensive PPP management plan for specific line ministries. / A selection of these will be included as outputs in the project logframe, which will be used by DFID as the main monitoring tool. They will also be included in the project workplan. DFID will scrutinize progress against these outputs and will look to structure the contract in a way that allows payments to be withheld if progress is off-track in delivering these outputs. DFID is unlikely to pursue a purely outputs-based contract, since delivery of outputs will depend on the functioning of the Unit as a whole, which is not solely within the scope of the Technical Advisor to control. Communication between the Technical Advisor and Head of the PPP Unit with DFID will be vital for a shared understanding of progress, obstacles and the need for possible changes in the workplan and logframe. / While fees and expenses will be paid monthly in arrears throughout the project, specific elements of the technical assistance such as the pre-feasibility studies and the study tour will be the responsibility of the Technical Advisor and DFID will explore options to only pay for these elements once they have been delivered to incentivize delivery and drive value for money.
[31] The Market Development Programme was tendered under the Wealth Creation Framework in May 2013 and attracted four bids, of which three were technically competent.

Financial Case

A. Who are the recipients of all proposed payments? / There will be four different recipients of payments: / The local supplier of office IT equipment / The local supplier of a diesel generator for the office / The supplier of three project vehicles / The supplier of technical expertise that will be procured through one of DFID’s framework agreements. / The specific organisations who receive the payments will be determined through the named procurement processes that will begin upon approval of this business case. The PPP Unit will in turn benefit from receipt of all these goods and services.
B. What are the costs to be incurred directly by DFID? / The total cost of the two year project is up to £1.2 million. Approximately £375,000 will be incurred in 2013/14, £550,000 in 2014/15 and £275,000 in 2015/16. / Equipment for the office will amount to around £45,000 and project vehicles will cost up to £80,000. The remainder of up to £1,075,000 will be managed by the Programme Implementer, who will manage a contract covering the PPP Technical Advisor, pre-feasibility studies and study tour. / Component of support 2013/14 (£) 2014/15 (£) 2015/16 (£) Total (£) / Office IT equipment 25,000 25,000 / Diesel Generator 20,000 20,000 / Project Vehicles 80,000 80,000 / PPP Technical Advisor 100,000 250,000 175,000 525,000 / Pre-feasibility Studies 100,000 300,000 100,000 500,000 / Study Tour 50,000 50,000 / TOTAL 375,000 550,000 275,000 1,200,000 / These costs are inclusive of management fees / overhead costs. For local procurement, there are no specific management / overhead costs, with installation and transport costs included in the total. Initial estimates and previous experience suggest that the procurement fee for project vehicles will be under 3% of the total cost. For technical assistance, we would expect administration and overhead costs to amount to around 13% of the total, but this will be negotiated and determined in the contracting process.
C. What are the costs to be incurred by third party organisations? / The total cost of the two year project is up to £1.2 million. Approximately £375,000 will be incurred in FY 2013/14. / The table above shows the breakdown of costs based on initial estimates and previous procurements of similar goods and services. All costs will initially be incurred by third party organisations – local suppliers for office equipment and the generator, international suppliers for vehicles and international suppliers of technical assistance chosen through a tender process. DFID will, however, ultimately incur all the costs shown above, reimbursing the suppliers of the goods and services upon receipt of invoices and delivery of services.
D. Does the project involve financial aid to governments? If so, please define the arrangements in detail. / No. The PPPU will sit within State House (the Office of the President), however DFID’s contracts will be with suppliers of goods and services, not directly with the Government of Sierra Leone.
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / The programme will be funded from the Wealth Creation pillar of the DFID Sierra Leone programme budget. Funds for the first two years fall within the current spending review period and come from the agreed budget under the DFID Sierra Leone operational plan. Expenditure in 2015/16 has been approved by HM Treasury.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting? / The profile of costs is shown in section B above of this financial case. Upon approval of this Business Case, the procurement process will begin. Quotations for office equipment and vehicles will be obtained and timelines for delivery of goods defined. This will allow the month in which these costs will be incurred to be forecast. These will be one off payments and so will not need to reforecast. / The costs of technical assistance will be defined once the services have been procured and the contract negotiated. DFID will require the contracted supplier to provide a budget forecast for the next twelve months on a monthly basis and on quarterly basis for the project period beyond the immediate 12 months. Costs will then be invoiced on a monthly basis, allowing DFID to scrutinise costs regularly and look for deviations from the forecast. Where deviations are significant DFID will ask for further explanation. / Forecasting and paying on a monthly basis in this way will allow regular and accurate forecasting against agreed budget lines. Cumulative expenditure in each budget line will be compared against the agreed maximum contracted amount, allowing DFID and the supplier to ensure costs will not escalate beyond the contracted amount. If costs that are beyond the control of the supplier do increase beyond forecast amounts, for example due to increased market rental accommodation or flight costs, the supplier will discuss this with DFID and consider whether contract amendments are justified.
G. What is the assessment of financial risk and fraud? / The likelihood of financial risk and fraud in the direct procurement of equipment and vehicles is minimal. Three quotes will be obtained and assessed against an agreed budget and criteria of value for money to ensure that the procurement process itself is fair and not subject to favouritism and that costs are not inflated. Project vehicles will be procured through a Procurement Agent that has already pre-qualified as meeting DFID standards on procurement procedures. The delivery of the equipment will be verified by the PPP Unit and DFID staff. The equipment will not be paid for until invoices have been received. An asset register will be established with the PPP Unit to ensure that the equipment remains in and is used by the PPP Unit. These will be subject to asset checks during the project lifecycle to verify this. / For the technical assistance component, DFID will mitigate the risk of financial impropriety and fraud firstly through requiring bidders to demonstrate robust financial and procurement systems and processes as one of the criteria for the competitive bidding process. The selected Programme Implementer will also undergo a due diligence assessment by DFID. Most information for this will come from the procurement process, but DFID will also ask for additional information on risks of fraud and corruption, including policies on fraud, bribery and corruption, any previous issues of fraud and mechanisms in place for reporting it. / Once the project starts, payments will be made monthly in arrears, ensuring that money is only transferred to the supplier once fees and expenses have been incurred. Given the technical assistance involves just one person, the fees and expenses will be relatively simple and therefore would be difficult to inflate falsely. They will also be benchmarked against fees and expenses for similar work. As with equipment supplied directly to the PPP Unit, any assets purchased by the Programme Implementer will be held on an asset register that will be submitted to DFID quarterly and subject to spot checks to ensure the equipment is there and being used as intended. Where possible payments for specific pieces of work, such as the pre-feasibility studies, will only be made on receipt of the product, again minimising the misuse of funds. The risk of fraud and corruption in the technical assistance component, in light of these measures to be taken before and during the project, is therefore also assessed as low. / DFID Sierra Leone introduced a Fraud and Anti-Corruption Strategy in December 2012. This establishes systems and procedures across all DFID programmes and requires contractors and suppliers to operate at the same standards as DFID does itself. The procurement process will include advice to potential bidders on these requirements, and DFID Sierra Leone will follow up at inception to ensure that the Programme Implementer adopts the strategy effectively and in full.
H. How will expenditure be monitored, reported and accounted for? / Office equipment and vehicles will be paid for on receipt of invoices and confirmation of their delivery to the PPP Unit office. The technical assistance will be required to provide monthly financial invoices and forecasting line with standard DFID practice, with this broken down by budget lines stated in the contract. Invoices will be compared with forecasts and any significant variance accounted for. Specific deliverables from the technical assistance, namely the pre-feasibility studies, will be paid for once delivered. / Any capital assets procured under this programme will be treated in accordance with DFID procedures and declared to the DFID programme manager. An asset register will be kept and asset checks will be conducted. Assets remaining at the end of the programme will be disposed of as determined by DFID in a way that ensures value for money.
I. Are there any accounting considerations arising from the project? / All expenditure outlined above will be resource accounted, that is money will be forecast and accounted for as goods and services are delivered. Assets will be recorded in an asset register and reviewed on a quarterly basis. At the end of the project DFID will decide how assets can be disposed of in a way that ensures value for money.

Management Case

A. What are the management arrangements for implementing the intervention? / DFID will oversee the procurement of equipment, procuring low value items directly through a local procurement officer and larger value items through an approved procurement agent. DFID will verify delivery of all these items to the PPP Unit office. / The technical assistance will be overseen by the DFID Sierra Leone Wealth Creation Team. Specifically, the project will be managed by the team’s Private Sector Development Advisor, Programme Manager and Programme Officer. / The main monitoring tool will be the project logframe, with specified outputs to be delivered by the PPP Technical Advisor and timeframes in which these should be delivered. This will align with the ToR for the PPP Technical Advisor. The contracted supplier will submit quarterly technical narrative reports, detailing progress against logframe outputs. DFID will also hold regular management meetings with the contracted PPP Technical Assistant to discuss project progress, financial expenditure and review risks to project implementation, taking remedial action where necessary. Within the PPP Unit itself, the PPP Technical Advisor will report to the Head of the Unit. / DFID’s support will be part of a wider package of donor support, with other donors funding other parts of the PPPU as set out in paragraph 41 of the Appraisal Case. For this reason there will also be a Steering Committee to provide strategic input and oversight and ensure donor support is coordinated in supporting the Unit as a whole. The Committee will comprise of: / the Chief of Staff; / a representative from each development partner, (one to be co-chair); / the Ministry of Finance and Economic Development; and / the Head of the PPP Unit. / The following line ministries will also be kept informed through regular meetings: Attorney General and Ministry of Justice, Bank of Sierra Leone, Director of the Strategy and Policy Unit, National Public Procurement Agency, Environmental Protection Agency, National Commission for Privatization, Chamber of Commerce and Industry, and Sierra Leone Investment and Export Promotion Agency. / The Committee will receive quarterly reports from the Head of the Unit. For DFID this will help track the overall progress being made by the Unit and that the outputs being delivered by the technical assistance DFID funds is contributing to broader outcomes. It will also highlight any broader obstacles the Unit is facing which will impact upon the specific outputs DFID technical assistance is seeking to achieve.
B. What are the risks and how these will be managed? / The table below sets out the risks associated with the programme and the actions which will be taken to mitigate those risks. / Risk / Category Risk Impact Probability Mitigating / Actions Residual / Risk / Governance Conflicting priorities between State House and line ministries result in limited usage of Unit capacity and/or poor quality PPPs through ad hoc negotiations. M M The use of the pre-feasibility study funds is safeguarded through the PPPTA. In the event that funds will not provide VFM, the studies would not be undertaken. / The PPPTA role aims to help agree priorities and to address conflicting interests between State House and line ministries. M/L / PPP Unit lacks authority to impose quality standards and to tackle corruption M M Promote transparency in Unit operations and publication of PPP agreements. / Continue support to Anti-Corruption Commission. / DFID funds specifically safeguarded through methods mentioned earlier M/L / Unit does not function coherently with objectives of different donors not aligning H L Steering committee will assess the performance of the unit. Specific deliverables all contribute to the over-arching goals set out by GoSL M / Environment / Risk & / Climate / Change Resilience Insufficient data on potential impact of poor planning and design of infrastructure on climate change (both inadequate preparation resulting in damage, and over-compensation resulting in excessive costs) M L Link with climate scientists (governments, universities and agencies) to assess the impact of climate change on infrastructure in Sierra Leone. M/L / Programme Management Risks Poor performance by Technical Advisor L L Initial procurement will select a well-qualified individual. Ongoing monitoring will assess project progress and risks to delivery. DFID will reserve the right to withhold payments and terminate the contract L / Sustainability PPP Unit becomes reliant on technical assistance and capacity is not built M M/L All donors should have a clear exit strategy. Experienced short-term specialists will work with local staff to pass on expertise M/L / Government becomes reliant on private sector suppliers without considering longer-term options of public sector provision M H Government and donors should review the value for money of private sector provision and benchmark these against alternatives including public sector provision. M
C. What conditions apply (for financial aid only)? / N/A
D. How will progress and results be monitored, measured and evaluated? / DFID will monitor the specific progress being made by the Technical Advisor by monitoring progress against the logframe. This will be monitored through quarterly narrative reports, the specifically state progress against outputs in the logframe. These will be monitored by the DFID Sierra Leone Private Sector Development Advisor and Programme Manager. Financial expenditure will be monitored on a monthly basis by the DFID Programme Manager and Programme Officer. They will scrutinise invoices and forecasts against the agreed budget lines in the contract. Payment for pre-feasibility studies will only be made upon satisfactory delivery of the study reports. DFID will also review the asset register and risk register on a quarterly basis with the Technical Advisor. / The overall progress being made by the PPP Unit as a whole will be monitored on a quarterly basis by the Steering Committee. All donors will sit on this committee and so can ensure that the inputs they are funding are contributing to the overall objectives of the Unit. / A logframe has been developed by the PPP Unit and this is used to demonstrate the overall impact and outcomes of the Unit. The logframe also links to the Results Monitoring Framework of the Agenda for Prosperity, strengthening the coordination within GoSL and ensuring effective ownership by the Unit themselves. DFID’s support will contribute to the outcomes of the PPP Unit, but it is more difficult to attribute outcomes to DFID resources. The results are therefore expressed in terms of the whole Unit and we will use more specific indicators and targets for the PPPTA recruitment and performance monitoring. / There are no plans for an evaluation of the project as it is relatively low in value and not a novel development concept. DFID will however conduct annual reviews of the project, looking both at the overall PPP Unit logframe and also the specific indicators and targets for the PPPTA. If the project is performing below expectations and project improvement plan will be put in place to remedy problems. DFID will also conduct a project completion review at the end of the project to review the overall success of the project. Annual reviews and project completion reviews will be published to allow lessons to be shared with others wishing to implement similar projects.
Logframe / Quest No of logframe for this intervention: 4048168 / The logframe for the PPP Unit as a whole is linked to this Business Case.