Annual Review – post April 2018

Title: / African Agriculture Technology Foundation Phase III (2015-2020)
Programme Value £ (full life): £10m		Review Date:
Programme Code: 204988	Start Date: 5th October 2015.	End Date: 30th September 2020

Summary of Programme Performance
Year	2016	2017	2018
Programme Score	A+	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case and logframe:	https://devtracker.dfid.gov.uk/projects/GB-1-204988/documents

A. Summary and Overview (1-2 pages)
Description of programme (1/2 page)
To achieve the Sustainable Development Goals, a step-change is needed in smallholder agricultural productivity, incomes, and resilience in Africa. Key to achieving this – and in line with ambition of DFID’s work on Strategic Direction regarding technology - is to ensure that African smallholder farmers have access to appropriate and effective agricultural technologies including mechanised equipment and high-quality seeds. However, smallholder farmers often lack the purchasing power to access new technologies, which reduces incentives for private sector companies to develop agricultural technologies that meet their needs.
To overcome barriers to technology adoption by smallholder farmers, DFID provides support to the African Agricultural Technology Foundation (AATF). AATF is internationally recognised as a leader in the identification and development of appropriate agricultural technologies and their delivery to smallholder farmers. Its central value is in bridging the crucial gap between agricultural technology researchers and smallholder farmers. AATF therefore directly contributes to DFID’s strategic direction on Harnessing Technology for Development by taking technologies to scale and promoting DFID’s role as a global leader.
This programme builds on the UK’s previous support to AATF from 2010-2015, during which AATF consistently met or exceeded expectations: AATF delivered drought tolerant maize varieties to over 57,000 households and developed a pipeline of new products including Water Efficient Maize for Africa (WEMA).
AATF has demonstrated that it is highly capable of overcoming barriers to delivering high-quality agricultural innovations into the hands of smallholder farmers. Its technical expertise and recognition as a key ‘go-to’ organisation in this sector justified funding. Ongoing support enables AATF to continue to deliver essential agricultural technologies to smallholder farmers, while also preparing the ground for a transition from DFID support. Funding will support AATF through institutional change to adapt and embrace a more inclusive and sustainable business model.
The programme supports AATF activities in two areas: support to organisational systems and support to specific projects. The expected impact of support to the proposed intervention is increased productivity of smallholder farmers in SSA.
This impact will be achieved through two outcomes:
1. Increased access/availability of appropriate agricultural technologies for smallholder farmers in target countries in SSA
2. A financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers in ensuring that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed.
Summary supporting narrative for the overall score in this review (1/2 page)
AATF has been assessed as scoring “A” this year, and has made significant progress this year towards meeting objectives.
AATF continues to make progress on increasing the access and availability of appropriate agricultural technologies for smallholder farmers in SSA. This is reflected in, amongst others, the following achievements over the reporting period:
- AATF has exceeded or met targets for accessing new technologies and developing/deploying projects.
- The TELA Maize Traits Launch Project was launched in May 2018 to build on and accelerate the gains from the WEMA Project.
- Two new rice hybrids were released and registered for commercialisation in Kenya in July 2018.
- Through the Seeds2B Project six seed companies (5 in Zimbabwe and 1 in Malawi) successfully identified commercially viable products from sorghum, pearl millet, and tomato varieties introduced by AATF for value chain development.
- AATF continues to be seen as a ‘go-to’ organisation for agricultural technology transfer in SSA and exceeded targets for requests for partnerships and knowledge sharing.
Additionally, in the past year AATF has made important institutional changes towards becoming a more financially sustainable organisation. Key developments are:
- New funding from the African Development Bank, with AATF leading on the Maize, Policy, and Mechanisation Compacts of the Technologies for African Agricultural Transformation (TAAT) initiative. This new funding - plus additional funding from established donors - has enabled AATF to overcome medium-term financial constraints.
- Successful launch of a new social enterprise to house AATF’s business ventures: Agridrive. While it is still early days, and more evidence is needed of its effectiveness as a sustainable business model, the establishment of Agridrive does represent progress towards AATF becoming more attractive to organisations preferring to invest in for-profit ventures.
- Steps taken to reduce AATF’s cost base, including ending staff contracts and reducing the number of international staff.
These are welcome developments in an area where progress has thus far been slow. The next year will be crucial in delivering their new strategy.

Key Acronyms
AATF	African Agriculture Technology Foundation
BMGF	Bill and Melinda Gates Foundation
CAMAP	Cassava Mechanisation and Agro-processing Project
CFT	Confined Field Trials
IITA	International Institute of Tropical Agriculture
IR-Maize	Imazapyr herbicide resistant maize
MLN	Maize Lethal Necrosis
NEWEST	Nitrogen-use Efficient, Water-use Efficient and Salt Tolerant Rice
NUE	Nitrogen Use Efficient
OFAB	Open Forum on Agricultural Biotechnology in Africa
PBR	Pod Borer Resistant
TAAT	Technologies for African Agricultural Transformation
USAID	United States Agency for International Development
WEMA	Water Efficient Maize for Africa

Recommendations for the year ahead (1/2 page)
1. AATF to assess and update the logframe to bring it more into line with shifts in focus and the new strategy and workplan. For example, the closure of WEMA project and creation of Agridrive need to be reflected. Logframe changes to be agreed between AATF and DFID by the end of March 2019.
2. AATF to implement plans and monitor the impact of increased social media interaction outside of key events, reporting specifically on this in the next report to DFID (October 2019).
3. As with some of the indicators under Output 1, Indicator 4.3 has been substantially exceeded. AATF is recommended to review whether these indicators and targets continue to align with AATF’s workplans, for example with the newly approved projects. Logframe changes to be agreed between AATF and DFID by the end of March 2019.
4. AATF to continue to report on the performance of Agridrive, integrating reporting into the logframe
5. AATF to share the TOR for the OFAB impact evaluation and the final report, along with the new evaluation framework.
6. DFID and AATF to agree performance indicators for Year 4 by the end of March 2019.
7. AATF to provide a clear plan of action with measurable indicators of progress on improving recruitment of women to improve the organisation’s gender balance (carried over from 2017 Annual Review).
8. AATF should have a clear plan in place for implementing the new approach to project overheads (by February 2019).
9. AATF to report to DFID on the categorising of downstream partners in terms of safeguarding, fraud, and anti-corruption procedures and how they will adapt their approach to limit risks (by June 2019).
10. AATF to take forward recommendations from the due diligence review (by May 2019).

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	AATF has developed a strong product pipeline (Cowpea, Maize, Hybrid rice, Newest rice, Seeds2B)
Output number per LF		1	Output Score	A+
Impact weighting (%):		30	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of new appropriate agricultural technologies / a) scouted: at least 10 / b) accessed: at least 4	15 / 4	Exceeded: / 121 Seeds2B[1] (121 Scouted): Malawi: Improved soybean (4), groundnut (30) and pigeon pea (6) public and private bred varieties identified for possible inclusion in trials in Malawi. Uganda: Improved bean (8) soybean (6), groundnut (5), pigeon pea (22), cowpea (19), sorghum (6), millet (10) and tomato (10) public bred varieties identified for possible inclusion in trials in Uganda. / Seeds 2B (89 technologies accessed): Malawi: Soybean (26), groundnut (8) and cowpea (3) Uganda: soybean (52)
1.2 Number of project feasibility assessments conducted	2	Exceeded: 3 / Market studies for PASTA Malawi and Uganda finalised. Baseline study for Hybrid process initiated and expected to be completed in December
1.3 Number of new projects initiated	3	Exceeded: 6 / TAAT Maize Compact (Approved by AfBD); TAAT Policy Compact (Approved by AfDB) AGRA Seed Policy (Approved by AGRA); TAAT Mechanization (Approved AfDB); TELA Maize Project (Approved by BMGF); and TELA-Nigeria Project (Under review by USAID)
1.4 Number of inbred line products deployed 5 per year for WEMA - 2 (C. Inbred, T. inbred); 6 per year for Hybrid rice - 2 (male [p] lines) & female [s] lines	20	Exceeded: 24 / a) Hybrid Rice (14 S lines): These are the fixed parental line and already being used for hybrid development. / b) WEMA (10): 4 Inbred lines of MON89034 for South Africa; and 6 Inbred lines of MON87460 for creating stacked traited hybrids. These 10 inbred lines are currently being used to develop TELA maize varieties in South Africa.
1.5 Number of products developed/deployed. A) Seed: 5 hybrids per year for WEMA, 5 hybrids per year Hybrid rice, 4 crops in Seeds2B (Varieties for Tomato, Sorghum, Soy bean and Pearl millet) / B) Machinery: CAMAP - 6 (Planting - 1, Harvesting - 1, Processing - 4)	20	Met: 20 / a) Hybrid Rice (5): These rice hybrids were released and registered in Kenya and are already licensed to private seed companies for seed production and commercialization. b) Seeds2B (9): 9 tomato lines under regulatory trials in Malawi. c) WEMA (6): MLN tolerant varieties (DroughtTEGO®) released and approved for commercialisation; 3 in Nov 2017 (WE6103; WE6105: WE6106) and 3 in May 2018 (WE7117; WE7118; WE7119).
[1] Seeds2B (Seeds to Business) aims to improve access to quality, affordable seed of a wide range of preferred better-performing and locally adapted crop varieties quality seed for higher yields, increased household income.

- AATF has substantially exceeded the milestones for Indicator 1.1 in terms of new Seeds2B technologies scouted and accessed. This was the result of additional funding from USAID and new collaborations with partners in Malawi and Uganda.
- The newly approved Technologies for African Agriculture Transformation (TAAT) work on Maize, Mechanisation, and Policy and the new TELA Maize project have enabled AATF to exceed its target on new projects initiated. These projects provide exciting new directions for the institution.
- Given the challenges of getting new seeds from development into use in SSA, it is promising to see that five hybrid rice varieties have been registered in Kenya and are already licensed to private seed companies.

Lessons identified this year, and recommendations for the year ahead linked to this output
The continued over-achievement of Indicator 1.1 (despite the targets being raised following the 2017 Annual Review) leads to questions about whether the logframe still aligns with AATF’s objectives and future directions. Much has changed since the logframe was created at the start of the programme, and the Annual Review process provides an opportunity to reassess outputs and indicators. This was discussed in the Annual Review Meeting, and AATF is subsequently recommended to propose alterations to the logframe to align more closely with its objectives and workplans.

AATF to assess and update the logframe to bring it more into line with shifts in focus and the new strategy and workplan. For example, the closure of WEMA project and creation of Agridrive need to be reflected. Logframe changes to be agreed between AATF and DFID by the end of March 2019.

Output Title	AATF positioned as a credible and responsible go-to organisation for agricultural technology transfer in SSA
Output number per LF		2	Output Score	B
Impact weighting (%):		20	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of requests for partnerships; specialist technical expertise/ experience and knowledge sharing on agricultural technology transfer among key targets*; requests for specific technologies (*regional bodies, policy/decision makers, farmers, professionals (researchers, lawyers, students), media, private sector e.g. seed companies etc)	15	Exceeded: 33 / A total of 33 requests received: 12 requests for partnerships, 12 requests for specialist technical expertise/experience and 9 requests for knowledge sharing on agricultural technologies
2.2 Increase (quality and quantity) in number of mentions in both traditional and social media	Traditional Media 865 / Social media 2000	Not Met: / 784 / Media mentions Oct - Dec 2017 = 270; Jan - Sept 2018 = 514; / New followers (1,487) / Total Followers (12,388) / Twitter followers up by 53% from 1,901 followers in Sept 2017 to 2,903 in Sept 2018. Facebook likes/followers up by 5% from 9,000 in 2017 to 9,485 Sept 2018.
2.3 Number of proactive communication products on AATF experiences and successes (e.g. Books & Booklets, Picture stories, Impact stories, Annual report, videos,)	Booklets/Booklet 1 / Picture Stories 15 / Impact Stories 25 / Annual Report 1 / Video clips 32	Not Met: / 2 / i. Media Reporting on Biotechnology in Africa; ii. Analysis of effects of Ban on importation of GM foods on food security, research and training in Kenya / 0 - Development ongoing - will achieved 4 by Dec 2018. / 2- 1 on Bt Cotton - https://aatfnews.aatf-africa.org/?p=993 / 1 on OFAB impact from Omolara Afolayan – OFAB 2018 Journalist of the Year 2018 / 1 - Delivering technologies to farmers through public-private partnerships. / 9 - (2 raw video footages done, (TELA MZ trials and n QBS participation at Farm-tech in Naivasha, Sept 2018; 7 OFAB Videos capturing impact posted on YouTube).

- AATF provided a list of requests as part of their annual reporting. The number of requests exceed the target, and shows that AATF continues to be considered a ‘go-to’ organisation. It is especially encouraging to see a substantial increase in the number of partnership requests. For example, AATF was requested by IDH in collaboration with Grow Africa, AfDB, and Rockefeller Foundation to partner in delivering a Cassava mechanisation project in Nigeria, and AFDB invited AATF to coordinate the TAAT Maize Compact. The latter came with additional funding. However, there were no requests for specific technologies over this reporting period.
- Traditional media mentions have increased slightly on the previous year, but not enough to meet the milestone target.
- Social media (Twitter and Facebook) followers have increased, but to a lesser extent than the previous year. Social media engagement continues to peak around key events. This is to be expected, but more work needs to be done to increase traffic outside of these events.
- AATF has developed a new Social Media Strategy. It provides analysis of social media engagements as well as followers, and details how they will adapt and focus their social media activity as a result of this analysis. It also provides detail on how AATF plans to increase social media engagement outside of key events, for example using monthly themes for activity.
- Overall, AATF did not meet targets for Indicator 2.3 on the number of proactive communication products on AATF experiences and successes. The number of video clips is down on the previous year. Progress on picture stories and impact stories continues to be slow, the explanation being that these are new activities for the organisation. More work is needed to speed up pipeline development and integrate it with other media activities, for example Facebook and Twitter.
- As a consequence of the new AATF Strategy, approved in May 2018, at the time of drafting this Review, AATF is in the process of implementing a new branding and communications strategy to update the public image of AATF.

Lessons identified this year, and recommendations for the year ahead linked to this output
AATF to implement plans and monitor the impact of increased social media interaction outside of key events, reporting specifically on this in the next report to DFID (October 2019).

Output Title	Regulatory environment and capacity for testing and commercialization of modern agricultural technologies in target countries improved
Output number per LF		3	Output Score	A
Impact weighting (%):		30	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of polices/legislation for testing and commercialization of modern technologies passed target countries	2	Met: 2 / Passage of Biosafety Bill in Uganda; Kenyans NPT guideline revised and published
3.2 Number of persons trained in risk assessment and/or regulatory compliance from partner institutions	75	Exceeded: 77
3.3 Number of permit authorizations for product testing obtained*	5	Exceeded: 15
3.4 Number of regulatory approvals for commercialization of products granted in target countries	3	Exceeded: 5 / TELA / 1 South Africa – Drought Tolerant varieties / 1 Kenya - Bt varieties / 1 Kenya - MLN resistant varieties / 1 South Africa - DT/Bt Varieties expected / 1 Kenya/Uganda- hybrid rice varieties

- AATF has continued to meet or exceed its targets under this output. This is a key area of AATF expertise and an important area of work as unfavourable regulatory environments pose a major risk to AATF. AATF’s work in this area is funded by BMGF under the OFAB project, and by the AfDB through the new TAAT Policy Enabler.
- The positive shift in regulatory environment continues, with approval of biosafety regulations and guidelines in key countries like Kenya and Uganda.

Lessons identified this year, and recommendations for the year ahead linked to this output
AATF reported that the risks relating to the regulatory environment have remained stable over the year, but with variations between countries. In Mozambique, Ethiopia, and Nigeria, the regulatory environment is quite positive, but AATF are facing challenges in Uganda, Kenya, and Tanzania, and the future success of projects in these countries is less certain. AATF has a presence on the ground in these countries, and is working to improve the regulatory environment and perceptions of new agricultural technologies.
With AATF’s involvement in the TAAT Policy Enabler it is expected that AATF’s work in this area will continue to perform well against targets.

Output Title 4	Appropriate agricultural technologies accessed and licensed for sustainable use by smallholder farmers in target countries
Output number per LF		4	Output Score	A
Impact weighting (%):		10	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of appropriate technologies negotiated and accessed	2	Not Met:1 / Pflp and Hrap License from Academia Sinica renewed for Banana and Potato
4.2 Number of trademarks /patents /PVP filed in project countries	2	Met: 2 / TELA and OFAB
4.3 Number of sub licenses negotiated and signed with partners	12	Exceeded: 39 / TELA & TAAT
4.4 Number of compliance returns filed in project countries	10	Almost met: 9 / Company Returns filed for AATF (Kenya and Nigeria), QBS (Kenya, Zambia, South Africa) Foreign Affairs Returns, Charity Commission Returns, KRA and USA

- AATF’s activities under this output are largely on track, with some discrepancies in achievement between the indicators. Demonstrating compliance with licensing agreements is important for maintaining the confidence of partners who have provided intellectual property.
- The number of sub-licenses negotiated and signed with partners was substantially exceeded in the reporting period. This is related to the initiation of new projects TELA and TAAT.

As with some of the indicators under Output 1, Indicator 4.3 has been substantially exceeded. AATF is recommended to review whether these indicators and targets continue to align with AATF’s workplans, for example with the newly approved projects. Logframe changes to be agreed between AATF and DFID by the end of March 2019.

Output Title	AATF is a well-managed, efficient, and effective organization with a diverse donor base.
Output number per LF		5	Output Score	A
Impact weighting (%):		10	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress
5.1 Board meetings are held twice a year with a high level of attendance.	3	Almost met: 2 / Two Board meetings held in November 2017, May 2018. Next meeting is planned for December 2018
5.2 Percentage of review/audit/evaluation recommendations implemented.	85%	Not met: / 77% fully and 23% partially
5.3 A diverse and robust funding pipeline is maintained / number of concept notes/proposals submitted / b) number of proposals funded / c) amount of funding raised / d) number of new donors	a) 12 / b) 3 / c) $5M / d) 2	Exceeded: / a) 25 / 7 / $33.8M / AfDB and USDA
5.4 Staff turnover rate below 10%	5%	As of November 2018 a total of 12 staff separated (23.5%) during 2018

- AATF’s Board continues to meet regularly and the three key investors - BMGF, DFID and USAID - are invited to observe. DFID attended in November 2017 and USAID in May 2018. Several new board members have been appointed who have skills and experience that are more closely aligned with AATF’s new strategy, digital technology and entrepreneurship.
- AATF has made a significant step forward in terms of expanding and diversifying its funding base. Not only have they submitted a significant number of concept notes or proposals, but they have also been successful in winning three TAAT projects bring the African Development Bank as a new investor. This is an important development in an area where progress has previously been slow.
- Additionally, they have received renewed funded from other current investors, BMGF and USAID.
- As well as making progress to diversify its funding base, AATF has made considerable steps towards becoming a more financially sustainable organisation that is less reliant on DFID funding. This year AATF has:
  - Initiated internal cost-saving measures, including reducing staff numbers;
  - Identified target donors to approach for additional funding;
  - Established a social enterprise, Agridrive, which will channel profits back into AATF.
  - Ensured all projects contribute to the organisations overheads.
This is part of a two-pronged approach to reduce costs and increase funding. Other measures are also being considered for the coming year.
- Staff turn-over was unusually high in the past year, with one staff member retiring and four leaving for opportunities elsewhere. Additionally, three posts were ended as part of cost saving measures and contracts for four staff were ended following disciplinary issues.
- AATF has set out annual plans for impact evaluations through its Impact Evaluation Strategy. The first will be OFAB, with impact evaluations planned for Agridrive and CAMAP, amongst others. This will provide valuable evidence to help track progress on programme outcomes and impact.

Lessons identified this year, and recommendations for the year ahead linked to this output
The progress made over the past year demonstrates that AATF is able to initiate institutional changes and is willing to adapt to changing circumstances. This goes some way to allaying the key concerns raised in the 2017 Annual Review. It will be important for AATF to continue to build on this momentum over the coming year.

AATF to continue to report on the performance on Agridrive, integrating reporting into the logframe (October 2019).

PERFORMANCE RELATED FUNDING ASSESSMENT
A key component of DFID funding to AATF in Phase III is the Performance Related Funding Component. This new component of funding is structured to incentivise more rapid progress by AATF as a whole in key areas of interest to DFID, including: achieving and assessing impact at scale, financial sustainability, and strengthening of the commercial product pipeline. Of the total funding of £2million/year, £500,000 is Performance Related Funding and is awarded following assessment of AATF’s performance against an agreed set of performance indicators, divided into two categories: Organisational Behaviours and Technical Areas. Performance Related Funding can be awarded in its entirety, partially, or not at all depending on performance. However, no specific sum is attached to each indicator as they are assessed as a whole. This objective has been clearly communicated to AATF management. Progress against each indicator is reported in the table.

Organisational Behaviours	Progress
Commercial/private sector focus: / Enhanced capacity of seed companies in the commercialisation pathway of AATF products; number of companies engaged, training and implementing the standard operating procedures.	ACHIEVED / Under the WEMA, TELA®, StrigAway, Seeds2B, Hybrid Rice, MLN, QBS and TAAT projects a total of 82 seed companies in 13 countries (5 countries in East Africa; 5 in Southern Africa and 3 in West Africa) were engaged. In addition, some companies where visited in the field to monitor the implementation and compliance with the general seed stewardship requirements.
Gender and inclusion: / Staff/Partner Training Modules on Gender Mainstreaming in place and being implemented. Institute gender analysis as a standard part of AATF’s problem analysis.	PARTIALLY ACHIEVED / A total of 36 (13 female and 23 male) AATF staff were trained on Gender Mainstreaming on the 25th to 27th September 2018. The training was intended to equip them with a deeper and practical understanding of gender concepts as well as enhance their skills in making programs and institutions more gender responsive. / Plans are underway to train partners on gender mainstreaming based on the revised gender strategy. / It is less clear from the documentation shared by AATF that gender analysis is fully integrated into their programmes.
Development of new AATF Strategy and Business Plan: / Strategy Implementation Plan and Business Plan Implementation being implemented and progress Report being shared.	ACHIEVED / The Corporate Strategy with its implementation plan for the first year was approved May 3rd, 2018 by the AATF. Progress on its implementation was reported at that Board Meeting as well as at the virtual Board meeting in July. Additionally, the AATF Business Plan 2018 – 2022 has been developed to outline how AATF will exploit emerging opportunities and harness its expertise in agribusiness to position agriculture in the global macro environment in SSA. / While some work is needed to refine the Business Plan that was presented to the investors, the organisation is starting to deliver on the new strategy. However, it will be crucial in the next year that this momentum is maintained if the strategy is to deliver a more dynamic organisation aligned with current trends in agricultural innovation in Africa.
Technical Areas	Progress
Impact evaluation: / AATF has commissioned at least one independent evaluation	PARTIALLY ACHIEVED / AATF has initiated an independent evaluation for the Open Forum for Agricultural Biotechnology (OFAB) project focusing on the OFAB’s desired outcomes and impacts in enhancing understanding and acceptance of agricultural biotechnology; building of an enabling environment for decision making; and generating lessons and trends with regards to biotechnology adoption. The Evaluation is projected to be completed by March 2019. / However, although a significant step forward, the TOR for the evaluation do not meet DFID’s requirements for an impact evaluation. / Additionally, AATF have drafted a new Impact Evaluation Framework which sets out plans for one independent impact assessment of a different project every year.
Reach/Scale of AATF products: / WEMA - 1250T (Kenya 625T, Mozambique 250T, South Africa 187,5T, Uganda 125T, Tanzania 62,5T: Distributed through 95% Seed Companies and Agrodealers and 5% AATF supported demonstrations); / STRIGA - 250T (Kenya 150T, Uganda 100T - Distribution Channel: 90% Seed Companies & Agrodealers, 10% NGOs, Goverments); / CAMAP - 4100 households (100 Nigeria, 500 Zambia, 400 Uganda: Delivery channel is through private service providers and AATF through full cost recovery).	ACHIEVED / a) WEMA - A total of 1,572 tons of TEGO hybrids seed were sold – 702t in Uganda; 688t in Kenya; 96t in Tanzania; 75t in Mozambique and 11t in South Africa. In addition, 16 tons of TELA (transgenic) seed were sold to smallholder farmers in South Africa. In total, 1,588 tons of certified seed were supplied to the farmers surpassing the targeted supply of 1,250 tons by 27%. The total seed supplied was sufficient to cultivate a total of 63,520ha, reaching about 158,800 households (157,200 households with TEGO hybrids and 1,600 households with TELA hybrids). / b) STRIGA - A total of 263 tons of IR seed was sold in 2018, which was 263 tons compared to 147 tons sold in 2017. In Uganda a total of 95 tons were sold and in Kenya 168 tons. The seed quantities achieved in Uganda and Kenya managed to surpass the target for 2018 of 250 tons by 5.2%. The total seed of 263 tons supplied was sufficient to cultivate about 164,38ha of land and reaching about 65,750 farm households. All the seeds were distributed 100% through Seed Companies and Agro-dealers. / c) CAMAP - A total of 4822 direct mechanisation and 6300 indirect (through partners) in Nigeria translating to 3,707 ha of land interpreted to 3,707 households assuming a farmer does an average of 3 operations and planting at least a hectare of land. In Uganda, a total of 558 mechanisation operations were done covering 176 households, and in Zambia, a total of 690 mechanisation operations covering 230 households were done. In total 4113 households benefited from CAMAP services
Fund Raising: / AATF has raised $5m from new investor(s).	ALMOST ACHIEVED (two new investors, $4.7m) / AATF secured a contribution from TAAT of a total of 4.5M USD for one year. Contracts are for a three-year period where the yearly disbursements are dependent on performance. In addition, after a 2-year period of discussions with AGRA on policy interventions, AATF secured a one-year pilot phase grant of 250k USD. Hence AATF has two new investors as of this period. In addition, the new TELA project of 24M USD from BMGF was granted, which eased some of the financial constraints at the beginning of the period. A total of 34M USD was secured for this period with 4.7M representing new donors.

Based on the analysis above, and discussions during the Annual Review meeting, DFID intends to award a Performance Related Payment of £400,000. AATF has made important steps this year, particularly in terms of organisational behaviours and fund raising, and this is commended. AATF is encouraged to continue building on this positive progress over the next reporting period.
1. AATF to share the OFAB impact evaluation report, along with the new evaluation framework.
2. Recommendation 5: DFID and AATF to agree performance indicators for Year 4 by the end of March 2019.
3. AATF to provide a clear plan of action with measurable indicators of progress on improving recruitment of women to improve the organisation’s gender balance (carried over from 2017 Annual Review), by March 2019.
## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)
Summarise the programme’s theory of change and any major changes in the past year (1/2 page)
The Theory of Change for AATF is that investment by DFID in both the project pipeline and institutional development will deliver the parallel outcomes of increased availability of technology and a financially sustainable organisation.
The Theory of Change is working in practice, and the assumptions outlined in the business case are largely holding. No modifications to the Theory of Change have been made in the past year, and none are required. However, some areas have progressed more slowly than others, and more evidence is needed that AATF has identified and transitioned to a sustainable business model that attracts more diverse funding sources. More evidence is also needed that the work of AATF is contributing to the expected impact of increased uptake of new technology in SSA. The impact evaluations planned for Agridrive and CAMAP should help generate this evidence.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)
Impact: increased productivity of smallholder farmers in SSA.
The programme is largely on track to contribute to the expected impact. However, targets and monitoring for smallholder farmers reached and hectares serviced are based on extrapolations from seed sales rather than from collection of field level data, and are therefore only estimates of adoption. More impact evaluations are needed to ensure that the work of AATF is contributing to the expected impact of increased productivity of smallholder farmers in SSA. It is hoped that the new Monitoring and Evaluation Framework and Impact Evaluation Strategy will lead to improvements in this area.

Outcome 1: Increased access/availability of appropriate agricultural technologies for smallholder farmers in target countries in SSA.
The programme is on track to contribute to Outcome 1. AATF continues to facilitate the development and deployment of a range of appropriate agricultural technologies, including both seeds and mechanisation technologies. AATF continues to be identified as a ‘go to’ organisation for partnerships and knowledge on appropriate agriculture technologies for smallholder farmers.

Outcome 2: a financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers in ensuring that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed.
Over the lifetime of the programme progress in achieving Outcome 2 has been slow. Over the reporting year, however, AATF has made promising steps towards becoming a financially sustainable organisation. Key developments are the establishment of the Agridrive social enterprise and the diversification of funding sources, for example through the TAAT work with the African Development Bank. A variety of new strategies have been proposed that focus on key institutional changes, for example the Corporate, Commercial, Gender, and Social Media Strategies, and the overall Business Strategy. However, the effectiveness and implications of these new strategies and business models in practice remain to be seen. AATF is at a crossroads, and needs to demonstrate its value through the achievement of impact at scale and diversification of its funding sources. The achievement of Outcome 2 depends on how the new Strategies are implemented over the coming year.

Explain major changes to the logframe in the past year (1/2 page)
The 2017 Annual Review recommended some changes to the logframe targets, which were addressed and agreed with DFID by February 2018. The target for Indicator 1.1 was increased from 10 new appropriate agricultural technologies scouted and 3 accessed, to 15 scouted and 4 accessed. This change was made to take into account continual over-achievement on this output.
AATF was also recommended to update Indicator 2.2 so that it tracks engagement with social media activity as well as number of social media followers. While the wording of the indicator was changed, the target still focuses on tracking followers. AATF explained that progress is ongoing to develop mechanisms for tracking social media interactions in a meaningful way. An external consultant has been engaged to provide expert guidance.

Describe any planned changes to the logframe as a result of this review (1/2 page)
Much has changed since the logframe was created at the start of the programme, and the Annual Review process provides an opportunity to reassess the outputs and indicators for the programme. This was discussed in the Annual Review Meeting, and AATF is subsequently recommended to propose alterations to the logframe to align more closely with its objectives and workplans.
Changes to the logframe are to be completed and agreed with DFID by the end of March 2019.

## D: VALUE FOR MONEY (1-2 pages)
Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
The key cost drivers for AATF are Personnel and Administration costs (including financial and audit), monitoring and evaluation, and accessing technical expertise.
AATF have maintained a consistent cost structure with a major proportion of the budgets being designated for project and programmatic work, with a lean budget for core functions (resource mobilisation, monitoring and evaluation, governance, administration). AATF also have robust systems in place to deliver VfM, both within the organisation and with their sub-grantees.

VfM performance compared to the original VfM proposition in the business case
Since the AATF Business Case was approved in 2015, Research and Evidence Division (RED) has articulated a ‘quality and value at each step’ approach to value for money which provides a more useful framework for ensuring VfM than the original metrics proposed. This framework recognises that assessing VfM for agriculture research investments is challenging, as the outcomes and impacts cannot be easily determined. While the evidence of positive rates of return from investment in agriculture research is clear, this is not sufficient for ensuring VfM at programme level. This is a common issue for all research programmes. VfM is delivered by:
- Picking the right problems – AATF have a robust process to identify constraints to smallholder agricultural productivity before identifying potential technological solutions to addressing the constraint.
- Working through strong partnerships – DFID has a strong partnership and working relationship with AATF, and they have good track record in meeting DFID management expectations. AATF has robust systems in place to manage their delivery chain to ensure VfM and reduce risk (see Risk section below)
- Always requiring good quality – AATF ensures that their product development is of high quality and conducts robust field trials of new technologies.
- Programme Management – AATF’s programme and financial management are strong and they have managed DFID resources effectively.

Assessment of whether the programme continues to represent value for money.
During the period of the report AATF reported many cases of how they have delivered VfM in the past year. The following are set out against the four E’s of the Value for Money Framework.
Economy:	AATF Introduced WebEx meetings reducing the number of costly face-to-face meetings. / Adoption of a synergistic approach to implementation of activities across projects, for example similar activities with same end goals were carried out together e.g. media trainings under WEMA, OFAB & PBR Cowpea. / Reducing staff per diems by 20%. / IT and cleaning services were outsourced and AATF have engaged Corporate Uber Services as an additional cost saving measures. / All AATF Projects steering committee members are on pro bono basis. AATF pays only the meeting costs (travel, visa, accommodation and per diem). The AATF office in Nigeria is provided free by Nigerian authorities. / Negotiated Accommodation rates /Use of Partner Rates where more cost effective
Efficiency	AATF use project management software and systems to reduce the complexity of project management and ensure the highest levels of project efficiency and effectiveness. These help to manage the flow of work through the entire project lifecycle. / Contracts are now paid in instalments to ensure payment is based on delivery of quality work. If the work is not satisfactory, the instalment is not paid. / AATF has continued to publish a number of articles in high impact journals and media outlets. AATF Staff have also had chapters in books published. / AATF selects best implementation partners based on their value proposition / contribution to the projects. Timelines and quality are central to the selection of partners and monitoring of the partner’s activities is done to ensure quality results.
Effectiveness:	AATF is partnering with policy actors like AU, FARA, FANRPAN, and ABNE to assist in creating a conducive regulatory environment for agricultural development in SSA. / AATF mode of operation is through Public Private Partnership (PPP) and involves a lot of consultations and advocacy with governments to position agriculture to be transformative. AATF works with the NARS and their representatives are members of project committees to assist in advising on how best to implement projects to get better outcomes. / CAMAP piloted full cost recovery in the provision of mechanisation services and after the positive progress in Nigeria, this approach is now being implemented in all CAMAP countries (Nigeria, Zambia and Uganda). / Results from market assessments, baseline and adoption studies, and impact assessments have been used to realign the project. Lessons from these assessments have also led to creating technology awareness creation campaigns to ensure that smallholder farmers are aware the new technologies that are available from AATF and partners. / AATF conducted a WEMA adoption study in Kenya to learn lessons during the first three years of selling WEMA seeds. Lessons from this study will be used to develop strategies for implementing WEMA in the other four countries. / From 2018, an independent evaluation will be carried out for AATF Projects. In 2018 the impact evaluation is scheduled for OFAB.
Equity:	AATF has a Gender Focal Person to enhance gender equity in participation and distribution of benefits to all (women, youths, men, and the underprivileged). This will be done through awareness workshops, trainings and demonstrations on the importance of gender inclusiveness in agriculture.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)
Tackling hunger and malnutrition (Sustainable Development Goal 2) is a key priority for the UK Government through helping to saves lives, preventing various illnesses, helping people escape from poverty and be more productive, and contributing to economic growth. The DFID Research Review highlights agriculture as a priority theme for spending and impact. DFID’s investment in AATF contributes to the continuation of large-scale research investment into sustainable agriculture, to improve nutrition and food security and increase resilience to climate change in developing countries. Agricultural research remains crucial to the DFID objective of accelerating economic growth, particularly in Africa, as reflected in the new Strategic Directions on sub-Saharan Africa and Harnessing Technology for Development. This is also reflected in DFID’s Economic Development Strategy and DFID strategy for private sector engagement on food systems and nutrition.
AATF is a well-managed organisation with a focus on results and delivery. It continues to deliver new agricultural innovations for smallholder farmers in SSA.
DFID support to AATF is through unrestricted Core Funding of £10m over 5 years (including up to £2.5m for performance related payments). AATF continues to meet the Output Indicators, and strives to ensure VfM in both the cost of running the programme and in building institutional capacity and developing and implementing projects. AATF are in the early stages of plans to move to a sustainable business model which has the potential to improve VfM from a commercial perspective.
Plans include:
- The spin-off social enterprise, Agridrive, which will channel a proportion of its revenue back into AATF. Agridrive was established in 2018, and aims to provide 15% AATF annual income by 2022;
- Securing of a 10% shareholding in Qualibasic Seed Company, which will provide approx. $300,000 per year additional source of income for AATF;
- Levying royalties on selected products to cover costs;
- Cost saving measures, including reducing staff on core funding and reduction of office rents;
- Sourcing additional funding from target donors.

AATF should have a clear plan in place for implementing the new approach to project overheads (by February 2019).

E: RISK (½ to 1 page)
Overview of programme risk (noting the rating from p.1) and mitigation
Overall risk rating: Moderate
Overview of programme risk
While there is one risk rated as major, on balance the overall risk remains as moderate. The risk trajectory over the next year is stable.
AATF have a robust approach to Risk Management and their Risk Management Committee reports to AATF Management and the Board. AATF have a detailed Strategic Risk Register which clearly sets out Risks and Mitigation steps being implemented by Management across a range of categories, including procurement, finance and project management. Of specific interest to DFID as a core investor in AATF is the strategic risks identified by AATF Management. A number of others relate to the regulatory environment and management of intellectual property. These risks are included in the DFID risk table below, as they are considered of particular relevance to the programme.
AATF have a zero-tolerance approach to any fraud or corruption. During the reporting period AATF demonstrated that the internal control systems they have in place were adequate to identify and prevent misuse of funds in Finance and Procurement. Internal procedures in the accounts unit identified potentially fraudulent expenses claims. Investigation of the claims found them to be inflated. The issue was dealt with swiftly in a professional and transparent way with staff contracts ended, in line with AATF procedures, and AATF identified additional improvements in policies to further strengthen internal controls.
A refresh of DFID’s Due Diligence Assessment, including Enhanced Safeguarding, was undertaken in October 2018 and is being finalised. A number of issues were identified and will be taken forward.
A particularly challenge is that AATF works with a diverse range of Downstream Partners, including large multi-nationals, local companies and government agencies. In order to give a clearer picture of the risks and challenges AATF have agreed to categorise the partners and based on these categories will consider making adjustments to policies accordingly. They have also conducted the UK Charity Commission for advice on this issue.

Risk category	Description of gross risk	Mitigation strategy	Residual risk rating / (minor/moderate/major/severe)	Risk Trajectory over next year
Context	Failure to adopt appropriate biosafety regulations in AATF target countries / A significant proportion of AATF’s technology portfolio includes traits introduced through genetic modification. If biosafety regulations and their implementation in AATF target countries prevent or ban the trialling and introduction of GM crop varieties AATF will not achieve its objectives. / As reported under Output 3, the positive changes in the regulatory environment have continued in the past year.	AATF is fully aware of this risk and continues to engage partners and countries in dialogue on biosafety through BMGF funding to the OFAB project.	Moderate	Stable
Context	Lack of/withdrawal of investor funding / The funding environment for AATF remains challenging, as reported under Output 5 and Performance Indicators. / The short-term risk to AATF is low, although increasing. This year, the medium to long-term risk to AATF has stabilised. / This continues to reinforce the need for AATF to change its business model, but also taking management time away from the transition process.	AATF Management and Board have started implementing a number of cost saving measures. / AATF’s discussions with new investors (Output 5) are a key part of the mitigation strategy.	Major	Stable
Delivery	There has been no change to risks in this category.		Minor	Stable
Safeguarding	There has been no change to risks in this category.		Minor	Stable
Operational	There has been no change to risks in this category.		Minor	Stable
Fiduciary	Poor financial management by downstream partners / This risk has not changed. However, as AATF works with 38 partners across 13 countries, issues with any of these partners could impact DFID’s reputation even if DFID funds are not directly involved. / Misappropriation of Funds by AATF Staff and Partners	AATF carries out regular audits of sub-grantees internal control systems at country level ensuring accountability of donor funding. AATF have provided a summary of audit findings to DFID. Findings are clearly set out, highlighting specific issues and follow on actions required. AATF follows up with partners to ensure actions are implemented. / AATF have robust policies in place to identify any potential misuse of funds and these have been successfully acted upon. These policies will be reviewed by both Internal and external auditors to identify any additions required.	Moderate	Stable
Reputational risk	Reputational Risk is linked to the Risks defined in other categories above		Moderate	Stable

Compliance with DFID commitments:
1. The programme complies with 2014 Gender Equality Act commitments.
2. The main supplier complies with the Equality Act 2010 according to its annual report.
3. The supplier complies with DFID branding. Branding guidance had been shared with the supplier and spot-checks confirmed that produced materials do use the DFID branding correctly.
4. Programme’s documents which fall into the 11 document types listed in the Transparency Smart guide are displayed on the Development Tracker.
5. Programme information is not published on the International Aid Transparency Initiative (IATI) website.

Outstanding actions from risk assessment
Enhanced Due Diligence assessment including Safeguarding to be finalised.
AATF have strengthened clauses in documentation issued to downstream partners to ensure full accountability for finance and management processes - although AATF will take action in 2019 to categorise their Downstream Partners they will need to ensure all fully adhere to policies in dealing with Fraud and Anti-corruption.

1. AATF to report to DFID on the categorising of downstream partners in terms of safeguarding, fraud, and anti-corruption procedures and how they will adapt their approach to limit risks, by June 2019.
2. AATF to take forward recommendations from the due diligence review (by May 2019).

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)
Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)
Funding remains at the same level as in the previous phase of funding (£1.5 million/year) under an Accountable Grant. In addition, a performance related component of up to £500,000/year is structured to incentivise more rapid progress in key areas: achieving and assessing impact at scale, financial sustainability, and strengthening of the product pipeline.

Quality of financial management
Invoices and Financial Reports are submitted quarterly to DFID outlining the expenditure incurred against the agreed budget from the previous quarter and the forecast for the next quarter. Full explanations are recorded for any significant differences between forecast and actual spend. Payments are now made quarterly in arrears.
AATF have submitted invoices against agreed forecasts during this period to maintain spend at agreed figures for each programme year. £1.5m was paid in Core Funding during Year 3, together with the performance related payment of £250,000 for 2017. AATF’s Organisational budget is planned in US Dollars. The Pound Sterling/Dollar exchange rate remained stable during the year and therefore had minimal impact on Budgets. AATF, however, did utilise their reserve funding where required, for example costs associated with the establishment of Agridrive for mechanisation operations.

Forecast	Year 1	Year 2	Year 3	Year 4	Year 5	Total
Core Funding	1,500,000	1,500,000	1,500,000	1,500,000	1,500,000	7,500,000
Performance Payment	500,000	500,000	500,000	500,000	500,000	2,500,000
Disbursement
Core Funding	1,500,000	1,500,000	1,500,000
Performance Payment	250,000	250,000	400,000
Total	1,750,000	1,750,000	1,750,000

Just over 50% of the Core funding budget has been used in the period Oct 2017 – Sep 2018, 70.2% of DFID funding was spent on core expenses and 29.8% on projects. Overall, DFID funded 9.7% of total expenses.
Overall, in the current DFID fiscal year, DFID-funded projects represent 3.2% of the total project expenses.
- CAMAP - DFID funded 41% of CAMAP costs ($205,556 out of a total of $507,274)
- Bacterial wilt resistant potato and sweet potato working with the International Potato Centre (CIP) using 100% of potato costs ($160,782). The total potato budget of $493,444 over 3 years is funded wholly by DFID). This project is however coming to an end, and DFID Funds will be used for preparing Concept notes for scoping out new Projects.
A full audit of AATF is carried out on a yearly basis by external auditors and the report provided to DFID.
AATF also carries out audits of sub-grantees’ control systems to ensure management and financial accountability and a summary report is provided to DFID. Generally, the controls in place are good; however, there were instances where financial controls could have been more robust. AATF follows up issues with the sub-grantees, and if necessary will withhold funds until satisfactorily resolved. In 2018 AATF provided managers with training on Fraud and Anti-Corruption. Project Managers were reminded of their financial management responsibilities, recommendations for improvement were agreed and will be implemented to ensure full accountability.
The AATF Management and the Board have approved the following cost reduction measures:
1. Retrenching staff on core funding: Following a job analysis four core positions were terminated in 2018 representing an estimated saving of about $212,000 per year.
2. Transfer of staff to projects: The funding from AfDB for TAAT has substantially contributed to alleviate AATF burden on staffing cost by about $525,000 per year.
3. Decreasing the within grade annual increment in 2018 and freezing it in 2019: This measure will help AATF to reduce the staffing cost in 2019 by about $108,000.
4. Computation of a new overhead rate to be applied fully to new projects.
5. Merit award not granted at the end of the year 2018 and 2019.
6. Reduction of rent: AATF is negotiating with the Government of Kenya to host its office pro-bono or to seek for government accommodation at cheaper rent cost. AATF is also exploring alternative lower cost office space elsewhere.
7. Salary survey: There has been a change of the interval of the salary survey usually conducted every 3 years to be every five years. The next one will be in 2021.
8. Exit from core funded projects: AATF will strictly only use current core money for strategic investment in resource mobilization. The Striga project has been discontinued in 2018 saving $250,000 per year from core funds. The Potato project will not receive any funds after 2018 and CAMAP, that is fully funded by core will also be discontinued from year 2020 as most activities will be handled by Agridrive.

Date of last narrative financial report(s)	November 2018
Date of last audited annual statement (s)

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)
Monitoring (1/2 page)
AATF continues to be a reliable and responsive delivery partner and have a good working relationship with DFID. They respond quickly to requests for information and provide reports on time.
Reports were received in November 2018 and the Annual Review was carried out by a Livelihoods Adviser, Natasha Watts, and Deputy Programme Manager, Anna Kelly. Duncan Barker (SRO) visited AATF as part of the annual review process. Amongst other supporting documents, AATF provided a Technical Progress Report, Social Media Strategy, Resource Mobilisation Update, and details of key achievements.
DFID works closely with the other core investors (USAID and BMGF) to ensure agreed objectives. Investors are represented at each Board Meeting (attending on a rotational basis) and provide feedback and regularly engage with each other over key issues.

Evidence (1/2 page)
The evidence of the need for support for the development and delivery of agriculture technologies appropriate for smallholder farmers in SSA has not changed from that set out in the Business Case for this programme.
While AATF mainly focuses on getting research into use rather than primary evidence generation, in this reporting period it has produced multiple book chapters and articles in academic journals, for example:
- Edge, M., Oikeh, S.O., Kyetere D., Mugo S., and Mashingaidze, K. (2018). Water Efficient Maize for Africa: A Public-Private Partnership in Technology Transfer to Smallholder Farmers in Sub-Saharan Africa. In: From Agriscience to Agribusiness: Theories, Policies and Practices in Technology Transfer and Commercialization. Nicholas Kalaitzandonakes; Elias G. Carayannis; Evangelos Grigoroudis; Stelios-Rozakis (Editors). Springer Publication, USA.
- Marechera,G.T., Muinga G. (2017) Value chain approaches to mechanization in cassava cultivation and harvesting in Africa. In Hershey, C. H. (ed.), Achieving sustainable cultivation of cassava Volume 1: Cultivation techniques, Burleigh Dodds Science Publishing, Cambridge, UK.
- Ertiro B.T., Beyene Y., Das B., Mugo S., Olsen M., Oikeh S., Juma C., Labuschage M., Prasanna B.M. (2017). Combining ability and testcross performance of drought tolerant maize 1 inbred lines under stress and non-stress environments in Kenya. Plant Breeding (in press: doi:10.1111/pbr.12464).
AATF has been less strong on conducting impact evaluations of its work. However, the new Impact Evaluation Strategy is a positive shift. There is an independent evaluation commissioned for the OFAB project to be completed by March 2019. One impact evaluation is planned each year, with Agridrive and CAMAP the next projects to be evaluated. This should generate evidence to help assess whether AATF is successfully contributing to the overall impact of the programme.

Learning (1/2 page)
AATF is actively engaged in academic and research networks and shares key lessons and findings (see above examples). The institution has demonstrated that they continue to be regarded as a ‘go-to’ organisation for agricultural technology transfer in SSA. This is reflected in the increase this year in the number of requests for partnerships, specialist expertise, and knowledge sharing.
AATF is making steps towards using social media platforms for sharing learning with wider audiences, as demonstrated in their new Social Media Strategy.
Lessons from the past year are:
Technical:
- Work on transgenics continues to be controversial and, despite regulatory progress in some countries, the context remains challenging. Negative public perceptions and restrictive policy contexts continue to pose delivery and reputational risks for this programme.
- With the shift in delivery mechanism of CAMAP to operating more commercially through the Agridrive social enterprise, the question of farmers’ willingness to pay for the Cassava mechanisation technologies has become crucial. Preliminary evidence suggests that farmers are willing to pay for at least a subset of mechanisation operations.
Institutional Transformation:
AATF has demonstrated that it is capable of kick-starting institutional transformation in a challenging environment, for example though the establishment of the new social enterprise and the new Strategies. However, the extent to which these lead to institutional transformation in practice, and can overcome resistance to change within the organisation, remains to be seen. It is likely that AATF will need to pursue a hybrid model, with a portion of their activities continuing to be funded by public donors and supplemented by the profits of the social enterprise.
Assumptions:
- The majority of assumptions made in the business case have been shown to hold. The 2017 Annual Review noted that there was weak evidence for two of the critical assumptions. This year evidence suggests that while progress is slow these assumptions may still hold.
  - The African Development Bank has come on board as a new investor, which is a step towards supporting the assumption that ‘new investors exist and are attracted by the impact of AATF technology on smallholders and AATF’s pipeline of new technology’.
  - AATF has made progress towards identifying and implementing a sustainable business model, although it remains to be seen how this will perform in practice.

Progress on recommendations from previous reviews (1/2 page)
AATF has made promising progress on some recommendations from last year’s reviews, notably in the launch of the social enterprise and in diversifying its funding sources. For others, activities are ongoing and impacts are yet to be seen.
#	Recommendation	Progress
1	AATF to update logframe targets for future years taking into account over-achievement in past year by February 2018.	Completed: Submitted to DFID in February 2018 following discussions between AATF and the DFID SRO. / Logframe targets for Indicator 1.1 still vastly exceeded despite being increased.
2	AATF to provide information on how they use social media data analysis to adapt or target future social media engagement.	Completed: AATF has developed a Social Media Strategy that sets out a plan to align social media use with business objectives. The strategy identifies different segments of the target audience and how to boost traffic, particularly outside of key events by using monthly themes. AATF also provided a Social Media Report that includes data analytics on social media usage. It remains to be seen how AATF will implement this strategy and the data analytics it produces to generate positive changes.
3	AATF to update Indicator 2.2 so that it doesn’t simply track followers, but also targets engagement with social media activity.	In progress: AATF did provide additional information regarding social media engagement through the new Social Media Strategy, and the wording of the indicator has been changed. However, the logframe target is still based on the number of followers. AATF are working towards developing methods for tracking interactions and engagements, and have involved an external contractor for expert advice.
4	AATF to continue to engage with DFID as the social enterprise venture plans develop.	Completed: AATF has reported on the development of the social enterprise. Agridrive Limited was incorporated and registered in Nigeria and Kenya in February 2018, and is now operational with mechanisation as its main business. A three-member Board was established in June 2018. For 2018 Agridrive’s target was 7500ha of mechanisation operations, By 10th October at least 4822ha (64%) of operations had been completed, meaning that Agridrive is on track to meet Year 1 targets. Agridrive is expected to break even by year 3, and is expected to pay dividends to AATF by 5th year of operating.
5	DFID and AATF to agree performance indicators for Year 3 by the end of January 2018	Completed: submitted in February 2018 and re-submitted in July 2018.
6	AATF to provide a clear plan of action with measurable indicators of progress on improving recruitment of women to improve the organisation’s gender balance.	In progress: Currently AATF has a total of 42 staff, of which 33% are female. Going forward, AATF will track the number of female applicants for each position advertised. A clause has been inserted into recruitment advertising to encourage women to apply, with benefits for women clearly outlined. / The indicators have not yet been developed as AATF first focused on gender awareness training to address gendered social norms amongst staff, and to develop a standard language surrounding gender issues. The training was completed in late September, and covered communication, gender awareness, intersectionality, and disaggregation of data. The indicators are in the workplan to be developed in the first quarter of next year.
7	AATF to strengthen clauses in documentation issued to downstream Partners to ensure full accountability for finance and management processes.	In progress: There has been an additional clause added to the current clause. For sub-grantees expected to receive funds over a long period, ‘any subsequent advance is conditioned to satisfactory management of fund and technical project activities. AATF reserves the right to take up the matter to the highest authority of the partner’s organisation’. AATF is working to categorise downstream partners for monitoring safeguarding procedures. They will develop an approach to share with DFID.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided