Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: African Agriculture Technology Foundation Phase 111 (2015-2020)
Programme Value: £10m		Review Date: 5 January 2017
Programme Code: 204988	Start Date: 5th October 2015	End Date: 30th September 2020

Summary of Programme Performance
Year	2016
Programme Score	A+
Risk Rating	Moderate

Summary of progress and lessons learnt
DFID support to the African Agricultural Technology Foundation (AATF) aims to deliver new agricultural innovation to small-holders in Africa through a financially sustainable organisation that is responsive to the needs of small-holder farmers in addressing market failures in the development and adoption of appropriate agricultural technologies. Although AATF has made good progress towards achieving its planned first year objectives in key areas, as listed below, progress towards institutional change has been too slow.

- Eight new technologies, including cassava cultivation equipment and maruca resistant cowpea cultivars have been accessed.
- AATF and the International Potato Centre have initiated a new project to develop potato varieties with resistance to bacterial wilt.
- Biosafety laws have been passed in Nigeria and amended in Ethiopia and 41 permits have been obtained for conduction field trials of AATF crop varieties.
- Twenty one sub-licences have been signed for commercialisation or research through partners.
- AATF has also achieved stringent USAID environmental regulatory compliance standards.
- A number of promising commercial partnerships have been fostered that also incorporate strong farmer outreach to ensure increased access and availability of AATF supported technologies to its customers.
- AATF has also developed a strong communication platform, promotional activities, educational materials and product branding and is looking to develop these further.
- 112,975 households are using maize varieties developed under the Water Efficient Maize for Africa project.

AATF is developing a new 2018-27 ten year strategy which will incorporate a detailed business plan designed to deepen AATF’s commercial linkages with private sector agribusiness partners. These relationships must generate the future inward private sector investment and revenues to drive AATF’s long term sustainability, shifting it from an institutional donor support paradigm to a longer-term commercially grounded operational model. This is a key area where DFID needs to see a much faster transition to a financially sustainable business model that is less reliant on donor funding.

Key Acronyms
AATF	African Agriculture Technology Foundation
BMGF	Bill and Melinda Gates Foundation
CAMAP	Cassava Mechanisation and Agro-processing Project
CFT	Confined Field Trials
IITA	International Institute of Tropical Agriculture
IR-Maize	Imazapyr herbicide resistant maize
NEWEST	Nitrogen-use Efficient, Water-use Efficient and Salt Tolerant Rice
NUE	Nitrogen Use Efficient
OFAB	Open Forum on Agricultural Biotechnology in Africa ():
PBR	Pod Borer Resistant
WEMA	Water Efficient Maize for Africa

Summary of recommendations for 2016/17
Recommendations are numbered in the order they appear in the main report.
Logframe recommendations
1.	The logframe must be reviewed and indicators revised by February 2017 to more succinctly capture and monitor progress towards achieving commercial outcomes and outputs by AATF. For example, households reached should be disaggregated by dissemination channel (AATF, government, NGO, private company). This will assist in demonstrating and underpinning the commercial viability of AATF supported technologies and also the potential to generate future revenue flows, e.g. royalties and commissions for future institutional sustainability.
3.	AATF should update the logframe targets for future years to reflect better than expected progress during the past year. Targets should be stretching. By February 2017.
5.	AATF to review Output 2 and indicators as the current indicators do not enable an assessment of whether AATF is a “go-to” organisation. This could be in the form of revised output wording, or an additional indicator (by February 2017)
6.	AATF to review and revise indicator 2.1 to provide a more accurate reflection of the range of the communication products delivered (by February 2017).
7.	AATF to clarify how they assess the “quality of media mentions” and how they track new media interactions, to ensure they are able to measure “new” engagement (by February 2017)
10.	DFID and AATF to agree performance indicators for Year 2 by the end of January 2017. Specific attention should be given to strengthening the Reach/Scale indicator by including sales/distribution figures, broken down by distribution channel.

Other recommendations
2.	By February 2017, AATF needs to more clearly demonstrate where the commercial market outlet/‘demand-pull’ is for increased cassava production with clear downstream linkages to aggregators, processors, financiers able to sustain a commercially viable value chains into the future.
4.	DFID to link AATF with other DFID funded Centrally Managed Programmes and implementing partners in East Africa, with the potential for positive commercial synergies with AATF programming and the new ten year AATF 2018-27 strategy and business plan. Specifically, this could include Trademark East Africa, M4D - Mobile for Development and the GSMA strategic partnership projects (by December 2016).
8.	AATF to consider how the successes achieved and lessons learned in research, certified seed production and dissemination of conventional and transgenic maize varieties can be translated to the other crop species with which AATF is now working in southern Africa (Tomatoes, Sorghum, Millet). This could be in the form of a “Lessons Learned” brief presented in the first quarter of 2017.
9.	Dependent on the commercial trials in South Africa, AATF needs to demonstrate how it will license and contract these varieties with commercial partners, that align with and support the new 10 year 2018-2027 Strategy and Business plan (by March 2017).
11.	AATF should up speed up the development of the new strategy and business plan to provide greater clarity on key areas, particularly their approach to commercialisation and institutional sustainability (completed by July 2017).
12.	AATF to update their Monitoring and Evaluation strategy to address the need for independent impact evaluations, with clearly articulated evaluation questions, to provide robust evidence on the impact of AATF technologies and more rigorous data on adoption of technologies (by May 2017).
12.	DFID to continue to work more closely with other investors, principally BMGF and USAID, through coordinated messaging to support AATF’s transition to a sustainable business model – ongoing.
13.	AATF to provide DFID with an updated Asset Register by March 2017.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204988/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204988/documents

The UK provides up to £10 million to the African Agricultural Technology Foundation (AATF) over the period 2015 – 2020 to support the organisation to tackle market failures in the development of appropriate agricultural technologies. Core funding will remain at the same level as in the previous phase of funding (£1.5 million/year). In addition, a performance related component of up to £500,000/year will be structured to incentivise more rapid progress in key areas: achieving and assessing impact at scale, financial sustainability and strengthening of the product pipeline. The performance related component will take on-board lessons from a similar mechanism developed for funding of international agriculture research centres.
This project builds on the UK’s previous support to AATF, an organisation with a proven track record of identifying, developing and deploying technology to increase the productivity of small-holder farmers in Sub-Saharan Africa. During the period 2010–2015, AATF consistently met or exceeded donor expectations. Among other notable achievements, AATF has delivered drought tolerant maize varieties to over 57,000 households and developed a pipeline of new products. UK support has been instrumental in AATF being able to attract significant new investment from other donor investors (BMGF and USAID) to take these agricultural products to scale.
Ongoing DFID core support will enable AATF to continue to expand both its existing programmes and also develop new technologies and enable the institution to maintain and diversify its investor base. This will prepare the ground for a transition from DFID core support as AATF adapts and embraces a more inclusive and sustainable business model.
The programme will support AATF activities in two areas support to organisational systems and support to specific projects.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Funding to AATF aims to deliver two outcomes. AATF is making good progress towards achieving the first of these: “AATF produced agricultural technologies are available and being used by smallholder farmers in target countries outcomes”.

AATF have reported against one outcome indicator, with achievements exceeding the target (table below) for the WEMA project. However, it should be noted that the figure is based on extrapolation from seed sales rather than field level data collection. AATF is aware that this is not a satisfactory solution and is working to improve data collection and its monitoring and evaluation system to deliver better data on the update of AATF technology. Data collection is also covered under Recommendation 11.

Indicator	Baseline	Planned 2015/16	Achieved 2015/16
Outcome Indicator 2 Number of households using agricultural technologies accessed or developed through AATF projects (WEMA Phase II ends 2017).	50,000	75,000	112,975

The second outcome is that AATF is “A financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers in ensuring that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed.” DFID has communicated this desired outcome clearly to AATF and the performance related component of funding aims to accelerate the transition. AATF have exceeded the majority of their targets at Output level, as reported below, demonstrating their capacity in their core areas of expertise – accessing and developing technology. However, the pace of change to becoming a more financially sustainable, commercially oriented organisation is slower than hoped for, and it is too early to assess whether this outcome will be achieved. This slow progress is reflected in the performance indicator assessment and the awarding of a performance related payment of only £250,000. The performance indicators are specifically designed to incentivise change within the organisation and are assessed in parallel to the Output indicators. While three of the six indicators have been fully achieved, the other three have not been achieved, or only partially achieved. Although AATF already charge overheads on projects to cover some central costs and are considering a number of business model options, DFID has specific concerns regarding impact assessment and the slow pace of development of the new AATF Strategy, which is not due to be finalised until November 2017.

Overall output score and description
A+: Outputs moderately exceeded expectations

The 2015 AATF institutional review described the substantial institutional credibility and the expanding number of products and customers developed by AATF. The current Phase III AATF logframe outputs are being substantively achieved, indicating the clear demand from private agribusiness, farmers and public institutions for AATF products and services. The challenge for AATF is to translate this success into sustainable product brands, grounded in a commercial rationale, accessed by fee paying customers and taken to scale. This will generate the long-term revenue flows needed for AATF to evolve into a commercial and sustainable institution, largely independent of donor support.

AATF has strong commitment to gender mainstreaming and over the past year has worked with African Women in Agricultural Research and Development (AWARD) to finalise AATF's gender mainstreaming strategy and implementation plan. AATF routinely report gender disaggregated data throughout their programmes. For example, under the WEMA project a total of 18,378 farmers have been reached through field days and training, 59.2% of which were women.

Has the logframe been updated since the last review? The logframe was finalised at the start of the reporting period.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	AATF has developed a strong product pipeline (Cowpea, Maize, Hybrid rice, Newest rice, Seeds2B)
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone	Progress
Number of new appropriate agricultural technologies: a) scouted : at least 10; b) accessed : at least 4.	a) 2 / b) 0	Milestone Exceeded: a) 8 b) 8 / CAMAP: 3 scouted and accessed (cassava cultivator, stem cutter and loader). / SEEDS2B: 5 maruca resistant cowpea cultivars scouted, accessed.
Number of project feasibility assessments conducted.	1	Milestone Met: 1 / Seeds2B project feasibility study finalised end 2015.
Number of new projects initiated.	1	Milestone Met: 1 / AATF/CIP collaboration in 3 year project. "Development and testing of transgenic potato with resistance to bacterial wilt, using pflp and hrap genes’’. Agreement signed, official launch pending.
Number of inbred line products deployed, 5 per year for WEMA - 2 (C. Inbred, T. inbred); 6 per year for Hybrid rice - 2 (male [p] lines) & female [s] lines.	11	Milestone Exceeded: 23 / WEMA: 9 new inbred lines from Monsanto and CIMMYT available for licensing in 2015. / Hybrid Rice: 14 parental lines produced.
Number of products developed / deployed. A) Seed: 5 hybrids per year for WEMA - 2 (C. Hybrid, T. hybrid), 5 hybrids per year for Hybrid rice, Seeds2B - 3 (4 varieties for Potato, 10 varieties for tomato, 4 varieties for sorghum, 2 varieties for soy bean, 2 varieties for pearl millet) B) Machinery: CAMAP - 6 (Planting - 1, Harvesting - 1, Processing - 4)	17	Milestone Exceeded: 53 / WEMA: 28 conventional released hybrids & 5 transgenic hybrids in 2016 (33 total). / SEEDS 2B: 5 (potato, tomato, soybean, pearl millet and sorghum) cultivars under evaluation. / HYBRID RICE: 15 hybrids produced and submitted for NPT in Kenya. / CAMAP: 3 - machinery acquired (not yet deployed).

Key Points

All milestones under this Output have been met or exceeded. Milestones for next year will be more ambitious to accelerate progress. Details for individual projects are provided below.

Cassava Mechanisation and Agro-Processing (CAMAP)
- This project is supported 100% by DFID and is working with eight private service providers and financial institutions in Nigeria, Zambia and Uganda to provide mechanisation services to targeted farmers. Nigeria has begun operations and Zambia will begin in November 2016. The Government in Uganda is yet to endorse a project agreement allowing CAMAP operations to proceed in early 2017.
- CAMAPs current cultivated area is 6,186 ha (5,876 ha in Nigeria and 310 ha in Zambia).
- The ‘full cost recovery’ model’ developed by CAMAP requires participating farmers to pay 50% of mechanisation costs in advance. By August 2016 the Nigerian revolving fund had a balance of approximately £60,000 and this is expected to double by December 2016. This sum includes brokerage fees paid by contracted service providers to AATF.
- Business modelling indicates the CAMAP mechanisation model is cost competitive. Commercial linkages have been made, for example with Allied Atlantic Distilleries in Nigeria. But quantitative, verifiable agronomic information, e.g. planting area, production yield, crop sales are required to evidence the sustainability of this approach.
- CAMAP has lodged a concept proposal with BMGF to further scale this approach in the future.

Additional AATF projects implemented through resources provided by other donors, i.e. USAID, USDA, BMGF, Monsanto, are indirectly supported from DFID via support to core functions. These are:

Water Efficient Maize for Africa (WEMA): an additional 28 hybrids are available for commercialisation, including two released for confined field trials in Mozambique. Some TEGO[1] hybrids have recorded yield benefits between 11-34% above the best available commercial checks. A total of 452 MT of certified seed have been sold or given as demos to farmers for cultivation in Apr–Sep 2016, extrapolated by AATF to reach 112,975 farm households and benefit 677,850 people. Five transgenic insect-pest protected hybrids, trademarked TELA™[2] are currently being licensed to six seed companies in the Republic of South Africa (RSA) for testing and demonstration in 2016-17. Maize is one of the most important and also politically sensitive staple food crops grown in Sub-Saharan Africa. Yet it is often grown at the extremes of its agronomic range, characterised by repetitive crop failure and resultant food insecurity. The current endorsement by legislators (cf Output 3) and wider uptake and use of WEMA drought and Imazapyr (IR) tolerant varieties by agribusiness and farmers should make this one of the key candidate crops upon which to build AATF’s future commercial vision within the upcoming 2018-2027 strategy and business plan.
[1] Brand name for WEMA varieties.
[2] Brand name for WEMA Bt varities.

Striga Control in Maize: AATF is now engaged with a total of seven seed companies (up from four in 2015) to produce, market and distribute certified IR-maize seed to smallholder farmers in Kenya, Tanzania, Uganda. IR-Maize seed available for sale by commercial partners in 2016 is 146.9 mt, sufficient to cultivate an area of 5,876 ha (valued at £236,000). Over 1,100 demonstrations were organised across three countries, 41% of these managed by women.

Hybrid Rice: A large number of hybrid lines are now available for commercial partners to develop. Research trials in Kenya, Tanzania have demonstrated yields of between 5-8 tonnes/ha for select varieties, setting the stage for commercial deployment. This is generating widespread publicity and media attention.

Nitrogen-use Efficient, Water-use Efficient and Salt Tolerant (NEWEST): Rice 18 new varieties have been made available by US based, Acadia Biosciences to three project countries (Nigeria, Uganda, Ghana) for Confined Field Trials. An early food safety evaluation for the Nitrogen Use Efficient (NUE) protein has been completed and published on the US Food and Drug Agency website.

Pod Borer Resistant (PBR) Cowpea Project: AATF conducted confined field trials in 2016 to test the efficacy of the Bt gene for Maruca pest resistance in Burkina Faso and Ghana. Trials results will be made available in the project review meeting in February 2017. A dossier for PBR Cowpea deregulation has been submitted to the Nigerian Biosafety Management Agency, a response is anticipated by February 2017.

Seed2B: AATF has agreed MoUs with germplasm providers and evaluated four crops: sorghum, pearl millet, tomato, potato in Malawi and Zimbabwe that best suit commercialisation profiles.

Banana Xanthomonas Wilt Project: AATF has begun activities under the license and service agreement with the International Institute of Tropical Agriculture (IITA). This requires conducting compliance audit visits to IITA operational facilities (laboratories, glass houses, growth chambers and CFTs) for three target crops, cassava, ensete and banana being transformed and evaluated.

Bio-pesticides: AATF works with the United States Department of Agriculture across five countries to engage regulators, policy makers, stakeholders to build consensus on registration of bio-pesticides, with special attention to Aflasafe. This includes procuring, sampling and testing equipment for aflatoxin in maize and groundnuts. AATF is engaging with the African Development Bank (AfDB) to support further dissemination of its technologies and has submitted a proposal to the BMGF for additional funding support.

AATF has a robust product pipeline of agricultural technologies and products. Future AATF project activities need to demonstrate clear linkages with the private sector, through legal licencing agreements that leads to increased production, distribution and sale of certified seed, benefitting a wide agriculture customer base that includes smallholders (both women and men).

By February 2017, AATF needs to more clearly demonstrate where the commercial market outlet/‘demand-pull’ is for increased cassava production with clear downstream linkages to aggregators, processors, financiers able to sustain a commercially viable value chains into the future.

AATF should update the logframe targets for future years to reflect better than expected progress during the past year. Targets should be stretching. By February 2017.

Output Title	AATF positioned as a credible and responsible Go-To organization for agricultural technology transfer in SSA
Output number per LF	2	Output Score	A
Risk:	Moderate	Impact weighting (%):	20
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of proactive communication products on AATF experiences and successes (e.g. expertise experiences, reports, picture stories, impact stories, videos, audio clips etc.)	Booklets: 1 / Picture story books: 2 / Impact Stories: 25	Milestone moderately exceeded / Booklet: 1 / Reports: 2, / Newsletters: 8, / Impact stories: 30,
Increase (quality and quantity) in number of mentions in both traditional and social media	a) Traditional Media, mentions: 500 - 618 / b) New Media Hits / No. Visitors: 1,500	Milestone Exceeded: / 618 CAMAP,15; Cowpea, 20; Hybrid Rice, 4; NEWEST Rice, 15; OFAB, 253; Striga, 30; WEMA, 204; Seed2B, 1; AATF Corporate 76. / Media Hits 48,471. Web Visits, 45,069; Twitter Followers, 535; Facebook likes; 2,867.
Number of invitations to participate/advice/share experiences and knowledge on agricultural technology transfer among key targets* (* regional bodies, policy/ decision makers, farmers, professionals (researchers, lawyers, students), media, private sector)	Requests / events annually: 100 - 113	Milestone Met: / WEMA, 33; OFAB, 30; Corporate, 16; Cowpea, 8; Striga, 6; NEWEST Rice, 5; Hybrid, 4; Seeds2B, 3.

Key Points
The DFID commissioned Institutional Review of AATF in 2014 highlighted that the organisation has established an excellent reputation with stakeholders and the wider. During the past year, AATF has continued to implement a range of activities to maintain this reputation and act as a ‘go-to’ organization both for downstream (farmer/smallholder) customers and upstream partners (research organisations, commercial agriculture sector, government). This is through the widespread dissemination of communications materials through both traditional and also modern media outlets (reports, newsletters, impact stories, booklets, Facebook, Twitter). However, while the progress against milestones is impressive, it does not automatically make AATF a “go-to” organisation.

AATF makes use of “off-the-shelf” analytical tools to enable them to analyse their social media presence. For example, they have over 1000 followers on Twitter distributed throughout the world, as show on the map to the right. Not surprisingly many followers are in the UK, USA and Kenya, but there are also followers in China, many European countries and Afghanistan.

During the year, AATF have also upgraded their analytical capacity to enable them to provide a more comprehensive picture of their social media interaction. They are also planning to update their online presence as part of their Brand Audit.

DFID to link AATF with other DFID funded Centrally Managed Programmes and implementing partners in East Africa, with the potential for positive commercial synergies that overlap ongoing AATF programming and the new ten year AATF 2018-27 strategy and business plan. Specifically, this could include Trademark East Africa, M4D - Mobile for Development and the GSMA strategic partnership projects (by December 2016).

AATF to review the output and indicators as the current indicators do not enable an assessment of whether AATF is a “go-to” organisation. This could be in the form of revised output wording, or an additional indicator (by February 2017)

AATF to review and revise indicator 2.1 to provide a more accurate reflection of the range of the communication products delivered (by February 2017).

AATF to clarify how they assess the “quality of media mentions” and how they track new media interactions, to ensure they are able to measure “new” engagement (by February 2017)

Output Title	Regulatory environment and capacity for testing and commercialization of modern agricultural technologies in target countries improved
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of polices/legislation for testing and commercialization of modern technologies passed in target countries	2	Milestone Met: 2 / Biosafety Law passed in Nigeria; / Biosafety Law amended in Ethiopia
Number of persons trained in risk assessment and/or regulatory compliance from partner institutions	30	Milestone Exceeded: 97 / 63 men and 34 women (Participants included seed sector regulators, seed companies, research scientists, NGO officers).
Number of permit authorizations for product testing obtained*	10	Milestone Partially Met: 9 / Confined Field Trials (CFT) permits for / WEMA: Tanzania, Kenya, Uganda, Mozambique. / Cowpea: Nigeria, Ghana, Burkina Faso. / Newest Rice: Uganda, Ghana
Number of regulatory approvals for commercialization of products granted in target countries	5	Milestone Exceeded: 33 / 28 WEMA conventional hybrids and 5 transgenic WEMA hybrids approved for Confined Field Trials release in project countries

Key Points
Ensuring a favourable regulatory environment for AATF technologies is a key part of project activities as unfavourable regulation poses a major risk to AATF (see risk section). During the past year AATF has successfully gained regulatory approval for Confined Field Trials (CFT) and commercialisation of their products, notably for the WEMA project. In Kenya and Uganda a valid permit authorisation to test drought tolerant maize was obtained and plans are underway to submit notifications to regulatory agencies for renewal of permits. In Mozambique the first ever transgenic CFT permit authorisation was granted by the National Biosafety Authority to allow for testing of transgenic drought tolerant maize. AATF is working with Monsanto to get a seed import permit from regulators, which is delaying the trial. Tanzania’s National Biosafety Committee granted the first ever permission to do a transgenic CFT in July 2016. Seed from Monsanto arrived in September 2016 and planting completed on 5 October. These CFT’s are also being used to introduce invited decision makers as guests to view the trials as part of a ‘seeing is believing’ strategy. Nigeria’s National Biosafety Management Agency (NBMA) made its first approvals for environmental release of Bt Cotton in April and Bt Maize for Confined Field Trials CFTs as a result of outreach to high-level policymakers, farmer group leaders, industry and regulatory authorities by AATF and OFAB.

AATF reporting in this period highlights the challenges in accessing the required internationally certified laboratory services in East Africa. These services are crucial to ensure compliance with regulatory approvals and other Sanitary and Phyto-Sanitary (SPS) standards (eg aflatoxin).

AATF to consider how the successes achieved and lessons learned in research, certified seed production and dissemination of conventional and transgenic maize varieties can be translated to the other crop species with which AATF is now working in southern Africa (Tomatoes, Sorghum, Millet). This could be in the form of a “Lessons Learned” brief presented in the first quarter of 2017.

Output Title	Appropriate agricultural technologies accessed and licensed for sustainable use by small holder farmers in target countries
Output number per LF		4	Output Score	A+
Risk:		Minor	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of appropriate technologies negotiated and accessed	2	Milestone Exceeded: 4 / New Crops: SEEDS 2B, 2 wheat, 9 groundnut, 6 soybean, 5 cowpea cultivars scouted and accessed
Number of trademarks /patents /PVP filed in project countries	2	Milestone Met: 2 / WEMA - One trademark filed for TELA (Bt Maize Brand Name) / OFAB - One trademark filed for OFAB in Nigeria, Uganda and Kenya.
Number of sub licenses negotiated and signed with partners	5	Milestone Exceeded: 21 / This includes both commercialization and research sub-licenses for all projects.
Number of compliance returns filed in project countries	2	Milestone Met: 2

Key Points

AATF have successfully negotiated and accessed new appropriate technologies, e.g. sub-licensing and conducting pre-evaluation commercial trials for sorghum, pearl millet, tomato and potato in Zimbabwe and Malawi. In addition, legal, regulatory and management compliance training has been completed in Nigeria, Ghana, Malawi and Burkina Faso.

WEMA TEGO hybrids have been successfully trademarked in South Africa for demonstration and testing and results from these trials will be reported in the first quarter 2017. This provides an opportunity for AATF to trial new approaches to licencing and contracting with commercial partners once trials are complete.

Dependent on the commercial trials in South Africa, AATF needs to demonstrate how it will license and contract these varieties with commercial partners, that align with and support the new 10 year 2018-2027 Strategy and Business plan (by March 2017).

Output Title	AATF is a well managed, efficient and effective organization with a diverse donor base.
Output number per LF		5	Output Score	A
Risk:		Minor	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Board meetings are held twice a year with a high level of attendance.	2	Milestone Met: 2 / Two board meetings held in April 2016 (Nairobi) and July 2016 (tele-conference).
Percentage of review/audit/evaluation recommendations implemented.	80%	Milestone Partially Met: 71% / The internal audit report shows AATF has fully implemented 5 of 7 recommendations (71%) and the remaining 2 are partially implemented, to be fully implemented by November 2016.
A diverse and robust funding pipeline is maintained / a) number of concept notes/proposals submitted / b) number of proposals funded / c) amount of funding raised / d) number of new donors	a) 12 / b) 0 / c) 0 / d) 0	Milestone Met / a) Submissions: 13 / Hybrid Rice, AfDB / TAAT; / CAMAP, AfDB / TAAT; / StrigAway, AfDB/TAAT; / Sahara Foundation Seed Company, BMGF; / ICT4D, IFAD; / CAMAP Nigeria, BMGF; / OFAB, BMGF; / Seed Systems Policy Advocacy, AGRA; / Seeds2B, SF/USAID/India; / Cassava Value Chain in Zambia, EU; / Marketing to Scale (M2S), USAID/FTF; / Drought TEGO, AfDB/TAAT; / MLN Control, CIMMYT/USAID.
Staff turnover rate below 10%	5%	Milestone Met: 4% / Two members of staff out of 53, as of September, 2016) exited AATF during the reporting period.

Key Points

AATF continues to be a stable and well managed organisation with sufficient resources to carry out its mandate. The organisation has a committed management team, as evidenced by the low staff turnover rate and the number of project concept notes/proposals submitted for funding.

PERFORMANCE RELATED FUNDING ASSESSMENT

A key component of DFID funding to AATF in Phase III is the Performance Related Funding Component. This new component of funding is structured to incentivise more rapid progress in key areas of interest to DFID, including: achieving and assessing impact at scale, financial sustainability and strengthening of the commercial product pipeline. This objective has been clearly communicated to AATF management. £500,000 of Performance Related Funding is available for each year of the programme and is awarded following assessment of performance against an agreed set of performance indicators, divided into two categories: Organisational Behaviours and Technical Areas. Performance Related Funding can be awarded in its entirety, or partially. However, no specific sum is attached to each indicator they are assessed as a whole. Progress against each indicator is reported in the table below.

Organizational Behaviours	Milestone and progress
Commercial/Private Sector Focus	The post of Director Commercial Operations is filled by a hi-calibre candidate: ACHIEVED. / Following a recruitment process, managed by SRI Executive Search, four strong candidates were interviewed and subsequently Donald Mavindidze joined AATF as Director Commercialization from 27th June 2016. He has an impressive CV and has worked for Monsanto in a number of roles for the past 18 years.
Gender and Inclusion	Gender strategy finalized. ACHIEVED. / AATF partnered with the African Women in Agricultural Research and Development (AWARD) team, for advisory and support services in finalizing the development of AATF's gender mainstreaming strategy and implementation plan. The AWARD team improved AATF’s initial draft and this new document has been finalized internally, and was approved by the Board in November 2016. / This demonstrates AATF’s commitment to ensuring gender equality. DFID will continue to engage with AATF on gender mainstreaming.
Development of new AATF Strategy and Business Plan	Having systems and policies in place for cost recovery and professional service delivery: ON TRACK, BUT NOT FULLY ACHIEVED. / Work on the new AATF Strategy and Business Plan is ongoing, and business models for cost recovery and professional service delivery are being implemented. AATF are considering a number of business model options both for individual projects (eg CAMAP) and the organisation as a whole, although thinking is more developed at project level. / The objective is to finalise the AATF 2018– 2027 Strategy by November 2017.
Technical Areas
Impact Evaluation	AATF has developed a robust evaluation strategy which includes an approach to collecting data on technology adoption: NOT ACHIEVED / While AATF has a M&E Strategy, approved by the Board in April 2015, it is weak in certain areas, particularly with respect to the commissioning of robust independent impact evaluations. Discussions with AATF during the year, and review of Terms of Reference, indicated that AATF is not yet in a position to meet DFID requirements with respect to delivering robust evidence of impact. / DFID has linked AATF with the CLEAR Initiative, a capacity building programme for institutions, supported by DFID’s Evaluation Department and the AATF M&E lead has attended a 2-week workshop to build evaluation capacity within AATF.
Reach/Scale of AATF products	Seed production WEMA - 500T ; STRIGA - 200T / Farmers reached CAMAP - 20000 Farmers: / PARTIALLY ACHIEVED. / AATF have met their seed production targets, below, and 3550 farmers have benefited from CAMAP activities. / Production (Mt) Sales (Mt) / Target Actual Target Actual / WEMA 500 1,261 451.9 / Striga 200 218 146.9 / This is a crucial indicator for DFID support to AATF and will be developed more fully in future years. The issue of scale is strongly related to that of impact evaluation as at present AATF is unable to provide robust figures on the adoption of their technology. Improvements to the indicator will take place alongside wider update to the AATF logframe to provide stronger indicators of commercial engagement. Specific areas to include are sales figures, disaggregation by country and gender.
Fund raising	2 additional concept notes/proposals developed and submitted: ACHIEVED / AATF have submitted a total of three concept notes/proposals to new investors in the past year.

Based on the assessment above, DFID intends to award a Performance Related Funding amount of £250,000.

DFID and AATF to agree performance indicators for Year 2 by the end of January 2017. Specific attention should be given to strengthening the Reach/Scale indicator by including sales/distribution figures, broken down by distribution channel.

AATF should up speed up the development of the new strategy and business plan to provide greater clarity on key areas, particularly their approach to commercialisation and institutional sustainability (finalised by July 2017).

AATF to update their Monitoring and Evaluation strategy to address the need for independent impact evaluations, with clearly articulated evaluation questions, to provide robust evidence on the impact of AATF technologies and more rigorous data on adoption of technologies (by May 2017).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers for AATF are Personnel and Administration costs (including financial and audit), monitoring and evaluation and accessing technical expertise.

AATF have maintained a consistent cost structure with a major proportion of the budgets being designated for project and programmatic work with a lean budget for core functions (resource mobilization, monitoring and evaluation, governance, administration). During the reporting period, core functions made up 8% of AATF’s total costs ($2.03m). AATF also have robust systems in place to deliver VfM, both within the organisation and with their sub grantees.

- They use a competitive tendering processes, both for procurement of goods and professional services.
- They are exploring mechanisms to increase cost recovery from its current low base. At present, they recover some development costs from seed companies licensed to produce seed of AATF varieties.
- AATF evaluate the net positive gain to society as part of the project design process. This is achieved by conducting feasibility studies and developing a business plan to outline the cost-benefit analysis as part of the initial preparation of a project.
- AATF have a web-based financial reporting system to facilitate entry and analysis of financial information across projects and countries of operation. With this system AATF managers can have an accurate picture of their budgets at any time thereby enhancing budget management.

AATF plan to move away from the use of MOU’s and demonstrate clear commercial linkages, potentially through legally binding/contracted licensing agreements. This will provide more direct control over project and programme costs.

VfM performance compared to the original VfM proposition in the business case
Since the AATF Business Case was approved in 2013, Research and Evidence Division (RED) has articulated a ‘quality and value at each step’ approach to value for money which provides a more useful framework for ensuring VfM than the original metrics proposed. This framework recognises that assessing Value for Money for agriculture research investments is challenging, as the outcomes and impacts cannot be determined. While the evidence of positive rates of return from investment in agriculture research is clear, this is not sufficient for ensuring value for money at programme level. This is a common issue for all research programmes. VfM is delivered by:-

- Picking the right problems – AATF have a robust process to identify constraints to small-holder agricultural productivity before identifying potential technological solutions to addressing the constraint.
- Working through strong partnerships – DFID has a strong partnership and working relationship with AATF and they have good track record in meeting DFID management expectations. AATF has robust systems in place to manage their delivery chain to ensure VfM and reduce risk (see Risk section below)
- Always requiring good quality – AATF ensures that their product development is of high quality, conducting robust field trials of new technologies.
- Programme Management – AATF’s programme and financial management are strong and they managed DFID resources effectively.

Specific examples of how AATF achieves VfM are provided below, against each of the 4 Es[3] in DFID’s VfM Framework.
[3] Economy, Efficiency, Effectiveness and Equity.

Efficiency: AATF undertook major enhancements of its Management Information and Accounting Systems over the past year. These include the AATF AMELIA M&E System and the SUNSystem Accounting System. Training/workshops accompanied these improvements. Budget processing has been made more efficient across both projects and departments, enhancing financial management and enabling a faster, more efficient generation of reports for internal and external reporting.

Efficiency: AATF continues to explore avenues to get technologies into farmers’ hands. They have developed strong partnerships with the private sector, where additional seed companies are supporting the production, marketing and sale of seeds across their seed-based projects. They are also aggregating farmers into clusters and cooperatives to ensure that they provide the technologies more efficiently. They have also developed other pathways of engaging farmers, such as use of service providers to provide mechanization services under the CAMAP project, inclusive financing where banks assist farmers to pay for mechanization services, and project Revolving Funds in each CAMAP country, where funds generated from cost recovery measures are deposited for use within the project to further AATF activities. These avenues have the potential to increase the VfM of AATF activities.

Effectiveness: Following AATF’s proof of concept work, funded by DFID, they are effective at obtaining substantially larger investment from other donors. DFID funding covers 4.3% of the overall projects’ budget and 9.2% of the overall budget.

Equity: AATF works with a diversity of partners across Africa (56 in 15 countries) and are proactive in mainstreaming gender, as evidenced by their new Gender Strategy. They are also devoting more effort to delivering impact at scale.

Assessment of whether the programme continues to represent value for money
DFID’s support to AATF is through unrestricted core funding of £10m (including up to £2.5m for performance related payments). AATF continues to use the funding following on from Phase II for building institutional capacity, developing and implementing projects, developing strong public/private partnerships and leveraging investment from other sources. AATF is currently developing a new 10 year strategy (2018-2027) to ensure the organisation achieves its mandate. Current available evidence indicates that the programme continues to represent value for money. AATF continues to meet the majority of indicators across all outputs and has embarked on the process of moving to a more sustainable business model. This has the potential to increase VfM from a DFID perspective, not only by protecting previous and existing investments but also bringing more commercial rigour to AATF management.

Quality of financial management
Invoices and Financial reports are submitted quarterly to DFID outlining the expenditure incurred against agreed budgets during the previous quarter and indicating the forecast for the upcoming quarter. These reports have been submitted on time, with the required narrative reports. Payments are made on the basis of 6 weeks in arrears and 6 weeks in advance – a process agreed from Phase II of the project.

AATF was scheduled to spend, and spent, £1,500,000 in the first year of the Project (15% of the agreed total budget of £10m). DFID funding covers 4.3% of the overall projects’ budget and 9.2% of the overall budget. This reflects the substantially larger investment by other donors following proof of concept work, supported by DFID. Additionally, AATF is aware of the fact that DFID wishes to transition out of core funding and has confirmed that DFID funds are not used to subsidise other donor funded projects.

AATF experienced a nine month funding gap between the final payment of Phase II of funding and this phase of funding. AATF handled this situation effectively, preparing a range of budget scenarios. One scenario was that they received no further funding from DFID, which was a possible outcome. 2015 therefore, saw a slow down in some activities to ensure AATF’s financial stability would not be negatively impacted, should DFID funding have not been confirmed.

This specific situation impacted the first year of funding as the renewal of DFID funding enabled activities that had been suspended or scaled back to move forward more quickly. Therefore, DFID committed the majority of funds in the 1st quarter of the reporting year. The CAMAP project moved ahead more quickly than planned during the year and AATF requested funding be pulled forward to support this.

The depreciation of the UK Pound has had an impact on the amount of DFID funding received by AATF as the organisational budget is prepared in US Dollars. At current exchange rates there is a potential shortfall of approximately 20% for 2017. AATF have advised that they will utilise revenue from their overhead charge to other projects to address any potential deficit. The situation will be kept under review and AATF have a number of new projects in the pipeline which, if funded, would address the funding shortfall.

Date of last narrative financial report	September 2016
Date of last audited annual statement	April 2016

## E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk
DFID considers funding to AATF to be moderate risk. The overall risk environment has not changed from that set out in the Business Case. AATF have a robust approach to risk management and have a Risk Management Committee that reports to AATF Management and the Board. The risk register which identifies the top strategic risks and mitigation steps being implemented by management is reviewed by the Audit Committee of the Board during Board Meetings which are held every six months. AATF have shared their risk register with DFID. The table below provides information against each risk category, with detail where there have been significant changes.

Risk Category	Rating	Comment
Context	Moderate	Key Risk: Failure to adopt appropriate biosafety regulations in AATF target countries / A significant proportion of AATF’s technology portfolio includes traits introduced through genetic modification. If biosafety regulations and their implementation in AATF target countries prevent or ban the trialling and introduction of GM crop varieties AATF will not achieve its objectives. AATF is fully aware of this risk and continues to engage partners and countries in dialogue on biosafety through BMGF funding, which was renewed during the past year. This risk has reduced with approvals for nine Confined Field Trials and adoption of appropriate biosafety regulations in 2 countries. Kenya also granted approval for environmental release of BT maize, which enables National Performance Trials to be conducted. While the risk remains, the threat to AATF’s portfolio has reduced in the past year.
Delivery	Minor	There has been no change to risks in this category. / DFID has a strong Partnership and good working relationship with AATF, and they have a good track record in meeting DFID Management expectations.
Operational	Minor	There has been no change to risks in this category.
Safeguarding	Minor	There has been no change to risks in this category.
Fiduciary	Moderate	Key Risk: Poor management of downstream partners by AATF / This risk has not changed, but discussions with AATF during the Annual Review process provided additional assurances regarding their processes. / Although DFID funds only flow to four partners in four countries, they work with a much wider group of 56 partners across 15 countries. Issues with any of these partners could impact DFID’s reputation even if funds are not directly involved. AATF is aware of this risk and, as identified during the Due Diligence assessment, has robust contracting and management process to address this risk including a clause in partner agreements obliging the partner to make its accounting books accessible to AATF whenever required. / AATF carries out regular audits of sub-grantees internal control systems at country level ensuring accountability of donor funding. AATF have provided a summary of audit findings to DFID. Findings are clearly set out, highlighting specific issues and follow on actions required. AATF follows up with partners to ensure actions are implemented. In some cases, additional training was provided by AATF to ensure the sub-grantees understood and followed processes, with an emphasis on full responsibility of the sub-grantee for donor funds. Where appropriate and necessary, AATF withholds funds from partners until issues are satisfactorily resolved. AATF demonstrate their clear understanding of reputational risk with their partners by quickly putting mitigating action in place
Reputational	Moderate	Reputational risk to DFID is partly linked to the Risks identified other categories above. And there has been no change.

Outstanding actions from risk assessment
There are no outstanding actions from the risk assessment. All recommendations made during the 2015 Due Diligence assessment of AATF have been addressed satisfactorily. The AATF Fraud and Anti Corruption policy was approved by the Board in November 2016.

## F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

DFID provides Core Funding to AATF with 25% of payment allocated on a performance basis. The programme is on track and has met or exceeded the majority of targets for the year. The CAMAP project has moved ahead more quickly than planned.

Performance of partnership(s)
- DFID’s relationship with AATF is good. They are a reliable delivery partner, respond promptly to requests for information and send in reports on time.
- DFID also works with AATF’s other main investors (BMGF and USAID) to ensure that investors are working towards the same or complimentary objectives. Investors are represented at each AATF Board Meeting and hold regular meetings to review engagement with AATF.
- DFID could engage more with AATF and other investors to support their transition to a sustainable business model.

DFID to continue to work more closely with other investors, principally BMGF and USAID, through coordinated messaging to support AATF’s transition to a sustainable business model– ongoing.

Asset monitoring and control
All assets acquired are recorded in an assets register managed by AATF. DFID has seen the latest assets register (31 December 2015)

AATF to provide DFID with an updated Asset Register by March 2017.

## G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable. The partnership principles are not used in monitoring this project as it does not provide funding through government systems.

## H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The 2014 Institutional Review of AATF supported the original justification for funding to AATF. AATF is fulfilling a role in the agricultural innovation landscape in Africa which other institutions/funding are not fulfilling by accessing and delivering agricultural innovation to small holders in Africa.

The Theory of Change is working in practice, although some assumptions are yet to be confirmed, specifically,

  1. New investors exist and are attracted by the impact of AATF technology on smallholders and AATF’s pipeline of new technology.
While AATF has invested considerable effort in identifying and engaging with investors, to date they have not been successful in winning new funding from new investors. However, there are a number of promising opportunities in the pipeline. They have also recently recruited a new Director to lead on investor engagement.

  1. A performance related funding component that is mutually agreed between DFID and AATF supports more rapid development of new technology and the transition to a financially sustainable organisation.
Although AATF have achieved the majority of their performance targets, it is too early to assess the impact of the performance related funding component.

Monitoring progress throughout the review period
DFID has been in regular contact with AATF through the reporting period. This has included two visits to Nairobi. The first in September 2015 was to work with AATF to develop their Theory of Change and finalise the logframe for the new phase of funding. Subsequently, in April 2016, DFID staff attended the AATF Board Meeting. This provided an opportunity to meet with AATF staff, visit a field site and assess the governance of AATF. The AATF Board of Trustees provides effective oversight of AATF and does not hesitate to challenge AATF staff to justify their work.

DFID also monitors progress through engagement with other key investors (BMGF and USAID) to keep abreast of progress on projects funded by them. This provides a useful cross-reference to AATF’s reports to DFID.

The DFID review team consisted of Vincent Langdon-Morris (Livelihoods Adviser), Anna Kelly (Deputy Programme Manager) and Duncan Barker (Livelihoods Adviser). An Annual Review discussion was held on 16th November with DFID and the AATF Management team. This was Vincent’s first engagement with AATF programme management so he has provided an independent assessment of their progress.

Review Documents:

Business Case: Quest Number:5021349
Logframe: Quest Number 5325129
AATF Reports: Quest Number 5607591
Terms of Reference: Quest number 5600548