## Page XX (hidden)
PROGRAMME NAME | DFID - Girls Education Challenge (GEC) | [5 empty] | Notes
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
Improve life chances of marginalised girls | Proportion of women married by age of 15 (Young people married by age of 15) (Maternal Health) | Planned |  |  |  |  | This section not to be completed by projects. These indicators are illustrative. Your project will be one activity that will contribute to this impact.
Achieved
Source
Demographic and Health Surveys (DHS) and the Multiple Indicator Cluster Surveys (MICS).
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Adolescent birth rate [Measures the annual number of births to women 15 to 19 years of age per 1,000 women in that age group] (MDG) (Maternal Health) | Planned
Achieved
Source
DHS and United Nations (UN)
| Impact Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Proportion of employed women living below $1 day (MDG) (Poverty reduction) | Planned
Achieved
Source
World Bank. NEED TO CHECK THIS DATA CAN BE SPLIT BY GENDER
| Impact Indicator 4 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Proportion of women in wage employment in non-agricultural sector (MDG) (Gender equality) | Planned
Achieved
Source
International labour Organisation (ILO)
| Impact Indicator 5 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Women in the intervention population in positions of influence over community, local and national decision-making processes (Empowerment) | Planned
Achieved
Source
GEC Longitudinal Survey
| Impact Indicator 6 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| * Number of marginalised girls supported by the GEC completing a full cycle of primary or lower secondary education (Learning) | Planned
Achieved
Source
GEC Fund Manager Monitoring Data and longitudinal evaluation
OUTCOME | Outcome Indicator 1 | Baseline (+ Year) | Milestone (+ Year) | Milestone (+ Year) | Target | Source | Notes
OUTCOME FOR GIRLS 1 million marginalised girls across 22 countries able to complete a full cycle of education and demonstrate learning | * Number of marginalized girls who have stayed in school through the life cycle of the project (RETENTION) | [5 empty] | This would use UIS survival by grade plus data on re-entrants and new enrolments.
| Outcome Indicator 2 | Baseline (+ Year) | Milestone (+ Year) | Milestone (+ Year) | Target | Source | Outcome Indicator 2
| * Number of marginalised girls supported by GEC with improved learning outcomes defined as number of impacted girls that demonstrate a greater mastery of formal and/or non-formal educational curriculum based on predefined benchmarks(LEARNING) | [5 empty] | Series of bespoke learning indicators to be developed for each project. these would cover: 1. types and levels of learning by ISCED level and measured by reference to either ASER (or ASER type) measurement (for primary) or national or regional testing (for secondary) 2. Change in ability for individuals - difference between intervention and control groups in the average change (for an individual) in their reading / numeracy ability over a 1-2 year period and also 3. Awareness (specific health information / life-skills) - difference in post-intervention levels between intervention and control group, adjusting for relevant group differences.[Ability and Attainment]. .
| Outcome Indicator 3 | Baseline (+ Year) | Milestone (+ Year) | Milestone (+ Year) | Target | Source | Outcome Indicator 3
| * Additional funds secured alongside DFID GEC funds to support the marginalised girls (LEVERAGE). | [5 empty] | Break this down into: a) Funds secured during the lifetime of GEC (monetary value of in-kind contributions plus any monetary contributions to the project) and b) Funds secured for the priod following the GECwhich will allow girls enrolling in GEC projects to complete a full cycle of education Each project will be expected to develop indicator(s) to measure other forms of leverage (Influencing policy makers, changing community and individual behaviour and attitude, improving a community, family, and/or girls’ economic position, uptake of intervention methods through demonstration of success).
| Outcome Indicator 4 | Baseline (+ Year) | Milestone (+ Year) | Milestone (+ Year) | Target | Source | Outcome Indicator 4
| Number of projects that have established mechanisms to enable marginalised girls to complete a full cycle of education.(LEVERAGE) |  |  |  |  | GEC Fund Manager M&E | Each project will be expected to develop indicator(s) to measure other forms of leverage (Influencing policy makers, changing community and individual behaviour and attitude, improving a community, family, and/or girls’ economic position, uptake of your intervention methods through demonstration of success)
INPUTS (£) | GEC (£) | Other (£) | Total (£) | GEC SHARE (%)
INPUTS (In kind) | In kind contributions

## Logframe
PROJECT NAME | DFID Rwanda GBV Prevention Programme | [6 empty] | Assumptions
IMPACT | Impact Indicator 1.1 |  | Baseline (Sept 2010) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
Women and children enjoy their human rights and live free of gender-based violence | Prevalence of physical and sexual violence against women = % of ever-married women aged 15-49 who (say they) have experienced physical or sexual violence (i) ever or (ii) in the last 12 months perpetrated by their (former) husband/partner (disaggregated by frequency, national and district level data) (a) (b) | Planned | (i) Ever = 56.4%; (ii) In last 12 months = 44.3% (often = 5.2%; sometimes = 39.1%) (2010) | Update baseline according to 2014/15 DHS (results due late 2015) | Not measured | Not measured | (i) Ever = 50% ; (ii) In last 12 months = 36%
Achieved
Source
Demographic and Health Survey (DHS 2010, then DHS 2014 and DHS 2017/2018)
| Impact Indicator 1.2 |  | Baseline (Sept 2010) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
| Women's decision-making power in the household = % of currently married women aged 15-49 who usually participate in all three of a list of three specified household decisions, for selected implementation districts (c) (b) | Planned | Bugesera = 46.6%; Burera = 28.1%; Kayonza = 44.7%; Musanze = 54.6%; Nyabihu = 53.6%; Rubavu = 57.7%; Rwamagana = 74.5% | Update baseline according to 2014/15 DHS (results due late 2015) | Not measured | Not measured | Bugesera = 61%; Burera = 43%; Kayonza = 59%; Musanze = 69%; Nyabihu = 68%; Rubavu = 72%; Rwamagana = 89%
Achieved
Source
Demographic and Health Survey (DHS 2010, then DHS 2014/15 and DHS 2017/2018)
OUTCOME | Outcome Indicator 1.1 |  | Baseline (Sept 2014) | Milestone 1 Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018) | Assumptions
Strengthened community-level mechanisms for the prevention of violence against women, girls and boys in Rwanda | Number, types and frequency of actions taken by community members to promote gender equality and challenge GBV among (i) Direct beneficiaries; (ii) Indirect beneficiaries of the programme (c) | Planned | TBC (evaluation baseline survey in late 2015) | TBC (evaluation baseline survey in late 2015) | TBC in early 2016 (evaluation baseline) | TBC in early 2016 (evaluation baseline) | TBC in early 2016 (evaluation baseline) | If more community members take specific actions to challenge and prevent violence, then perpetration of violence will decrease as individuals will either fear the social consequences of perpetration or not wish to perpetrate violence.
Achieved
Source
Baseline survey to be conducted in targeted districts in late 2015. Endline survey to be conducted in early 2018, CARE programme monitoring data for milestones and triangulation.
| Outcome Indicator 1.2 |  | Baseline (Sept 2010) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
| Acceptability of violence against women and children in target districts* compared to national average = % and trajectory of women and men who state that it is acceptable for (i) a husband to beat his wife in at least one specified circumstance (d); (ii) a parent to beat a child in at least one specified circumstance. (b) | Planned | (i) Bugesera W = 55.3% M =30.8%; Burera W = 78.1% M = 17.1%; Kayonza W = 69.4%; M = 25.0%; Musanze W = 73.4% M = 13.3%; Nyabihu W = 61.0% M = 43.1%; Rubavu W = 69.4%; M = 46.6%; Rwamagana W = 54.2% M = 30.3% (ii) TBC (following VAC survey due Nov 2015) | Update baseline according to 2014/15 DHS (results due late 2015) and VAC survey (due Nov 2015) | Not measured | Not measured | (i) Bugesera W = 40%; M = 20%; Burera W = 63% M = 13%; Kayonza W = 54% M = 18%; Musanze W = 58% M = 9% ; Nyabihu W = 46% M = 33%; Rubavu W = 54%; M = 31% Rwamagana W = 39% M = 20% (ii) TBC (following VAC survey due Nov 2015) | If there is decreased acceptability of violence in the population, then perpetration of violence will decrease as individuals will either fear the social consequences of perpetration or not wish to perpetrate violence.
Achieved
Source
Demographic and Health Survey (DHS 2010, then DHS 2014 and DHS 2017/2018) + baseline survey 2015 / endline survey 2018
| Outcome Indicator 1.3 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (May 2016) | Milestone 3 (May 2017) | Target (Sept 2018)
| Quality and sustainability of community-level GBV prevention mechanisms (e) | Planned | No mechanisms in place | Indashyikirwa programme model fully developed. | Couples undertaking the indashyikirwa couples' curriculum have completed 20 training sessions. Women's spaces have been established and sector-level activism with opinion leaders has started. | Community Activism training completed and Activism component underway, supported by ongoing activism with opinion leaders and the work of women's spaces | Community and sector activism components continue to implement effective initatives and strategy in place for their sustainability after the programme ends | A minimum level of support and incentives will be available to enable community activists and gender clubs to continue their work.
Achieved
Source
CARE programme monitoring data
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018) | Assumption
Best practice community-based GBV prevention package developed and implemented | Evidence-based package: Community GBV prevention package improved and agreed based on evidence, lesson learming and exchange between CSOs and the GOR. | Planned | Existing CARE package with VSLA peer educators, JOT couples and GBV case managers | New package developed on basis of learning across Rwandan civil society + GOR + SASA! Model + global evidence base. | Preparations for first lesson learning workshop underway to review GBV prevention package in light of operational research and programme monitoring data | Refined GBV prevention package is under implementation | Best practice GBV prevention package is scaled up in Rwanda | 1. Funding is in place for scale up of community-based prevention package 2. Government of Rwanda maintains high level commitment to GBV prevention
|  | Achieved |  | Milestone Achieved. A new intervention model has been designed, based on the best available evidence.
Source
CARE programme monitoring data
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
30% | Geographical coverage = Number of sectors in which community-based GBV prevention model is being evenly and consistently implemented. | Planned | 0 | Target number of sectors to be agreed during inception period | Couples training evenly and consistently delivered in 28 clusters across 14 sectors | Couples training transitions into ongoing community activism in 28 clusters across 14 sectors | Community activism ongoing in 28 clusters across 14 sectors
|  | Achieved |  | Milestone Achieved. Agreement on the overall number of sectors has been reached (n=15)
Source
CARE programme monitoring data
| Output Indicator 1.3 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (May 2016) | Milestone 3 (May 2017) | Target (Aug 2018)
| Population coverage = Number of (i) direct and (ii) indirect beneficiaries of the GBV prevention package (f) (g) | Planned | 0 | Trajectory to be agreed during inception period | Direct beneficiaries: 840 couples have been selected and have completed all 20 training sessions, 600 Opinion Leaders have been trained, 300 Women's Space Facilitators have been trained, 3,150 incidents of people engaging in Women's Spaces. (Give details of number of unique participants in Women's Spaces for beneficiary numbers) | Direct beneficiaries: 6 monthly catch up meetings for 1260 individuals trained but not activists, 420 community activists are operating in communities and supported in activism actions, 42,525 community members have been reached by community activists, 600 Opinion Leaders and Local Authorities continue to be engaged in supporting GBV prevention messaging at sector level (via training and meetings), 300 Women's Space Facilitators continue to be active in their work, 9,870 incidents of people engaging in Women/s Spaces(Give details of number of unique participants in Women's Spaces for beneficiary numbers) | Direct beneficiaries: 6 monthly catch up meetings for 1260 individuals trained but not activists, 420 community activists continue to operate in communities, 56,700 community members reached by community activists, 600 Opinion Leaders and Local Authorities continue to be engaged in supporting GBV prevention messaging at sector level (via training and meetings), 300 Women's space facilitators continue to be active in their work, a total of 22,890 women to date (in Y2, Y3 and Y4) participated in the Women's Space. (Give details of number of unique participants in Women's Spaces for beneficiary numbers) Indirect beneficiaries: 236,250 community members Indirect beneficiaries: 236,250 community members reached by Indashyikirwa Project
|  | Achieved |  | Milestone Achieved. Direct number of beneficiaries (n=82,455). Indirect beneficiaries (15 sectors, n= 236,250)
Source
CARE programme monitoring data
| Output Indicator 1.4 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
| GOR participation = GOR participation (at appropriate level within appropriate ministry) in development, refinement and scale up of GBV prevention package | Planned | GOR aware of work of CARE and Rwandan partners | Director of Family Promotion and Child Protection actively participates in the development of GBV prevention package, while PS MIGEPROF has oversight | PS MIGEPROF and her team participates in lesson learning workshop to develop refined GBV prevention package | PS MIGEPROF and her team supports scale up of refined GBV prevention package | Refined GBV prevention package is in process of scale up across Rwanda with the collaboration of PS MIGEPROF and her team
|  | Achieved |  | Milestone Achieved. Director of Family Promotion and Child Protection and the PS MIGEPROF are explicitly supportive of the programme
|  | Source | [5 empty] | RISK RATING
|  | CARE programme monitoring data | [5 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| £1,400,000 (40% of Indashyikirwa spend) | [5 empty] | 100%
INPUTS (HR) | FTEs
SDA DESA and Deputy Programme Manager
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018) | Assumption
Community members have the knowledge, skills, motivation and support to promote gender equality and challenge GBV | Number of Indashyikirwa curriculum-trained couples with positive attitudes towards gender equality and against GBV (h) | Planned | 0 | Trajectory to be agreed at the end of inception phase | TBC in early 2016 (evaluation baseline) | TBC in early 2016 (evaluation baseline) | TBC in early 2016 (evaluation baseline) | If individuals have the knowledge skills, motivation and support, then they take action to promote gender equality and challenge GBV in their own relationships and through influencing others in their community.
|  | Achieved |  | Milestone off-track. Baseline data will provide source for agreeing trajectory this is due Dec 2015
Source
What Works evaluation baseline (2015) and endline (2018) data
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (May 2016) | Milestone 3 (May 2017) | Target (Aug 2018)
40% | No, types and frequency of interventions taken by Community Activists to promote gender equality and challenge GBV | Planned | 0 | Trajectory to be agreed at the end of inception phase, including typical types of interventions | 420 community activists identified. | Community activists are trained and activism starts in August 2016 with 8,400 activism actions taken in year 3 by 420 activists (2 activism actions/activist/month). Each community activist is engaging in a variety of types of activism action e.g. dramas, dialogue sessions | 10,080 activism actions taken in year 4 by 420 activists (2 activism actions/activist/month). Each community activist Activism actions uncluding a variety of types of activism e.g. dramas, dialogue sessions.
|  | Achieved |  | Milestone delivered. Number of activists agreed (n=420). Types defined, 2 actions per activist per month.
Source
CARE programme monitoring data
| Output Indicator 2.3 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (May 2016) | Milestone 3 (May 2017) | Target (Aug 2018)
| Proportion of local authorities at sector level who include indicators related to GBV prevention and response in their performance contacts (imihigo) | Planned | 0 | Baseline and trajectory to be set at the end of inception phase | Review of Imihigo performance contract to inform advocacy action and determine target for proportion of sectors underway. Sector engagement strategy is devised and aligned by CARE and project partners with existing programme plans for introducing the implementation at local levels and with the annual cycle of imihigo planning. Women's Space Facilitators Engage in advocacy action in response to issues raised in sector-level opinion leader quarterly meeting | Advocacy strategy with targets based on review of imigiho performance contract agreed. GBV activity related reports from imihigo performance contracts reviewed against the plan to see whether they were implemented. Women's Space Facilitators Engage in advocacy action in response to issues raised in sector-level opinion leader quarterly meetings. | Proportion TBC (in Year 2) of sectors that imihigo performance contracts that include GBV prevention and response related indicators. Women's Space Facilitators Engage in advocacy action in response to issues raised in sector-level opinion leader quarterly meetings.
|  | Achieved |  | Milestone off-track. Baseline and trajectory due December 2015
Source
CARE programme monitoring data
| Output Indicator 2.4 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
| Number of community members reporting hearing messages promoting gender equality or challenging GBV: (i) From community leaders; (ii) Via the radio or print media | Planned | 0 | Baseline and trajectory to be set at the end of inception phase | TBC in early 2016 (evaluation baseline) | TBC in early 2016 (evaluation baseline) | TBC in early 2016 (evaluation baseline)
|  | Achieved |  | Milestone on-track. Information to be derived from the Research Protocol due for consideration at the MINEDUC ethics committee meeting in August 2015.
|  | Source | [5 empty] | RISK RATING
|  | What Works evaluation baseline (2015) and endline (2018) data | [5 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| £1,400,000 (40% of Indashyikirwa spend) | [5 empty] | 100%
INPUTS (HR) | FTEs
SDA DESA and Deputy Programme Manager
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (June 2016) | Milestone 3 (June 2017) | Target (Aug 2018) | Assumptions
Partnerships and systems to prevent VAW and VAC at community level strengthened. | Development and roll-out of national community-based child protection system | Planned | Design of community-based child protection system model agreed | Curriculum for Child Protection Workers developed based on international good practice and adapted to Rwandan context | Child Protection Workers operational at community level in 5 districts. 4,608 child protection workers receive initial training based on agreed curriculum. | Child Protection Workers operational at community level in 12 additional districts (17 total). 12,360 additional child protection workers (16,968 total to date) receive initial training based on agreed curriculum. | Child Protection Workers operational at community level in 13 additional districts (all 30 districts total). 12,706 additional child protection workers (29,674 total to date) receive initial training based on agreed curriculum. | Funding is available to continue to sustain the child protection system and the work of the GOR and civil sociert organisations.
|  | Achieved |  | Milestone on track. Curriculum under development. Procurement by UNICEF delayed, but training roll out due late August/September 2015.
|  | Source | Source
UNICEF programme monitoring data; consultations with NCC and MIGEPROF
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
15% | MIGEPROF coordination of implementation of national GBV-prevention programme | Planned | MIGEPROF aware of proposed GBV-prevention programme | Programme Advisory Committee set and up running effectively, with relevant membership agreed and engaged. | Two PAC meetings per year which are effectively documented with any recommendations arising considered and responded to (frequency reduced at end of inception phase). | Two PAC meetings per year which are effectively documented with any recommendations arising considered and responded to. | Two PAC meetings per year which are effectively documented with any recommendations arising considered and responded to.
|  | Achieved |  | Milestone delivered. PAC established and meeting according to quarterly timetable (minutes produced and shared with partners)
|  | Source | Source
|  | Source | Source
Consultations with MIGEPROF; DFID meeting records; GOR reporting on GBV policy implementation.
| Output Indicator 3.3 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
| Quality of information sharing and lesson learning between CSOs and with GOR on violence against women and children | Planned | CSO GBV network set up in 2013, but not meeting regularly; occasional engagement between CSOs working on GBV and child protection and MIGEPROF and GMO | Initial lesson learning workshop of CSO GBV network to discuss community-level GBV prevention approaches; Initial meeting between CSO GBV network and GOR to share information and lessons on community-level GBV prevention approaches | CSO GBV network meeting quarterly to share lessons and evidence; CSO GBV network and GOR representatives agree mechanisms for regular sharing of lessons and evidence. | CSO GBV network meeting quarterly to share lessons and evidence and produce agreed action points; Regular sharing of information between GOR and CSO via agreed mechanisms | CSO GBV network meeting quarterly to share lessons and evidence and produce agreed action points; Regular sharing of information between GOR and CSO via agreed mechanisms
|  | Achieved |  | Milestone not delivered. CARE has brokered agreement that Profemme Twese Hamwe (a Rwanda national women’s organisation) will lead this work. Lesson learning workshop not yet planned for.
|  | Source | Source
CARE programme monitoring data; UNICEF monitoring data; consultations with CSO GBV network and MIGEPROF and GMO
CARE partner capacity assessments; programme monitoring framework;CSO annual workplans; CSO partner reports
| Output Indicator 3.4 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
| Quality of programme delivery by Rwandan CSO partners (RWN and RWAMREC) | Planned | Some staff experience of programme delivery from previous ISARO programme | Due diligence checks on CARE international conducted by DFID; RWN and RWAMREC staff recruited and trained to implement agreed GBV prevention package; Programme monitoring and data collection systems developed. Annual workplan for 2015/16 in place. | RWN and RWAMREC implement programme tracking system and produce and quarterly reports; Annual workplan for 2016/17 in place. | Improved quality of RWN and RWAMREC programme tracking and quarterly reports; Annual workplan for 2017/18 in place. | Final CSO partner capacity assessment by CARE shows progress in RWN and RWAMREC staff knowledge and skills and improvements in programme monitoring and perfomance assessment systems.
|  | Achieved |  | Milestone on track. Due diligence and due diligence spot checks completed (Quest no. 5063887). All partners completed staff recruitment. Initial training of trainers sessions held in June. Remaining training (pre-testing) planned to be completed before end Sept. M+E systems development on track, due for finalisation before Sept 2015 - following submission of research protocols. 2015/2016 Annual Workplan drafted - to be finalised with partners by due date (Sept).
|  | Source | Source
|  | Source | Source |  |  |  |  | RISK RATING
|  | CARE partner capacity assessments; programme monitoring framework;CSO annual workplans; CSO partner reports | [5 empty] | MEDIUM
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE %
| £800,000 (10% of Indashyikirwa spend+100% UNICEF spend) | [5 empty] | 100%
INPUTS (HR) | FTEs
SDA DESA and Deputy Programme Manager
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018) | Assumptions
Improved evidence base on ‘what works’ to prevent GBV in Rwanda | Independent impact evaluation for DFIDR GBV programme delivers high quality research findings | Planned | DFID submits full concept note for a DFID VAWG 'What Works' evaluation (decision expected by January 2015) | Evaluation fully designed, agreed with implementing partners and DFIDR, and has ethical approval. | Baseline study complete, operations research underway and value of baseline indicators generated for this logframe | Operations research feeding regular findings and recommendations to implementing partners and DFIDR | Endline Study complete. Final impact evaluation report produced. | There is take up of this evidence and it is used to inform policies and programming on GBV in Rwanda.
|  | Achieved |  | Milestone on track. Evaluation component designed and agreed. Due for submission to ethics committee early August.
|  | Source | Source
RIF reports and documentation
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline (Sept 2014) | Milestone 1 (Sept 2015) | Milestone 2 (Aug 2016) | Milestone 3 (Aug 2017) | Target (Aug 2018)
15% | Evidence from impact evaluation is disseminated to relevant policy, programme and academic stakeholders in Rwanda | Planned | Only one substantive study undertaken on programming (Promundo / CARE 'Mind the Gap' study 2012) | National-level evaluation communications strategy developed and agreed | Research paper based on formative research published and disseminated to policy, programme and academic stakeholders | Key findings from baseline study and operations research disseminated to policy, programme and academic stakeholders | Full impact evaluation findings published. Policy working paper disseminated with clear recommendations on future GBV prevention programming in Rwanda
|  | Achieved |  | Milestone on track – partners to develop and agree a strategy by September 2015.
|  | Source | Source
|  | Source | Source |  |  |  |  | RISK RATING
|  | RIF reports and documentation | [5 empty] | LOW
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE %
10% of Indashyikirwa spend
INPUTS (HR) | FTEs
SDA DESA and Deputy Programme Manager
* Target districts = Kayonza, Bugesera, Rwamagana (Eastern Province); Rubavu, Nyabihu (Western Province), Burera and Musanze (Northeren Province)
(a) Of currently-married women age 15-49 who report experience of physical violence since age 15, 95.4% identified their current husband/partner as the perpetrator
(b) Overall score will be determined through measuring individual district progress and discussing the overall trajectory
(c) Three specified decisions in the DHS (i) = Woman's own health care; (ii) = Major household purchase; (iii) = Vists to family or relatives
(d) Specified circumstances in DHS = (i) Burns the food; (ii) Argues with him; (iii) Goes out without telling him; (iv) Neglects the children; (v) Refuses to have sexual intercourse with him
(e) Criteria to be reported on to assess quality and sustainability: (i) Proportion of JoT+ training cohorts completing full 20week training period (ii) Proportion of JoT+ training cohorts going to on become Community Activists (iii) Frequency of initiatives taken by Community Activists;
(iv) Views of members of Gender Clubs JoT+ couples and Community Activists on the impact of their work; (v) Programme montoring reports on impacts of their work; (vi) Views of indirect beneficiaries on the impact of their work (in endline survey 2018);
(vii) Level of engagement with other community GBV structures (e.g. anti-GBV committees; parents' evenings)
(f) For example, in the CARE Indashyikirwa project, direct beneficiaries are couples undergoing the Journey of Transformation Plus (JOT+) programme, Community Activists and Women's Space Facilitators and opinion leaders
(g) Indirect participants are reached through different channels - VSLA members, VSLA and JOT+ family members and the wider community at village cluster and sector levels
(h)Attitudes to be assessed: (i) Express support for flexible gender and social roles; (iii) Make a commitment to non-violence; (iii) Demonstrate knowledge of non-violent strategies to manage tensions in relationships