Annual Review

Title: DFID Rwanda Programme Evidence Facility (PEF)
Programme Value £ (full life): £1,632,203		Review Date: 18/06/2018
Programme Code: 204793	Start Date: June 2014	End Date: March 2019

Summary of Programme Performance
Year	2014-15	2015-16	2016-17	2017-18
Programme Score	A	A	A+	A+
Risk Rating	M	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-204793/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-204793/

A. Summary and Overview

Description of programme

The DFID Rwanda programme remains focused on helping the Government of Rwanda (GoR) to achieve its development objectives, as outlined in the second Economic Development and Poverty Reduction Strategy (EDPRS II) and GoR’s recently designed seven-year development programme, the “National Strategy for Transformation” – NST (2017-24). The NST’s main aspiration is to work towards Rwanda becoming an inclusive and upper mid-income country through three key pillars: economic transformation, social transformation and transformative governance. The policy shift as articulated in the NST involves efforts to drive significant changes in Rwanda’s growth model alongside a step change in the financing instruments for the strategy. Progressive shifts in policy choices from both EDPRSI to EDPRSII and EDPRSII to NST create a large need for evidence and analytical work to inform policy dialogue between GoR and its Development Partners (DPs), as well as support the design and implementation of relevant bilateral programmes in support of GoR’s growth and poverty reduction agenda.

In order to support this needed policy shift, DFID Rwanda needs to be able to address knowledge gaps in a timely manner with pieces of analysis that are of wider relevance to the GoR and its DPs. Although DFID has been supporting Rwanda’s National Institute of Statistics (NISR) to increase its capacity, there is limited capacity to analyse the data produced or to undertake primary research across public institutions. Therefore, there is a need to address knowledge gaps, both in terms of carrying out secondary analysis of existing data as well as collection of primary data where a need is identified, and which would not otherwise occur through organisations such as NISR. It is therefore necessary to have a flexible and demand driven facility through which commissioning of analytical and data gathering work can occur in a timely manner whilst minimising transaction costs so as to maximise value.

DFID Rwanda’s Programme Evidence Facility is a GBP 1.6 million programme that was initially designed for the period from August 2014 to March 2017 to fund evidence products to meet the needs described above. A cost extension to March 2019 was approved last year bringing the total project amount to £1,632,203. The key objective of the programme is to provide greater opportunities for more evidence gathering and use within sufficient time to engage strategically with GoR and key stakeholders, including DPs, private sector and civil society.

PEF is an internally managed facility for which outputs are delivered through short term consultancy contracts where payment is made only upon the delivery of the agreed output. Interactions with government and other relevant stakeholders are carried out through existing policy dialogue platforms such as sector working groups (SWG), or the Development Partners’ Coordination Group (DPCG). As the facility helps DFID to be responsive to stakeholders’ request for pieces of work to fill knowledge gaps, interactions can also be between DFID and the relevant government agency/ministry. In both cases, the funding decision is carefully assessed by the PEF management committee based on a number of criteria related to the pertinence and relevance of the proposed study.

A component of PEF to support the Ministry of Finance and Economic Planning (MINECOFIN)’s Effective Development Cooperation for Results project was approved in June 2016. It takes the form of a UNDP/DFID Contribution Agreement for up to £550,000 by June 2018[1].Under the contribution agreement, PEF supports MINECOFIN’s action plan to improve evidence analysis, capacity and systems for better resource mobilisation and aid effectiveness in Rwanda. Relevance of studies and evidence products to be conducted is assessed and approved by the Steering Committee made of Government of Rwanda and DPs supporting the project (UNDP, DFID and Switzerland).
[1] Extension to March 2019 has been recently agreed

Programme funding mechanisms and respective roles of DFID Rwanda’s PEF internal management committee and the Steering Committee for the Effective Development Cooperation for Results Project have been designed to ensure that PEF is aligned with GoR’s relevant needs, thus supporting effective delivery of the EDPRS-2 and the NST.

Summary supporting narrative for the overall score in this review

The programme has performed well against its two outputs. In total, during the year under review, twelve studies/evidence products were completed and nine of them discussed in appropriate policy dialogue forums such as Sector Working Groups, Steering Committee Meetings and DFID bilateral meetings with relevant government agencies. Out of the total evidence products completed in the period under review, six were directly commissioned by DFID and six others by UNDP under the contribution agreement with DFID.

Although this performance is well above the target milestones of 5 PEF products completed (output 1) and 5 products discussed in relevant policy forums (output 2), it is worth noting that two of the reported six studies completed (directly commissioned by DFID) were commissioned last year but completed in the year under review. Furthermore, the relatively small size of the evidence pieces commissioned by DFID (and the use of a fee repository/database to bring down consultancy rates), and delays in the implementation of studies managed by government institutions and UNDP have resulted in a lower programme budget execution (underspend) compared to the initial spending plan.

The output indicators are unsophisticated (measuring simply the number of products produced and disseminated), but the studies and evidence products delivered by PEF are rich and varied. Products from consultancies undertaken have been reported by both DFID sector lead advisers and stakeholders (including GoR, DPs and private sector) to be significantly useful in terms of improving their knowledge base and potential to influence policy work and project execution. For example:
- Evidence gathered on the constraints to private sector development in Rwanda, and consultations made with relevant private sector forums have been instrumental in shaping the new Private Sector Development and Youth Employment Strategy (PSDYE 2017/18-2021/22).
- The review of Rwanda’s privatisation law and strategy has suggested policy recommendations and procedures to improve the process and maximise returns from the privatisation of state own enterprises.
- The Meetings, Incentives, Conferences and Events (MICE) study has suggested specific policy actions to strengthen economic linkages between the agriculture and the hospitality sector, policy actions that relevant public institutions have started implementing through different policies and strategies including the Made in Rwanda Strategy and campaign.
- Findings from the ongoing Needs Assessment for Economic Diplomacy program for Rwanda are expected to inform design of a trade diplomacy strategy and a detailed implementation plan based on international best practice.
- Findings from the ongoing consolidated record on Land Tenure Reform in Rwanda will be an important showcase of a unique success story and a lesson sharing approach across Africa/and the world on the process through which Rwanda has successfully implemented a national land reform, experience that could be replicated elsewhere.
- Evidence gathering on the status of disability in Rwanda has delivered useful documentation to inform Rwanda’s inputs to the global Disability Summit, including (i) a summit report on the Rwanda Disability Summit that builds on existing evidence of Rwanda’s progress in advancing the rights of Persons with Disabilities (PWD), and highlights knowledge and implementation gaps, and areas of future commitment for GoR, Civil Society organisations (CSOs), Disabled Persons Organisations (DPOs) and DPs; and (ii) an evidence-based Communiqué of Recommendations from the Rwanda’s summit that informs GoR’s commitments and engagement at Global Disability Summit (GDS18).
- The latest Effective Development Cooperation for Results Project evaluation suggested that despite delays in the UNDP-GoR procurement processes (and subsequent budget underspends), studies completed have been useful in informing GoR’s policy design and implementation. Examples include a capacity needs assessment for CSOs that resulted into a well-informed strategy in support of CSOs in Rwanda, and the ongoing review of Rwanda’s aid policy and manual that intends to re-shape the mechanism for financing the NST beyond traditional Official Development Assistance (ODA).

Based on the above, the project has been scored an A+ for the 2017/18 financial year.

Recommendations for the year ahead

The SRO should continue to engage regularly with external stakeholders including GoR and DPs in order to identify and commission research that produces evidence relevant to Rwanda’s development path.

Internal use of the programme beyond DFID’s Economic Growth Team (EGT) should be strengthened through a monthly re-advertisement of the facility across teams by the SRO.

A new programme with potential broader scope should be considered and developed. The SRO could work towards the approval of a new business case by February 2019.

The SRO and programme manager should monitor the remaining budget and carefully manage the risks of underspend given the current unspent resources and implementation pace. A quarterly review of the programme spends and identification of actions required should be considered.

## B: DETAILED OUTPUT SCORING

Output Title	Evidence Products
Output number per LF		1	Output Score	A+
Impact weighting (%):		70	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of activities completed such as evaluations, data gathering exercises to fill knowledge gaps, analysis of existing datasets, and studies that provide policy options and/or recommendations to support economic growth and poverty reduction	5	12 (Details are in the tables 1 and 2 below)

Output 1 moderately exceeded expectation. Twelve studies/evidence products were completed (listed in tables 1 and 2 below) against a milestone of five. This strong performance was achieved at a lower rate of spend than expected due to a number of factors including the nature of the pieces of work (short research and analytical works with relatively low unit costs), and delays in the implementation of approved work plans (particularly activities managed by government institutions and UNDP).

The commissioned studies cover a wide range of areas and the current status is summarised in the tables below.

 Table 1: Status of DFID studies commissioned in 2017/18
	Budget	Status
Total commitment on studies 2017/18
Consolidated Record on Land Tenure Reform in Rwanda	58,850	On going
Enhancing the local content of Meetings, Incentives, Conferences and exhibition (MICE) in Rwanda	94,999	Completed
Review of Rwanda’s Privatisation Law and strategy	64,380	Completed
Evidence gathering for the new Private Sector Development and Youth Employment Strategy- (2017/18-2021/22)	19,250	Completed
Knowledge sharing and evidence gathering on peace building in Rwanda through organisation of an international impact event – Impact Conference	10,895	Completed
UK Horticulture connect conference	21,577	Completed
Needs Assessment for Economic Diplomacy program for Rwanda	15,968	On going
Evidence gathering on status of disability in Rwanda to inform Rwanda’s inputs to global Disability Summit	35,000	Completed
Total	320,919

Table 2: status of studies commissioned by UNDP under the DFID/UNDP contribution agreement (2017/18

Studies/workshops	Status
Development Partners Retreat in 2018	Completed
Capacity Needs assessment for Civil Society Organisations (CSO) covering the full scope of their work ( study and validation workshop)	Completed
Technical support to pre-selected Private Sector Federation (PSF) Golden Circle members to develop sound business plans ( the activity included engaging specialized technical support from a consultancy firm to produce a sound business plan for the Rwanda International Trade Exhibition)	Completed
Production of Development Performance Assessment Framework (DPAF) and External Development Finance Reports	Completed
Development Assistance Data assessment (DAD)	Completed
Organize annual Network of Planners event between central government & local government planners to strengthen planning functions for effective delivery of EDPRS 2 and in support of EDPRS 3 and the Sustainable Development Goal (SDGs)	Completed
Effective Development Cooperation for results project evaluation	On going
Review of Aid Policy and Manual of Procedures	On going

Lessons identified this year, and recommendations for the year ahead linked to this output

Increase the frequency of events (DFID policy meetings and brown bag lunches) to strengthen knowledge sharing and dissemination of the evidence built and ensure full uptake of the facility.

Output Title	Dissemination activities
Output number per LF		2	Output Score	A+
Impact weighting (%):		30	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of presentations made on Programme Evidence Facility Products (e.g. at office wide policy meetings, SWGs, DPCG)	5	9

Briefly describe the output and provide supporting narrative for the score

Output 2 - Moderately exceeded expectation. Nine evidence products were discussed in relevant forums, informing policy and programme discussions with GoR and its DPs. Evidence products and their respective contribution to policy and programming in Rwanda are briefly described below:

1. Evidence gathering on constraints to private sector development in Rwanda has informed the design of the new Private Sector Development and Youth Employment Strategy (PSDY 2017/18-2021/22).
2. The International Aegis Trust Impact Event has created a platform for critical, interdisciplinary exchanges on peacebuilding in Rwanda. The conference provided Rwandan scholars with the opportunity to present research papers and policy briefs on Rwandan peace building efforts to international actors such as academics, Northern policy-maker (donors) and civil society actors. The three-day conference was a great showcase of the work of Rwandan researchers produced over the last two years with DFID funding through Aegis Trust’s Research, Policy and Higher Education (RPHE) programme. The attendance to the conference by Rwandan scholars funded through PEF has potential to improve research on peace building and publication through international journals.
3. The study on enhancing the local content of Meetings, Incentives, Conferences and Exhibitions (MICE) in Rwanda has identified lessons learnt from actions to implement Rwanda’s strategy on MICE and has suggested measures and policy actions to strengthen economic linkages between the agriculture and the hospitality sector. As reported by government institutions, particularly Rwanda Development Board, policy actions as suggested by the MICE study are among the key inputs to the implementation of the Made in Rwanda Strategy and campaign.

1. The Review of Rwanda’s Privatisation Law and Strategy will improve the process of, and maximise proceedings from, the privatisation of state own enterprises.
2. Connect Horticulture conference aimed at sharing knowledge on local supply as well as access to market constraints and opportunities. As a result of the conference, Rwandan horticultural exporters were connected with UK’s leading investors in the sector.
3. Evidence gathered on the status of disability in Rwanda has informed the communiqué of recommendations from the Rwanda summit that will inform GoR’s commitments and engagement at the Global Disability Summit (GDS18).
4. UNDP Effective Development Cooperation for Results: the support to MINECOFIN through the contribution agreement with UNDP is reported by GoR, UNDP and confirmed by the latest project evaluation report to be useful in informing GoR’s policy design and implementation. Most of the studies commissioned by UNDP have been discussed in relevant policies and programme forums (SWGs and Steering Committees).

Lessons identified this year, and recommendations for the year ahead linked to this output

- Keep the momentum and engage further with teams and externals stakeholders for more evidence gathering products.
- Fully explore all opportunities to disseminate the knowledge and evidence generated.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The starting point of the PEF’s theory of change is that GoR’s development plans (EDPRS II and NST) have set ambitious goals across sectors, yet in many instances there is a lack of evidence to support the development of a roadmap with detailed interventions to support their realisation. This in turn has an impact on the design and execution of GoR and DPs projects and policies. The purpose of this facility is to help address the evidence gaps. It has the potential to influence design of evidence-based interventions, thus improving the implementation of GoR’s policies and DPs’ projects in support of EDPRII and NST. However, for the evidence products to effectively influence policy and programming a number of conditions have to be met, including: clear plans on how the output of any commissioned work will be used, outputs delivered at the appropriate point in the project cycle so that there is scope to be acted upon, and strong appetite by stakeholders to be receptive to new evidence and act in a way that improves effectiveness since the outputs by themselves will not deliver change. Therefore, learning-by-doing and willingness to adapt/respond to evidence are paramount. There have been no changes to the Theory of Change during the last year.

The PEF’s outcome target of three evidence products used to inform policy and programme discussions with GoR and DPs has been significantly exceeded. 9 evidence products have been used in appropriate policy dialogue forums including Sector Working Groups, Steering Committee Meetings and DFID bilateral meetings with relevant government agencies. Further, the decision on commissioning any of these studies (both directly by DFID and indirectly through the UNDP managed contribution agreement) is made on the basis of a thorough assessment of its relevance and contribution to generating evidence for policy dialogue and programming[2].. These arrangements ensure that all research products/studies commissioned respond to evidence needs to support the implementation of the EDPRS-II and have informed the design of the NST. As a result, studies selected, have strong alignment to the outcome objective of enhanced evidence base to inform policies and programmes of the Government of Rwanda and Development partners. Since the completed studies/ evidence products have been actively discussed in appropriate fora involving Government of Rwanda and Development Partners, there is a strong case to conclude that the programme will achieve its outcome objectives of enhanced evidence base to inform policies and programmes at the programme closure in 2018.
[2] Studies directly commissioned by DFID are selected and approved by the PEF management committee while studies managed under UNDP contribution agreement are selected and approved by the Steering Committee which includes Ministry Finance, UNDP, DFID and Swiss.

The fact that studies/evidence products funded through PEF appear to be short term products with lower unit cost does not comprise chances of achieving the initial programme outcome and impact. As highlighted above and reported by different stakeholders, PEF’s products have contributed to filling the knowledge gap and influencing policy work and project execution through generation of the needed evidence. The extent of the influence of a given study/evidence product (despite its size) on policy and programming has mostly depended on a thorough assessment of relevance of the proposed study/evidence product before it is commissioned and its timing, and discussions of findings at the appropriate forum.

Overall output score and description - “A+”

Output 1 moderately exceeded expectation. Twelve against a target of five studies/evaluations to fill knowledge gaps were completed while three others are underway. But this strong performance could not be reflected in the spending plan due to lower unit costs of the short-term studies/evidence products commissioned and important delays in the implementation of activities managed by GoR and UNDP.

Output 2 moderately exceeded expectation. Nine of out twelve completed studies/evidence products have been discussed in different forums to inform policy and programming including Sector Working Groups, and Steering Committee meeting in which GoR officials and Development Partners are involved.

Key lessons

- DFID sector advisors particularly from the Economic Growth team have been proactive in identifying new opportunities to use the facility to fund new evidence pieces that are of short term nature but with strong impacts into policies and programmes to support economic growth and poverty reduction.
- The proactive approach and flexibility to use the programme funds to commission alternative options for knowledge products has helped to reduce the possibility of keeping funds locked in on slow spending budgets such as the contribution to Support for “Effective Cooperation for Results”, under DFID-UNDP contribution arrangement
- However, the implementation of the contribution agreement with UNDP has experienced delays in disbursements. Measures to increase the implementation pace are now in place including regular meetings of the technical steering committee to push the work plan ahead and avoid the unnecessary administrative delays.
- DFID advisers have recognised the usefulness of PEF, particularly its flexible nature that allows the office to address knowledge gaps in a timely manner with pieces of analysis that are of relevance to respective DFID programmes and wider pertinence to the Government of Rwanda’s development agenda. Government institutions strongly recognise the value of PEF in their respective works, appreciating how the pieces of studies/evidence products are filling knowledge gaps and helping them to test and improve different assumptions in various policy documents and strategies.

Key recommendations

Engagement with external stakeholders (including GoR and DPs) in the implementation of the DFID/UNDP Contribution agreement in support of MINECPOFIN’s Effective Development Cooperation for results should be strengthened and enhanced; ensuring that agreed work plan is delivered at pace within the agreed timeline.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Experience from the PEF implementation so far suggests that the programme outcome of an enhanced evidence base to inform policies and programmes of Government of Rwanda and Development Partners is being progressively achieved. Evidence products have been used in different policy dialogue platforms and stakeholders’ meetings to inform discussions on policy and programming.

Explain major changes to the log-frame in the past year

The log-frame has been revised to reflect changes in timeframe and budget following the last cost-extension to accommodate increasing requests for evidence gathering exercises, especially in the 2017/18 financial year.

Describe any planned changes to the log frame as a result of this review (1/2 page)

None

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

Key cost drivers and performance
Key cost drivers for outputs delivered by consultants are daily consultancy rates and the number of days required to deliver a piece of commissioned work.

VfM performance assessment (using 4Es) compared to the original VfM proposition in the business case

The indicators proposed at the time of business case development were:
- Daily rates of any externally hired consultants. For all consultancies from July 2017 to July 2018, DFID procurement procedures were used under an existing DFID framework contract to attract a highly skilled team to deliver high quality work. In so doing, we ensure daily rates for the consultants are in line with the framework and deliver value for money. To drive costs down, we ensure that negotiations on fee rates are well conducted.
- A repository capturing the number of days required to deliver a piece of commissioned work alongside daily rates has been established in order to enable benchmarking of fee rates/days for comparable kinds of work. The same process of negotiations on fee rates is followed by UNDP’s procurement unit for studies undertaken under the contribution agreement to support the Ministry of Finance. These practices support assessment of Economy.
- In order to ensure that consultancies deliver best possible products that effectively fill the identified knowledge gaps, constructive strategic discussions on the exact need to be filled are held in the PEF management committee meetings, and Terms of Reference are carefully reviewed. For studies procured by UNDP under the contribution agreement, policy relevance of the studies and knowledge gap to be filled are assessed by the Steering Committee comprised of representatives from MINECOFIN, UNDP, DFID and Switzerland. This process supports assessment of Effectiveness.
- These management and procurement arrangements in place ensure that high quality work is achieved at an optimum cost. This supports Efficiency of the programme.
- Strengthening backward linkages between the hospitality sector and agriculture as suggested by the MICE study, will potentially improve incomes of the poor farmers by bringing them into the supply chain of products consumed through national and international events/conference. Evidence gathered on the status of disability in Rwanda has informed the communiqué of recommendations from the Rwanda summit that will inform GoR’s commitments and engagement at the Global Disability Summit (GDS18). These products contribute to the equity and the living none behind commitments.

Assessment of whether the programme continues to represent value for money

Based on the above analysis, and the fact that the programme has exceeded its outputs (and is expected to deliver its outcome) at a lower cost than expected in the business case, we conclude that overall, the programme continues to represent value for money.

Quality of financial management

The budget execution has significantly improved over the last year of the programme, although it remains financially under-committed. Out of the approved budget of £1,632,603, £1,001,500 has been spent to date and £120,000 is committed to be spent by September 2018. The balance of £511,103 is not committed yet. Efforts are being made to guide DFID Rwanda in identifying and undertaking relevant studies and exercises to improve the evidence base that will support the implementation of the NST to improve the effectiveness of DFID and other DPs’ programmes and interventions. Further, the forthcoming DFID-wide country development diagnostic process, and UK government Spending Review which will follow provide opportunities to further utilise the facility to inform DFID’s thinking and future programming. No audit requirement is needed for this programme[3]. Most of the outputs are delivered through short term consultancy contracts where payment is made only upon the delivery of the agreed output, putting forecast under high variance risks as it depends on how the process of completing a study. The financial forecast is done when the assignment is approved at the PEF management quarterly meeting. The big challenge is that this programme is owned by the Economic Growth Team but funds are managed by teams leading on the assignment(s). This means that the team will have to adjust the forecast as per the contract awarded. To some extent, these challenges are expected in a flexible, demand driven facility such as PEF.
[3] With the exception of the Annual Audited Statement that UNDP will need to provide for the cost of the performance of SWGs. This particular study was managed by UNDP and funded by DFID under a bilateral Memorandum of Understanding.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The programme has proven to be of important use through provision of the much needed evidence and analytical works for better stakeholder engagement, policy dialogue and evidence and context based programming. Products from consultancies undertaken have been reported by both DFID sector lead advisers and stakeholders we have engaged with (including GoR, DPs and private sector) to be significantly useful in terms of improving their knowledge base and potential to influence policy work and project execution. The newly approved NST and its significant policy shifts create a large need for evidence and analytical works, paramount for an effective policy dialogue, and design and implementation of relevant and evidence based bilateral programmes in support of GoR’s growth and poverty reduction agenda. These new developments offer greater opportunities for PEF to influence wider policy environment and development programme design and implementation; justifying the continuation of the programme from a VfM perspective.

E: RISK

Overall of programme risk: Moderate

Overview of programme risk (noting the rating from p.1) and mitigation

Key delivery risks are around delays in spending linked to long and inefficient contract management, especially for studies managed by public institutions. In fact, since the facility is managed by DFID, procurement of consultants is relatively quick and responsive. But once the contract is signed and a government institution is leading on the execution of the study, the process of interaction with the consultant and other stakeholders (such as providing inputs, feedbacks and agreement on the findings of the study) is generally long and inefficient.

Another important risk is linked to less engagement of sector advisers given the many competing demands on their time, thus inability to identify knowledge gaps and prepare subsequent proposals for funding on time. More often, identifying knowledge gaps and needs for research has required a proactive and challenging push by the programme lead.

As a result, payment schedules have slowed down, putting the programme under significant risks of low spending by March 2019. Proactive and appropriate measures should be considered to revise the spending plan in consideration of the above. However, it should be recognised that PEF, as a flexible and demand driven facility will always have challenges in predictability of spend, by its very nature.

Outstanding actions from risk assessment

Lead adviser to work closely with relevant government institutions in the process of managing contracts that are funded through the PEF. This would include (to the extent possible) provision of technical skills such as reviewing ToRs, engagement in the process of providing timely feedbacks to the consultant on inception as well as draft reports, and involvement in the organisation of validation meetings/reviews.

Continuous reminder through the weekly Senior Management Team (SMT) of the opportunities for Team Leaders and advisers to use the facility for increasing the evidence base on issues related to their respective sectors.

Engage closely and regularly with UNDP and the steering committee for the effective management of the contribution arrangement, for which a no-cost extension until the end of the overall PEF has just been agreed.

Assets monitoring and control

The programme does not involve any assets

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

In terms of output delivery, programme timescales are on track as expected milestones for the fourth year have been relatively surpassed. Completed studies have been discussed in appropriate forums involving Government of Rwanda and Development Partners. On the basis of that, it is expected that the outcome of enhanced evidence base to inform policies and programmes is likely to be achieved within the programme timeframe.

While the programme has done well on the output delivery, challenges remain on the commercial and financial performance sides. In fact, execution of projects (studies) have taken longer than expected (especially those involving government institutions and UNDP), with significant implications on the budget execution. This has increased the risk of underspend that needs to be closely monitored.

The decision on commissioning any of these studies (both directly by DFID and indirectly through the UNDP managed cooperation agreement) is made on the basis of a thorough assessment of its relevance and contribution to generating evidence for policy dialogue and programming[4]. These arrangements provide insurance that all research products/studies commissioned respond to evidence needs to support the implementation of the EDPRS-II and to inform the design of the new EDPRS-III. As a result, studies selected, have strong alignment to the outcome objective of enhanced evidence base to inform policies and programmes of the Government of Rwanda and Development partners.
[4] Studies directly commissioned by DFID are selected and approved by the PEF management committee while studies managed under UNDP contribution agreement are selected and approved by the Steering Committee which includes Ministry Finance, UNDP, DFID and Swiss.

G: MONITORING, EVIDENCE & LEARNING

Monitoring

The review was internally conducted by DFID Rwanda’s Programme Manager under the supervision of the DFID Rwanda’s Economic Adviser, who is SRO of the programme. The review included a desk review of the business case, log-frame and other relevant documentation, complemented by interviews with key project partners including DFID Rwanda sector advisors, Development Partners (UNDP) and the Government of Rwanda (MINECOFIN).

Evidence

PEF is strongly linked to the DFID-Rwanda evidence plan which has the objectives of streamlining and strengthening DFID’s approach to produce, access and use ‘good evidence’ about development in Rwanda, and development more broadly; to gain a better understanding of the changing context in which we are working and to design better targeted and more effective programmes. PEF is also consistent with and complementary to DFID’s East Africa Regional Research Hub. Complementarity of the two facilities is based on the fact that PEF is more focused on local needs, responding to short term needs for analysis and studies in a quick and flexible way. The regional facility on the other hand focuses on the regional needs of evidence and bigger scale research and evaluations.

Learning

Significant progress has been achieved on the two outputs of the programme in the fourth year of the PEF implementation. Types of studies conducted included data gathering exercises to fill knowledge gaps, and studies that provide policy options and/or recommendations to support economic growth and poverty reduction in Rwanda. Given the fact that completed studies are being discussed in appropriate forums involving government of Rwanda and Development Partners, and the evidence about how evidence generated is informing policy dialogue and programming, the outcome of enhanced evidence base to inform policies and programmes is likely to be achieved at the end of this evidence facility programme. However, following recent discussions with Government of Rwanda and UNDP, an agreement was reached to support the implementation of an action plan to improve evidence-based policy and analysis, capacity and systems for better resource mobilisation and aid effectiveness in Rwanda. This will represent greater opportunities for more relevant studies and evaluations to be funded through PEF.

Progress on recommendations from previous reviews

Key recommendations from last year were:

- A cost extension of the project is highly recommended in response to the increasing demand for research and evidence.
- Encourage the wider use of the facility across all DFID teams.
- Strengthen the use of evidence products to inform policy and programme discussions through relevant platforms including SWG, policy meetings, and DPCG.
- Closely engage with UNPD in the management of the contribution agreement to ensure delays in the implementation and disbursement plans are minimised.

Summary of progress made on the key recommendations

Following the rising demand for PEF products, a cost extension to March 2019 was approved. Although the Economic Growth Team (EGT) has increased demand and use of PEF following SRO’s increasing efforts to re-advertise the facility, other teams (social sector team and governance) have responded to a lesser degree. Following contribution arrangement with UNDP in support of MINECOFIN’s effective cooperation for results project, the SRO sits on the steering committee and engage regularly (alongside the programme manager) with UNDP on the implementation of the agreed work-plan.