Type of Review: Annual Review

Project Title: Health Partnership Scheme
Date started: 1 July 2011
Date review undertaken: July 2014

## Introduction and Context

What support is the UK providing?
The Health Partnership Scheme (HPS) supports partnerships between UK health institutions and those in low income countries. Its aims are: / Improving health services in developing countries through sharing skills and capacity development / Bringing benefits back to the UK through volunteer NHS staff returning with stronger skills / The scheme has two main components: a grant for partnership projects, as well as activities to support and develop the health partnership community in the UK and overseas. / The original grant provided £20 million over 4 years (July 2011 – June 2015). In April 2014 an extension of HPS was announced providing another £10 million to extend the programme to 2017.

What are the expected results?
The impact of the HPS will be more effective and efficient health service provision (with a special interest in MDGs 4, 5 & 6 as well as rural and underserved populations). / The outcome will be more effective and efficient health systems, with an emphasis on strengthening the health workforce in participating countries and the UK. / The outputs of the programme will be: / Improved and strengthened knowledge and capability in participating health institutions / Improved and strengthened policies and practices in participating health institutions / Improved and strengthened teaching in participating health education institutions / Stronger and more institutional and country health partnerships that promote and enable mutual learning and skills and technology transfer / Effective and efficient grant funding and strategic management support to projects and health partnership community by the managing agent / The HPS uses the expertise of UK health professionals and health institutions to build capacity of their counterparts in developing countries. It is also intended that the HPS will build the evidence base that returning volunteers bring benefits back to their UK institutions.

What is the context in which UK support is provided?
A strong health workforce is an essential component of a functioning health system. Improving access to better basic services requires skilled and motivated health workers in the right place at the right time. DFID invests significant resources in human resources for health in partner countries. The HPS complements other DFID health initiatives by using UK expertise to strengthen health worker training. The HPS aims to make the most of the high quality of UK health professionals and the international reputation of the UK’s health institutions. / In 2006-7 Lord Crisp led a review of the UK contribution to health in developing countries, culminating in the publication of the Global Health Partnerships Report in early 2007. The recommendations of this report fed into the development of the International Health Links Programme and, subsequently, the Health Partnership Scheme. The HPS was launched in June 2011. It extends in scope and ambition the work of earlier health partnership initiatives. / The Tropical Health and Education Trust (THET) is the service provider. The design of the HPS has benefited greatly from learning from the International Health Links Funding Scheme (IHLFS).

## Section A: Detailed Output Scoring
Output 1: Improved and strengthened knowledge and capability in participating health institutions
Output 1 and performance description / A++ (Outputs substantially exceeded expectation). / In the third year of its operation the HPS has substantially exceeded expectations by providing training and education to 22,324 health workers in developing countries. This is an indication that health partnership can take a substantial amount of time to develop but that once established they are capable of delivering at scale. It is also an indication that milestones, which were revised up last year, were insufficiently ambitious. / The project includes a wide variety of different training types and different methods of assessment are therefore required. For example: / Training in clinical procedures. The partnership between Imperial College and Butare University Teaching Hospital aims to reduce newborn mortality through training clinical staff in establishing Continuous Positive Airway Pressure. Staff were trained using a manikin and coached until they could perform the procedure correctly. All those taking part, therefore, were recorded as having improved skills immediately after training. / Mentoring and on-the-job training. The Kambia Appeal works to improve neonatal and maternal health through long-term volunteer placements in Kambia hospital, Sierra Leone. The partnership has introduced a competency chart that outlines a checklist of core skills. These are ticked off once a Volunteer Nursing Aide has successfully demonstrated each skill ten times, as observed by a local nurse over a period or weeks or months. / Measuring ‘soft skills’. The partnership between NHS Highland and Wa Hospital in the Upper Western Region of Ghana (MPIP21) aimed to minimise alcohol related health harm through training and mentoring of champions in screening, medical management and behaviour change training. This included equipping staff with the confidence to deal with challenging situations on mental health wards. Formative assessments were used to measure improvements in confidence and most trainees self-reported an increased level of confidence sometime after the training. / The headline result of 22,324 health workers trained fails to capture the diversity of activities under this output. The number of workers trained, for example, disguises huge variation in the type, length and effects of training conducted under the HPS. Work is needed to develop indicators which reflect some of this diversity. Moreover, currently indicators focus on training inputs and immediate results. Work needs to be done to develop indicators which show the effects of training in terms of behaviour change in trainees, on the quality of health services and, ultimately, health outcomes for patients. / Progress against expected results: / Indicator Milestone 2013-2014 Results Reported / 1.1 Number of developing country health workers who participated in education and training 9,000 26,588 / 1.2 Percentage of tested trainees showing improved skills or performance immediately after training or education. 80% 87% / 1.3 Number of developing country institutions with improved medical equipment, ICT or health information management systems. 50 75
Output indicator 1.1: Number of developing country health workers who participated in education and training (provided directly by project or by trainers trained in project) / A++ (Outputs substantially exceeded expectation). / The actual number of health workers trained since the start of the project (26,588) is almost three times the expected milestone (9,000). The vast majority of these (22,324) have been trained in the last year. Though results last year exceeded expectations (with 4,264 trained compared to 3,000 expected) this year’s results show a huge scaling-up in activity by health partnerships and suggest that the capacity of partnerships to deliver training was significantly underestimated at the start of the project. The results also suggest that it has taken some time for partnerships to establish themselves and begin to maximise their results. The unexpectedly large jump in numbers trained between last year and this year is one reason why milestones were not set sufficiently high. / Disaggregated data shows that (for those trainees whose gender was recorded) 60% were female, though the gender of 8,319 (of the 26,588 trained) was not recorded. The most common health theme for training was maternal & newborn health (8,598 trained) followed by child health (6,458 trained), general health (4,621) and non-communicable diseases (2,037). / All the partnerships have, to some extent, under-estimated the number of health workers they could train and have exceeded their own targets. Partnerships, for example, often did not take into account the number of health workers that would be trained by newly trained trainers. These trained trainers have started to cascade training thus expanding the reach of the project. In future, it would be helpful to collect disaggregated data on the numbers of health workers trained directly by UK volunteers and those trained indirectly through the cascade effect. / In addition, demand has often increased once projects have started to implement activities. Partnerships have received requests from other departments within partner institutions and other organisations, such as nearby hospitals, to include their health workers in training. / Increasingly, partnerships are finding that distance learning and online communication techniques are useful and appropriate methodologies to support project delivery and minimise international travel. / Example: Three Palestinian surgeons are to complete a seven-month limb reconstruction training fellowship at King’s College Hospital as part of the King’s – Shifa Hospital project, with the first surgeon having recently returned to Gaza. Since the project started in March 2013, five teleconferences have been held between participants from KCH, the Palestinian Ministry of Health and major hospitals in Gaza, which have allowed participants to discuss clinical cases. Weekly FaceTime discussions between King’s and the first Fellow have also helped maintain contact and project momentum following his return to Gaza and appointment as Head of the Shifa Trauma Team Committee. / Output indicator 1.2: Percentage of tested trainees showing improved skills or performance immediately after training or education. / A+ (Outputs moderately exceeded expectation) / This indicator has been amended since last year to measure the percentage rather than the number of trainees showing improvement. Of those tested, 87% of trainees showed improvement compared to the target of 80%. The methods used to test improved skills immediately after training are highly varied and depend on the type of training being given (see examples above under Output 1). / For many partnerships testing health worker performance immediately after training is not appropriate because they provide on-the-job mentoring and informal training in the workplace. In these cases it may be more appropriate to measure the changes in performance over a longer period. / The proportion of trainees whose performance and skills are being assessed after training has increased from 17% last year to 56% this year. THET does have plans in place to further increase the proportion of trainees whose performance and skills are formally assessed after training. They are supporting every health partnership to consider how to measure changes in health worker skills, and in longer-term performance (see outcome indicator 1 below), more systematically. THET are encouraging each partnership to focus on a small number of quantitative indicators that best capture its achievements in health workforce strengthening and that are practically measurable given the resources available. / Output indicator 1.3: Number of developing country institutions with improved medical equipment, ICT or health information management systems. / A++ (Outputs substantially exceeded expectation). / The actual result of 75 comfortably exceeded the milestone of 50. / In addition to those grants with a pre-planned medical equipment component, other health partnerships have begun to realise that the effective management and maintenance of medical equipment is essential for the sustainability of their interventions. Many have provided equipment not funded by the HPS grant by facilitating donations of used or spare equipment. This ranges from larger items like oxygen saturation monitors to surgical or maintenance tools. / For example: VSO Malawi has implemented a Ministry of Health (MoH) supported human resources information system across ten institutions. The RCPCH ETAT+ project is responsible for providing equipment to 11 institutions for their emergency centres in order to properly implement the triage procedure, ETAT+. / Recommendations: / THET to amend data collection for output indicator 1.1 to disaggregate numbers trained by direct and indirect training types (i.e. trained by UK volunteers and trained by trainers). / Improve completeness of data on gender and other demographic characteristics of trainees. THET to develop a plan for this by the end of September 2014. / THET to implement plans to improve the proportion of trainees whose skills and performance is formally assessed after training. / Start collecting data on health impacts where appropriate. DFID and THET to agree parameters by the end of September 2014. / Reset milestones for output indicators 1.1, 1.2, and 1.3 to be more stretching. New milestone to be agreed between DFID and THET by the end of September 2014. / Review output 1 and related indicators to increase focus on the effects of training on behaviour change in health-workers and on the quality of health services taking into account the problems inherent in reporting on a very diverse range of projects and training types. DFID and THET to agree revisions by November 2014. / Impact Weighting (50%): / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? Yes. Improved results this year mean that all output milestones have been comfortably exceeded. As health partnerships have become more established the risk that they will fail to deliver expected outputs has fallen.

Output 2: Improved and strengthened policies, protocols and curricula in participating health and health education institutions or across health systems
Output 2 score and performance description: / A++ (Outputs substantially exceeded expectation). / Strengthening policies, protocols and curricula is an important way in which partnerships can make sustainable improvements to the quality of healthcare in partner institutions. If these are signed off at an appropriate level, the changes they bring can make a long-term difference. This is an area of work that has expanded greatly in the last year and the current results substantially exceed expectations.
Progress against expected results: / Indicator Milestone 2013-2014 Results Reported / 2.1 Number of national and institutional health strategies and professional standards / protocols to which projects have contributed for development, review or update. 75 266 / 2.2 Number of new or improved policies and professional standards approved and signed off, by end of programme. 45 198 / 2.3 Number of medical education curricula to which projects have explicitly contributed for development, review or update. 30 65 / 2.4 Number of new and or improved medical education curricula explicitly approved for teaching. 18 41 / 2.1 Number of national and institutional health strategies and professional standards / protocols to which projects have contributed for development, review or update. / A++ (Outputs substantially exceeded expectation). / This result requires that the UK institution has worked with partners in developing countries to improve strategies, standards or protocols. The milestone was increased after better-than-expected performance last year. The revised milestone of 75 was very substantially exceeded by the actual result of 266. Many more health partnerships than anticipated took opportunities to contribute to or revise institutional protocols and procedures, often as a strategy to ensure sustainable improvements. Strategies, protocols and standards are often used in partnerships which are focussed on improving the quality of health care. / For example: The University of Edinburgh Palliative Care Partnership is working to achieve integration of palliative care into National Health plans in Uganda, Zambia, Rwanda and Kenya. As palliative care integration is at different stages in each country the activities needed varied between countries. With support from the University of Edinburgh, the Palliative Care Association of Uganda (PCAU) is working with the MoH to develop indicators to be included in the country’s health management information system. In Kenya, the national association (KEHPCA) has supported advocacy activities that have led to an increased availability of morphine in hospitals. / 2.2 Number of new or improved policies and professional standards approved and signed off, by end of programme. / A++ (Outputs substantially exceeded expectation). / The milestone of 45 was greatly exceeded by the actual result of 198. Of the strategies, protocols and standards counted in outcome indicator 2.1, 74% were approved or signed off where it had been expected that only 60% would be signed off or approved. Of these, 28 were approved at the national or MoH level, two at professional association or professional council level, and 168 at hospital level (primary, secondary/tertiary, or all levels). / For example, the National Institute for Health and Care Excellence (NICE) has supported the introduction of new policies related to priority setting in China and India. In India, what was originally a state-level partnership has evolved into engagement at national level with NICE providing technical assistance aligned to healthcare reforms. In particular, the partnership is strategically focused on building local institutional capacity for priority-setting in health with the aim of improving quality of care, reducing waste and increasing access for the most vulnerable. / 2.3 Number of medical education curricula to which projects have explicitly contributed for development, review or update. / The milestone for this indicator was revised upwards after better than expected results last year. This year’s results, however, were more than twice as high as the revised milestone of 30. A number of health partnerships worked with professional associations or teaching hospitals to build a faculty’s capacity to deliver training. They also contributed to the development or revision of the training curricula for a number of specialties including basic surgical skills, ophthalmology for clinical officers, and paediatric mental health. Partnerships which did not initially plan to be involved in curriculum development were often requested to contribute to developing or revising curricula. / 2.4 Number of new and or improved medical education curricula explicitly approved for teaching. / Forty-one of the 65 curricula contributed to were approved by the end of this reporting year. This substantially exceeded the milestone of 18.It had been expected that 60% of curriculum developments would be approved, the actual result is 69%. / For example the Royal College of Paediatrics and Child Health Global Links project contributed to the development and approval of 16 curricula including: a training package adapted for use for neonatal resuscitation in Jinja Hospital, Uganda; and malaria protocol development and accompanying training for Ola During Hospital, Sierra Leone. / Recommendations: / Reset milestone for outcome indicators 2.1, 2.2, 2.4, and 2.5. DFID and THET to agree on revised milestones by the end of September 2014. / Impact Weighting (25%): / Revised since last Annual Review? Yes. This output now incorporates the old outputs 3.1 and 3.2 in line with previous recommendations. The impact weighting has been revised from 10% to 25% to take account of this. Output 3 previously had 15% weighting. / Risk: Low / Revised since last Annual Review? Yes. Outcome indicators have changed since last year and incorporated some low risk indicators. The risk of failure to meet expected results is now judged to be low.

Output 3: Stronger and more institutional and country health partnerships that promote and enable mutual learning and skills and technology transfer
Output 3 score and performance description / A (Outputs met expectations). / There were generally strong results in this area though the number of volunteer days spent overseas was slightly lower than expected. In general, the number and strength of partnerships has continued to improve. / Indicator Milestone 2013-2014 Results Reported / 3.1 Number of new institutional health partnership Memoranda of Understanding or other formal written commitments. 30 54 / 3.2 Number of institutional health partnerships strengthened. 30 45 / 3.3 Number of UK health professional days spent volunteering overseas. 32,000 31,039
Progress against expected results: / Indicator 3.1: The number of new institutional health partnership Memoranda of Understanding or other formal written commitments. / A+ (Outputs moderately exceeded expectation). / It is important that health partnerships are recognised and accepted by the health authorities in country, with activities coherent with national and local policies. Formal agreements are taken to be a proxy for this recognition. Agreements are made with a range of different implementation partners, including national associations, research partners, training partners and volunteer recruitment partners. This indicator measures the formal establishment of new partnership as opposed the formal strengthening of existing partnerships, which is captured in 3.2. / Performance has been strong this year. As well as new partnerships being established, existing partnerships have reached out to new partners to collaborate and expand their work. This has resulted in 29 new partnerships being formed since last year. This takes the total result to 54 against a milestone of 30. / Indicator 3.2: The number of institutional Health Partnerships strengthened. / A+ (Outputs moderately exceeded expectation). / The milestone of 30 was again comfortably exceeded with a result of 65. / This indicator is a measure of the activities taken by partnerships that are specifically intended to build relationships and strengthen the partnership itself. These formalise existing relationships through the establishment of MOUs as well as the development of new structures such as steering groups to help manage the work. The establishment of new partnerships (captured in 3.1) is not included in this result. / Indicator 3.3: Number of UK health professional days spent volunteering overseas. / B (output moderately did not meet expectation) / This result (31,039) has fallen short of the milestone (32,000) by 3%. This milestone was revised downwards after under-performance last year. It is possible that this indicator under-represents the amount of time given to the partnerships by volunteers since it measures only the amount of time which volunteers spend overseas. Increasingly partnerships are using technological solutions to allow volunteers to interact with overseas partners from the UK. / Recommendations: / Revise wording of output. Wording to be agreed between DFID and THET by end of September 2014. / Revise output indicator 3.3 to include volunteer time invested in training remotely from the UK. Wording to be agreed between DFID and THET by end of September 2014. / Impact Weighting (15%): / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 4: Effective and efficient grant funding and strategic management support to projects and health partnership community by the managing agent
Output score and performance description / A+ (Outputs moderately exceed expectation) / The HPS performed well in its management of funding and its strategic management of partnerships. It is responsive to grant holders, providing technical assistance and support where appropriate. THET has been active in making it easier for NHS workers to volunteer overseas.
Progress against expected results: / Indicator Milestone 2013-2014 Results Reported / 4.1 The amount of grant funding disbursed, within agreed timeframes £10,715,042 £10,831,855 / 4.2 The percentage of timely and appropriate provision of technical assistance to grant-holders and other eligible stakeholders in a 12 month period 85% 93% / 4.3 Number of advocacy and communication activities undertaken by THET in support of an enabling NHS environment for overseas volunteering. 120 132 / 4.4 Online audience and registered users 41,000 60,584 / Progress against expected results: / Indicator 4.1: The amount of grant funding disbursed, within agreed timeframes. / A (outputs met expectations) / Actual disbursement of grants in the last year was £10,831,855. This was 101% of the expected figure (£10,715,042). This small amount of extra disbursement reflects the fact that THET tries to be responsive to the progress of projects and approves payments based on past performance as well as adherence to financial controls. / Indicator 4.2: The percentage of timely and appropriate provision of technical assistance to grant-holders and other eligible stakeholders in a 12 month period / A+ (Outputs moderately exceed expectation) / The actual result was 93% compared to a milestone of 85%. THET provides a range of support to grant-holders, particularly in the fields of project management, monitoring and evaluation. This includes running monitoring and evaluation workshops for partner organisations. It also facilitates networking between grant-holders through ‘sharing and learning’ events. It is particularly encouraging that a number of these capacity-building events take place in developing countries involving partners from the South. An online forum is also available for grant-holders to network. In conversation with DFID, grant-holders have expressed appreciation of THET’s support. / Indicator 4.3: Number of advocacy and communication activities undertaken by THET in support of an enabling NHS environment for overseas volunteering. / A+ (Outputs moderately exceed expectation) / The result of 132 was slightly higher than the milestone of 120. This activity incudes events, presentations, workshops and publications aimed at making it easier for NHS workers to volunteer overseas. / For example: THET issued an official response to the All Party Parliamentary Group on Global Health report on overseas volunteering and partnerships from the NHS, and led a campaign to urge those currently involved in health partnerships to write to their local MP or newspaper about the benefits of volunteering. THET has been closely involved in drafting the new Framework for NHS Involvement in International Development. / Advocacy and communications work could be strengthened by developing a written communications strategy. / Recommendation: Develop written communications strategy covering all HPS advocacy and communications work. THET to prepare and agree with DFID by the end of September 2014. / Indicator 4.4: Online audience and registered users / The result of 60,584 was considerably higher than the milestone of 41,000. THET uses a number of online platforms (including THET’s website, Healthbay, Facebook, and e-bulletins) to facilitate networking and learning in the partnership community. / Recommendations: / Update logframe to remove outcome indicator 4.4 as it does not directly affect the outcome. / Impact Weighting (%): 10% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Yes / A number of recommendations to revise the logframe were made in the last annual review. An updated version of the logframe was agreed with THET. Changes include: / Milestones revised upwards for output indicators: 2.1, 2.2, 2.3, 2.4, 3.3 / New output indicators added: 4.3 and 4.4 to capture advocacy work done by THET. / Output indicator 1.2 was revised from the number of trainees showing improvement to measure the proportion of trainees showing improvement. / Outcome indicator 2 was revised to capture contributions to curricula. / Outcome indicator 2 / 1.2 Overall Output Score and Description: / A++ Outputs substantially exceeded expectation. / The project’s results have exceeded milestones in several areas. It is clear that the milestones (which were revised upwards after last year’s annual review) were not sufficiently stretching. This is the third annual review in what was originally designed as a four year project. The results this year are likely to be the highest of the four years. In the first two years the project took time to get established and to award grants. After grants were awarded a it took time for partnerships to establish themselves. The groundwork laid in previous years has come to fruition this year and we underestimated the momentum that had been built up in previous years. Over the next 12 months most projects will be winding down, as many grants expire in March 2015. The time taken for partnerships to build their work up to full capacity is a lesson which can be applied in setting milestones for the extension period. / 1.3 Direct feedback from beneficiaries / THET sees the health workers receiving training as their key beneficiaries. They aim to visit all projects over their lifespan and will interview a selection of health workers trained in each project. The independent evaluation of the HPS planned for early 2015 should be a good opportunity to gain more insight from the experience of beneficiaries – ideally, not just health workers, but patients as well. / DFID staff have met with a number of partner organisation funded by HPS who expressed their appreciation of the support given to them by THET. They particularly value the facilitation of learning between different partnerships. Partner organisations have also stressed the long timescales involved in establishing effective partnerships overseas. Building of trust and effective methods of working in partnership can take years rather than months. / All project partners get feedback from trainees about the training undertaken and some of this feedback is included in 6-monthly reporting to THET. Some examples include: / From VSO Malawi: “Already from the pilot, this system [the Integrated Human Resource Information System) is helping us to know where each health worker is and with that we are able to tell which centres have more staff and which ones need more staff. For example, we were able to know that there are more drivers at Lilongwe District Health Office.” Gillian Nkhalamba, Human Resource Planning Officer for Ministry of Health / VSO Malawi: Commending the work a volunteer, “She has helped with setting up of stock management and financial management systems. From this systems’ improvement, we have been able to save more money.” Mrs Ndege, Principal for Nkhoma College / The partnership between the University of Oxford and College of Surgeons of East, Central and Southern Africa combining broad Primary Trauma Care (PTC) training courses with intensive orthopaedic surgery placements to improve trauma care: "This course is so helpful. Now I know how to deal with any traumatic patient. I can now serve many patients with injuries that I couldn’t serve before. Thank you so much for this course." (Consolata Kilawe, Nurse, Mount Meru Regional Hospital Arusha Tanzania). / Currently, there are few mechanisms allowing feedback directly from beneficiaries (trainees and Southern partner institutions) to THET or DFID. There is a risk, therefore, that only positive feedback is reported by grantees to THET and, then to DFID. It would be beneficial to develop systems to allow direct feedback to THET from trainees and Southern partner organisations. / Recommendations: / More feedback to be collected directly from beneficiaries and Southern partners including constructive criticism. This should include requirements being written into new grant contracts awarded in the extension period. THET and DFID to agree a plan by the end of November 2014.
1.4 Summary of overall progress / This is the third year of the HPS and it has seen a significant shift away from start-up and grant awarding activities and into the core business of partnership activity and advocacy. The project enables a wide variety of projects ranging from individual mentoring and training of clinical workers to developing systems of training and strengthening professional associations. / After 2 years of ground work in awarding grants and establishing good working relationships between partners, the partnerships are now delivering results well above expected levels. Since the inception of the programme, the HPS has delivered training (directly or indirectly) to over 26,500 health workers in the developing countries and over 84% (~22,000) of these have been in the last year. Partnerships have also continued to show strong performance in the development of policies, protocols and educational curricula. They have also made strong contributions to improving equipment and ICT within institutions, often going beyond their original project plans to the improve systems necessary for health care. / The confirmation of a 2 year extension of the programme will require a new round of grants to be awarded in the next year and should enable many of the best-performing partnerships to continue as well as allowing others to scale-up or establish new partnerships.
1.5 Key challenges / Data, reporting and evaluation. The variety and complexity of projects funded through the HPS makes data gathering and reporting an on-going challenge, particularly in relation to demonstrating long-term outcomes. A number of the indicators (e.g. 1.1 number of health workers trained) involve aggregating data from hugely varied training types ranging from single-day training events to several months of one-to-one mentoring. Similarly, measuring the impact of training in terms of improved performance is difficult to do in a consistent way. A variety of methods of data collection are used including grant-holder reporting, project visit, mile-stone meetings and one-to-one support. Relevant recommendations are made in relation to outcome 1. / Relationship breakdown. The HPS model depends on good working relationships between two or more partner organisations. Therefore, the breakdown of the relationships between partners can result in projects having to close down. This happens to a small proportion of partnerships. / In the last year, the closure of two partnerships was initiated by the developing country partner due to a lack of commitment by senior management. In both cases, the partnership did not have a signed-off Memorandum of Understanding, which highlights the need to have a formalised agreement in place. THET plans to ensure this is a requirement for future partnerships. / In another case, the relationship between two UK partner organisations broke down in spite of efforts to encourage the resolution of disputed issues. This led to the project being closed down and to a letter of concern being sent to DFID’s by MoH officials in country. In future DFID will be given early notification of partnership breakdowns which could carry political or reputational risk. / Infrastructure issues have delayed or impeded a number of projects. For example, problems with building new clinical facilities in some partner organisations have delayed some projects. Increasingly, partnerships are looking to information technology to deliver training and mentoring as well as for communication between partners. The lack of reliable IT infrastructure, however, has been a significant barrier in some projects. / Staff turnover in institutions receiving training can threaten the performance of partnership projects. This is a problem inherent to the HPS model. If key members of staff or champions leave the institution it can significantly weaken partnerships. There are some examples of projects which have taken action to mitigate this risk by, for example, implementing a shorter design, making more frequent visits to partner institutions or establishing honorary positions which can be taken up by incoming staff. / Institutional hierarchies can make the systemic change necessary to improve care difficult to achieve in some partnerships. This has been particularly evident in Medical Equipment Grants where the low status of engineers and technicians within hospitals in the South can threaten the effectiveness of the partnerships. Some partnerships now focus specifically on raising the status of their partner cadres. / NHS systems. The majority of Health Partnerships administer the grant payment through their NHS institution’s finance department. The sums are relatively small and there have been problems with partnerships being able to access their funds or keep track of them within complex NHS systems. In practice, this has led to delays in remitting funds to partners or to volunteers. Some Health Partnerships have navigated this issue by setting up a charitable arm that manages the funds and brings the added benefit of a formal structure for fundraising and promoting the partnership. / Recruiting UK volunteers. This was identified as a potential challenge early in the project. Grant applications were assessed for the ability of partners to recruit sufficient volunteers and this has not proved to be a significant problem so far.
1.6 Annual Outcome Assessment / Generally, progress against outcomes has been satisfactory though measurement issues related to demonstrating improved performance of health workers remain to be resolved. The evaluation (see section 3.2) will consider progress towards outcomes and assess how synergistic the HPS partnerships are. / Outcome indicator 1: Number of developing country health workers demonstrating improved performance, following education or training / Milestone: 7,200 / Result: 3,568 / This outcome requires performance to be measured after training, though the timescale for measurement is not specified. This should be clarified for future. Since the start of HPS 26,313 health workers have participated in some kind of training or education. The subsequent performance of 5,346 (20%) health workers was assessed and 3,568 (67%) of them were found to have improved. The actual result is lower than the milestone primarily because most trained health workers did not have their subsequent performance measured after 6 months. In some cases this is due to a time lag – 9,445 workers were trained in the last 6 months so there has not been enough time to measure their performance – in other cases this is due to methodological difficulties in assessing improved performance. / Some progress has been made. Data exist on performance change for 20% of trained health workers in 2013/14, compared with 2% in the 2012/13 annual report. Improvements in measuring outcomes will need to be continued. As stated above THET is supporting every health partnership to consider how to measure changes in health worker skills, and in longer-term performance (see outcome indicator 1 below), more systematically. Assessment of performance improvement over time will be particularly important for health workers who have been mentored, where immediate measurement of improvement (i.e. output indicator 1.2) is not appropriate. / Recommendation: / Amend outcome indicator 1 to specify a 6 month timeframe for measurement. Final wording to be agreed between DFID and THET by end of September 2014. / Outcome indicator 2: Number of participating institutions demonstrating implementation of improved policies and curricula, 12 months after sign-off or approval / Milestone: 50 / Result: 65 / Progress against this output exceeds the milestone. One example of progress comes from the Edinburgh Palliative Care Project. The Zambian and Ugandan Ministries of Health have adopted 11 clinical management protocols developed with support from the partnership, for nation-wide use. / Outcome indicator 3: Number of participating institutions using and maintaining improved equipment, ICT or health information management systems, 12 months after delivery / Milestone 20 / Result: 29 / Progress against this output exceeds the milestone. One example of progress comes from the work of the Royal College of Paediatrics and Child Health ETAT+ project, working in Kenya, Uganda and Rwanda. They report 11 institutions that are now using a range of new equipment including triage and emergency room furniture, oxygen piping, resuscitation ventilator bags, oxygen masks, nasal prongs, suction machines, phototherapy equipment and space heaters. / Outcome indicator 4: Number of UK volunteers self-reporting or demonstrating improved clinical and leadership skills / Milestone: 436 / Result: 167 / While there is extensive evidence that volunteers believe their experiences have improved their skills, this is rarely appraised independently, in terms of competencies and performance. THET is working with a range of stakeholders to publish guidance for NHS volunteers and managers in appraisal of volunteering experiences in respect of performance back in the UK health service. This toolkit will include a survey for volunteers to provide feedback on how their volunteering experience was appraised. THET ran a pilot as part of the toolkit development and the data above includes results from 18 participating volunteers. The pilot data show clear improvements in volunteer performance after returning to work. By the next annual report, THET hopes to have near-comprehensive, quantitative data on how health worker competencies have been affected by volunteering experiences. The data set will be big enough to allow comparisons between short- and long-term volunteers or with other variables.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / Yes. For the 12 months to June 2014, actual expenditure was 99.5% of the budgeted expenditure. / Reasons for minor underspends include: / Savings made on subsistence; / Some monitoring and evaluation work has been postponed pending the outcome of an independent evaluation which will make recommendations on how to improve monitoring and evaluation; / Some communication activities have been postponed to accommodate the launch of the HPS extension in the second half of 2014. / Savings have been made on THET’s finance costs by arranging flexible payments from DFID to THET. / Fees £ Budget / Jul 13 –Jun 14 £ Expenditure / Jul 13 – Jun 14 % of total spend / Personnel Inputs / THET / Consultants 574,493 / 54,975 546,081 / 137,603 8.3% / 2.1% / Project expenses / Travel 34,000 42,597 0.6% / Daily Living Costs 34,620 11,936 0.2% / Any Other Expenses / Grants 5,511,465 5,525,631 83.4% / Monitoring & Evaluation 19,000 8,086 0.1% / Communication & Engagement 110,700 51,737 0.8% / Other Costs 89,850 97,442 1.5% / Finance Costs 30,435 19,471 0.3% / Contingency 5,787 - - / Government Tax £190,772 182,991 2.8% / TOTAL FEES AND EXPENSES 6,656,097 6,623,576 100% / 2.2 Key cost drivers / Grants, staffing, communication and engagement, and international travel continue to be the key cost drivers for the HPS. The project moved from a grant allocation phase last year to one more focussed on grant management and monitoring. This has led to increased international travel costs (see table). / Key Cost Driver 2011/121 2012/131 2013/142 / Grants £1,045,523 £4,216,318 £5,525,631 / Staffing (THET) £407,900 £529,444 £546,081 / Communication & Engagement £87,159 £42,211 £51,737 / Travel & Subsistence £22,311 £49,455 £54,532 / 1July – June, 2July - May / The main cost drivers within grants are travel and training costs. Training costs include venue higher, training materials and resources. Grant administration costs are limited to 10% of grants. / Consultants are used to provide independent expertise. This includes an agreement with HLSP to provide independent monitoring and evaluation. The average consultant rate per day is £506. / 2.3 Is the project on-track against original timescale: / Yes. The project is on-track against the original timescale. All grants within the original HPS funding have been awarded and have commenced with end dates within the HPS timescale, including those which have been granted extensions. Forty two (our of 85) grants have now been completed whilst monitoring activities for ongoing projects continue. Activities relating to the HPS extension have commenced and are progressing in accordance with expected timelines.

3. Evidence and Evaluation
Assess any changes in evidence and implications for the project / The theory of change and the assumptions remain valid. There is no new evidence that challenges the project design or rationale. / There is anecdotal evidence that good health partnerships bring benefits to developing country health workers and that volunteers return to the NHS with enhanced skills and confidence, but there is relatively little hard evidence for either. This project is extending the available evidence. So far it has provided good evidence of short-term improvements in health worker performance for some types of partnership project. There are opportunities to enhance this further by extending performance measurement to more project types and to longer-term follow-up. Plans to enhance measurement of improvements in the performance of volunteers after they return from developing countries could make a significant contribution to the evidence base for partnership work. / The project has reported positive feedback thus far but needs to ensure that both positive and constructive feedback is captured during monitoring and evaluation especially from Southern partners and recipients of training. / Data about health workers involved in the projects is disaggregated by gender and cadre; data about health services and health systems strengthening is disaggregated by health theme and level of healthcare; data about health institutions is disaggregated by population served; data about patients is disaggregated by gender. / 3.2 Where an evaluation is planned what progress has been made? / An external evaluation of the project is planned for early 2015. This will be carried out by external consultants. The Terms of Reference for this evaluation are currently being developed. / HLSP is currently undertaking a mid-term review of the HPS ‘mega-grants’ (Multi-Country Partnerships and Long Term Volunteering grants) examining them against Development Assistant Committee and value for money criteria. The report will include a summary of progress and lessons learned as well as recommendations for improving partnership management and support during the remainder of the grant period. It will also draw out some programme-level themes and lessons. The report is expected to be completed in late July 2014.
4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The risk matrix for the programme has recently been updated. A number of risks are identified as medium/high impact though the probability of most is medium or low. Given the excellent results achieved this year, the risk of the programme failing to meet result milestones is low. A number of other risks have been identified and mitigating measures have been put in place. / The main risks are: / Lack of interest from UK volunteers. This would have a high impact. The ability of partnerships to engage with and recruit UK volunteers was assessed during the grant-making process and so far this has not proved to be a problem for partnerships. Probability is low. / Projects are not effective due to lack of project management experience. THET continues to provide advice and support on project design, budgeting and monitoring and evaluation. Progress and spending is reviewed quarterly or biannually and funds are withheld or redeployed if necessary. Milestone meetings and project visits also take place for larger grants (£250k+) in order to review progress as well as barriers to success in more detail. / Projects are not effective due to lack of Southern partner engagement. Under the initial phase of HPS, meaningful southern partner engagement was included within the selection criteria. As part of the selection process for the larger grants, southern partner interviews were also conducted. In future phases of grant giving, a full Partnership Assessment will be completed for all shortlisted applicants. / Security problems create risk for volunteers, local staff and the project. This includes disease outbreaks. For example, expatriate volunteers were recently evacuated from one project affected by the Ebola outbreak in West Africa. Potential impact is high but mitigating measures are in place including procedures for risk assessment, incident management, and programme extensions where appropriate. Probability is medium. / Risk of funds not being used as intended / The risk of fraud or misuse of funds is MEDIUM. The programme does not carry out any large scale procurement but the large number of small grant holders increases the likelihood of some small-scale misuse of funds. The risk of fraud is mitigated by a number of systems including: / Reporting. Grants holders are required to provide detailed financial reports to THET on a quarterly or biannual basis depending on the size of the grant. Receipts for expenses are supplied as part of these reports and THET undertakes a detailed analysis of the financial status of each grant / In-country financial verification visits. THET has begun to perform project visits to verify the financial expenditure of grants valued over £249,000. This has happened in Uganda and will take place in Malawi and Kenya later this year. It will ensure that all grants valued over this threshold will have at least one in-country visit. / THET’s Grant Management Group (GMG) meets regularly to review grant progress including assessing the use of grant holders’ funds against budget and to identify any inconsistencies or potential areas for closer monitoring. / Audit. THET has an annual external audit of its accounts. Large HPS grants (Multi Country Partnerships and Long Term Volunteering grants) require grant-holders to have THET funded projects audited annually with the results made available to THET. In July 2013 THET commissioned an external process audit of the HPS systems and procedures to confirm that proper controls have been devised and make recommendations for improvement. The findings were overall very positive, with six recommendations made that will be included in the grant awarding process for the next round of HPS grants. / Example of following the money / THET has begun a process of visiting projects with a total value of over £249,000 to spot check the in-country expenditure and verify that systems are in place to ensure financial accountability and transparency, and alignment with project activities. / In April 2014, two members of the THET team visited Uganda and undertook site visits to six projects. Each visit entailed meeting the local project manager as well as the person responsible for the financial management of all in-country expenditure. A number of checks were performed including: / A sample of transactions was reviewed and verified, with the team looking to find proper requisitions or vouchers, original invoices, receipts of payment and appropriate signatories. / Sample verification of results data was undertaken. Prior to the visit, a sample of reported results was taken for which the in-country team was required to provide evidence. / Five of the six projects visited on this trip had good financial systems and records to support these. The documentation provided to support the reports was clear and the team felt that the project was being managed in-country in a transparent and efficient manner. One project, however, failed to produce all the receipts requested and did not have vouchers, invoices or receipts for all payments. Although the expenditure in-country was minimal, with most transactions under £100 and the total expenditure in-country less than £40,000 over the three years, the team felt that the lack of clear process and proper documentation warranted further action. As a result two members of the THET finance Team visited the project in the UK and followed an audit process in which they sampled and verified expenditure in the UK, audited bank accounts and assessed the systems in place. The findings of this audit highlighted some weaknesses of process but no evidence of mismanagement of funds. As a result, a list of requirements for improvement was given to the grant holder and the project given until October to put more robust systems in place. / 4.4 Climate and Environment Risk / The main negative environmental impact relates to international flights. Although travel is likely to remain a significant part of health partnership projects, THET is encouraging partnerships to utilise supplementary ‘distance’ approaches to project delivery although this is limited by communications infrastructure and preferences for face to face engagement. / Methods to further reduce the carbon footprint of the project will be incorporated into the design of the project extension.

5. Value for Money
5.1 Performance on VfM measures / Economy / The project memorandum does not include measures of value for money. Last year’s annual review recommended that DFID and THET should develop VfM measures. Further work will be needed to agree an appropriate set of VFM indicators for the HPS programme, and should build on the outputs of the external evaluation in early 2015, / The diversity of the projects funded by HPS makes calculating meaningful VfM measures at programme level challenging. One measure which has been calculated this year is the cost per health worker trained. With costs calculated as health partnerships’ total expenditure excluding costs of project management, medical equipment and evaluation, this works out at £170 per worker trained. / However, as explained above, the diversity of training types included in HPS projects makes this figure hard to interpret. Also, cost figures include some non-training activities such as partnership development, advocacy and building the capacity of networks and professional associations. / Following the completion of the HLSP evaluation of mega-grants this year, a detailed VfM plan will be developed for the remainder of the grant period and agreed by DFID and THET by the end of November 2014. This will be revised following the completion of the external evaluation in 2015 to cover the extension period. / Efficiency/cost-effectiveness / HPS grants allow health partnerships to leverage significant additional contributions such as volunteer time, additional grant funding, and the facilities and services offered by partners. A study commissioned for the International Health Links Funding Scheme identified the scale of matched funding and in-kind support in health partnerships. In their assessment of one health link, a project with a grant of £155,395 was found to have a true cost of £431,822 when all direct and indirect contributions were included. / Effectiveness / The project has made excellent progress against its milestones though direct measurement of its impact is limited. The HLSP mid-term review of HPS grants, which is currently underway, will include some assessment of value for money for Muliti Country Partnerships and Long Term Volunteering grants. The external evaluation of HPS planned for early 2015 should provide greater evidence on its effectiveness of HPS as a whole. / Recommendations: / Detailed VfM plan to be developed for the remainder of the grant period and agreed by DFID and THET by the end of November 2014. This will be revised following the completion of the external evaluation in 2015 to cover the extension period. / 5.2 Commercial Improvement and Value for Money / Each year of the HPS, THET is required to review expenditure and financial forecasts as part of the contract renewal process with DFID’s procurement office. Grant holders complete spending reviews as part of their reporting and follow transparent procurement and recruitment processes to ensure value for money. / THET has a number of systems in place to ensure value for money in it operations especially in key areas such as salaries, travel and procurement. Staff salaries are benchmarked against the appropriate charity sector median and they operate in comparatively low cost offices. THET staff travel by standard class only both in UK and overseas, using charity fares for flights wherever possible. Aid flights operated by various agencies are used whenever this is a cost-effective option for travel. Any procurement (e.g. consultancy services, website development etc.) is subject to proper process and always includes obtaining multiple quotes and detailed assessment of value. / THET has undertaken internal audits and a systems review to ensure proper stewardship of funding, and to ensure that their business processes is fit for purpose. As a result of these reviews THET has will modify its procedures for future grant awards to make the process more efficient. For example, an external selection panel will not be used as this involves a significant level of additional documentation and meeting costs. THET staff are now well-placed to make informed judgements about grant applications, being able to use information and experience gained from previous rounds. Staff will use video conferencing and telephone meetings wherever possible to reduce the amount of staff time lost to travel and the additional travel cost that would be incurred. / 5.3 Role of project partners / Partnership. / HPS grants were awarded in a highly competitive process allowing high quality partnerships to be selected. Many had previously been funded through the IHLS and so had a track record in effective partnership work. The award of grants in the extension period will focus on building on the success of existing partnerships which have proved to be effective and efficient though some extension funding will be available for novel or innovative partnership projects. / The health consultancy HLSP works with THET on the HPS in the role of “critical friend”, providing particular support to monitoring and evaluation. Its current review will look at the value for money provided by some grant holders. / 5.4 Does the project still represent Value for Money : Yes / A significant amount of work still needs to be done to develop quantitative VfM measures of economy. However, based on the information currently available the project still represents good value for money and the better-than-expected results achieved this year are a sign that this investment is producing far more than originally expected. / 5.5 If not, what action will you take? N/A

6. Conditionality
6.1 Update on Partnership Principles and specific conditions - NA

7. Conclusions and actions
The HPS has performed well against most of the indicators and milestones set for it, warranting an A++ score. The scale of its activity has increased since last year. This reflects the fact that a lot of groundwork done in the first 2 years of its operation has now come to fruition. Many projects funded by the HPS performed much better than expected partly because demand for their services was greater than expected but also because there was a greater-than-expected cascade effect of training trainers. / It is now clear, however, that many of the milestones set previously were insufficiently ambitious. This needs to be avoided in future, taking account of the fact that projects build up momentum at the start of their work and that results are likely to taper off in the final year of their operation. / More fundamentally, some of the outcomes and indicators currently contained in the log frame (and used for this review) are problematic. In particular, they require the aggregation of hugely diverse project activities (such as very diverse types of health worker training) into single numbers. Therefore, the meaning of the results for some indicators (e.g. number of health workers trained) is currently difficult to assess. It is also hard to be sure how some of the projects’ activities affect the quality of health services and patient health, and whether all the projects are synergistic. / Some of these issues will be addressed through external evaluation work, though work to improve current outcome indicators and assessment of the effects of training, is included in the recommendations below. Future reviews of the programme’s performance will be strengthened by the development of improved methods for assessing the behaviour change which follows training. Gathering more direct beneficiary feedback will also be important. / Actions/Recommendations: / Reset milestones for output indicators 1.1, 1.2, and 1.3 to be more stretching. New milestone to be agreed between DFID and THET by the end of September 2014. / THET to amend data collection for output indicator 1.1 to disaggregate numbers trained by direct and indirect training types (i.e. trained by UK volunteers and trained by trainers) / THET to implement plans to improve the proportion of trainees whose skills and performance is formally assessed after training. Improve completeness of data on gender and other demographic characteristics of trainees. THET to develop a plan for this by the end of September 2014. / Review output 1 and related indicators to increase focus on the effects of training on health-worker performance and the quality of health services taking into account the problems inherent in reporting on a very diverse range of projects and training types. DFID and THET to agree revisions by November 2014. / Start collecting data on health impacts where appropriate. DFID and THET to agree parameters by the end of September 2014. / Reset milestone for outcome indicators 2.1, 2.2, 2.4, and 2.5. DFID and THET to agree on revised milestones by the end of September 2014. / Revise output indicator 3.3 to include volunteer time invested in training remotely from the UK. Wording to be agreed between DFID and THET by end of September 2014. / Develop written communications strategy covering all HPS advocacy and communications work. THET to prepare and agree with DFID by the end of September 2014. / Update logframe to remove outcome indicator 4.4 as it does not directly affect the outcome. / Amend outcome indicator 1 to specify a 6 month timeframe for measurement. Final wording to be agreed between DFID and THET by end of September 2014. / Detailed VfM plan to be developed for the remainder of the grant period and agreed by DFID and THET by the end of November 2014. This will be revised following the completion of the external evaluation in 2015 to cover the extension period. / Amend outcome indicator 1 to specify a 6 month timeframe for measurement. Final wording to be agreed between DFID and THET by end of September 2014. / More feedback to be collected directly from beneficiaries and Southern partners including constructive criticism. This should include requirements being written into new grant contracts awarded in the extension period. THET and DFID to agree a plan by the end of November 2014. / Update logframe adding an output indicator related to the performance of THET in awarding grants for the extension period. Details to be agreed between DFID and THET by the end of September 2014. / The external evaluation planned for 2015 should include the terms of reference an assessment of the health impacts of the project, examination of possible measures of VfM and a look at the pro-poor impact of the project. / The Annual Review in 2015 should include fieldwork and validation at the project activity level.

8. Review Process
The review was carried out by Tim Elwell-Sutton, Health Adviser in the Health Services Team with input from Iain Jones (Economic Adviser in Health Services Team) and Peter Clarke (Policy Officer, Health Services Team). / The review was carried out in June and July 2014. Evidence was drawn from: / The THET annual report. / Detailed one-to-one briefings with THET staff covering progress all areas of the project. / Meetings with UK grantees through sharing and learning events and Royal College of Midwives annual conference. / Meeting Southern partners when representatives from professional midwife associations of Nepal, Cambodia and Uganda visited the UK as part of HPS partnerships.