## Ignore_BC version
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Promotion and protection of human rights of refugees and vulnerable members of the host community in Jordan.
IMPACT | Impact Indicator 1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Refugees and vulnerable members of the host community live in safety, security and enhanced wellbeing | Percentage of beneficiaries who report confidence in the protection of their basic rights | Planned | 96% |  |  |  | 50% |  |  |  | 50% |  |  |  | 50% | 50%
|  | Achieved |  |  |  |  | 88%
Source
Outcome monitoring exercise, beneficiary surveys. Results are disaggregated by gender and nationality
| Impact Indicator 2 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| Percentage of beneficiaries reporting an overall improvement in their wellbeing | Planned | N/A |  |  |  | 80% |  |  |  | 80% |  |  |  | 80% | 80%
|  | Achieved |  |  |  |  | 58%
Source
Clients records; beneficiary wellbeing assessment
| Impact Indicator 3 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| Percentage of beneficiaries reporting an overall improvement in their social participation | Planned | 65% |  |  |  | 70% |  |  |  | 75% |  |  |  | 80% | 80%
|  | Achieved |  |  |  |  | 46%
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Needs of the most vulnerable met by greater access to expanded and strengthened protection, rehabilitation and legal services | % of NRC beneficiaries who report exercising their legal rights | Planned | 90% |  |  |  | 80% |  |  |  | 80% |  |  |  | 80% | 80%
|  | Achieved |  |  |  |  | 98%
Source
Beneficiary surveys; outcome monitoring exercises.
| Outcome Indicator 2 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| % of beneficiaries surveyed who rate the service provided positively | Planned | N/A |  |  |  | 75% |  |  |  | 80% |  |  |  | 85% | 85%
|  | Achieved |  |  |  |  | 84%
Source
Beneficiary satisfaction surveys
| Outcome Indicator 3 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| % of HI and IMC beneficiaries showing improvement in functional independence | Planned | N/A |  |  |  | 70% |  |  |  | 75% |  |  |  | 80% | 80%
|  | Achieved |  |  |  |  | 67%
Source
Individual beneficiary files, post-intervention monitoring, IMC client functioning scale
| Outcome Indicator 4 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # instances where partner recommendations are reflected in targeted policies, decisions and/or other arenas by the GOJ | Planned | N/A |  |  |  | 2 |  |  |  | 4 |  |  |  | 5 | 11
|  | Achieved |  |  |  |  | 9
Source
Minutes of meeting of humanitarian working groups, media reports, stakeholder feedback
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Training and capacity building of key stakeholders including NGO staff, GOJ staff and community leaders | # of national, local authorities, lawyers, jurists, law students and legal aid providers trained on access to justice issues for refugees | Planned | 0 |  |  |  | 75 |  |  |  | 80 |  |  |  | 45 | 200
|  | Achieved |  |  |  |  | 166
Source
Training invitation, agenda, attendance sheets
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
15% | # primary health care providers receive training, for example mhGAP, ED/EI and MHPSS | Planned | 0 |  |  |  | 124 |  |  |  | 33 |  |  |  | 31 | 188
|  | Achieved |  |  |  |  | 144
Source
Training attendance sheets, training reports
| Output Indicator 1.3 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # of community actors and leaders that are empowered to support protection needs needs both in community settings and camps to influence service provision | Planned | 0 |  |  |  | 139 |  |  |  | 136 |  |  |  | 137 | 412
|  | Achieved |  |  |  |  | 159
Source
Training invitation, agenda, attendance sheets
| Output Indicator 1.4 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # of projects which reflects improved inclusive pratices after HI tailored coaching to the service provider | Planned | 0 |  |  |  | 4 |  |  |  | 3 |  |  |  | 3 | 10
|  | Achieved |  |  |  |  | 0
Source
Coaching assessment reports, partner action plans, follow-up assessments
| Output Indicator 1.5 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| % of training participants demonstrating an improved knowledge in topics covered | Planned | N/A |  |  |  | 70% |  |  |  | 70% |  |  |  | 70% | 70%
|  | Achieved |  |  |  |  | 85%
Source
Pre and post-training surveys
INPUTS (£) | DFID (£) |  | Govt (£) | [12 empty] | DFID SHARE (%) | Risk Rating
Low
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Awareness is raised amongst beneficiaries and other community members on protection issues, and research is produced to influence advocacy and policy change | # of social media campaigns run to promote refugee rights and social cohesion | Planned | 0 |  |  |  | 2 |  |  |  | 2 |  |  |  | 2 | 6
|  | Achieved |  |  |  |  | 1
Source
Partner data, social media statistics
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
30% | # of direct beneficiaries and community members who received information | Planned | 0 |  |  |  | 30200 |  |  |  | 35300 |  |  |  | 35500 | 101000
|  | Achieved |  |  |  |  | 24096
Source
Information sessions booking sheets, partner database, partner reports, community mobilisers reports, knowledge/ understanding spot-checks
| Output Indicator 2.3 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| Number of periodic reports and policy briefs produced on barriers to rights for refugees in Jordan | Planned | 0 |  |  |  | 2 |  |  |  | 3 |  |  |  | 3 | 8
|  | Achieved |  |  |  |  | 3
Source
Reports and policy briefs produced
INPUTS (£) | DFID (£) |  | Govt (£) | [12 empty] | DFID SHARE (%) | Risk Rating
Low
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Vulnerable persons receive direct assistance, and have increased access to services | # of direct NRC beneficiaries who received (a) legal counselling and (b) direct legal services | Planned | 0 |  |  |  | (a) 12,086 (b) 1,168 |  |  |  | (a) 8232 (b) 1568 |  |  |  | (a) 8236 (b) 1567 | (a) 24700 (b) 4700
|  | Achieved |  |  |  |  | (a) 18,468 (b) 2,396
Source
Beneficiary intake information, NRC database, partner reports
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
55% | # of vulnerable people who received comprehensive rehabilitation services (HI beneficiaries) | Planned | 0 |  |  |  | 600 |  |  |  | 800 |  |  |  | 0 | 1400
|  | Achieved |  |  |  |  | 1638
Source
MEAL system, beneficiary database, individual beneficiary files, post intervention monitoring reports
| Output Indicator 3.3 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # of IMC beneficiaries receiving specialised MH and CP case management services at static centres and from MMUs | Planned | 0 |  |  |  | 1888 |  |  |  | 1778 |  |  |  | 1790 | 5456
|  | Achieved |  |  |  |  | 1959
Source
Mental health database, client records, best interest assessment documents, care plans, follow-up records
| Output Indicator 3.4 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # IMC beneficiaries receiving the social assistance protection package for three months (incremental) | Planned | 0 |  |  |  | 100 |  |  |  | 100 |  |  |  | 100 | 300
|  | Achieved |  |  |  |  | 103
Source
Signed list of clients who received 3 cash payments, completed application forms for clients, committee member scores and applications
| Output Indicator 3.5 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # of most vulnerable people referred by HI to external services | Planned | 0 |  |  |  | 243 |  |  |  | 372 |  |  |  | 109 | 724
|  | Achieved |  |  |  |  | 847
Source
MEAL system, beneficiary database, referral database and records
INPUTS (£) | DFID (£) |  | Govt (£) | [12 empty] | DFID SHARE (%) | Risk Rating
Moderate
INPUTS (HR) | DFID (FTEs)

## detailed version
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Promotion and protection of human rights of refugees and vulnerable members of the host community in Jordan.
IMPACT | Impact Indicator 1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
Refugees and vulnerable members of the host community live in safety, security and enhanced wellbeing | Percentage of beneficiaries who report increased protection of rights (NRC) | Planned | 70% |  |  |  | 70% |  |  |  | 70% |  |  |  | 70% | 70%
|  | Achieved |  |  |  |  | 88% |  |  |  | 75%
Source
Outcome monitoring exercise, beneficiary surveys. Results are disaggregated by gender and nationality
Impact Indicator 2
| Percentage of beneficiaries reporting an overall improvement in their wellbeing (IMC) | Planned | 82% |  |  |  | 85% |  |  |  | 85% |  |  |  | 85% | 85%
|  | Achieved |  |  |  |  | 58% |  |  |  | 77%
Source
Clients records; beneficiary wellbeing assessment
Impact Indicator 3
| Percentage of beneficiaries reporting an overall improvement in their social participation (HI) | Planned | 65% |  |  |  | 70% |  |  |  | 75% |  |  |  | 80% | 80%
|  | Achieved |  |  |  |  | 46% |  |  |  | 60%
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Needs of the most vulnerable met by greater access to expanded and strengthened protection, rehabilitation and legal services, as well as advocacy efforts to promote policy change | % of beneficiaries who report exercising their legal rights (NRC 2) | Planned | 71% |  |  |  | 75% |  |  |  | 75% |  |  |  | 75% | 75%
|  | Achieved |  |  |  |  | 98% |  |  |  | 89% |  |  |  | 88% | 98%
Source
Beneficiary surveys; outcome monitoring exercises.
| Outcome Indicator 2 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| % of beneficiaries surveyed who rate the service provided positively (IMC 1 and HI) - HI indicator from PIM, only on rehabilitation services | Planned | N/A |  |  |  | 75% |  |  |  | 80% |  |  |  | 85% | 85%
|  | Achieved |  |  |  |  | 77% |  |  |  | 83% |  |  |  | 91.5% | 91.5%
Source
Beneficiary satisfaction surveys
| Outcome Indicator 3 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| % of HI and IMC beneficiaries showing improvement in functional independence (HI 1, IMC 2) | Planned | N/A |  |  |  | 70% |  |  |  | 75% |  |  |  | 80% | 80%
|  | Achieved |  |  |  |  | 67% |  |  |  | 80% |  |  |  | 84.5% | 84.5%
Source
Individual beneficiary files, post-intervention monitoring, IMC client functioning scale
| Outcome Indicator 4 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # instances where partner recommendations are reflected in targeted policies, decisions and/or other arenas by the GOJ (NRC 4, HI 3) | Planned | N/A |  |  |  | 2 |  |  |  | 4 |  |  |  | 5 | 11
|  | Achieved |  |  |  |  | 9 |  |  |  | 14 |  |  |  | 4 | 27
Source
Minutes of meeting of humanitarian working groups, media reports, stakeholder feedback
| Outcome Indicator 5 |  | Baseline |  |  |  | Y1 |  |  |  | Y2 |  |  |  | Y3 (Sept 2020) | Target (March 2021)
| Two national ED/EI guidelines developed and approved by MoH and MoSD (HI) | Planned | N/A |  |  |  | N/A |  |  |  | N/A |  |  |  | 2 | 2
|  | Achieved | [12 empty] | 2 | 2
Source
HI reporting
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Training and capacity building of key stakeholders including NGO staff, GOJ staff and community leaders (all) | # of national, local authorities, lawyers, jurists, law students and legal aid providers trained on access to justice issues for refugees (NRC 3.1) | Planned | 0 |  |  |  | 75 |  |  |  | 80 |  |  |  | 45 | 200
|  | Achieved |  |  |  |  | 166 |  |  |  | 157 |  |  |  | 0 | 323
Source
Training invitation, agenda, attendance sheets
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
20% | Number of primary health care providers receive training, for example mhGAP, ED/EI and MHPSS (IMC combined indicators 3.1 and 3.2, HI 2.3) | Planned | 0 |  |  |  | 136 |  |  |  | 49 |  |  |  | 43 | 228
|  | Achieved |  |  |  |  | 143 |  |  |  | 160 |  |  |  | 113 | 416
Source
Training attendance sheets, training reports
| Output Indicator 1.3 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # of community actors and leaders that are empowered to support protection needs both in community settings and camps to influence service provision (NRC 3.2 and HI 3.4 combined) | Planned | 0 |  |  |  | 139 |  |  |  | 136 |  |  |  | 137 | 412
|  | Achieved |  |  |  |  | 159 |  |  |  | 138 |  |  |  | 186 | 483
Source
Training invitation, agenda, attendance sheets
| Output Indicator 1.4 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # of projects assessed and for which inclusion action plans have been developed for implementation (HI 3.2) | Planned | 0 |  |  |  | 4 |  |  |  | 3 |  |  |  | 3 | 10
|  | Achieved |  |  |  |  | 0 |  |  |  | 8 |  |  |  | 1 | 9
Source
Coaching assessment reports, partner action plans, follow-up assessments
| Output Indicator 1.5 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| % of training participants demonstrating an improved knowledge in topics covered (all) - HI 1.4, NRC outcome 3, IMC outcome 6 | Planned | N/A |  |  |  | 70% |  |  |  | 70% |  |  |  | 70% | 70%
|  | Achieved |  |  |  |  | 83% |  |  |  | 90% |  |  |  | 98% | 98%
Source
Pre and post-training surveys
INPUTS (£) | DFID (£) |  | Govt (£) | [12 empty] | DFID SHARE (%) | Risk Rating
Minor
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Awareness is raised amongst beneficiaries and other community members on protection issues | # of direct beneficiaries and community members who received information (NRC 1.1, HI 3.1) | Planned | 0 |  |  |  | 30200 |  |  |  | 28634 |  |  |  | 22168 | 81002
|  | Achieved |  |  |  |  | 24096 |  |  |  | 28081 |  |  |  | 31801 | 83978
Source
Information sessions booking sheets, partner database, partner reports, community mobilisers reports, knowledge/ understanding spot-checks
IMPACT WEIGHTING (%)
10%
INPUTS (£) | DFID (£) |  | Govt (£) | [12 empty] | DFID SHARE (%) | Risk Rating
Minor
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Research is produced to influence advocacy and policy change | Number of periodic reports and policy briefs produced on barriers to rights for refugees in Jordan (NRC 4.1) | Planned | 0 |  |  |  | 2 |  |  |  | 3 |  |  |  | 3 | 8
|  | Achieved |  |  |  |  | 3 |  |  |  | 6 |  |  |  | 9 | 18
Source
Reports and policy briefs produced
IMPACT WEIGHTING (%)
10%
INPUTS (£) | DFID (£) |  | Govt (£) | [12 empty] | DFID SHARE (%) | Risk Rating
Moderate
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021) | Assumptions
Vulnerable persons receive direct assistance, and have increased access to services (all) | # of direct beneficiaries who received (a) counselling and (b) direct legal services (NRC 2.1,2) | Planned | 0 |  |  |  | (a) 15,120 (b) 698 |  |  |  | (a) 15940 (b) 926 |  |  |  | (a) 15940 (b) 1976 | (a) 47000 (b) 3600
|  | Achieved |  |  |  |  | 20864 |  |  |  | 17986 |  |  |  | 16494 | 55344
Source
Beneficiary intake information, NRC database, partner reports
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
60% | # of vulnerable people who received comprehensive rehabilitation services (HI 1.2) | Planned | 0 |  |  |  | 600 |  |  |  | 2850 |  |  |  | 150 | 3600
|  | Achieved |  |  |  |  | 1638 |  |  |  | 2323 |  |  |  | 635 | 4596
Source
MEAL system, beneficiary database, individual beneficiary files, post intervention monitoring reports
| Output Indicator 4.3 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # of beneficiaries receiving specialised MH and CP case management services at static centres and MMUs (IMC 1.2, 1.3 and 2.3) | Planned | 0 |  |  |  | 1888 |  |  |  | 1778 |  |  |  | 1790 | 5456
|  | Achieved |  |  |  |  | 1959 |  |  |  | 1864 |  |  |  | 1718 | 5541
Source
Mental health database, client records, best interest assessment documents, care plans, follow-up records
| Output Indicator 4.4 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| Number of beneficiaries receiving the social assistance protection package for three months (incremental) (IMC 1.4) | Planned | 0 |  |  |  | 100 |  |  |  | 100 |  |  |  | 100 | 300
|  | Achieved |  |  |  |  | 103 |  |  |  | 101 |  |  |  | 96 | 300
Source
Signed list of clients who received 3 cash payments, completed application forms for clients, committee member scores and applications
| Output Indicator 4.5 |  | Baseline | Q1 | Q2 | Q3 | Y1 | Q5 | Q6 | Q7 | Y2 | Q9 | Q10 | Q11 | Y3 | Target (March 2021)
| # of most vulnerable people referred to external services (HI 1.5) | Planned | 0 |  |  |  | 243 |  |  |  | 1368 |  |  |  | 180 | 1791
|  | Achieved |  |  |  |  | 847 |  |  |  | 1040 |  |  |  | 780 | 2667
Source
MEAL system, beneficiary database, referral database and records
INPUTS (£) | DFID (£) |  | Govt (£) | [12 empty] | DFID SHARE (%) | Risk Rating
Moderate
INPUTS (HR) | DFID (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.